## Dashboard
MCL DEVELOPMENTAL PROJECTS - CONSOLIDATED SUMMARY
By Fund / Quota Type
Fund Type | No. of Works | Total Est. Cost (Lacs) | Total Tender Cost (Lacs)
MC Funds / General Quota | 426 | 18470.39 | 19409.2223
Councillor Quota (CQ) | 94 | 2392.69 | 2866.96
MDF / SASCI | 37 | 9762.44 | 9378.78
MPLAD Funds | 35 | 235.38 | 210.703
Rangla Punjab | 25 | 667.14 | 441.38
SIDBI | 13 | 1389.68 | 1062.47
Viveki Funds | 5 | 60 | 48.79
N-CAP | 5 | 229.1 | 174.4531
Other / Unspecified | 1 | 57.55 | 38.79
CSAG | 2 | 1033.68 | 933.24
SBM (Swachh Bharat Mission) | 1 | 0 | 28.7
RPVS | 1 | 60.95 | 42.67
By Status
Completed | 4
In Progress | 354
Delayed/Held Up | 145
Not Started | 129
By Constituency
Atam Nagar | 57
Central | 74
East | 113
North | 123
Sahnewal | 45
South | 79
West | 154
Overall Totals
Total No. of Ongoing Works | 637
Total Estimated Cost (Lacs) | 34359
Total Tender Cost (Lacs) | 34636.1585

## Master
Sr. No. | Project ID | Branch | Zone | Sub-Zone | Assembly Constituency | Ward | Nature of Work | E office number | Name of Work / Description | Length (Rmt) | Road Width (Ft) | No. of Units | Fund / Quota Type | Quota (as recorded) | Current Status | Est./Vetted Cost (Lacs) | OAS % | Resolution No. & Date | AA (Y/N) | TS (Y/N) | TS Accorded By | Accounts / SE Certificate (Y/N) | Tender Float Date | Tender End Date | Technical Evaluation (Y/N) | Financial Evaluation (Y/N) | Work Order No. & Date | Executing Agency | Tender Cost (Lacs) | Start Date | Time Limit (Months) | Scheduled End Date | Actual Completion Date | Supervising Officer (JE/SDO/XEN) | Third Party Inspection (Y/N) | Completion Certificate (Y/N) | Physical Progress % | Financial Progress % | Expenditure / Payment (Lacs) | Status | Issues / Bottlenecks | Remarks / Status Notes | Geo-tagged Photograph (Link) | Last Updated On
1 | MCL-0001 | B&R | B | B4 | East | 19 | Parks & Green Belts |  | Repair & Renovation of various parks in LIG W No.19 |  |  |  | MC Funds / General Quota | General |  | 62.03 | 39.99 | 3189 22.11.2024 | [8 empty] | 82 dt 04.12.2024 | M/s Prince Sharma | 37.22 | 04.12.2024 | 6 | 03.06.2025 |  |  |  |  | 80 |  | 24.61 | In Progress |  | Work is in Progress
2 | MCL-0002 | B&R | B | B3 | East | 12 | Roads - Interlocking Tiles |  | P/F I/tiles in various streets of W No.12 | 2100 | 11 |  | MC Funds / General Quota | General |  | 93.51 | 42.99 | 3190 22.11.2024 | [8 empty] | 83 dt 04.12.2024 | M/s Apex Developers | 53.31 | 04.12.2024 | 5 | 03.05.2025 |  |  |  |  | 60 |  | 30.00 | Delayed/Held Up |  | Work was held up due to non-laying of W/s line in Guru Nanak Estate . Now same has been laid. Work is in progress
3 | MCL-0003 | B&R | B | B2 | East | 17 & 19 | Roads - Interlocking Tiles |  | P/F I/tiles in streets of Guru Arjun Dev Nagar, Jaswant Nagar and Indrapuri St No.4 W No.17 & 19 | 430.49 | 11 |  | MC Funds / General Quota | General |  | 20.81 | 41.65 | 3141 22.11.2024 | [8 empty] | 86 dt 04.12.2024 | Capital Const Co. | 12.14 | 04.12.2024 | 3 | 03.03.2025 |  |  |  |  | 25 |  | 5.00 | Delayed/Held Up |  | Heldup due to Dispute at site for the balance work
4 | MCL-0004 | B&R | B | B2 | East | 16 | Parks & Green Belts |  | Const of Park on Bhamian Road Near Football Ground W No.16 | 0 |  |  | MC Funds / General Quota | General |  | 50 | 31.89 | 355 dt 26.03.2025 | [8 empty] | 01 16.04.2025 | M/s Teg Builders | 34.06 | 16.04.2025 | 6 | 15.10.2025 |  |  |  |  | 10 |  | 0.0 | In Progress |  | Heldup due to construction of water tank by O&M Cell
5 | MCL-0005 | B&R | B | B3 | East | 12 | Roads - Interlocking Tiles |  | P/F I/tiles in streets of Juneja Colony and Karamsar Colony W No.12 | 1022.87 | 11 |  | MC Funds / General Quota | General |  | 50 | 41.99 | 177 dt 26.03.2025 | [8 empty] | 9 16.04.2025 | Apex Developers | 29 | 16.04.2025 | 4 | 15.08.2025 |  |  |  |  | 15 |  | 0 | In Progress |  | Work is in Progress
6 | MCL-0006 | B&R | B | B3 | East | 10 | Roads - Interlocking Tiles |  | P/F 80mm thick Interlocking tiles in streets of Mohalla New Subhash Nagar on Towerline No. 2 & 5 and St No.10 & St No.2/10 & 2/11 of Subhash Nagar W No.10 | 679.27 | 11 |  | MC Funds / General Quota | General |  | 29.69 | 41.55 | 179 dt 26.03.2025 | [8 empty] | 10 16.04.2025 | Capital Const Co. | 17.35 | 16.04.2025 | 3 | 15.07.2025 |  |  |  |  | 30 |  | 0 | In Progress |  | Work heldup due to upgradation of W/s lines, Now same has been completed. Work is in progress now.
7 | MCL-0007 | B&R | B | B3 | East | 9 | Roads - Interlocking Tiles |  | P/F I/tiles in remaining streets of Shastri Nagar and link of New Shakti Nagar W No.09 | 656.71 | 11 |  | MC Funds / General Quota | General |  | 34.61 | 42.61 | 180 dt 26.03.2025 | [8 empty] | 11 16.04.2025 | T&G Const Co. | 19.86 | 16.04.2025 | 3 | 15.07.2025 |  |  |  |  | 70 |  | 8.78 | In Progress |  | Work heldup due to upgradation of W/s lines in the balance area
8 | MCL-0008 | B&R | B | B4 | East | 21 | Roads - Interlocking Tiles |  | P/F I/tiles in streets No.2 of Hargobindpura & Links W No.21 | 733.54 | 11 |  | MC Funds / General Quota | General |  | 34.21 | 41.55 | 185 dt 26.03.2025 | [8 empty] | 13 16.04.2025 | Capital Const Co. | 19.99 | 16.04.2025 | 3 | 15.07.2025 |  |  |  |  | 90 |  | 13.50 | In Progress |  | Balance work was heldup due to upgradation of W/S line in the balance area, now same has been laid. Work is in Progress now.
9 | MCL-0009 | B&R | B | B3 | East | 11 | Roads - Interlocking Tiles |  | P/F I/tiles in streets of Sandhu Colony | 3484.15 | 11 |  | MC Funds / General Quota | General |  | 145.87 | 44.09 | 1483 dt 13.10.2025 | [8 empty] | 20 11.07.2025 | T&G Const Co. | 81.55 | 11.07.2025 | 6 | 10.01.2026 |  |  |  |  | 90 |  | 75.64 | In Progress |  | Work is in Progress
10 | MCL-0010 | B&R | B | B2 | East |  | Others |  | Providing & Fixing of Sign Boards in different areas of Sub Zone B2 | 0 | 0 |  | MC Funds / General Quota | General |  | 34.03 | 32 | Approved inanticipation of F&CC | [8 empty] | 22 14.08.2025 | Glisten | 23.14 | 14.08.2025 | 3 | 13.11.2025 |  |  |  |  | 50 |  | 13.62 | In Progress |  | Work is in Progress
11 | MCL-0011 | B&R | B | B3 | East |  | Others |  | Providing & Fixing of Sign Boards in different areas of Sub Zone B3 | 0 | 0 |  | MC Funds / General Quota | General |  | 43.13 | 32 | Approved inanticipation of F&CC, | [8 empty] | 23 14.08.2025 | Glisten | 29.33 | 14.08.2025 | 4 | 13.12.2025 |  |  |  |  | 60 |  | 17.43 | In Progress |  | Work is in Progress
12 | MCL-0012 | B&R | B | B3 | East | 12 | Parks & Green Belts |  | Development of Green Belt on Towerline No.2 and 5 | 0 | 0 |  | MC Funds / General Quota | General |  | 309.16 | 29.99 | 1787 dt 13.10.2025 | [8 empty] | 24 27.08.2025 | RK Const Co. | 216.44 | 27.08.2025 | 6 | 26.02.2026 |  |  |  |  | 60 |  | 70.00 | In Progress |  | Work is in Progress |  | As per councillor, work is extremely slow.
13 | MCL-0013 | B&R | B | B3 | East | 16,18,20 &29 | Others |  | Construction of Central Verge on Tajpur raod . | 0 | 0 |  | MC Funds / General Quota | General |  | 217.47 | 14.15 | 1786 dt 13.10.2025 | [8 empty] | 25 27.08.2025 | Navyug Comapany | 186.7 | 27.08.2025 | 6 | 26.02.2026 |  |  |  |  | 40 |  | 82.88 | In Progress |  | Work is in Progress
14 | MCL-0014 | B&R | B | B4 | East | 19 | Parks & Green Belts |  | P/F different type of Open garden gym machines in ward no 19. | 0 | 0 |  | MC Funds / General Quota | General |  | 16.03 | 36.99 | 1669 dt 13.10.2025 | [8 empty] | 27 15.01.2026 | Khalsa Exports Pvt Ltd. | 10.1 | 15.01.2026 | 2 | 14.03.2026 | [6 empty] | 0 | Not Started |  | Inauguration is to be done
15 | MCL-0015 | B&R | B | B4 | East | 19 | Parks & Green Belts |  | Repair & Renovation of various Park in Sec 39 Block-I | 0 | 0 |  | MC Funds / General Quota | General |  | 36.2 | 28.59 | 1666 dt 13.10.2025 | [8 empty] | 32 15.01.2026 | RK Const Co. | 25.85 | 15.01.2026 | 3 | 14.04.2026 |  |  |  |  | 75 |  | 14.68 | In Progress |  | Work is in Progress
16 | MCL-0016 | B&R | B | B4 | East | 19 | Parks & Green Belts |  | Repair & Renovation of various Park in Sec 39 Block-II | 0 | 0 |  | MC Funds / General Quota | General |  | 38.85 | 28.59 | 1667 dt 13.10.2025 | [8 empty] | 33 15.01.2026 | RK Const Co. | 27.74 | 15.01.2026 | 3 | 14.04.2026 |  |  |  |  | 75 |  | 19.77 | In Progress |  | Work is in Progress
17 | MCL-0017 | B&R | B | B4 | East | 19 | Others |  | Renovation of Disposal site and Fixing of Information Board at enterance of Sec-39 near Vardhman Chowk W No.19 | 0 | 0 |  | Councillor Quota (CQ) | Councillor |  | 20.7 | 5.89 | 2493 dt 05.01.2026 Workorder to be issued | [8 empty] | 43 15.01.2026 | Teg Builders | 19.48 | 15.01.2026 | 2 | 14.03.2026 |  |  |  |  | 80 |  | 10.10 | In Progress |  | Work is in Progress
18 | MCL-0018 | B&R | B | B3 | East | 16 | Roads - RMC / Cement Concrete |  | Const of Road by laying RMC from Gita Nagar Pully to Vijay Nagar Pully W No.16 | 1085.06 | 11 |  | MC Funds / General Quota | General |  | 66.47 | 36.69 | 2488 dt 05.01.2026 | [8 empty] | 44 15.01.2026 | RK Const Co. | 42.08 | 15.01.2026 | 4 | 14.05.2026 |  |  |  |  | 5 |  | 0 | In Progress |  | Work heldup due to upgradation of Sewer line
19 | MCL-0019 | B&R | B | B4 | Sahnewal |  | Others |  | Providing & Fixing of Sign Boards in different areas of Sub Zone B4 | 0 | 0 |  | MC Funds / General Quota | General |  | 36.92 | 32 | 1571 dt 13.10.2025 | [8 empty] | 46 29.01.2026 | Glisten | 25.11 | 46 29.01.2026 | 3 | 28.04.2026 |  |  |  |  | 50 |  | 2.49 | In Progress |  | Work is in Progress
20 | MCL-0020 | B&R | B | B4 | East | 19 | Parks & Green Belts |  | P/F of Garden Benches in various park of W No.19 | 0 | 0 |  | MC Funds / General Quota | General |  | 7.91 | 18.5 | 1668 dt 13.10.2025 | [8 empty] | 48 29.01.2026 | Glisten | 6.45 | 48 29.01.2026 | 1 | 28.02.2026 | [6 empty] | 0 | Not Started |  | Inauguration is to be done
21 | MCL-0021 | B&R | B | B4 | East | 28 | Parks & Green Belts |  | P/F Garden Benches, Open Gym Machines & Children Playing Equipments in W No.28 | 0 | 0 |  | MC Funds / General Quota | General |  | 12.92 | 20.5 | 1671 dt 13.10.2025 | [8 empty] | 49 16.02.2026 | Glisten | 10.27 | 49 16.02.2026 | 1 | 15.03.2026 | [6 empty] | 0 | Not Started |  | Inauguration is to be done
22 | MCL-0022 | B&R | B | B3 | East | 13 | Others |  | Development of Badminton Court in Banda Bhadur Colony near Shamshanghat W No.13 | 0 | 0 |  | MC Funds / General Quota | General |  | 7.92 | 2.22 | Approved inanticipation by W/Mayor vide dt 21.01.2026 & Regular approval by F&CC 2779 dt 19.02.2026 | [8 empty] | 50 16.02.2026 | Sachdeva Art Gallery | 7.74 | 16.02.2026 | 1 | 15.03.2026 |  |  |  |  | 70 |  | 4.00 | In Progress |  | Work is in Progress
23 | MCL-0023 | B&R | B | B4 | East | 21 | Roads - Bituminous |  | Const.of bituminous road in GRD colony | 2329.27 | 11 |  | MC Funds / General Quota | General |  | 49.88 | 19.05 | 2522 dt 05.02.2026 | [8 empty] | 52 16.02.2026 | Somaya Infrastructure | 40.38 | 16.02.2026 | 5 | 15.07.2026 | [6 empty] | 0 | Not Started |  | Work heldup due to upgradation of W/S lines
24 | MCL-0024 | B&R | B | B3 | East | 11 | Parks & Green Belts |  | Re-devlopment of New Shastri Nagar Park W No.11 | 0 |  |  | MC Funds / General Quota | General |  | 4.7 | 7.89 | 2520 dt 05.02.2026 | [8 empty] | 54 16.02.2026 | Teg Builders | 4.33 | 16.02.2026 | 3 | 15.05.2026 |  |  |  |  | 90 |  | 0 | In Progress |  | Work is in Progress
25 | MCL-0025 | B&R | B | B4 | East | 19 | Roads - Interlocking Tiles |  | P/F Perforated I/tiles on side berms of GRD Colony W NO.19 | 2329.27 | 11 |  | Councillor Quota (CQ) | Councillor |  | 24.53 | 30.35 | 2518 dt 05.02.2026 | [8 empty] | 55 16.02.2026 | Navyug Company | 17.08 | 16.02.2026 | 3 | 15.05.2026 |  |  |  |  | 5 |  | 0 | In Progress |  | Work heldup due to upgradation of sewerline.
26 | MCL-0026 | B&R |  |  | East |  | Roads - Bituminous |  | Upgradation of Gurudwara road urban estate phase 1&2 from Metro road to Jeewan Nagar chowk, Road along budha nallah from NHAI to MC limit , Main Bhadur Ke Road from Sabji Mandi upto MC Limit, Main New Azad Nagar 30' Road from Kainth Property Dealer upto Gaur Property Dealer and Roads of Onkar Vihar. | 14377.74 | 11 |  | MDF / SASCI | Special Assistance Scheme |  | 535.05 | 3.25 | 2675 dt 11.02.2026 | [8 empty] | 60 18.02.2026 | CH Builders Pvt. Ltd. | 517.66 | 18.02.2026 | 3 | 17.05.2026 |  |  |  |  | 10 |  | 0 | In Progress |  | Work is in Progress
27 | MCL-0027 | B&R |  |  | East |  | Roads - Bituminous |  | Upgradation of Main Metro Road from Jamalpur Chowk to Kangaroo Industry, Jaswant Singh Dental College to Delhi road via Sethi Sweets, Internal Roads of Sec-39, Road from Primary Govt School to NRI Police Station in Sec-39, Main Jain Colony road from Rahon Road to Swastik Enclave and Main Road of Guru Arjun Dev Nagar from GT Road upto Greenland School, Sabji Mandi Road from Chd road to Puda road, EWS colony main road from Jacha Bacha Hospital upto Tajpur road. | 28676.52 | 11 |  | MDF / SASCI | Special Assistance Scheme |  | 718.12 | 4.25 | 2873 dt 19.02.2026 | [8 empty] | 61 20.02.2026 | Kabir Infra Pvt. Ltd. | 687.6 | 20.02.2026 | 3 | 19.05.2026 |  |  |  |  | 25 |  | 0 | In Progress |  | Work is in Progress
28 | MCL-0028 | B&R | B | B2 | East | 20 | Roads - Bituminous |  | Const.of bituminous road in Sukhdev Nagar | 2009.45 | 11 |  | MC Funds / General Quota | General |  | 49.95 | 19.05 | 2769 dt 19.02.2026 | [8 empty] | 66 09.03.2026 | Somaya Infrastructure | 40.43 | 09.03.2026 | 5 | 08.08.2026 |  |  |  |  | 0 |  | 0 | Not Started |  | Heldup due to non avaiability of Bitumen
29 | MCL-0029 | B&R | B | B3 | East | 7 | Roads - Interlocking Tiles |  | P/F I/tiles in street No.5/1 to 5/6 & Links of New Subhash Nagar on Towerline No.5 W No.7 | 2015.85 | 11 |  | MC Funds / General Quota | General |  | 78.55 | 35.39 | 2771 dt 19.02.2026 | [8 empty] | 67 09.03.2026 | Navyug Company | 50.75 | 09.03.2026 | 5 | 08.08.2026 |  |  |  |  | 50 |  | 0 | In Progress |  | Work is in Progress
30 | MCL-0030 | B&R | B | B4 | East | 19 | Parks & Green Belts |  | Renovation of remaining Parks in Sec-39 Block- II W No.19 | 0 | 0 |  | Councillor Quota (CQ) | Councillor |  | 97.59 | 30.66 | 2761 dt 19.02.2026 | [8 empty] | 71 09.03.2026 | Apex Developers | 67.67 | 09.03.2026 | 5 | 08.08.2026 |  |  |  |  | 5 |  | 0 | In Progress |  | Work is in Progress
31 | MCL-0031 | B&R | B | B3 | East | 12 | Parks & Green Belts |  | Repair & Renovation of Sawtantar Nagar Park in W No.12 | 0 | 0 |  | MC Funds / General Quota | General |  | 18.99 | 13.89 | 2878 dt 19.02.2026 | [8 empty] | 72 09.03.2026 | Teg Builders & Varinder Singh Govt Contractor | 16.35 | 09.03.2026 | 3 | 08.06.2026 |  |  |  |  | 70 |  | 9.00 | In Progress |  | Work is in Progress
32 | MCL-0032 | B&R | B | B3 | East | 13 | Others |  | Development of Box Cricket in Banda Bhadur Colony near Shamshanghat W No.13 | 0 | 0 |  | MC Funds / General Quota | General |  | 30.16 | 5.89 | 2760 dt 19.02.2026 | [8 empty] | 75 09.03.2026 | Teg Builders & Varinder Singh Govt Contractor | 28.38 | 09.03.2026 | 4 | 08.07.2026 |  |  |  |  | 50 |  | 15.00 | In Progress |  | Work is in Progress
33 | MCL-0033 | B&R | B | B3 | East | 13 | Others |  | Construction of Entrance Gates for Karamsar Colony & Sutantar Nagar in w no.13. | 0 | 0 |  | MC Funds / General Quota | General |  | 26.34 | 2.89 | 2791dt 19.02.2026 | [8 empty] | 76 09.03.2026 | Teg Builders & Varinder Singh Govt Contractor | 25.58 | 09.03.2026 | 4 | 08.07.2026 | [6 empty] | 0 | Not Started |  | Inauguration is to be done
34 | MCL-0034 | B&R | B | B3 | East | 13 | Roads - Interlocking Tiles |  | P/Fixing I/tiles in Karamsar Colony & Nalwa Coloiny W No.13 | 2099.7 | 11 |  | Councillor Quota (CQ) | Councillor |  | 83.89 | 36.99 | 2770 dt 19.02.2026 | [8 empty] | 77 12.03.2026 | Apex Developers | 52.86 | 12.03.2026 | 4 | 11.07.2026 |  |  |  |  | 20 |  | 0 | In Progress |  | Work is in Progress
35 | MCL-0035 | B&R | B | B3 | East | 13 | Roads - Interlocking Tiles |  | P/Fixing I/tiles in streets of Grewal Colony & Raju Colony W No.13 | 1330.18 | 11 |  | Councillor Quota (CQ) | Councillor |  | 49.53 | 11.89 | 3436 dt 21.04.2026 | [8 empty] | 09 13.05.2026 | Teg Builders | 43.64 | 13.05.2026 | 4 | 12.09.2026 | [6 empty] | 0 | Not Started |  | Inauguration is to be done
36 | MCL-0036 | B&R | B | B3 | East | 13 | Roads - Interlocking Tiles |  | P/Fixing I/tiles in streets of Heera Vihar & Sutantar Nagar W No.13 | 1102.44 | 11 |  | Councillor Quota (CQ) | Councillor |  | 49.8 | 11.89 | 3435 dt 21.04.2026 | [8 empty] | 10 13.05.2026 | Varinder Singh Govt Contractor | 43.88 | 13.05.2026 | 4 | 12.09.2026 |  |  |  |  | 25 |  | 0 | In Progress |  | Work is in Progress
37 | MCL-0037 | B&R | B | B4 | East | 19 | Roads - RMC / Cement Concrete |  | Laying RMC in streets of New Kirti Nagar W No.19 | 222.87 | 11 |  | MC Funds / General Quota | General |  | 18.07 | 15.89 | 3434 dt 21.04.2026 | [8 empty] | 11 13.05.2026 | Teg Builders | 15.2 | 13.05.2026 | 3 | 12.08.2026 |  |  |  |  | 25 |  | 0 | In Progress |  | Work is in Progress
38 | MCL-0038 | B&R | B | B4 | East | 28 | Roads - Interlocking Tiles |  | P/F I/tiles in street of Saini Colony W No.28 | 1640.24 | 11 |  | Councillor Quota (CQ) | Councillor |  | 88.68 | 28.89 | 3433 dt 21.04.2026 | [8 empty] | 12 13.05.2026 | Teg Builders | 63.06 | 13.05.2026 | 5 | 12.10.2026 | [6 empty] | 0 | Not Started |  | Work heldup due to W/s Line
39 | MCL-0039 | B&R | B | B4 | East | 19 | Others |  | Const of RCC Boundary wall adj GRD Colony Sec-39 W No.19 | 0 |  |  | MC Funds / General Quota | General |  | 24.65 | 5.89 | 3432 dt 21.04.2026 | [8 empty] | 13 13.05.2026 | Varinder Singh Govt Contractor | 23.5 | 13.05.2026 | 3 | 12.08.2026 |  |  |  |  | 10 |  | 0 | In Progress |  | Work is in Progress
40 | MCL-0040 | B&R | B | B4 | East | 28 | Roads - Bituminous |  | Const.of bituminous road of Moti Nagar Block-C W No.28 | 1776.52 | 11 |  | Councillor Quota (CQ) | Councillor |  | 65.52 | 5 | 3431 dt 21.04.2026 | [8 empty] | 14 13.05.2026 | Shiva Construction | 62.24 | 13.05.2026 | 5 | 12.10.2026 | [6 empty] | 0 | Not Started |  | Inauguration is to be done
41 | MCL-0041 | B&R | B | B3 | East | 13 | Roads - Interlocking Tiles |  | P/Fixing I/tiles in left side streets of Banda Singh Bhadur Colony W No.13 | 1812.5 | 11 |  | MC Funds / General Quota | General |  | 88.4 | 39.99 | 3429 dt 21.04.2026 | [8 empty] | 16 13.05.2026 | Varinder Singh Govt Contractor | 53.05 | 13.05.2026 | 6 | 12.11.2026 |  |  |  |  | 10 |  | 0 | In Progress |  | Work is in Progress
42 | MCL-0042 | B&R | B | B3 | East | 13 | Roads - Interlocking Tiles |  | P/Fixing I/tiles in right side streets of Banda Singh Bhadur Colony W No.13 | 1513.72 | 11 |  | MC Funds / General Quota | General |  | 68.69 | 39.99 | 3428 dt 21.04.2026 | [8 empty] | 17 13.05.2026 | Varinder Singh Govt Contractor | 41.22 | 13.05.2026 | 5 | 12.10.2026 | [6 empty] | 0 | Not Started |  | Inauguration is to be done
43 | MCL-0043 | B&R | B | B3 | East | 13 | Roads - Interlocking Tiles |  | P/Fixing I/tiles in various Streets of juneja colony W No.13 | 2386.28 | 11 |  | MC Funds / General Quota | General |  | 76.4 | 28.64 | 3427 dt 21.04.2026 | [8 empty] | 18 13.05.2026 | Varinder Singh Govt Contractor | 54.52 | 13.05.2026 | 5 | 12.10.2026 | [6 empty] | 0 | Not Started |  | Inauguration is to be done
44 | MCL-0044 | B&R | B | B2 | East | 20 | Roads - Bituminous |  | Const.of bituminous road Guru Nanak Nagar Bhamian 27' Road | 698.48 | 11 |  | MC Funds / General Quota | General |  | 35.74 | 8.35 | Approved by W/Mayor dt 14.05.2026 inanticipation of F&CC, | [8 empty] | 23 27.05.2026 | Shiva Construction | 32.76 | 27.05.2026 | 5 | 26.10.2026 |  |  |  |  | 80 |  | 0 | In Progress |  | Work is in Progress
45 | MCL-0045 | B&R | B | B4 | Sahnewal | 28 | Roads - RMC / Cement Concrete |  | Const of road by laying RMC (M-30) in Ishwar colony W No.28 | 1298.17 | 11 |  | MC Funds / General Quota | General |  | 52 | 41.65 | 3205 29.11.2024 | [8 empty] | 75 dt 04.12.2024 | Capital Const Co. | 30.34 | 04.12.2024 | 4 | 03.05.2025 |  |  |  |  | 0 |  | 0 | Not Started |  | Heldup due to non laying of Sewerline
46 | MCL-0046 | B&R | B | B4 | Sahnewal | 28 | Roads - Interlocking Tiles |  | P/F 80mm thick I/Tiles in Balance streets of Prem Nagar & New Durga Colony W No.28 | 1578.96 | 11 |  | MC Funds / General Quota | General |  | 71.89 | 42.89 | 361 dt 26.03.2025 | [8 empty] | 15 16.04.2025 | T&G Const Co. | 41.06 | 16.04.2025 | 5 | 15.09.2025 |  |  |  |  | 50 |  | 20.66 | In Progress |  | Work was heldup due to upgradation of W/S Line, now same has been laid. Work is in Progress
47 | MCL-0047 | B&R | B | B4 | Sahnewal | 24 | Parks & Green Belts |  | Re-Development of Main Jeevan Nagar Park W No.24 | 0 |  |  | MC Funds / General Quota | General |  | 26.72 | 30.4 | 186 dt 26.03.2025 | [8 empty] | 16 16.04.2025 | Asis Builders | 18.6 | 16.04.2025 | 3 | 15.07.2025 |  |  |  |  | 80 |  | 17.46 | In Progress |  | Work is in Progress
48 | MCL-0048 | B&R | B | B4 | Sahnewal | 28 | Parks & Green Belts |  | Re-Development of Park Backside Gov.Sen.Sec School Dhandari Khurd Ludhiana W No.28 | 0 |  |  | MC Funds / General Quota | General |  | 25.74 | 33.99 | 188 dt 26.03.2025 | [8 empty] | 17 16.04.2025 | Apex Developers | 16.99 | 16.04.2025 | 3 | 15.07.2025 |  |  |  |  | 70 |  | 8.77 | In Progress |  | Work is in Progress
49 | MCL-0049 | B&R | B | B2 | Sahnewal | 22 | Roads - Interlocking Tiles |  | P/F I/tiles in streets of Jyoti Colony | 603.05 | 11 |  | MC Funds / General Quota | General |  | 23.07 | 34.4 | 1670 dt 13.10.2025 | [8 empty] | 26 15.01.2026 | Capital Const Co. | 15 | 15.01.2026 | 2 | 14.03.2026 |  |  |  |  | 5 |  | 0 | In Progress |  | Work is in Progress
50 | MCL-0050 | B&R | B | B2 | Sahnewal | 22 | Parks & Green Belts |  | Renovation of Tikoni park | 0 |  |  | MC Funds / General Quota | General |  | 15.02 | 24.99 | 2524 dt 05.02.2026 | [8 empty] | 57 16.02.2026 | Varinder Singh Govt Contractor and Maa Chintpurni Const | 11.27 | 16.02.2026 | 3 | 15.05.2026 | [6 empty] | 0 | Not Started |  | Inauguration is to be done
51 | MCL-0051 | B&R | B | B4 | Sahnewal | 21 | Parks & Green Belts |  | Renovation of park in Urban Estate Phase-II on Chd Road | 0 |  |  | MC Funds / General Quota | General |  | 105.91 | 34.1 | 2582 dt 11.02.2026 | [8 empty] | 59 16.02.2026 | Ram Parkash Kakkar | 69.79 | 16.02.2026 | 6 | 15.08.2026 |  |  |  |  | 30 |  | 0 | In Progress |  | Work is in Progress
52 | MCL-0052 | B&R | B | B2 | Sahnewal | 22 | Roads - RMC / Cement Concrete |  | Laying RMC in streets of Village Kuliewal W No.22 | 828.35 | 11 |  | Councillor Quota (CQ) | Councillor |  | 86.8 | 38.7 | 2763 dt 19.02.2026 | [8 empty] | 74 09.03.2026 | KS Constructions | 53.21 | 09.03.2026 | 5 | 08.08.2026 |  |  |  |  | 30 |  | 0 | In Progress |  | Heldup due to non laying of W/s line
53 | MCL-0053 | B&R | B | B2 | Sahnewal | 22 | Roads - RMC / Cement Concrete |  | Laying RMC in streets of Jamalpur Awana W No.22 | 621.95 | 11 |  | Councillor Quota (CQ) | Councillor |  | 69.91 | 39.99 | 2762 dt 19.02.2026 | [8 empty] | 78 12.03.2026 | Apex Developers | 41.95 | 12.03.2026 | 5 | 11.08.2026 |  |  |  |  | 45 |  | 0 | In Progress |  | Work is in Progress
54 | MCL-0054 | B&R | B | B2 | Sahnewal | 24 | Roads - Bituminous |  | Const of Bituminous roads in GK Estate main Road | 5382.01 | 11 |  | MC Funds / General Quota | General |  | 117.76 | 5 | 3309, dt 25.02.2026 | [8 empty] | 80 20.03.2026 | CH Builders Pvt. Ltd. | 111.87 | 20.03.2026 | 6 | 19.09.2026 |  |  |  |  | 15 |  | 0 | In Progress |  | Work is in Progress
55 | MCL-0055 | B&R | B | B4 | Sahnewal | 25 | Roads - Interlocking Tiles |  | P/F 80mm thick I/Tiles in Shiv colony | 2596.65 | 11 |  | MC Funds / General Quota | General |  | 112.48 | 41.72 | 3324 dt 25.02.2026 | [8 empty] | 85 24.03.2026 | T&G Const Co. | 65.55 | 24.03.2026 | 6 | 23.09.2026 |  |  |  |  | 40 |  | 26.2 | In Progress |  | Work is in Progress
56 | MCL-0056 | B&R | B | B4 | Sahnewal | 21 | Roads - Bituminous |  | Const of Bituminous Road of Jeewan Nagar & Guru Bag Colony Main Road of W No.21 | 1719.51 | 11 |  | MC Funds / General Quota | General |  | 48.52 | 5.3 | 3438 dt 21.04.2026 | [8 empty] | 20 13.05.2026 | Maruti Const Co. | 45.95 | 13.05.2026 | 4 | 12.09.2026 | [6 empty] | 0 | Not Started |  | Inauguration to be done
57 | MCL-0057 | B&R | B | B4 | Sahnewal | 21 | Parks & Green Belts |  | Renovation and Development of various parks Urban Estate Phase-II, Jamalpur of W No.21 | 0 |  |  | Councillor Quota (CQ) | Councillor |  | 78.46 | 24.9 | 3437 dt 21.04.2026 | [8 empty] | 21 13.05.2026 | Ram Parkash Kakkar | 58.92 | 13.05.2026 | 5 | 12.10.2026 | [6 empty] | 0 | Not Started |  | Inauguration to be done
58 | MCL-0058 | B&R | B | B2 | Sahnewal | 24 | Roads - Bituminous |  | Const of Bituminous Road from Chandigarh Road to GTB Nagar Near Jassal Factory | 745.12 | 11 |  | MC Funds / General Quota | General |  | 15.02 | 8.35 | Approved by W/Mayor dt 14.05.2026 inanticipation of F&CC, workorder to be issued | [8 empty] | 24 27.05.2026 | Shiva Construction | 13.77 | 27.05.2026 | 3 | 26.08.2026 |  |  |  |  | 10 |  | 0 | In Progress |  | Work is in Progress
59 | MCL-0059 | B&R | B | B2 | Sahnewal | 22 | Roads - RMC / Cement Concrete |  | P/L RMC(M-30) in Streets of Bank Colony W. No. 22 | 1493.9 | 11 |  | MC Funds / General Quota | General |  | 65.95 | 38.7 | Approved by W/Mayor dt 14.05.2026 inanticipation of F&CC, | [8 empty] | 25 27.05.2026 | LRY Labour Contractor | 40.43 | 27.05.2026 | 6 | 26.11.2026 | [6 empty] | 0 | Not Started |  | Inauguration to be done
60 | MCL-0060 | B&R | B | B4 | Sahnewal | 21 | Roads - Bituminous |  | Const of Bituminous Road of Guru Bag Colony W No.21 | 5132.62 | 11 |  | MC Funds / General Quota | General |  | 99.8 | 17.27 | Approved by W/ Mayor dt 28.05.2026 inanticipation approval by F&CC | [8 empty] | 26 01.06.2026 | Rajesh Kumar Sood | 82.56 | 01.06.2026 | 5 | 30.11.2026 |  |  |  |  | 5 |  | 0 | In Progress |  | Just Started
61 | MCL-0061 | B&R | B | B3 | East | 17 | Roads - RMC / Cement Concrete |  | Laying RMC from Main Tibba road upto Mahavir Jain Colony W No.17 | 1144.82 | 11 |  | MC Funds / General Quota | General |  | 114.55 | 33 | Inanticipation approval by W Mayor dt 16.06.2026 | [8 empty] | 27 19.06.2026 | Capital const Co. | 76.75 | 19.06.2026 | 6 | 18.12.2026 | [6 empty] | 0 | Not Started |  | Heldup due to laying of Sewerline
62 | MCL-0062 | B&R | B | B4 | Sahnewal | 28 | Roads - RMC / Cement Concrete |  | Const of Road by laying RMC in Prem Nagar W No.28 | 4964.33 | 11 |  | MDF / SASCI | MDF |  | 191.52 | 32.87 | 1005 13.10.2023 | [8 empty] | 23 dt 20.10.2023 | M/s Capital Const Co. | 128.57 | 20.10.2023 | 6 | 19.04.2024 |  |  |  |  | 55 |  | 45.64 | In Progress |  | Work heldup due to upgradation of W/s & Sewer lines in the balance streets
63 | MCL-0063 | B&R | B | B4 | Sahnewal | 28 | Roads - RMC / Cement Concrete |  | Laying RMC in street of New Durga Colony W No.28 | 4287.8 | 11 |  | MDF / SASCI | MDF |  | 196.63 | 8.05 | 1321 20.11.2023 | [8 empty] | 44A & 44B dt 20.11.2023 | M/s Glisten and Ashok Kumar Sobti (50%-50% allotted) | 180.8 | 20.11.2023 | 6 | 19.05.2024 |  |  |  |  | 55 |  | 40.48 | In Progress |  | Work heldup due to upgradation of W/s lines in the balance streets
64 | MCL-0064 | B&R | B | B3 | East | 15 | Roads - Bituminous |  | Const of Bituminous Road on Mata Karam Kaur Road W No.15 | 1205.79 | 11 |  | MDF / SASCI | MDF |  | 25 | 1.5 | 1324 20.11.2023 | [8 empty] | 47 dt 20.11.2023 | Shiva Construction | 24.62 | 20.11.2023 | 3 | 19.02.2024 |  |  |  |  | 20 |  | 0 | In Progress |  | Work is in Progress
65 | MCL-0065 | B&R | B | B4 | East | Focal Point | Parks & Green Belts |  | Development of Green Belt along Surpal cycle Road Phase-I Focal Point | 0 |  |  | MDF / SASCI | 50%MDF &50%MC |  | 146.06 | 18.2 | 3307, dt 25.02.2026 | [8 empty] | 01 10.04.2026 | Navyug Company | 119.48 | 10.04.2026 | 6 | 9.10.2026 |  |  |  |  | 10 |  | 0 | In Progress |  | Work is in Progress
66 | MCL-0066 | B&R | B | B4 | East | Focal Point | Parks & Green Belts |  | Const of Green Belt on Sanatan Dharam Mandir Road Phase-III Focal Point Ludhiana | 0 |  |  | MDF / SASCI | 50%MDF &50%MC |  | 79.02 | 32.2 | 2481 dt 05.01.2026 | [8 empty] | 40 15.01.2026 | Ram Parkash Kakkar | 53.58 | 15.01.2026 | 4 | 14.07.2026 |  |  |  |  | 20 |  | 0 | In Progress |  | Work is in Progress
67 | MCL-0067 | B&R | B | B4 | East | Focal Point | Parks & Green Belts |  | Re-Development of Green Belts & Parks near E-76 to E-92, E-93 to E-106, E-107 to E-145 & E-21, E-173 & E-190 in Phase-IV Focal Point Ludhiana | 0 |  |  | MDF / SASCI | 50%MDF &50%MC |  | 99.85 | 27.99 | 2482 dt 05.01.2026 | [8 empty] | 41 15.01.2026 | Apex Developers | 71.9 | 15.01.2026 | 5 | 14.07.2026 |  |  |  |  | 5 |  | 0 | In Progress |  | Work is in Progress
68 | MCL-0068 | B&R | B | B4 | East | Focal Point | Roads - RMC / Cement Concrete |  | Laying RMC along Kangaroo Industry & Upgradation of Junction Near BJ Computer Kanda on Metro Road Phase-IV Focal Point Ludhiana | 1495.12 | 11 |  | MDF / SASCI | 50%MDF &50%MC |  | 117.69 | 37.8 | 2773 dt 19.02.2026 | [8 empty] | 02 10.04.2026 | LRY Labour Contractor | 73.2 | 10.04.2026 | 5 | 09.10.2026 |  |  |  |  | 80 |  | 0 | In Progress |  | Work is in Progress
69 | MCL-0069 | B&R | B | B4 | Sahnewal | Focal Point | Roads - RMC / Cement Concrete |  | Const of road by laying RMC from Rishi Raj D-40 to Udehra Mechanical Works and other various locations in Focal Point Phase V, Ludhiana . | 2263.41 | 11 |  | MDF / SASCI | 50%MDF &50%MC |  | 151.9 | 37.8 | 2775 dt 19.02.2026 | [8 empty] | 03 10.04.2026 | LRY Labour Contractor | 94.48 | 10.04.2026 | 6 | 09.10.2026 |  |  |  |  | 10 |  | 0 | In Progress |  | Work is in Progress
70 | MCL-0070 | B&R | B | B4 | Sahnewal | Focal Point | Roads - Bituminous |  | Widening of Road from Jeewan Nagar Chowk upto Junction of Akal Spring Road, Phase-V and laying RMC in links between C-215 & C-216 near Dainik Jagran Road and Rectification of level at various Junctions in Focal Point, Ludhiana. | 1542.68 | 11 |  | MDF / SASCI | 50%MDF &50%MC |  | 169.46 | 37.8 | 2772 dt 19.02.2026 | [8 empty] | 04 10.04.2026 | LRY Labour Contractor | 105.4 | 10.04.2026 | 6 | 09.10.2026 |  |  |  |  | 20 |  | 0 | In Progress |  | Work is in Progress
71 | MCL-0071 | B&R | B | B4 | Sahnewal | Focal Point | Parks & Green Belts |  | Development of Green Belt From Jeewan Nagar Road to Rotar Kanda Phase-V Focal Point Ludhiana (Park No.1,2,3, 4,5 & 6) | 0 | 0 |  | MDF / SASCI | 50%MDF &50%MC |  | 173.65 | 21.89 | 2774 dt 19.02.2026 | [8 empty] | 62 09.03.2026 | Navyug Co. | 135.64 | 09.03.2026 | 7 | 08.10.2026 |  |  |  |  | 5 |  | 0 | In Progress |  | Work is in Progress
72 | MCL-0072 | B&R | B | B4 | Sahnewal | Focal Point | Parks & Green Belts |  | Re-Development of Green Belts & Parks near D-119, C-207 C-82, B-37, D-42 D-51 & D-70 in Phase-V Focal Point Ludhiana (Park No.12,13,15,18,21 & 22) | 0 | 0 |  | MDF / SASCI | 50%MDF &50%MC |  | 215.85 | 18.83 | 3305, dt 25.02.2026 | [8 empty] | 05 10.04.2026 | Navyug Company | 175.21 | 10.04.2026 | 6 | 09.10.2026 |  |  |  |  | 5 |  | 0 | In Progress |  | Work is in Progress
73 | MCL-0073 | B&R | B | B4 | Sahnewal | Focal Point | Parks & Green Belts |  | Re-Development of Green Belts & Parks near D-190d, E-362 & E-393 in Phase-VI Focal Point Ludhiana (Park No.9,10,11 & 12) | 0 | 0 |  | MDF / SASCI | 50%MDF &50%MC |  | 99.41 | 31.6 | 2483 dt 05.01.2026 | [8 empty] | 42 15.01.2026 | Ram Parkash Kakkar | 68 | 15.01.2026 | 4 | 14.07.2026 |  |  |  |  | 5 |  | 0 | In Progress |  | Work is in Progress
74 | MCL-0074 | B&R | B | B4 | Sahnewal | Focal Point | Parks & Green Belts |  | Re-Development of Green Belts & Parks near E-581, E-626 & C-202A in Phase-VII Focal Point Ludhiana (Park No.2 & 3) | 0 | 0 |  | MDF / SASCI | 50%MDF &50%MC |  | 198.84 | 19.59 | 2777 dt 19.02.2026 | [8 empty] | 79 12.03.2026 | RK Const Co. | 159.89 | 12.03.2026 | 8 | 11.10.2026 |  |  |  |  | 65 |  | 66.25 | In Progress |  | Work is in Progress
75 | MCL-0075 | B&R | B | B4 | Sahnewal | Focal Point | Roads - Bituminous |  | Const of mettaled Road Opp ESI Dispensery Phase - V and Residential pocket Phase VIII Focal Point, Ludhiana. | 3159.76 | 11 |  | MDF / SASCI | 50%MDF &50%MC |  | 147.05 | 29.5 | 2776 dt 19.02.2026 | [8 empty] | 06 10.04.2026 | Somaya Infrastructures | 103.67 | 10.04.2026 | 6 | 09.10.2026 |  |  |  |  | 80 |  | 73.46 | In Progress |  | Work is in Progress
76 | MCL-0076 | B&R | B | B4 | Sahnewal | Focal Point | Parks & Green Belts |  | Re-Development of Parks near C-246, C-256, 164 & 241 & Residential Pocket in Phase-VIII (Park No.2,3,6 & 9) & Parks in 34 Acre Scheme Focal Point Ludhiana (Park No.2) | 0 |  |  | MDF / SASCI | 50%MDF &50%MC |  | 113.02 | 9 | 3308, dt 25.02.2026 | [8 empty] | 07 10.04.2026 | Ashok Kumar Sobti | 102.85 | 10.04.2026 | 8 | 09.10.2026 |  |  |  |  | 5 |  | 0 | In Progress |  | Work is in Progress
77 | MCL-0077 | B&R | B | B4 | Sahnewal | Focal Point | Roads - Bituminous |  | Const of Various Bituminous Roads in Phase - V & VII Focal Point Ludhiana (Roter Kanda towards Jiwan Nagar Chown, Disposal Rd.and E-654) & (E-773 to E-778 and Roter Kanda Rd to Fortis Hospital Chd Rd) | 7056.4 | 11 |  | SIDBI | SIDBI |  | 158.55 | 7.19 | 3439 dt 21.04.2026 | [8 empty] | 08 13.05.2026 | Maruti Const Co. | 147.15 | 08 13.05.2026 | 6 | [5 empty] | 15 |  | 0 | In Progress |  | Work is in Progress
78 | MCL-0078 | B&R | B | B4 | Sahnewal | Focal Point | Roads - RMC / Cement Concrete |  | Const of Various Roads by laying RMC(M-40) in Phase-V,VI,VII & VIII Focal Point Ludhiana (Satya Industry Phase 5, D-51 to D-58 )(A13E & A13A) (Opp. RCJ Auto Forge E-756 and C-202 A to C-203 C(E-701 to E-706 | 1876.52 | 11 |  | SIDBI | SIDBI |  | 136.09 | 41.99 | 1484 dt 13.10.2025 | [8 empty] | 30 15.01.2026 | Apex Developers | 78.95 | 30 15.01.2026 | 6 | 14.07.2026 |  |  |  |  | 45 |  | 34.43 | In Progress |  | Work is in Progress
79 | MCL-0079 | B&R | B | B4 | East | Focal Point | Parks & Green Belts |  | Development of various Parks in Phase-I Focal Point (OPP Kay Jay Forjing and Opp E-2) | 0 | 0 |  | SIDBI | SIDBI |  | 53.25 | 28.89 | 2486 dt 05.01.2026 | [8 empty] | 34 15.01.2026 | Teg Builders | 37.87 | 34 15.01.2026 | 5 | 14.06.2026 |  |  |  |  | 60 |  | 0 | In Progress |  | Work is in Progress
80 | MCL-0080 | B&R | B | B4 | East | Focal Point | Parks & Green Belts |  | Development of various Parks in Phase-IV Focal Point (OPP E-90 and Opp E-132) | 0 | 0 |  | SIDBI | SIDBI |  | 78.08 | 28.89 | 2485 dt 05.01.2026 | [8 empty] | 35 15.01.2026 | Teg Builders | 55.52 | 35 15.01.2026 | 5 | 14.06.2026 |  |  |  |  | 90 |  | 40.34 | In Progress |  | Work is in Progress
81 | MCL-0081 | B&R | B | B4 | East | Focal Point | Parks & Green Belts |  | Development of various Parks in Phase-IVA Focal Point (Opp D-145, Opp D-148 and Opp D-152) | 0 | 0 |  | SIDBI | SIDBI |  | 8.05 | 21.26 | 2263, dt 21.11.2025 | [8 empty] | 29 15.01.2026 | Varinder Singh Contractor | 6.34 | 29 15.01.2026 | 3 | 14.05.2026 |  |  |  |  | 80 |  | 0 | In Progress |  | Work is in Progress
82 | MCL-0082 | B&R | B | B4 | Sahnewal | Focal Point | Parks & Green Belts |  | Construction of Various Parks of Focal Point Phase-V , Ludhiana (D-114, C-86,B-37, C-115, D-130) | 0 | 0 |  | SIDBI | SIDBI |  | 217.72 | 28.1 | 2484 dt 05.01.2026 | [8 empty] | 36 15.01.2026 | RK Const Co. | 156.54 | 36 15.01.2026 | 6 | 14.07.2026 |  |  |  |  | 30 |  | 35.75 | In Progress |  | Work is in Progress
83 | MCL-0083 | B&R | B | B4 | Sahnewal | Focal Point | Parks & Green Belts |  | Construction of Various Parks of Focal Point Phase-VI , Ludhiana (Park No.1,2,4,6,7 & 8) | 0 | 0 |  | SIDBI | SIDBI |  | 348.82 | 18.2 | 2487 dt 05.01.2026 | [8 empty] | 37 15.01.2026 | Navyug Company | 285.33 | 37 15.01.2026 | 6 | 14.07.2026 |  |  |  |  | 5 |  | 0 | In Progress |  | Work is in Progress
84 | MCL-0084 | B&R | B | B4 | Sahnewal | Focal Point | Parks & Green Belts |  | Construction of Various Parks of Focal Point Phase-VII Ludhiana (Park No.2,3,4,5 & 6) | 0 | 0 |  | SIDBI | SIDBI |  | 123.11 | 28.99 | 2492 dt 05.01.2026 | [8 empty] | 38 15.01.2026 | RK Const Co. | 87.42 | 38 15.01.2026 | 6 | 14.07.2026 |  |  |  |  | 25 |  | 19.95 | In Progress |  | Work is in Progress
85 | MCL-0085 | B&R | B | B4 | Sahnewal | Focal Point | Parks & Green Belts |  | Development of various Parks in Phase-VIII Focal Point (Adj F-170 & F171,Adj F-155 & F156 , Adj F-179 & F176, Adj F-194 & F195 and Opp F-251) | 0 | 0 |  | SIDBI | SIDBI |  | 168.7 | 23.51 | 2489 dt 05.01.2026 | [8 empty] | 39 15.01.2026 | KS Constructions | 129.04 | 39 15.01.2026 | 6 | 14.07.2026 |  |  |  |  | 30 |  | 0 | In Progress |  | Work is in Progress
86 | MCL-0086 | B&R | B | B4 | Sahnewal | Focal Point | Parks & Green Belts |  | Repair & Renovation of various Parks in 34 Acre Scheme Focal Point (Park Opp F-309, Opp K-312) | 0 | 0 |  | SIDBI | SIDBI |  | 25.32 | 31.26 | 2172 dt 13.10.2025 | [8 empty] | 31 15.01.2026 | Varinder Singh Contractor | 17.4 | 31 15.01.2026 | 4 | 14.05.2026 |  |  |  |  | 90 |  | 15.99 | In Progress |  | Work is in Progress
87 | MCL-0087 | B&R | A | A1 | Central | 83 |  |  | Construction Of Retaining Wall And Road Along Budha Nallah From Madhopuri Pulli To Sunder Nagar Pulli, Ludhiana. |  |  |  | MC Funds / General Quota | MC Funds |  | 366.48 |  | 931 dt. 06-05-2025 | [8 empty] | 88/EEA dt. 15-05-2025 | Gaaneshkartikey Construction Pvt. Ltd. | 301.02 | 15-05-2025 | 18 months | 14-11-2026 |  |  |  |  | 60 |  | 90 | Delayed/Held Up |  | Work delayed due to shortage of bitumen. Notice issue to Contractor
88 | MCL-0088 | B&R | A | A1 | Central | 9 & 10 |  |  | Construction of Main 70' Road Sunder Nagar in w.no.8 & 58. |  |  |  | MC Funds / General Quota | MC Funds |  | 57.19 |  | 102 dt. 26-03-2025 | [8 empty] | 83/EEA dt. 21-04-2025 | M/s C.H Builders Pvt. Ltd. | 42.89 | 21-04-2025 | 6 months | 22-10-2025 |  |  |  |  | 0 |  | NIL | Delayed/Held Up |  | Work delayed due to shortage of bitumen. Final Notice issued to Contractor
89 | MCL-0089 | B&R | B | B1 | Central | 81 |  |  | Repair and Maintenance of Zone-B Main Building of Municipal Corporation Ludhiana. |  |  |  | MC Funds / General Quota | MC Funds |  | 123.69 |  | 124 dt. 26-03-2025 | [8 empty] | 91/EEA dt. 15-05-2025 | Teg Builders (Govt. Contractor) | 97.55 | 15-05-2025 | 6 months | 16-10-2025 |  |  |  |  | 95 |  | 86.12 | In Progress |  | Revised est. has been prepared due to increase of electrical item, sanitation items.
90 | MCL-0090 | B&R | A | A1 | Central | 83 & 85 |  |  | Laying RMC M-30 in various streets in vakilla Mohalla & Krishana Gali in ward no.59 & 61.(New w.no. 83 & 85) |  |  |  | MC Funds / General Quota | MC Funds |  | 25.19 |  | Tender F&CC Reso.no. 97 dt. 26-03-2025 | [8 empty] | 94/EEA dt. 01-08-2025 | Capital Construction Co. | 13.96 | 01-08-2025 | 6 months | 02-01-2026 |  |  |  |  | 75 |  | 8.36 | In Progress |  | Work in progress
91 | MCL-0091 | B&R | B | B1 | Central | 76 |  |  | Laying 30mm thick SDBC Kucha no.16 adjoining Janj Ghar w.no.63. (New w.no.76) |  |  |  | MC Funds / General Quota | MC Funds |  | 20.32 |  | Tender F&CC Reso.no. 100 dt. 26-03-2025 | [8 empty] | 95/EEA dt. 01-08-2025 | Capital Construction Co. | 13.18 | 01-08-2025 | 6 months | 02-01-2026 |  |  |  |  | 10 |  | NIL | Delayed/Held Up |  | Work delayed due to shortage of bitumen.
92 | MCL-0092 | B&R | C |  | Central | 74 |  |  | Laying BM&PC on various streets of Industrial Area B adjoining overlock road in w.no.51. |  |  |  | MC Funds / General Quota | MC Funds |  | 175.23 |  | Tender F&CC Reso.no. 761 dt. 09-04-2025 | [8 empty] | 101/EEA dt. 01-08-2025 | Hitesh Aggarwal Cont. | 110.39 | 01-08-2025 | 6 months | 02-01-2026 |  |  |  |  | 10 |  | NIL | Delayed/Held Up |  | Work delayed due to shortage of bitumen.
93 | MCL-0093 | B&R | A | A2 | Central | 78 |  |  | Renovation of various parks in ward no. 78, Ludhiana. |  |  |  | MC Funds / General Quota | MC Funds |  | 37.41 |  | Tender F&CC reso.no. 1821 dt. 13-10-2025 | [8 empty] | 103/EEA dt. 19-11-2025 | M/s Dynamic tiles | 29.55 | 19-11-2025 | 6 months | 20-06-2026 |  |  |  |  | 50 |  | NIL | In Progress |  | The work of one park has been completed balance work in progress Notice issued to contractor
94 | MCL-0094 | B&R | B | B1 | Central | 80 |  |  | Laying SDBC in streets of Janakpuri Part-I in w.no.80. |  |  |  | MC Funds / General Quota | MC Funds |  | 39.89 |  | Tender F&CC reso.no. 2147 dt. 13-10-2025 | [8 empty] | 105/EEA dt. 19-11-2025 | M/s Soham Construction Company | 36.81 | 19-11-2025 | 6 months | 20-06-2026 |  |  |  |  | 0 |  | NIL | Delayed/Held Up |  | Work delayed due to shortage of bitumen.
95 | MCL-0095 | B&R | A | A1 | Central | 9 |  |  | Construction of New Toilets and Repair & Renovation of Sunder Nagar Fire Station. |  |  |  | MC Funds / General Quota | MC Funds |  | 24.33 |  | Tender F&CC reso.no. 1811 dt. 13-10-2025 | [8 empty] | 106/EEA dt. 19-11-2025 | M/s Prince Sharma | 19.32 | 19-11-2025 | 6 months | 20-06-2026 |  |  |  |  | 60 |  | 12.61 | In Progress |  | Work will be completed 30-07-2026 Work in progress
96 | MCL-0096 | B&R | A | A2 | Central | 78 |  |  | Laying RMC M30 In Streets No.1,2,3,4 & Links of Mohar Singh Nagar, W.No.78, Ludhiana. |  |  |  | MC Funds / General Quota | MC Funds |  | 93.11 |  | Tender F&CC reso.no. 1823 dt. 13-10-2025 | [8 empty] | 108/EEA dt. 19-11-2025 | K.S Constructions | 53.35 | 19-11-2025 | 6 months | 20-06-2026 |  |  |  |  | 80 |  | 50.7 | Delayed/Held Up |  | Work delayed due to laying Water supply line by O&M Cell.
97 | MCL-0097 | B&R | A | A1 | Central | 10 |  |  | Laying RMC in street of Mohalla New Madho Puri in w.no.58 (New w.no.10) Part-II. |  |  |  | MC Funds / General Quota | MC Funds |  | 83.72 |  | Tender F&CC reso.no. 1819 dt. 13-10-2025 | [8 empty] | 110/EEA dt. 19-11-2025 | K.S Constructions | 47.97 | 19-11-2025 | 7 months | 20-05-2026 |  |  |  |  | 60 |  | 18.75 | In Progress |  | Work in progress
98 | MCL-0098 | B&R | A | A1 | Central | 83 |  |  | Laying RMC M-30 in street of Mohalla Mehmoodpura in w.no.61. (New w.no.83) |  |  |  | MC Funds / General Quota | GQ |  | 71.84 |  | Tender F&CC reso.no. 1814 dt. 13-10-2025 | [8 empty] | 111/EEA dt. 19-11-2025 | K.S. Constructions | 41.16 | 19-11-2025 | 6 months | 20-05-2026 |  |  |  |  | 30 |  | 7.89 | In Progress |  | Work in progress
99 | MCL-0099 | B&R | B | B1 | Central | 81 |  |  | Laying RMC M-30 in streets of Harcharan Nagar in w.no.57. |  |  |  | MC Funds / General Quota | MC Funds |  | 56.74 |  | Tender F&CC reso.no.758 dt. 09-04-2025 | [8 empty] | 114/EEA dt.19-11-2025 | Varinder Singh Govt. Contractor | 30.88 | 19-11-2025 | 4 months | 20-02-2026 |  |  |  |  | 10 |  | NIL | Delayed/Held Up |  | Work stopped due to upgradation of water supply line.
100 | MCL-0100 | B&R | A | A2 | Central | 82 |  |  | P/F 60/80mm I/Tiles on RMC in Streets of Dhoka Mohalla, Ludhiana. (Rs. 33,89,445.15 Only (1/2 of total Tender Cost: 67,78,890.30) ) |  |  |  | MC Funds / General Quota | MC Funds |  | 121.03 |  | Tender F&CC reso.no. 1795 dt. 13-10-2025 | [8 empty] | 115/EEA dt.19-11-2025 & 116/EEA dt.19-11-2025 | M/s Apex Devlopers & M/s K.S. Constructions | 67.78 | 19-11-2025 | 7 months | 20-05-2026 |  |  |  |  | 40 |  | 13.72 | Delayed/Held Up |  | Work delayed due to laying Water supply line by O&M Cell.
101 | MCL-0101 | B&R | A | A1 | Central | 83 |  |  | Laying RMC M-30 in street of Bharam Puri in w.no.83. |  |  |  | MC Funds / General Quota | MC Funds |  | 24.93 |  | Tender F&CC reso.no. 2153 dt. 13-10-2025 | [8 empty] | 124/EEA dt.18-02-2026 | Godwyn Infra | 14.19 | 18-02-2026 | 6 months | 17-07-2026 |  |  |  |  | 0 |  | NIL | Not Started |  | Work not started Notice issued
102 | MCL-0102 | B&R | A | A2 | Central | 78 |  |  | Laying RMC M30 In Streets No. 5,6 & Links of Mohar Singh Nagar, W.No.78, Ludhiana. |  |  |  | MC Funds / General Quota | GQ |  | 73.03 |  | Tender F&CC reso.no. 1809 dt. 13-10-2025 | [8 empty] | 127/EEA dt.18-02-2026 | LRY Labour Contractor | 42.13 | 18-02-2026 | 6 months | 17-07-2026 |  |  |  |  | 40 |  | NIL | Delayed/Held Up |  | Work delayed due to laying Water supply line by O&M Cell.
103 | MCL-0103 | B&R | A | A2 | Central | 78 |  |  | Laying RMC M30 In Streets No.7, 8 & Links of Mohar Singh Nagar, W.No.78, Ludhiana. |  |  |  | Councillor Quota (CQ) | CQ |  | 99.68 |  | Tender F&CC reso.no. 1890 dt. 13-10-2025 | [8 empty] | 128/EEA dt.18-02-2026 | LRY Labour Contractor | 57.51 | 18-02-2026 | 6 months | 17-07-2026 |  |  |  |  | 20 |  | NIL | Delayed/Held Up |  | Work delayed due to laying Water supply line by O&M Cell.
104 | MCL-0104 | B&R | A | A1 | Central | 85 |  |  | Repair & Renovation of Sub Zone-A1 Office at Daresi. W. No. 85. |  |  |  | MC Funds / General Quota | GQ |  | 35.53 |  | Tender F&CC reso.no. 3266 dt. 25-02-2026 | [8 empty] | 131/EEA dt.18-03-2026 & 132/EEA dt.18-03-2026 | The Sobha Gram Co Operative Labour and Construction Society Ltd. & Apex Devlopers | 28.42 | 18-03-2026 | 7 months | 17-09-2026 |  |  |  |  | 10 |  | NIL | In Progress |  | Work in progress
105 | MCL-0105 | B&R | B | B1 | Central | 75 |  |  | Laying 30mm thick SDBC on Kidwai Nagar Main Road & Road from Suffian Chowk to Janakpuri in w.no.75. |  |  |  | MC Funds / General Quota | GQ |  | 38.33 |  | Tender F&CC reso.no. 3263 dt. 25-02-2026 | [8 empty] | 133/EEA dt. 18-03-2026 | Capital Construction Co. | 34.11 | 18-03-2026 | 6 months | 17-08-2026 |  |  |  |  | 10 |  | NIL | Delayed/Held Up |  | Work delayed due to shortage of bitumen.
106 | MCL-0106 | B&R | A | A1 | Central | 83 |  |  | Laying RMC M-30 in St.no.1 Madhopuri & Links in w.no.83. |  |  |  | MC Funds / General Quota | GQ |  | 46.89 |  | Tender F&CC reso.no. 3267 dt. 25-02-2026 | [8 empty] | 135/EEA dt. 18-03-2026 | N.S. Infra | 25.79 | 18-03-2026 | 6 months | 17-08-2026 |  |  |  |  | 0 |  | NIL | Delayed/Held Up |  | Inaguration pending
107 | MCL-0107 | B&R | A | A1 | Central | 83 |  |  | Laying RMC M-30 in street of Ghati Mohalla in ward no. 83. |  |  |  | Councillor Quota (CQ) | CQ |  | 11.4 |  | Tender F&CC reso.no. 3265 dt. 25-02-2026 | [8 empty] | 137/EEA dt. 18-03-2026 | K.S. Constructions | 6.72 | 18-03-2026 | 6 months | 17-08-2026 |  |  |  |  | 10 |  | NIL | Delayed/Held Up |  | Work stopped due to laying of water supply line.
108 | MCL-0108 | B&R | A | A2 | Central | 82 |  |  | Laying RMC M-30 in street of Mohalla Taj Ganj in ward no.82. |  |  |  | Councillor Quota (CQ) | CQ |  | 24.65 |  | Tender F&CC reso.no. 3264 dt. 25-02-2026 | [8 empty] | 139/EEA dt. 18-03-2026 | K.S. Constructions | 13.97 | 18-03-2026 | 3 months | 17-05-2026 |  |  |  |  | 20 |  | NIL | In Progress |  | Work in progress Work will be completed within 20 days.
109 | MCL-0109 | B&R | A | A2 | Central | 75 |  |  | Laying RMC (M-30) in various streets of ward no.75. |  |  |  | Councillor Quota (CQ) | CQ |  | 63.32 |  | Tender F&CC reso.no. 3268 dt. 25-02-2026 | [8 empty] | 141/EEA dt. 18-03-2026 | K.S. Constructions | 34.74 | 18-03-2026 | 6 months | 17-08-2026 |  |  |  |  | 65 |  | 14.62 | In Progress |  | Work in progress
110 | MCL-0110 | B&R | A | A2 | Central | 78 |  |  | Re-Development of Children Friendly Park on Old Jail Road, Ludhiana. |  |  |  | MC Funds / General Quota | GQ |  | 66.68 |  | Tender F&CC reso.no. 2788 dt. 19-02-2026 | [8 empty] | 142/EEA dt. 18-03-2026 | Navdeep Gupta and Company | 42.68 | 18-03-2026 | 6 months | 17-08-2026 |  |  |  |  | 40 |  | NIL | In Progress |  | Repair work of Satpal prasher park has been completed work in progress.
111 | MCL-0111 | B&R | B | B1 | Central | 80 |  |  | Laying RMC M-30 in St.no.1,2,3 & 4 of Janakpuri w.no.80. |  |  |  | MC Funds / General Quota | GQ |  | 69.55 |  | Tender F&CC reso.no. 2794 dt. 19-02-2026 | [8 empty] | 143/EEA dt. 18-03-2026 | Vansh Engineers | 37.89 | 18-03-2026 | 7 months | 17-09-2026 |  |  |  |  | 0 |  | NIL | Delayed/Held Up |  | Inaguration pending
112 | MCL-0112 | B&R | A | A2 | Central | 77 |  |  | Laying RMC streets in internal streets of Mochpura Bazar. |  |  |  | MDF / SASCI | Under Special Central Assistance Scheme |  | 26.98 |  | Tender F&CC reso.no. 2574 dt. 11-02-2026 | [8 empty] | 144/EEA dt. 20-03-2026 | Maa Chintpurni Construction | 14.84 | 20-03-2026 | 3 months | 21-05-2026 |  |  |  |  | 45 |  | 14.51 | Delayed/Held Up |  | Work delayed due to core area. Work in progress.
113 | MCL-0113 | B&R | B | B1 | Central | 80 |  |  | Laying SDBC in streets of Janakpuri Part-II in w.no.80. |  |  |  | MC Funds / General Quota | GQ/MLA |  | 24.15 |  | Tender F&CC reso.no. 3578 dt. 21-04-2026 | [8 empty] | 151/EEA dt. 06-05-2026 | Capital Construction Co. | 18.93 | 06-05-2026 | 6 months | 07-10-2026 |  |  |  |  | 10 |  | NIL | Delayed/Held Up |  | Work delayed due to shortage of bitumen. Notice issue
114 | MCL-0114 | B&R | A | A1 | Central | 85 |  |  | Laying RMC M-30 in street of Mohalla Shankar Puri, Veer Nagar & SDP College Quilla Mohalla in w.no.85. |  |  |  | Rangla Punjab | Under Rangla Punjab Vikas Scheme Ph-I |  |  |  | 3196 dt. 25-02-2026 | [8 empty] | 150/EEA dt. 05-05-2026 | Maa Chintpurni Construction | 46.39 | 05-05-2026 | 7 months | 06-11-2026 |  |  |  |  | 45 |  | NIL | In Progress |  | Work in progress. Work will be completed upto 15-07-2026
115 | MCL-0115 | B&R | A | A2 | Central | 82 |  |  | Laying RMC M-30 in Shanti Niketen School St & Links Streets of Mohalla Fateh Ganj in Ward No-82. |  |  |  | Rangla Punjab | Under Rangla Punjab Vikas Scheme Ph-I |  |  |  | 3271 dt. 25-02-2026 | [8 empty] | 148/EEA dt. 05-05-2026 | LRY Labour Contractor | 26.49 | 05-05-2026 | 3 months | 06-07-2026 |  |  |  |  | 10 |  | NIL | In Progress |  | Work in progress. Work will be completed upto 15-07-2026
116 | MCL-0116 | B&R | A | A2 | Central | 82 |  |  | Laying RMC M-30 in streets near Gajja Jain Mandir in Tilak Nagar w.no.82. |  |  |  | Rangla Punjab | Under Rangla Punjab Vikas Scheme Ph-I |  |  |  | 3274 dt. 25-02-2026 | [8 empty] | 147/EEA dt. 05-05-2026 | LRY Labour Contractor | 17.1 | 05-05-2026 | 4 months | 06-08-2026 |  |  |  |  | 25 |  | NIL | In Progress |  | Work in progress. Work will be completed upto 15-07-2026
117 | MCL-0117 | B&R | B | B1 | Central | 79 |  |  | Laying RMC M-30 in Hargobind Nagar & its adjoining streets of w.no.79. |  |  |  | Rangla Punjab | Under Rangla Punjab Vikas Scheme Ph-I |  |  |  | 3273 dt. 25-02-2026 | [8 empty] | 149/EEA dt. 05-05-2026 | Capital Construction Co. | 30.2 | 05-05-2026 | 4 months | 06-08-2026 |  |  |  |  | 10 |  | NIL | In Progress |  | Work in progress. Work will be completed upto 15-07-2026
118 | MCL-0118 | B&R | B | B1 | Central | 80 |  |  | Laying RMC M-30 in streets of New Kidwai Nagar in w.no. 80. |  |  |  | Rangla Punjab | Under Rangla Punjab Vikas Scheme Ph-I |  |  |  | 3272 dt. 25-02-2026 | [8 empty] | 146/EEA dt. 05-05-2026 | Godwyn Infra | 22.61 | 05-05-2026 | 7 months | 06-11-2026 |  |  |  |  | 10 |  | NIL | In Progress |  | Work in progress. Work will be completed upto 15-07-2026
119 | MCL-0119 | B&R |  |  | Central | Gen. |  |  | Remodeling of Nallah & Constructions of roads from Shingar Cinema Bridge to Shamshan Ghat Bridge. |  |  |  | MC Funds / General Quota | PUEIP Ph-III |  |  |  | 26-11-2021 | [8 empty] | 153/EEA/LOA dt. 13-12-2021 | M/s Kabir Infra | 939.21 | 13-12-2021 | 12 months | 14-12-2021 |  |  |  |  | 60 |  | 300.62 | Delayed/Held Up |  | Work delayed because of pending IPS construction work causing obstruction at the site. Work in progress (Amt. approved from under PUEIP PH-III 600 lacs) but Orginal Est. Cost is 948.70 & vetted Est. amt. 942.05 lacs
120 | MCL-0121 | B&R | A |  | Central | Gen. |  |  | Laying SDBC Links between Vijay Nagar Road & Suffian Chowk Road, Links Nearby Night Shelter Moti Nagar, Main Road from Basti Jodhewal to Sunder Nagar Pulley Both Sides, Gaushalla Main Road, Ghora Colony & Links and Links between RK Road & Kabir Road in central Constituency. |  |  |  | MDF / SASCI | MDF Funds |  | 877.87 | [23 empty] | Not Started |  | Under technical evaluation
121 | MCL-0122 | B&R | A |  | Central | Gen. |  |  | Laying RMC M-30 in streets of Old Madho Puri Part-I & II, Janakpuri, Hargobind Nagar Road, Ambedkar Nagar & Ram Nagar, Industrial area, Basti Sheikh Mohamadh, Mohalla Vijay Nagar & New Shiva Ji Nagar of Central Constituency. |  |  |  | MDF / SASCI | MDF Funds |  | 601.4 | [23 empty] | Not Started |  | Under technical evaluation
122 | MCL-0123 | B&R | A |  | Central | Gen. |  |  | Laying RMC M-40 in Various Streets of Transport Nagar Part-II Ward No.30. |  |  |  | MDF / SASCI | MDF Funds |  | 701.92 | [23 empty] | Not Started |  | Under technical evaluation
123 | MCL-0124 | B&R | A |  | Central | Gen. |  |  | Laying BM & SDBC on Guru Nanak Dev Market, Main Hargobind Marg, Main Textile Colony Road and Brown Road & Islamia School Road and Main Road from 3 No. Division to CMC Chowk. |  |  |  | MDF / SASCI | MDF Funds |  | 553.56 | [23 empty] | Not Started |  | Under technical evaluation
124 | MCL-0125 | B&R | A |  | Central | Gen. |  |  | Laying RMC M-30 in streets of Mohalla Islam Ganj, Mustak Ganj and Ucha Tibba in w.no.75, Various Kuchas in w.no.76, Various Streets of Shivaji Nagar in w.no.79, Streets of Kashmir Nagar & Narinder Nagar in w.no.81 and Main Road of Dal Bazar, Hindi Bazar & Chawal Bazar and Main Hosiery Road. |  |  |  | MDF / SASCI | MDF Funds |  | 652.17 | [23 empty] | Not Started |  | Under technical evaluation
125 | MCL-0126 | B&R | B | B1 | Central | 30 |  |  | Laying RMC M-30 in Various Streets of Bihari Colony in ward no.30. |  |  |  | Rangla Punjab | Rangla Punjab-II |  | 73.82 | [23 empty] | Not Started |  | F&CC approved in anticipation Tender to be called
126 | MCL-0127 | B&R | B | B1 | Central | 79 |  |  | Laying RMC M-30 in Street No.1,2,3 & Links Hari Kartar Colony in ward no.79. |  |  |  | Rangla Punjab | Rangla Punjab-II |  | 53.46 | [23 empty] | Not Started |  | F&CC approved in anticipation Tender to be called
127 | MCL-0128 | B&R | B | B1 | Central | 76 |  |  | Laying RMC M-30 in link Streets of Kusht Ashram Road in ward no.76. |  |  |  | Rangla Punjab | Rangla Punjab-II |  | 72.81 | [23 empty] | Not Started |  | F&CC approved in anticipation Tender to be called
128 | MCL-0129 | B&R | B | B1 | Central | 76 |  |  | Laying RMC M-30 in Different Streets of Prem Nagar Part-II in ward no.76. |  |  |  | Rangla Punjab | Rangla Punjab-II |  | 49.81 | [23 empty] | Not Started |  | F&CC approved in anticipation Tender to be called
129 | MCL-0130 | B&R |  |  | Central | Gen. |  |  | Upgradation of RMC Roads in various wards of Central Constituency. |  |  |  | MDF / SASCI | Special Central Assistance Scheme |  |  |  | 2676 dt. 11-02-2026 | [8 empty] | 123/EEA dt. 18-02-2026 | M/s J.K.Infocon Pvt. Ltd | 741.93 | 18-02-2026 | [6 empty] | 90 |  |  | In Progress |  | Work will be completed upto 30-06-2026
130 | MCL-0132 | B&R | D | D1 | North | 68 | Roads - RMC / Cement Concrete |  | P/Laying RMC M-30 in streets of Chander nagar & Jagan nath puram road ward no. 68. | 750 |  |  | MC Funds / General Quota | MC Funds |  | 55.3 |  | 2639 dt 11.02.2026 | [8 empty] | 29/EED dt 23.02.2026 | M/s Prince Sharma | 31.78 | 23.02.2026 | 4 | 30.07.2026 |  |  |  |  | 50 |  | NiL | In Progress |  | Work in Progress
131 | MCL-0133 | B&R | D | D1 | North | 70 | Roads - RMC / Cement Concrete |  | P/Laying RMC M-30 in streets of Wadhwa street, Gandhi street , Prem nagar & kundanpuri ward no. 70. | 930 |  |  | Councillor Quota (CQ) | CQ |  | 57.3 |  | 2648 dt 11.02.2026 | [8 empty] | 27/EED dt 23.02.2026 | M/s Navdeep Gupta & Company | 32.75 | 23.02.2026 | 4 | 30.06.2026 |  |  |  |  | 70 |  | 21.24 | Delayed/Held Up |  | Work in Progress. balance 2 no.st which is pending will be completed by 30.06.2026
132 | MCL-0134 | B&R | D | D1 | North | 70 |  |  | P/L 60mm thick Perforated tiles on side berms of Pavillion chowk to Kailash chowk , Petrol pump street w.no.70. |  |  |  | MC Funds / General Quota | MC Funds |  | 18.72 |  | 2641 dt 11.02.2026 | [8 empty] | 25/EED dt 23.02.2026 | M/s Navdeep Gupta & Company | 11.42 |  | 2 | 30.07.2026 | [6 empty] | NiL | Delayed/Held Up |  | Inauguration pending
133 | MCL-0135 | B&R | D | D1 | North | 70 | Parks & Green Belts |  | Repair & Renovation of Tanki wala park (prem nagar), Park lane & Gol park in ward no. 70. | __ | __ |  | Councillor Quota (CQ) | CQ |  | 27.82 |  | 2640 dt 11.02.2026 | [8 empty] | 26/EED dt 23.02.2026 | M/s Deepak Madaan | 18.64 | 23.02.2026 | 3 | 30.07.2026 |  |  |  |  | 30 |  | NiL | In Progress |  | Work in Progress
134 | MCL-0136 | B&R | D | D1 | North | 66 | Roads - Bituminous |  | P/Laying Bm & Pc from Lal Kothi chowk to Sheller road, main road Bank colony w.no. 66. |  |  |  | MC Funds / General Quota | GQ |  | 46.64 |  | 2643 dt 11.02.2026 | [8 empty] | 23/EED dt 23.02.2026 | M/s Soham Construction Co. | 39.59 |  | 3 | 30.07.2026 | [6 empty] | NiL | Delayed/Held Up |  | Inauguration pending & bitumen work delay due to non-avalibility of bitumen
135 | MCL-0137 | B&R | D | D1 | North | 91 | Roads - RMC / Cement Concrete |  | P/Laying RMC M-30 in streets of Guru Nanak pura ward no. 91. | 575 |  |  | Councillor Quota (CQ) | CQ |  | 31.5 |  | 2647 dt 11.02.2026 | [8 empty] | 28/EED dt 23.02.2026 | M/s Navdeep Gupta & Company | 18.71 | 23.02.2026 | 3 | 15.07.2026 |  |  |  |  | 70 |  | 14.3 | In Progress |  | Work in progress
136 | MCL-0138 | B&R | D | D1 | North | 66 | Roads - RMC / Cement Concrete |  | P/Laying RMC M-30 in New Deep Nagar ward no. 66. | 120 |  |  | MC Funds / General Quota | MC Funds |  | 11.81 |  | 2644 dt 11.02.2026 | [8 empty] | 21/EED dt 23.02.2026 | M/s Prince Sharma | 6.77 |  | 2 | 30.07.2026 | [6 empty] | NiL | Delayed/Held Up |  | Inauguration pending (council. Quota)
137 | MCL-0139 | B&R | D | D1 | North | 66 | Roads - RMC / Cement Concrete |  | P/Laying RMC M-30 in streets of Om Park Part -I ward no. 66. | 820 |  |  | MC Funds / General Quota | GQ |  | 50.15 |  | 2642 dt 11.02.2026 | [8 empty] | 22/EED dt 23.02.2026 | M/s Navdeep Gupta & Company | 28.38 |  | 4 | 30.07.2026 | [6 empty] | NiL | Delayed/Held Up |  | Inauguration pending
138 | MCL-0140 | B&R | D | D1 | North | 66 | Roads - RMC / Cement Concrete |  | P/Laying RMC M-30 in streets of Om Park Part -II ward no. 66. | 870 |  |  | MC Funds / General Quota | GQ |  | 52.76 |  | 2646 dt 11.02.2026 | [8 empty] | 24/EED dt 23.02.2026 | M/s Prince Sharma | 29.42 | 23.02.2026 | 4 | 10.07.2026 |  |  |  |  | 95 |  | 29.41 | Delayed/Held Up |  | only 300 feet length of sts. pending due to W/S supply Work in Progress
139 | MCL-0141 | B&R | D | D1 | North | 70 | Roads - RMC / Cement Concrete |  | P/Laying RMC M-30 in Bhandari street ward no. 70. | 440 |  |  | Councillor Quota (CQ) | CQ |  | 27.91 |  | 2645 dt 11.02.2026 | [8 empty] | 30/EED dt 23.02.2026 | M/s Navdeep Gupta & Company | 15.95 |  | 3 | 30.07.2026 | [6 empty] | NiL | Delayed/Held Up |  | Inauguration pending (Council. Quota)
140 | MCL-0142 | B&R | D | D1 | North | 68 | Roads - RMC / Cement Concrete |  | P/Laying RMC M-30 in streets of Jagannath puram ward no. 68. | 610 |  |  | MC Funds / General Quota | MC Funds |  | 36.79 |  | 1876 dt 13.10.2025 | [8 empty] | 15/EED dt 23.12.2025 | M/s Prince Sharma | 22.22 | 23.12.2025 | 3 | 30.07.2026 |  |  |  |  | 30 |  | NiL | In Progress |  | Work in progress
141 | MCL-0143 | B&R | D | D1 | North | 68 |  |  | P/L 60mm thick Perforated tiles on both side berms of Malhi road ward no. 68. |  |  |  | MC Funds / General Quota | MC Funds |  | 47.6 |  | 1877 dt 13.10.2025 | [8 empty] | 14/EED dt 23.12.2025 | M/s Navdeep Gupta & Company | 30.47 |  | 3 | 30.07.2026 | [6 empty] | NiL | Delayed/Held Up |  | Inauguration pending
142 | MCL-0144 | B&R | D | D1 | North | 92 | Parks & Green Belts |  | Repair & Renovation of Parks in Pritam Nagar ward no. 92. | __ |  |  | MC Funds / General Quota | MC Funds |  | 18.62 |  | 172 dt | [8 empty] | 19/EED dt 16.01.2026 | M/s Dynamic tiles | 13.41 | 16.01.2026 | 3 | 15.07.2026 |  |  |  |  | 50 |  | NiL | In Progress |  | Work in Progress
143 | MCL-0145 | B&R | D | D1 | North | 68 | Others |  | PROVIDING AND FIXING M.S.SIGN BOARDS IN WARD NO 68 LUDHIANA | __ |  |  | MC Funds / General Quota | MC Funds |  | 15.66 |  | 161 dt | [8 empty] | 18/EED dt 16.01.2026 | M/s Dynamic tiles | 10.78 | 16.01.2026 | 3 | 30.07.2026 |  |  |  |  | 10 |  | NiL | In Progress |  | Work in Progress
144 | MCL-0146 | B&R | D | D1 | North | 70 | Others |  | Repair & Renovation of Govt. Primary school, kundan puri ward no. 70. | __ |  |  | Viveki Funds | Un-tied/ Viveki Funds |  | 10 |  | 298 dt 26-03-2025 | [8 empty] | 9/EED/D1-N dt 25/04/2025 | M/s Prince Sharma | 8.62 | 25.04.2025 | 2 | 10.07.2026 |  |  |  |  | 40 |  | NiL | In Progress |  | ਇਹ ਕੰਮ ਵਿਵੇਕੀ ਫੰਡ ਅਧੀਨ ਅਲਾਟ ਕੀਤਾ ਗਿਆ ਸੀ । ਪਰੰਤੂ ਮੌਕੇ ਤੇ ਪਰਾਇਵੇਟ ਲੋਕਾਂ ਵੱਲੋ ਇਸਦਾ ਮਾਲਕੀ ਦਾ ਹੱਕ ਜਤਾਇਆ ਜਾ ਰਿਹਾ ਹੈ ਅਤੇ ਕੋਰਟ ਕੇਸ ਦਾ ਸਟੇ ਹੋਣ ਕਰਕੇ ਇਹ ਕੰਮ ਬੰਦ ਕੀਤਾ ਗਿਆ ਹੈ ।
145 | MCL-0147 | B&R | D | D1 | North | 91 | Others |  | Construction of Retainnig wall from Budha Nallah towards Baba Balak Nath Mandir in New Kundanpuri ward no. 91. | __ |  |  | MC Funds / General Quota | MC Funds |  | 125.95 |  | 843 dt 06-05-2025 | [8 empty] | 11/EED dt 22.05.2025 | M/S LRY Contractor | 94.21 | 22.05.2025 | 6 | 15.07.2026 |  |  |  |  | 85 |  | 77.37 | Delayed/Held Up |  | 300 ft length pending which will be completed
146 | MCL-0148 | B&R | D | D1 | North | 91 | Others |  | Construction of Volleyball Ground in Dusshera ground Upkar nagar ward no. 91. | __ |  |  | MC Funds / General Quota | General quota |  | 17.68 |  | 2823 dt 19.02.2026 | [8 empty] | 33/EED dt 15.03.2026 | M/s Subodh Batish | 15.53 |  | 3 | 30.07.2026 | [6 empty] | NiL | Delayed/Held Up |  | Inauguration pending
147 | MCL-0149 | B&R | D | D1 | North | 93 | Roads - RMC / Cement Concrete |  | Prov. and laying of RMC M-30 in L.H.S streets of Mohalla Smart City in ward no. 94.(site change P//L of RMC M-30 at Main Haibowal puli upto MLA Office via Bhuriwala Gurudwara road & streets of Pahalwan colony ) | 650 |  |  | MC Funds / General Quota | MC funds |  | 75.76 |  | 3094 dt 22-11-2024 | [8 empty] | 35/EEA dt 27-11-2024 | Navdeep Gupta & Company | 43.56 | 27.11.2024 | 6 | 10.07.2026 |  |  |  |  | 90 |  | 27.67 | Delayed/Held Up |  | Work held up due to world bank project
148 | MCL-0150 | B&R | D | D1 | North | 93 | Roads - RMC / Cement Concrete |  | Prov. and laying of RMC M-30 in streets of Sunil Nagar and balance streets of New Friends colony in ward no. 93. | 1540 |  |  | MC Funds / General Quota | MC funds |  | 95.63 | [10 empty] | 66/EEA dt 05-12-2024 | Neeraj Joshi | 53.4 | 05.12.2024 |  | 30.07.2026 |  |  |  |  | 30 |  | NiL | Delayed/Held Up |  | work held up due to water & sewerage line pending & Now work started
149 | MCL-0151 | B&R | D | D1 | North | 93 | Roads - RMC / Cement Concrete |  | Prov. and laying of RMC M-30 in R.H.S streets of Mohalla Smart City in ward no. 93. | 1380 |  |  | MC Funds / General Quota | MC funds |  | 70.65 |  | 3093 dt 22-11-2024 | [8 empty] | 34/EEA dt 27-11-2024 | Navdeep Gupta & Company | 40.62 | 27.11.2024 | 6 | 30.07.2026 |  |  |  |  | 0 |  | NiL | Delayed/Held Up |  | work held up due to water & sewerage line , Now sewerage line work just completed.
150 | MCL-0152 | B&R | D | D1 | North | 68 | Roads - RMC / Cement Concrete |  | P/Laying RMC M-30 in various streets of Hargobind nagar w.no 68. | 470 |  |  | MC Funds / General Quota | MC Funds |  | 35.43 |  | 3328 dt 21.04.2026 | [8 empty] | 03/EED dt 07.05.2026 | R.K Construction | 22.62 |  | 4 | 07.09.2026 | [6 empty] | NiL | Delayed/Held Up |  | Inauguration pending
151 | MCL-0153 | B&R | D | D1 | North | 68 | Roads - RMC / Cement Concrete |  | P/Laying RMC M-30 in remaining streets of Chander nagar ward no. 68. | 1610 |  |  | Councillor Quota (CQ) | CQ |  | 93.29 |  | 3329 dt 21.04.2026 | [8 empty] | 04/EED dt 07.05.2026 | Neeraj Joshi | 79.16 |  | 6 | 07.11.2026 | [6 empty] | NiL | Delayed/Held Up |  | Inauguration pending
152 | MCL-0154 | B&R | D | D1 | North | 68 |  |  | Construction of Retaining wall at Malhi puli existing bitumen road side. | __ |  |  | MC Funds / General Quota | GQ |  | 23.28 |  | 3326 dt 21.04.2026 | [8 empty] | 06/EED dt 07.05.2026 | Rajesh Kumar Sood | 20.13 |  | 3 | 07.08.2026 | [6 empty] | NiL | Delayed/Held Up |  | Inauguration pending
153 | MCL-0155 | B&R | D | D1 | North | 67 |  |  | Construction of Retainnig wall at Main haibowal puli to life line puli existing bitumen road side. | __ |  |  | MC Funds / General Quota | GQ |  | 27.91 |  | 3333 dt 21.04.2026 | [8 empty] | 05/EED dt 07.05.2026 | Rajesh Kumar Sood | 24.55 |  | 2 | 07.07.2026 | [6 empty] | NiL | Delayed/Held Up |  | Inauguration pending
154 | MCL-0156 | B&R | D | D1 | North | 70 | Parks & Green Belts |  | Repair & Renovation of Shahi Mohalla park in ward no. 70. | __ |  |  | MC Funds / General Quota | GQ |  | 26.07 |  | 3330 dt 21.04.2026 | [8 empty] | 10/EED dt 07.05.2026 | Navdeep Gupta & Company | 18.52 | 07.05.2026 | 3 | 07.08.2026 |  |  |  |  | 60 |  | 14.96 | In Progress |  | Work in Progress
155 | MCL-0157 | B&R | D | D1 | North | 91 | Parks & Green Belts |  | Repair & Renovation of Park 1 & Park 2 in New Deep Nagar ward no. 91. | __ |  |  | Councillor Quota (CQ) | CQ |  | 17.81 |  | 3335 dt 21.04.2026 | [8 empty] | 08/EED dt 07.05.2026 | Navdeep Gupta & Company | 12.88 | 07.05.2026 | 3 | 07.08.2026 |  |  |  |  | 90 |  | 8.57 | In Progress |  | Work in Progress
156 | MCL-0158 | B&R | D | D1 | North | 91 | Parks & Green Belts |  | Repair & renovation of Parks along with Road Dusshera ground to damoria chowk in ward no. 91. | __ |  |  | Councillor Quota (CQ) | CQ |  | 43.8 |  | 3336 dt 21.04.2026 | [8 empty] | 09/EED dt 07.05.2026 | M/s Prince Sharma | 28.56 | 07.05.2026 | 4 | 07.09.2026 |  |  |  |  | 5 |  | NiL | In Progress |  | Work just started
157 | MCL-0159 | B&R | D | D1 | North | D1 | Roads - Bituminous |  | Scrapping by Cold Milling Machine and P/L BM & SDBC in Haibowal Main road (hambran road to churpur road ) |  |  |  | MC Funds / General Quota | MC Funds |  | 130.41 |  | 3334 dt 21.04.2026 | [8 empty] | 07/EED dt 07.05.2026 | Vansh Engineers | 117 |  | 6 | 07.11.2026 | [6 empty] | NiL | Delayed/Held Up |  | Work held up due to world bank project
158 | MCL-0160 | B&R | D | D1 | North | 91 |  |  | Upgradation of Road From Shamshan Ghat Puli & Malhi Pulli backside New Deep nagar ward no. 91. |  |  |  | MDF / SASCI | Special Assistenace scheme |  | 674.61 | -7.75% | 2674 dt 11.02.2026 | Yes | Yes | Chief Engineer | [5 empty] | 35/EED dt 25.03.2026 | M/s J.K Infcon Pvt. Ltd | 622.32 | 25.03.2026 | 3 | Completion of work depends on the availabilty of bitumen material. |  |  |  |  | 97 |  | 150.03 | In Progress |  | Work will be completed by 30.07.2026
159 | MCL-0161 | B&R | D | D1 | North | D1 | Roads - Bituminous |  | Upgradation of various roads in different wards with RMC & Bitumen roads in sub zone D1 North Constituency. |  |  |  | MDF / SASCI | MDF |  | 564.8 | -21.16% | 3288 dt 25.02.2026 | [8 empty] | 36/EED dt 25.03.2026 | M/s Dass Builders Pvt. Ltd | 445.29 | 25.03.2026 | 3 | Completion of work depends on the availabilty of bitumen material. |  |  |  |  | 30 |  | 80.06 | In Progress |  | Work will be completed by 15.08.2026
160 | MCL-0162 | B&R | D | D1 | North | 93,67&92,91 | Roads - Bituminous |  | P/Laying 40mm BC at Sangam chowk towards Jassian road, Dusshera ground to shahi mohalla park road, Luxmi nagar main road in subzone D1 North Constituency. |  |  |  | MDF / SASCI | MDF-3 |  | 171.24 | [23 empty] | Not Started
161 | MCL-0163 | B&R | D | D1 | North | 93,92,66,70, 91,68 | Roads - RMC / Cement Concrete |  | P/Laying RMC in streets of Kesari Enclave, Mohalla Smart City, Jagat Nagar, Luxmi nagar st no. 5,7,9 & Links & st.s of Kehar singh nagar road, Durgapuri st no. 8,9,10 & Mandir st, Piara singh chakki main road & Links, Mohini resort road to damoria chowk along dusshera ground, st no. 10 & Links & Garg optical shop humbran road to shamshanghat chowk,Bassi hospital to Lifeline puli road, Chander nagar councillor off to shakti nagar roads in subzone D1 North Constituency. |  |  |  | MDF / SASCI | MDF-3 |  | 672.05 | [23 empty] | Not Started |  | Estimate approval in anticipation. Tender has been called which is under Technical Evalution.
162 | MCL-0164 | B&R | D | D1 | North | 66 | Parks & Green Belts |  | Construction of Playground/JoyBox opp. Bhatia School, Bank Colony ward no. 66. |  |  |  | Rangla Punjab | Rangla punjab Ph-I | Awarded | 25 | -12.1% | Approved in anticipation | Yes | N/A | [6 empty] | 11/EED dt 25.02.2026 | M/s Subodh Batish | 21.96 |  | 3 | [5 empty] | 5 |  |  | In Progress |  | work in progress
163 | MCL-0165 | B&R | D | D1 | North | 70 | Building / Community Centre |  | Construction of Room & Shed in Community Health Center in North Consitutency. Ward no. 70. |  |  |  | Rangla Punjab | Rangla punjab Ph-I |  | 20 | [14 empty] | 3 | [8 empty] | Not Started |  | 4th time tender recall dt of invitation tender 21.07.2026
164 | MCL-0166 | B&R | D | D1 | North | 67 | Roads - RMC / Cement Concrete |  | Construction of Road with RMC from Karanvir hospital to Jassian chowk (22 ft road) w.no. 67. |  |  |  | Rangla Punjab | Rangla punjab Ph-II |  | 35 |  | 3331 dt 21.04.2026 | [9 empty] | M/S Apex Developers | 33.01 |  | 3 | [8 empty] | Not Started |  | File sent to F&CC for approval of tender.
165 | MCL-0167 | B&R | D | D1 | North | 68 | Roads - RMC / Cement Concrete |  | Construction of Road with RMC from Lala Jagat Narain chowk to B.K Building Material store w.no. 68 |  |  |  | Rangla Punjab | Rangla punjab Ph-II |  | 30 | [14 empty] | 3 | [8 empty] | Not Started |  | 2nd time tender recalled dt 21.07.2026
166 | MCL-0168 | B&R | A | A3 | East | 5 |  |  | Laying RMC M-30 in roads between from Kakowal Road via MD Factory to Kailash Nagar Main Road w.no.5. |  |  |  | MC Funds / General Quota | GQ |  |  |  | 2709 dt.24-09-2024 | [8 empty] | 3 16.04.2025 | Capital Const Co. | 32.85 | 16-04-2025 | 5 | [5 empty] | 50 |  | 12.85 | In Progress |  | Work was heldup due to non upgradation of Water supply lines, now same has been laid by 30/04/26 & work is in progress now.
167 | MCL-0169 | B&R | A | A3 | East | 3 & 4 |  |  | Laying RMC M-30 in Mohalla Inder Vihar, New Basant Vihar, Basant Vihar Ext., Anand Puri in w.no.3 & 4. |  |  |  | MC Funds / General Quota | GQ |  |  |  | 2708 dt. 24-09-2024 | [8 empty] | 4 16.04.2025 | Capital Const Co. | 20.57 | 16-04-2025 | 4 | [5 empty] | 85 |  | 4.58 | Delayed/Held Up |  | The work of streets of new basant vihar,Basant vihar ext. is completed and inder vihar and anandpuri streets work in process which is delayed due to water supply line now balance work will be completed by 10/07/26
168 | MCL-0170 | B&R | A | A3 | East | 5 |  |  | P/Fixing I/tiles in Mohalla Royal Estate, Green City W No.5 |  |  |  | MC Funds / General Quota | GQ |  |  |  | 1518 dt. 13-10-2025 | [8 empty] | 51 16.02.2026 | M/s T&G Const Co. | 61.31 | 16-02-2026 | 6 | [5 empty] | 15 |  | NIL | Delayed/Held Up |  | Initally work was stopped by area councillor due to upgradation of sewer line but now work is in progress which will be completed within time limit upto 15/8/26
169 | MCL-0171 | B&R | A | A3 | East | 2 |  |  | P/Fixing I/tiles in Golden Vihar W.No.02. |  |  |  | Councillor Quota (CQ) | CQ |  |  |  | 1624 dt. 13-10-2025 | [8 empty] | 53 16.02.2026 | Varinder Singh Govt Contractor | 23.33 | 16-02-2026 | 4 | [5 empty] | 0 |  | NIL | Delayed/Held Up |  | Work was delayed due to inauguration pending by worthy MLA .Now worthy MLA has directed to start the work.
170 | MCL-0172 | B&R | A | A3 | East | 5 |  |  | Laying RMC in street of Mohalla New Shimla Colony and Jaiswal Colony in W No.05 |  |  |  | Councillor Quota (CQ) | CQ |  |  |  | 1946 dt. 13-10-2025 | [8 empty] | 56 16.02.2026 | NS Infra | 27.42 | 16-02-2026 | 5 | [5 empty] | 0 |  | NIL | Delayed/Held Up |  | Work is held up due to pending of laying W/S lines to be laid by o&m cell street has been katcha at site.
171 | MCL-0173 | B&R | A | A3 | East | 2 |  |  | P/Fixing I/tiles in Ekjot Nagar & Banda Bahadur Nagar in W No.02 |  |  |  | MC Funds / General Quota | GQ |  |  |  | 3268 dt. 29-11-2024 | [8 empty] | 58 16.02.2026 | Varinder Singh Govt Contractor | 43.64 | 16-02-2026 | 6 | [5 empty] | 0 |  | NIL | Delayed/Held Up |  | Work was delayed due to inauguration pending by worthy MLA .Now worthy MLA has directed to start the work.
172 | MCL-0174 | B&R | A | A3 | East | 2 |  |  | P/Fixing I/tiles in Banda Bhadur Colony, New Azad Nagar & Masjid Wali Gali Ward No.02. |  |  |  | Councillor Quota (CQ) | CQ |  |  |  | 1663 dt. 13-10-2025 | [8 empty] | 68 09.03.2026 | Apex Developers | 53.83 | 09-03-2026 | 5 | [5 empty] | 0 |  | NIL | Delayed/Held Up |  | Work was delayed due to inauguration pending by worthy MLA .Now worthy MLA has directed to start the work.
173 | MCL-0175 | B&R | A | A3 | East | 3 |  |  | P/F of I/tiles in Guru Gobind Singh Nagar, Panchsheel Colony & Basant Valley W No.03 |  |  |  | Councillor Quota (CQ) | CQ |  |  |  | 1893 dt. 13-10-2025 | [8 empty] | 69 09.03.2026 | Varinder Singh Govt Contractor | 44.37 | 09-03-2026 | 5 | [5 empty] | 60 |  | 12.75 | In Progress |  | The panchsheel colony streets completed and basant balley streets is in progress and the work of the work of guru gobind nagar streests will be started after completion of water supply lines to be laid by O&M cell
174 | MCL-0176 | B&R | A | A3 | East | 5 |  |  | P/fixing I/tiles in Amrit Vihar in ward no.5. |  |  |  | Councillor Quota (CQ) | CQ |  |  |  | 1936 dt. 13-10-2025 | [8 empty] | 70 09.03.2026 | Varinder Singh Govt Contractor | 40.39 | 09-03-2026 | 4 | [5 empty] | 80 |  | 24.46 | In Progress |  | Work is in Progress
175 | MCL-0177 | B&R | A | A3 | East | 3&4 |  |  | Construction of bituminious roads between Main Noorwala Road & Kakowal Road via Raghunath Mandir & DVM School Road |  |  |  | MC Funds / General Quota | GQ |  |  |  | 2710 dt. 24-09-2024 | [8 empty] | 73 09.03.2026 | Maruti Const Co. | 33.18 | 09-03-2026 | 3 | [5 empty] | 20 |  |  | Delayed/Held Up |  | Road gully work completed bitumen work pending due to shortage of bitumen
176 | MCL-0178 | B&R | A | A3 | East | 4&5 |  |  | Construction of Main Kakowal Road w.no.4& 5 |  |  |  | MC Funds / General Quota | GQ |  |  |  | 813 dt. 09-04-2025 | [8 empty] | 85 10.04.2026 | Apex Builders | 76.19 | 10-04-2026 | 4 | [7 empty] | NIL | Not Started |  | Work heldup due to upgradation of w/s Lines , (24/7)
177 | MCL-0179 | B&R | A | A3 | East | 3&4 |  |  | Construction of Main Noorwala Road |  |  |  | MC Funds / General Quota | GQ |  |  |  | 814 dt. 09-04-2025 | [8 empty] | 86 10.04.2026 | VKBS Constructions Pvt. Ltd. | 69.16 | 10-04-2026 | 4 | [7 empty] | NIL | Not Started |  | Work heldup due to upgradation of & sewerage lines now same has been completed and work will start after rainy season
178 | MCL-0180 | B&R | A | A3 | East | 3 |  |  | Beautification of Lajpat Nagar Entry Point on Noorwala Road. |  |  |  | MC Funds / General Quota | GQ |  |  |  | 1973 dt. 13-10-2025 | [8 empty] | 87 10.04.2026 | Teg Builders | 6.36 | 10-04-2026 | 2 | [5 empty] | 80 |  | NIL | In Progress |  | Work is in Progress
179 | MCL-0181 | B&R | A | A3 | East | 4 |  |  | P/Fixing I/tiles in Prem Vihar, Pink City, Vivek Dham & Sant Singh Cheema Nagar W No.04 |  |  |  | Councillor Quota (CQ) | CQ |  |  |  | 1958 dt. 13-10-2025 | [8 empty] | 87 10.04.2026 | Varinder Singh Govt Contractor | 55.39 | 10-04-2026 | [6 empty] | 20 |  | NIL | In Progress |  | Work is in Progress
180 | MCL-0182 | B&R | A | A3 | East | 5&6 |  |  | Construction of Main Kailash Nagar Road w.no.5 |  |  |  | MC Funds / General Quota | GQ |  |  |  | 463 dt. 09-04-2025 | [8 empty] | 15 13.05.2026 | Somaya Infrastructure | 73.3 | 13-05-2026 | 6 | [5 empty] | 25 |  | NIL | Delayed/Held Up |  | R/G work completed & bituminious work is pending due to shortage of Bitumen.
181 | MCL-0184 | B&R | C |  | Atam Nagar | 48 |  |  | Laying SDBC on various roads of W.No.43 |  |  |  | MC Funds / General Quota | MC |  | 106.79 |  | 2269 dt 24.07.24 | [8 empty] | 140/EEC DT 11.10.24 | Rajesh Kumar Sood | 75.83 |  | 6 | [5 empty] | 65 |  |  | Delayed/Held Up |  | Work stopped due to 24X7 W/S
182 | MCL-0185 | B&R | C |  | Atam Nagar | 46 |  |  | Development of Green Belt Dhuri Line to Gill Bridge along Sidhwan Canal |  |  |  | MC Funds / General Quota | MC |  | 137.66 |  | 1452 dt 22.02.23 | [8 empty] | 116/EEC DT 15.02.24 | Glisten | 95.09 |  | 6 | [5 empty] | 70 |  |  | In Progress |  | Work not completed due to enchroachment at site.
183 | MCL-0186 | B&R | C |  | Atam Nagar | 45 |  |  | Renovation of Municipal Corporation Ludhiana Zone C Main Office Gill Road. |  |  |  | MC Funds / General Quota | MC |  | 45.56 |  | 1664 dt 14.02.24 | [8 empty] | 124/EEC DT 20.02.24 | The Gill Co Op Diploma Holder Society Ltd | 34.17 |  | 6 | [5 empty] | 80 |  |  | In Progress |  | Work in progress.
184 | MCL-0187 | B&R | C |  | Atam Nagar | 41& 42 |  |  | Construction of RCC road from Labour chowk to Harkrishan Sahib School. |  |  |  | MC Funds / General Quota | MC |  | 118.84 |  | 721 dt 09.04.25 | [8 empty] | 169/EEC dt 28.04.25 | M/S Ashok Kumar Sobti | 84.78 |  | 6 | [5 empty] | 55 |  |  | Delayed/Held Up |  | Work held up due to upgradation of s/w line.
185 | MCL-0188 | B&R | C |  | Atam Nagar | 40 |  |  | Laying RMC in link of Kwality Road & Link of Maya Soap. |  |  |  | MC Funds / General Quota | MC |  | 43.73 |  | 1982 dt 13.10.25 | [8 empty] | 196/EEC dt 11.11.25 | N.S.Infra | 25.07 |  | 3 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Work held up due to upgradation of w/s line.
186 | MCL-0189 | B&R | C |  | Atam Nagar | 40 |  |  | P/F of Informatory Sign Board in various streets of W.No.40 |  |  |  | MC Funds / General Quota | MC |  | 4.06 |  | 1839 dt 13.10.25 | [8 empty] | 197/EEC dt 11.11.25 | Glisten | 3.57 |  | 1 | [5 empty] | 10 |  |  | Delayed/Held Up |  | work stopped due to dispute
187 | MCL-0190 | B&R | C |  | Atam Nagar | 45 |  |  | Laying RMC in main street Ram nagar market ,mohalla parbhat nagar and labour colony ward no.45 |  |  |  | MC Funds / General Quota | MC |  | 64.56 |  | 1840 dt 13.10.25 | [8 empty] | 199/EEC dt 11.11.25 | K.S.Constructions | 37.83 |  | 3 | [5 empty] | 25 |  |  | Delayed/Held Up |  | work stopped due to dispute
188 | MCL-0191 | B&R | C |  | Atam Nagar | 42 |  |  | P/F of Informatory Sign Board in various streets of W.No.42 |  |  |  | MC Funds / General Quota | MC |  | 7.6 |  | 1951 dt 13.10.25 | [8 empty] | 200/EEC dt 11.11.25 | Ram Parkash Kakar | 5.42 |  | 1 | [5 empty] | 0 |  |  | Not Started |  | Not Started
189 | MCL-0192 | B&R | C |  | Atam Nagar | 41 |  |  | Laying RMC in Streets of daba colony and new janta nagar ward no.41 |  |  |  | MC Funds / General Quota | MC |  | 88.55 |  | 1802 dt 13.10.25 | [8 empty] | 203/EEC dt 11.11.25 | Apex Devlopers | 51.36 |  | 4 | [5 empty] | 80 |  |  | In Progress |  | Work in progress.
190 | MCL-0193 | B&R | C |  | Atam Nagar | 40 |  |  | Laying RMC in Main Streets of Maya Soap W.No.40 |  |  |  | MC Funds / General Quota | MC |  | 76.67 |  | 1801 dt 13.10.25 | [8 empty] | 204/EEC dt 11.11.25 | K.S.Constructions | 44.92 |  | 3 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Work held up due to upgradation of water supply.
191 | MCL-0194 | B&R | C |  | Atam Nagar | 45 |  |  | Laying RMC in streets of mohalla parbhat nagar and vishvakarma colony ward no.45 |  |  |  | MC Funds / General Quota | MC |  | 29.51 |  | 1804 dt 13.10.25 | [8 empty] | 206/EEC dt 11.11.25 | R.K.Construction Co. | 18.07 |  | 3 | [5 empty] | 50 |  |  | In Progress |  | Work in progress.
192 | MCL-0195 | B&R | C |  | Atam Nagar | 40 |  |  | Laying BM&PC on Seerat Hospital Road upto Gurudwara Sahib. Site Change Lappar Paint Main Street & Links. |  |  |  | MC Funds / General Quota | MC |  | 57.13 |  | 2085 dt 13.10.25 | [8 empty] | 208/EEC dt 21.11.25 | Apex Builders | 36.07 |  | 5 | [8 empty] | Delayed/Held Up |  | Inaugration pending
193 | MCL-0196 | B&R | C |  | Atam Nagar |  | Roads - Bituminous |  | Upgradation of various roads of Atam Nagar constituency Zone C. |  |  |  | CSAG | CSAG |  | 522.08 |  | 2683 dt 11.02.2026 | [8 empty] | 03/EEC dt 20.02.26 | M/S VKBS Construction Pvt Ltd. | 498.58 |  | 3 | [5 empty] | 30 |  |  | In Progress |  | Work in progress.
194 | MCL-0197 | B&R | C |  | Atam Nagar |  | Roads - RMC / Cement Concrete |  | Upgradation of various roads of Atam Nagar constituency Zone C. |  |  |  | CSAG | CSAG |  | 511.6 |  | 2865 dt 19.02.2026 | [8 empty] | 04/EEC dt 20.02.26 | M/S Dass Builders | 434.66 |  | 3 | [5 empty] | 30 |  |  | In Progress |  | Work in progress.
195 | MCL-0198 | B&R | C |  | Atam Nagar | 40 |  |  | Laying RMC from Gill Road to Gurudwara Sahib (Seerat Hospital Road) |  |  |  | MC Funds / General Quota | MC |  | 96.65 |  | 2423 dt 05.01.2026 | [8 empty] | 11/EEC dt 27.02.2026 | LRY Labour Contractor | 62.73 |  | 4 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Inaugration pending
196 | MCL-0199 | B&R | C |  | Atam Nagar | 40 |  |  | P/F of cat eyes & laying Thermoplastic lines in different streets of W.No.40 |  |  |  | MC Funds / General Quota | MC |  | 13.9 |  | 2352 dt 05.01.26 | [8 empty] | 07/EEC dt 27.02.2026 | Anand Sales | 9.93 |  | 2 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Decision pending
197 | MCL-0200 | B&R | C |  | Atam Nagar | 40 |  |  | Laying RMC in Nippy Public School Street W.No.40 |  |  |  | MC Funds / General Quota | MC |  | 49.15 |  | 2440 dt 05.01.2026 | [8 empty] | 08/EEC dt 27.02.2026 | M/S Ashok Kumar Sobti | 33.59 |  | 3 | [5 empty] | 75 |  |  | In Progress |  | Work in progress.
198 | MCL-0201 | B&R | C |  | Atam Nagar | 40 |  |  | Laying RMC in various streets of mohalla Shimlapuri W.No.40. |  |  |  | MC Funds / General Quota | MC |  | 84.21 |  | 2441 dt 05.01.26 | [8 empty] | 09/EEC dt 27.02.2026 | M/S Ashok Kumar Sobti | 57.55 |  | 4 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Inaugration pending
199 | MCL-0202 | B&R | C |  | Atam Nagar | 41 |  |  | Construction of Road by Laying RMC from Bedi Chowk to Harkrishan Chowk. (GQ) |  |  |  | MC Funds / General Quota | MC Funds(GQ) |  | 76.1 |  | 2842 dt 19.02.2026 | [8 empty] | 20/EEC dt 02.03.2026 | The Gill Co Op Diploma Holder Society Ltd | 46.64 |  | 4 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Work held up due to upgradation of sewer line.
200 | MCL-0203 | B&R | C |  | Atam Nagar | 42 |  |  | Laying RMC in Streets of New Janta Nagar W.No.42 |  |  |  | Councillor Quota (CQ) | MC Funds (CQ) |  | 98.29 |  | 2838 dt 19.02.2026 | [8 empty] | 17/EEC dt 02.03.2026 | Capital Const.Co. | 57.22 |  | 5 | [5 empty] | 5 |  |  | In Progress |  | Work in progress.
201 | MCL-0204 | B&R | C |  | Atam Nagar | 45 |  |  | Providing and Laying Perforated interlocking tiles adjoining Road from Sangeet Cinema to Gabria Office Road, W.No.45 |  |  |  | Councillor Quota (CQ) | MC Funds (CQ) |  | 14.6 |  | 2730 dt 19.02.26 | [8 empty] | 21/EEC dt 02.03.2026 | Dynamic Tiles | 9.93 |  | 2 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Inaugration pending
202 | MCL-0205 | B&R | C |  | Atam Nagar | 45 |  |  | Construction of new park near Partap Chowk, W.No.45. |  |  |  | Councillor Quota (CQ) | MC Funds (CQ) |  | 64.41 |  | 2820 dt 19.02.2026 | [8 empty] | 28/EEC dt 02.03.2026 | Ram Parkash Kakar | 44.31 |  | 5 | [5 empty] | 35 |  |  | In Progress |  | Work in progress.
203 | MCL-0206 | B&R | C |  | Atam Nagar | 45 |  |  | Providing and Laying Perforated interlocking tiles adjoining Road Vishkarma Park. |  |  |  | N-CAP | NCAP Funds |  | 21.84 |  | 2729 dt 19.02.2026 | [8 empty] | 23/EEC dt 02.03.2026 | T and G Construction Co. | 16.38 |  | 2 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Inaugration pending
204 | MCL-0207 | B&R | C |  | Atam Nagar | 45 |  |  | Providing and Laying Perforated interlocking tiles adjoining Road Basant Park. |  |  |  | MC Funds / General Quota | MC Funds |  | 13.51 |  | 2735 dt 19.02.2026 | [8 empty] | 19/EEC dt 02.03.2026 & 29/EEC dt 02.03.2026 | Dynamic Tiles & T and G Construction Co. | 10.13 |  | 2 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Inaugration pending
205 | MCL-0208 | B&R | C |  | Atam Nagar | 48 |  |  | Laying RMC in various streets of mohalla Himmat Singh Nagar, Shaheed Karnail Singh Nagar & Guru nanak Colony W No. 48 |  |  |  | Councillor Quota (CQ) | CQ |  | 89.41 |  | 2863 dt 19.02.2026 | [8 empty] | 26/EEC dt 02.03.2026 | V.S.Infra | 48.28 |  | 5 | [5 empty] | 45 |  |  | In Progress |  | work in progress.
206 | MCL-0209 | B&R | C |  | Atam Nagar | 42 |  |  | Construction of Road by Laying RMC from Jeet Sweet Shop to Itta Wala Chowk Halka Atam Nagar. (Rangla Punjab Vikas Scheme). |  |  |  | RPVS | RPVS |  | 60.95 |  | 3463 dt 21.04.2026 | [8 empty] | 54/EEC dt 30.04.2026 | Apex Devlopers | 42.67 |  | 4 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Inaugration pending
207 | MCL-0210 | B&R | C |  | Atam Nagar | 46 |  |  | P/F of Informatory Sign Board in various streets of W.No.46 |  |  |  | Councillor Quota (CQ) | MC Funds (CQ) |  | 7.61 |  | 3409 dt 21.04.2026 | [8 empty] | 58/EEC dt 08.05.2026 | Glisten | 6.21 |  | 2 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Decision pending
208 | MCL-0211 | B&R | C |  | Atam Nagar | 44 |  |  | Laying RMC in street no 3,4,5 & Links of SAS Nagar W.No.44 |  |  |  | Councillor Quota (CQ) | MC Funds (CQ) |  | 75.05 |  | 3482 dt 21.04.2026 | [8 empty] | 60/EEC dt 08.05.2026 | Capital Const.Co. | 43.69 |  | 4 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Inaugration pending
209 | MCL-0212 | B&R | C |  | Atam Nagar | 46 |  |  | Laying RMC in streets of super cycle market & mohalla chet singh nagar W.No.46 |  |  |  | Councillor Quota (CQ) | MC Funds (CQ) |  | 41.51 |  | 3417 dt 21.04.2026 | [8 empty] | 62/EEC dt 08.05.2026 | Capital construction Co. | 24.16 |  | 3 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Inaugration pending
210 | MCL-0213 | B&R | C |  | Atam Nagar | 40 |  |  | P/F of Stainless Steel Sign boards in ward no.40 |  |  |  | MC Funds / General Quota | MC Funds(GQ) |  | 12.31 |  | 3414 dt 21.04.2026 | [8 empty] | 66/EEC dt 08.05.2026 | Glisten | 10.58 |  | 2 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Decision pending
211 | MCL-0214 | B&R | C |  | Atam Nagar | 46 |  |  | Laying RMC in Streets No 5, 7 New Janta Nagar( Gill Road) , Street No.20 Janta Nagar, W.No 46 |  |  |  | Councillor Quota (CQ) | MC Funds (CQ) |  | 44.3 |  | 3418 dt 21.04.2026 | [8 empty] | 71/EEC dt 08.05.2026 | Capital construction Co. | 25.79 |  | 3 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Inaugration pending
212 | MCL-0215 | B&R | C |  | Atam Nagar | 46 |  |  | Repair & Renovation of Central Verge of Gill Road from Gill Chowk to Gill Canal.(GQ) |  |  |  | MC Funds / General Quota | GQ |  | 19.76 |  | 3410 dt 21.04.2026 | [8 empty] | 73/EEC dt 08.05.2026 | Teg Builders | 19.18 |  | 3 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Inaugration pending
213 | MCL-0216 | B&R | C |  | Atam Nagar | 40 |  |  | Repair & Renovation of Green belt from gill road to Guru Arjun Dev Gurudwara Sahib and Const. of Canopies in ward no 40 |  |  |  | MC Funds / General Quota | MC Funds(GQ) |  | 39.75 |  | 3420 dt 21.04.2026 | [8 empty] | 74/EEC dt 08.05.2026 | Teg Builders | 37.43 |  | 5 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Inaugration pending
214 | MCL-0217 | B&R | C |  | Atam Nagar | 44 |  |  | Laying RMC in street no. 01 & 04 of mohalla Partap Nagar ward no.44. |  |  |  | Councillor Quota (CQ) | MC Funds (CQ) |  | 25.83 |  | 3483 dt 21.04.2026 | [8 empty] | 75/EEC dt 08.05.2026 | Capital Const.Co. | 15.04 |  | 2 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Inaugration pending
215 | MCL-0218 | B&R | C |  | Atam Nagar | 44 |  |  | Laying RMC in streets no.2 & Links of SAS Nagar W.No.44. |  |  |  | Councillor Quota (CQ) | MC Funds (CQ) |  | 40.88 |  | 3481 dt 21.04.2026 | [8 empty] | 76/EEC dt 08.05.2026 | Capital Const.Co. | 23.8 |  | 3 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Inaugration pending
216 | MCL-0220 | B&R | C |  | South | 35 |  |  | Construction of Stadium at Village Daba |  |  |  | MDF / SASCI | MDF |  | 323.39 |  | 931 dt 12.10.23 | [8 empty] | 100/EEC dt 13.10.23 | Asis Builders | 290.89 |  | 12 | [5 empty] | 95 |  |  | In Progress |  | File sent for revision of work
217 | MCL-0221 | B&R | C |  | South |  |  |  | Relocation and construction of Lohara Bridge in alignment with the Missing Link-2 Part C with Southern Bye Pass Project Ludhiana |  |  |  | MC Funds / General Quota | MC |  | 1194.48 |  | 3333 dt 05.12.24 | [8 empty] | 145/EEC DT 26.11.24 | M/s Tarmac Road and Roof Builders. | 1194.48 |  | 12 | [5 empty] | 80 |  |  | In Progress |  | Work will start after Canal Closure
218 | MCL-0222 | B&R | C |  | South | 43 |  |  | Laying RMC in st.no.19,20 and link of Mohalla Kot Mangal and St.No.1 Mohalla Gurpal Nagar. |  |  |  | MC Funds / General Quota | MC |  | 51.92 |  | 3341 dt 05.12.24 | [8 empty] | 156/EEC dt 24.12.24 | M/s Capital Construction Co. | 28.01 |  | 4 | [5 empty] | 90 |  |  | Delayed/Held Up |  | Work held up due to 24X7 W/S line.
219 | MCL-0223 | B&R | C |  | South | 43 |  |  | Laying RMC in St.No.2, St.No. 7 ½ and Main street of Mohalla Hargobind Nagar. |  |  |  | MC Funds / General Quota | MC |  | 75.15 |  | 3335 dt 05.12.24 | [8 empty] | 157/EEC dt 24.12.24 | M/s Capital Construction Co. | 40.54 |  | 5 | [5 empty] | 30 |  |  | Delayed/Held Up |  | Work stopped due to dispute
220 | MCL-0224 | B&R | C |  | South | 38 |  |  | Construction of Road from Shamshan Ghat to Bapu market via Radha Swami Satsang Ghar Lohara. |  |  |  | MC Funds / General Quota | MC |  | 84.28 |  | 720 dt 09.04.25 | [8 empty] | 165/EEC dt 28.04.25 | Apex Builders | 57.07 |  | 3 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Work held up due to 24X7 W/S line.
221 | MCL-0225 | B&R | C |  | South | 34 |  |  | Construction of 33' road from Giaspura Park to Pippal Chowk. |  |  |  | MC Funds / General Quota | MC |  | 172.89 |  | 726 dt 09.04.25 | [8 empty] | 166/EEC dt 28.04.25 | M/s Hitesh aggarwal contractor | 107.19 |  | 6 | [5 empty] | 95 |  |  | In Progress |  | File sent for revision of work
222 | MCL-0226 | B&R | C |  | South |  |  |  | Construction of RCC road from wine shop to Giaspura Chowk |  |  |  | MC Funds / General Quota | MC |  | 124.53 |  | 820 dt 06.05.25 | [8 empty] | 181/EEC dt 22.05.25 | Apex Devlopers | 74.73 |  | 8 | [5 empty] | 85 |  |  | In Progress |  | Work in progress
223 | MCL-0227 | B&R | C |  | South | 38 |  |  | Construction of road from Simran palace to Morgan crossing. |  |  |  | MC Funds / General Quota | MC |  | 99.94 |  | 729 dt 09.04.25 | [8 empty] | 182/EEC dt 22.05.25 | Hitesh Aggarwal | 61.96 |  | 8 | [5 empty] | 30 |  |  | Delayed/Held Up |  | Work held up due to 24X7 W/S line.
224 | MCL-0228 | B&R | C |  | South | 35 |  |  | Laying 80mm thick I/tiles balance streets mohalla Maha Singh Nagar. |  |  |  | MC Funds / General Quota | MC |  | 67.42 |  | 830 dt 06.05.25 | [8 empty] | 189/EEC dt 26.06.25 | Apex Devlopers | 38.44 |  | 5 | [5 empty] | 95 |  |  | In Progress |  | Work in progress.
225 | MCL-0229 | B&R | C |  | South | 31 |  |  | Construction of RCC roads from NPC upto Daba road and link on GT road. |  |  |  | MC Funds / General Quota | MC |  | 179.36 |  | 1021 dt 06.05.25 | [8 empty] | 195/EEC dt 20.08.25 | LRY labour Contractor. | 97.84 |  | 8 | [5 empty] | 20 |  |  | In Progress |  | Work in progress.
226 | MCL-0230 | B&R | C |  | South | 32 |  |  | Construction of RCC road from Giaspura Chowk to Eastman Chowk. |  |  |  | MC Funds / General Quota | MC |  | 326.57 |  | 1020 dt 06.05.25 | [8 empty] | 192/EEC dt 20.08.25 | LRY labour Contractor. | 178.14 |  | 12 | [5 empty] | 60 |  |  | In Progress |  | Work in progress.
227 | MCL-0231 | B&R | C |  | South | 32 |  |  | P/ Fixing 80mm thick I/Tiles in Mohalla Makkar Colony, Dhandari Kalan & Shanti Nagar, W. No. 32. |  |  |  | Councillor Quota (CQ) | MC Funds (CQ) |  | 76.48 |  | 1033 dt 06.05.2025 | [8 empty] | 05/EEC dt 27.02.2026 | Navyug Company | 42.66 |  | 3 | [5 empty] | 30 |  |  | In Progress |  | Work in progress
228 | MCL-0232 | B&R | C |  | South | 27 |  |  | Construction Of Rooms, Boundary wall and I/ Tiles adjoining Sewa Kendra Water Tank Sherpur |  |  |  | MC Funds / General Quota | GQ |  | 49.73 |  | 1027 dt 06.05.25 | [8 empty] | 10/EEC dt 27.02.2026 | Teg Builders | 42.82 |  | 6 | [5 empty] | 25 |  |  | In Progress |  | Work in progress
229 | MCL-0233 | B&R | C |  | South | 35 |  |  | Laying RMC in St.No. 2,3 & 5 of Mohalla Fateh Singh Nagar W.No.35 |  |  |  | Councillor Quota (CQ) | MC FUNDS (CQ) |  | 19.37 |  | 2721 dt 19.02.2026 | [8 empty] | 27/EEC dt 02.03.2026 | Varinder Singh Govt. Contractor | 11.62 |  | 2 | [5 empty] | 10 |  |  | In Progress |  | work in progress
230 | MCL-0234 | B&R | C |  | South | 36 |  |  | Laying RMC in various streets of Lohara Village and Basant Nagar W.No.36 |  |  |  | Councillor Quota (CQ) | MC FUNDS (CQ) |  | 54.86 |  | 2840 dt 19.02.26 | [8 empty] | 30/EEC dt 02.03.2026 | T And G Construction Co | 35.7 |  | 3 | [5 empty] | 30 |  |  | In Progress |  | work in progress
231 | MCL-0235 | B&R | C |  | South | 38 |  |  | Laying RMC in various streets of Ishar Nagar W.No-38 |  |  |  | Councillor Quota (CQ) | MC FUNDS (CQ) |  | 21.21 |  | 2722 dt 19.02.26 | [8 empty] | 15/EEC dt 02.03.2026 | Neeraj Joshi | 12.17 |  | 2 | [5 empty] | 60 |  |  | In Progress |  | work in progress
232 | MCL-0236 | B&R | C |  | South | 31 |  |  | Laying RMC in Streets of Mohalla Bhagwan Nagar W. No.31 |  |  |  | Councillor Quota (CQ) | MC FUNDS (CQ) |  | 72.79 |  | 2841 dt 19.02.2026 | [8 empty] | 18/EEC dt 02.03.2026 | Capital Const.Co. | 44 |  | 4 | [5 empty] | 0 |  |  | Delayed/Held Up |  | inaugration pending.
233 | MCL-0237 | B&R | C |  | South | 27 |  |  | Construction of central Verge HP Dharam Kanda, upto Opp Govt.High School Sherpur W.No.27 |  |  |  | MC Funds / General Quota | MC |  | 98.83 |  | 2727 dt 19.02.2026 | [8 empty] | 37/EEC dt 02.03.2026 | M/S Apex Devlopers | 69.19 |  | 5 | [5 empty] | 10 |  |  | In Progress |  | work in progress
234 | MCL-0238 | B&R | C |  | South | 27 |  |  | Laying RMC in various streets of baba gajjamall Jain Colony & Mohindra Colony, W.No.27 |  |  |  | Councillor Quota (CQ) | MC Funds (CQ) |  | 16.48 |  | 2708 dt 19.02.2026 | [8 empty] | 33/EEC dt 02.03.2026 | Asis Builders | 9.7 |  | 2 | [5 empty] | 20 |  |  | In Progress |  | work in progress
235 | MCL-0239 | B&R | C |  | South | 37 |  |  | Laying RMC Balance Streets of Basant Nagar Halka South, W.No.37 |  |  |  | Councillor Quota (CQ) | MC Funds (CQ) |  | 24.96 |  | 2726 dt 19.02.26 | [8 empty] | 34/EEC dt 02.03.2026 | Asis Builders | 14.69 |  | 2 | [5 empty] | 0 |  |  | Delayed/Held Up |  | inaugration pending.
236 | MCL-0240 | B&R | C |  | South | 32& 34 |  |  | Laying RMC in Asian Bike Street Dhandari Kalan Sua Road w.no. 32 and various streets of Guru Nanak Nagar W.No. 34 |  |  |  | MC Funds / General Quota | MC Funds (GQ) |  | 63.73 |  | 2757 dt 19.02.26 | [8 empty] | 36/EEC dt 02.03.2026 | Neeraj Joshi | 36.56 |  | 4 | [5 empty] | 60 |  |  | In Progress |  | work in progress
237 | MCL-0241 | B&R | C |  | South | 34 & 35 |  |  | Laying RMC in St. no. 2,3 & links of Captain Sewa Singh Nagar W.No. 34 and various roads of Daba Village adjoining Nanka Darbar Gurudwara Sahib and JB Karyana Store in W. no. 35 |  |  |  | MC Funds / General Quota | MC Funds (GQ) |  | 93.65 |  | 2846 dt 19.02.26 | [8 empty] | 41/EEC dt 02.03.2026 | The Gill Co op Diploma Holder Society. | 57.4 |  | 5 | [5 empty] | 0 |  |  | Delayed/Held Up |  | inaugration pending.
238 | MCL-0242 | B&R | C |  | South | 32 & 39 |  |  | Laying RMC in street no. 5 of Guru Gobind Singh Nagar in W.No. 39 and Street near Mini Rose Garden W.No. 32 |  |  |  | Councillor Quota (CQ) | MC Funds (CQ) |  | 49.87 |  | 2724 dt 19.02.26 | [8 empty] | 31/EEC dt 02.03.2026 | T And G Construction Co | 33.67 |  | 3 | [5 empty] | 20 |  |  | In Progress |  | work in progress
239 | MCL-0243 | B&R | C |  | South | 32 |  |  | Laying RMC in Dhandari Kalan road W.No. 32 |  |  |  | MC Funds / General Quota | MC Funds (GQ) |  | 57.6 |  | 2710 dt 19.02.2026 | [8 empty] | 40/EEC dt 02.03.2026 | M/S Apex Devlopers | 33.41 |  | 3 | [5 empty] | 0 |  |  | Delayed/Held Up |  | inaugration pending.
240 | MCL-0244 | B&R | C |  | South | 33 |  |  | Laying RMC in various streets of Makkar Colony W.No. 33 |  |  |  | MC Funds / General Quota | MC Funds (GQ) |  | 76.08 |  | 2758 dt 19.02.26 | [8 empty] | 35/EEC dt 02.03.26 | Neeraj Joshi. | 43.64 |  | 4 | [5 empty] | 20 |  |  | In Progress |  | work in progress
241 | MCL-0245 | B&R | C |  | South | 32 |  |  | Laying RMC near PSPCL road street and Mohalla Shanti Nagar Link in W.No. 32 |  |  |  | MC Funds / General Quota | MC Funds (GQ) |  | 59.95 |  | 2711 dt 19.02.26 | [8 empty] | 39/EEC dt 02.03.2026 | M/S Apex Devlopers | 34.77 |  | 3 | [5 empty] | 40 |  |  | In Progress |  | work in progress
242 | MCL-0246 | B&R | C |  | South | 32 |  |  | Reconstruction of Road Dhandari Phirni W.No.32.(NCAP Funds). |  |  |  | MC Funds / General Quota | MC Funds (GQ) |  | 94.37 |  | 2837 dt 19.02.26 | [8 empty] | 38/EEC dt 02.03.2026 | Dugra Construction Co. | 70.58 |  | 5 | [5 empty] | 10 |  |  | In Progress |  | work in progress
243 | MCL-0247 | B&R | C |  | South | 38 |  |  | Laying RMC in Various street of Captain Nagar W.No. 38, St. no. 9 link and Isher Nagar Block-C streets in w. no. 38 and Various Streets of Mohalla Ishar Nagar And begoana Street |  |  |  | Councillor Quota (CQ) | MC Funds (CQ) |  | 67.18 |  | 2728 dt 19.02.2026 | [8 empty] | 50/EEc dt 09.04.2026 | M/S Apex Devlopers | 40.31 |  | 4 | [5 empty] | 0 |  |  | Delayed/Held Up |  | inaugration pending.
244 | MCL-0248 | B&R | C |  | South | 37 |  |  | Laying RMC in street no. 8 of Guru Gobind Singh Nagar W. no. 37 |  |  |  | Rangla Punjab | Rangla Punjab |  | 32.43 |  | 3448 dt 21.04.2026 | [8 empty] | 51/EEC dt 30.04.2026 | K.S. Constructions | 21.37 |  | 3 | [5 empty] | 40 |  |  | In Progress |  | work in progress
245 | MCL-0249 | B&R | C |  | South | 32 |  |  | Providing and Installation of Open air Gym Equipments Dhandari Kalan W.no. 32 |  |  |  | Rangla Punjab | Rangla Punjab |  | 8 |  | 3455 dt 21.04.26 | [8 empty] | 52/EEC dt 30.04.2026 | Aggarwal Builders | 4.64 |  | 2 | [5 empty] | 20 |  |  | In Progress |  | work in progress
246 | MCL-0250 | B&R | C |  | South | 33 |  |  | Laying RMC in various streets of Satguru Nagar & Karamjit Nagar Halka South W. no. 33 |  |  |  | Rangla Punjab | Rangla Punjab |  | 76.57 |  | 3450 dt 21.04.2026 | [8 empty] | 55/EEC dt 30.04.2026 | M/S Ashok Kumar Sobti | 49.77 |  | 4 | [5 empty] | 20 |  |  | In Progress |  | work in progress
247 | MCL-0251 | B&R | C |  | South | 35 |  |  | Laying RMC in Streets No-1 & 5 of Mohalla Guru Gobid Singh Nagar w. No-35 |  |  |  | MC Funds / General Quota | MC FUNDS |  | 35.91 |  | 3465 dt 21.04.2026 | [8 empty] | 56/EEC dt 08.05.2026 | Godwyn | 20.02 |  | 1.5 | [5 empty] | 0 |  |  | Delayed/Held Up |  | inaugration pending.
248 | MCL-0252 | B&R | C |  | South | 33 |  |  | Construction of Bathrooms in Shamshan Ghat Lohara W.no.33 |  |  |  | MPLAD Funds | MP LAD |  | 4.5 |  | 3461 dt 21.04.2026 | [8 empty] | 57/EEC dt 08.05.2026 | Kohinoor Builders | 4.39 |  | 3 | [5 empty] | 0 |  |  | Delayed/Held Up |  | inaugration pending.
249 | MCL-0253 | B&R | C |  | South | 35 |  |  | P/F 80MM Thick I/Tiles Streets No-18,1 and Links Mohalla Fateh Singh Nagar W. No-35 |  |  |  | MC Funds / General Quota | MC FUNDS |  | 38.14 |  | 3464 dt 21.04.2026 | [8 empty] | 59/EEC dt 08.05.2026 | Godwyn | 21.26 |  | 1.5 | [5 empty] | 0 |  |  | Delayed/Held Up |  | inaugration pending.
250 | MCL-0254 | B&R | C |  | South | 36 |  |  | Laying RMC in Streets of Mohalla Gurmail Nagar Dhillon Nagar and Basatn Nagar in W. No-36 |  |  |  | Councillor Quota (CQ) | MC FUNDS (CQ) |  | 27.63 |  | 3413 dt 21.04.2026 | [8 empty] | 61/EEC dt 08.05.2026 | Godwyn infra | 18.42 |  | 2 | [5 empty] | 0 |  |  | Delayed/Held Up |  | inaugration pending.
251 | MCL-0255 | B&R | C |  | South | 50 |  |  | Construction of Bathrooms in Shamshan Ghat Dholewal W.no.50 |  |  |  | MPLAD Funds | MP LAD |  | 4.5 |  | 3456 dt 21.04.2026 | [8 empty] | 63/EEC dt 08.05.2026 | Kohinoor Builders | 4.44 |  | 3 | [5 empty] | 0 |  |  | Delayed/Held Up |  | inaugration pending.
252 | MCL-0256 | B&R | C |  | South | 35 |  |  | P/F of informatory sign board in various streets of W.No.35 |  |  |  | Councillor Quota (CQ) | MC FUNDS (CQ) |  | 8.5 |  | 3421 dt 21.04.2026 | [8 empty] | 64/EEC dt 08.05.2026 | Glisten | 6.94 |  | 2 | [5 empty] | 0 |  |  | Delayed/Held Up |  | inaugration pending.
253 | MCL-0257 | B&R | C |  | South | 43 |  |  | Laying RMC in street no. 11/5,11/6 and 11/7 of Kabir Nagar in W.No. 43 |  |  |  | MC Funds / General Quota | MC Funds (GQ) |  | 49.99 |  | 3416 dt 21.04.2026 | [8 empty] | 65/EEC dt 08.05.2026 | Prince Sharma | 29.66 |  | 3 | [5 empty] | 0 |  |  | Delayed/Held Up |  | inaugration pending.
254 | MCL-0258 | B&R | C |  | South | 37 |  |  | P/F 80MM thick I/Tiles in Streets of Mohalla Gobind Nagar and Azad Nagar in W. No-37 |  |  |  | MC Funds / General Quota | MC Funds (GQ) |  | 39.71 |  | 3415 dt 21.04.2026 | [8 empty] | 67/EEC dt 08.05.2026 | N.S.Infra | 26.21 |  | 3 | [5 empty] | 0 |  |  | Delayed/Held Up |  | inaugration pending.
255 | MCL-0259 | B&R | C |  | South | 32 |  |  | P/F 80mm thick I/Tiles in various streets Shanti Nagar in W.No. 32 |  |  |  | Councillor Quota (CQ) | MC Funds (CQ) |  | 48.65 |  | 3411 dt 21.04.2026 | [8 empty] | 68/EEC dt 08.05.2026 | N.S.Infra | 31.63 |  | 3 | [5 empty] | 0 |  |  | Delayed/Held Up |  | inaugration pending.
256 | MCL-0260 | B&R | C |  | South | 38 |  |  | P/F 60MM I/Tiles in Streets 5L, 6L, 13R & Links of Mohalla Isher Nagar W. No.38 |  |  |  | MC Funds / General Quota | MC FUNDS |  | 31.45 |  | 3480 dt 21.04.2026 | [8 empty] | 70/EEC dt 08.05.2026 | Godwyn | 17.53 |  | 1.5 | [5 empty] | 0 |  |  | Delayed/Held Up |  | inaugration pending.
257 | MCL-0261 | B&R | C |  | South | 35 |  |  | P/F 60mm I/Tiles Streets of 6 to 12 & St No. 17 in Mohalla Fateh Singh Nagar W. No. 35 |  |  |  | MC Funds / General Quota | MC FUNDS |  | 87.31 |  | 3474 dt 21.04.2026 | [8 empty] | 72/EEC dt 08.05.2026 | M/S Apex Devlopers | 50.65 |  | 3 | [5 empty] | 0 |  |  | Delayed/Held Up |  | inaugration pending.
258 | MCL-0262 | B&R | C |  | South |  |  |  | Construction of various roads in South Constituency Zone C. |  |  |  | MDF / SASCI | SASCI Funds |  | 564.33 |  | 2681 dt 11.02.2026 | [8 empty] | 77/EEC dt 08.05.2026 | M/S Hitesh Aggarwal Cont. | 537.8 |  | 3 | [5 empty] | 25 |  |  | In Progress |  | Work in progress.
259 | MCL-0263 | B&R | C |  | South | Gen |  |  | Construction of Fire Station at Dhandari Kalan in South Constituency. |  |  |  | MC Funds / General Quota | MC Funds (GQ) |  | 189.77 |  | in-anticipation by Worthy Mayor on dt 21.05.2026 | [8 empty] | 78/EEC dt 21.05.2026 | M/S Parveen Sehgal | 187.68 |  | 8 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Dispute at Site
260 | MCL-0264 | B&R | C |  | South | 35 |  |  | Construction of RCC road from Mair Di Chakki Chowk to Near Daba Village W. No. 35 |  |  |  | Rangla Punjab | Rangla Punjab |  | 61.02 |  | 3110 dt 25.02.26 | [8 empty] | 79/EEC dt 22.06.26 | Varinder Singh Govt Contractor | 51.46 |  | 4 | [5 empty] | 20 |  |  | In Progress |  | Work in progress.
261 | MCL-0265 | B&R | C |  | South | 38 |  |  | Construction of Dispensary on Shamshan Ghat road Lohara W. NO. 38 |  |  |  | Rangla Punjab | Rangla Punjab |  | 14.99 |  | in-anticipation by Worthy Mayor on dt 13.06.26 | [8 empty] | 80/EEC dt 22.06.26 | Smridhi Construction | 13.67 |  | 4 | [5 empty] | 5 |  |  | In Progress |  | Work in progress.
262 | MCL-0266 | B&R | C |  | South | 32 |  |  | Reconstruction of community centre on Campa Cola road in village Dhandari kalan. W. no. 32 |  |  |  | Rangla Punjab | Rangla Punjab |  | 25 |  | 3472 dt 21.04.26 | [8 empty] | 81/EEC dt 22.06.26 | Smridhi Construction | 22.61 |  | 4 | [5 empty] | 5 |  |  | In Progress |  | Work in progress.
263 | MCL-0268 | B&R | A | A4 | North | 86&88 |  |  | Estimate for Bridge across Budha Naala Near Shivpuri Ludhina |  |  |  | MC Funds / General Quota | MC |  |  |  | 03 Dt.26-03-2025 | [8 empty] | 72/LOA dt. 28-01-2025 | M/s Hitesh Aggarwal | 204.76 | 02-05-2026 | 9 Months | 27-10-2025 |  |  |  |  | 95 |  | 252.71 | In Progress |  | Work in Progress.
264 | MCL-0269 | B&R | A | A4 | North | Gen |  |  | Estimate for Bridge across Budha Naala Near Manna Singh Nagar Ludhina |  |  |  | MC Funds / General Quota | MC |  |  |  | 04 Dt.26-03-2025 | [8 empty] | 73/LOA dt. 28-01-2025 | J.K. Infocon Pvt. Ltd | 275.94 | 18-02-2025 | 9 Months | 27-10-2025 |  |  |  |  | 85 |  | 214.71 | In Progress |  | Work in Progress.
265 | MCL-0270 | B&R | A | A4 | North | 89 |  |  | Construction of Senior Citizen Home cum Community Center in Peeru Banda in Ward No.84. |  |  |  | MC Funds / General Quota | MC |  |  |  | 3099 Dt.22-11-2024 | [8 empty] | 40/EEA dt. 27-11-2024 | M/s Smridhi Constructions | 23.53 | 13-12-2024 | [6 empty] | 90 |  | 20.93 | In Progress |  | Work in Progress.
266 | MCL-0271 | B&R | A | A4 | North | 89 |  |  | Construction of Senior Citizen Home cum Community Center in ward no.84. |  |  |  | MC Funds / General Quota | MC |  |  |  | 2645 Dt.24-09-2024 | [8 empty] | 168/EEA dt. 23-10-2024 | The Saharan Majra Co-op | 18.83 | 11-11-2024 | 3 Months | 22-01-2025 |  |  |  |  | 80 |  | 0 | In Progress |  | Work in Progress.
267 | MCL-0272 | B&R | A | A4 | North | 95 |  |  | Construction of Badminton Indoor Stadium Backside Duke factory near Jalandhar Byepass Ludhiana. |  |  |  | MC Funds / General Quota | MC |  |  |  | 3097 Dt.22-11-2024 | [8 empty] | 38/EEA dt. 27-11-2024 | M/s Apurva Inc | 69.9 | 14-12-2025 | 6 Months | 26-05-2025 |  |  |  |  | 20 |  | 0 | In Progress |  | Work in Progress.
268 | MCL-0273 | B&R | A | A4 | North | 87 |  |  | Construction of Metailed Road to Join Missing Link of Service Lane Backside Petrol Pump in Ward No.87. |  |  |  | MC Funds / General Quota | MC |  |  |  | 1741 Dt.13-10-2025 | [8 empty] | 01/EEA dt 25-08-2025 | M/s Soham Construction Company | 47.18 | 15-09-2025 | 3 Months | 24-11-2025 |  |  |  |  | 85 |  | 42.08 | In Progress |  | Work in Progress.
269 | MCL-0274 | B&R | A | A4 | North | 90 |  |  | Construction of Bijli Market Main Road & Streets Near Lakkar Bazar With RMC in Field Ganj Ward No.90. |  |  |  | MC Funds / General Quota | MC |  |  |  | 1747 Dt.13-10-2025 | [8 empty] | 06/EEA dt 24-10-2025 | M/S Capital Construction Co. | 49.15 | 15-11-2025 | 6 Months | 23-04-2026 |  |  |  |  | 40 |  | 27.67 | Delayed/Held Up |  | Work in Progress delayed due to internal city area.
270 | MCL-0275 | B&R | A | A4 | North | 90 |  |  | P/F Painting Road Marking & Cat Eyes at Various Main Roads of Ward No.90. |  |  |  | MC Funds / General Quota | MC |  |  |  | 1830 Dt.13-10-2025 | [8 empty] | 07/EEA dt 24-10-2025 | M/S Capital Construction Co. | 18.13 | 18-11-2025 | 3 Months | 23-01-2026 |  |  |  |  | 40 |  | 9.96 | Delayed/Held Up |  | Work in Progress delayed due to bitumen Work.
271 | MCL-0276 | B&R | A | A4 | North | 90 |  |  | Construction of Lekhi Vehra With RMC in Ward No.90. |  |  |  | MC Funds / General Quota | MC |  |  |  | 1744 Dt.13-10-2025 | [8 empty] | 08/EEA dt 24-10-2025 | M/s Godwyn Infra | 13.34 | 19-11-2025 | 3 Months | 23-01-2026 |  |  |  |  | 25 |  | 0 | In Progress |  | Work in Progress.
272 | MCL-0277 | B&R | A | A4 | North | 90 |  |  | Construction of Side Berms With RMC of Main Gurudwara Dukhniwaran Sahib Road Ward No.90. |  |  |  | MC Funds / General Quota | MC |  |  |  | 1746 Dt.13-10-2025 | [8 empty] | 09/EEA dt 24-10-2025 | M/s Godwyn Infra | 24.81 | 11-11-2025 | 3 Months | 23-01-2026 |  |  |  |  | 50 |  | 9.91 | In Progress |  | Work in Progress.
273 | MCL-0278 | B&R | A | A4 | North | 88 |  |  | P/L of RMC M-30 in Damage Streets of Mohalla Shivpuri in Ward No.88. |  |  |  | MC Funds / General Quota | MC |  |  |  | 1832 Dt.13-10-2025 | [8 empty] | 10/EEA dt 24-10-2025 | M/s Neeraj Joshi | 35.54 | 13-11-2025 | 4 Months | 23-02-2026 |  |  |  |  | 50 |  | 0 | In Progress |  | Work in Progress.
274 | MCL-0279 | B&R | A | A4 | North | 84 |  |  | Laying RMC M-30 in Streets of Near Guru Ravidass Mandir of Main Peeru Banda Ward No 84.(New Ward No.89) |  |  |  | MC Funds / General Quota | MC |  |  |  | 1749 Dt.13-10-2025 | [8 empty] | 12/EEA dt 24-10- 2025 | M/s Neeraj Joshi | 26.83 | 11-12-2025 | 3 Months | 23-01-2026 |  |  |  |  | 35 |  | 8.41 | In Progress |  | Laying of Water Supply Line Work in Progress.
275 | MCL-0280 | B&R | A | A4 | North | 95 |  |  | P/L of RMC M-30 in Streets of New Ashok Nagar in Ward No.95 |  |  |  | MC Funds / General Quota | MC |  |  |  | 1748 Dt.13-10-2025 | [8 empty] | 13/EEA dt 24-10-2025 | M/s LRY Labour Constractor | 57.6 | 13-11-2025 | 6 Months | 22-04-2026 |  |  |  |  | 90 |  | 0 | In Progress |  | Work in Progress.
276 | MCL-0281 | B&R | A | A4 | North | 94 |  |  | P/L of RMC M-30 in Streets of Mohalla Saroop Nagar New Janak Puri & Suiyan Wala Hospital Road in Ward No.89. (New Ward no.94) |  |  |  | MC Funds / General Quota | MC |  |  |  | 1745 Dt.13-10-2025 | [8 empty] | 14/EEA dt 24-10-2025 | M/s LRY Labour Constractor | 52.87 | 11-11-2025 | 6 Months | 22-04-2026 |  |  |  |  | 35 |  | 0 | In Progress |  | Work in Progress.
277 | MCL-0282 | B&R | A | A4 | North | 85 |  |  | Laying RMC M-30 in Streets of Mohalla Gandhi Nagar & Mohalla Basant Nagar St no.6 in Ward No.85. (New Ward No.88) |  |  |  | MC Funds / General Quota | MC |  |  |  | 1742 Dt.13-10-2025 | [8 empty] | 16/EEA dt 24-10-2025 | M/s Navdeep Gupta & Company | 41.12 | 13-11-2025 | 4 Months | 23-02-2026 |  |  |  |  | 25 |  | 0 | Delayed/Held Up |  | Delayed due to Water Supply Line.
278 | MCL-0283 | B&R | A | A4 | North | Gen |  |  | Painting of Elevated Road Deck Slab Roof,Jagroan Bridge,Ludhiana. |  |  |  | MC Funds / General Quota | MC | [12 empty] | 18/EEA dt 12-12-2025 | M/s K.S Constructions | 43.35 |  | 3 Months | 03-11-2026 |  |  |  |  | 0 |  | 0 | Delayed/Held Up |  | Inauguration Pending. Will start after Elevated road work.
279 | MCL-0284 | B&R | A | A4 | North | Gen |  |  | Painting of Kerb Stone Elevated Road Pillars & Walls Below Elevated Road Jagroan Bridge,Ludhiana. |  |  |  | MC Funds / General Quota | MC | [12 empty] | 19/EEA dt 12-12-2025 | M/s N.S Infra | 17.15 | 01-05-2026 | 3 Months | 03-11-2026 |  |  |  |  | 5 |  | 0 | In Progress |  | Work in Progress.
280 | MCL-0285 | B&R | A | A4 | North | 86 |  |  | Laying RMC M-30 in Streets of Farid Nagar in Ward No.86. (New Wrad No.8). |  |  |  | MC Funds / General Quota | MC |  |  |  | 2274 DT.21-11-2025 | [8 empty] | 20/EEA dt 22-12-2025 | M/s Neeraj Joshi | 25.07 | 13-01-2026 | 3 Months | 21-03-2026 |  |  |  |  | 60 |  | 19.81 | In Progress |  | Work in Progress.
281 | MCL-0286 | B&R | A | A4 | North | 87 |  |  | Laying RMC M-30 in Streets of Arjun Nagar & Vai Kunth Nagar in Ward No.87 |  |  |  | MC Funds / General Quota | MC |  |  |  | 2272 Dt.21-11-2025 | [8 empty] | 21/EEA dt 22-12-2025 | M/s Neeraj Joshi | 26.39 | 14-01-2026 | 5 Months | 21-05-2026 |  |  |  |  | 90 |  | 26.03 | In Progress |  | Work in Progress.
282 | MCL-0287 | B&R | A | A4 | North | 90 |  |  | Construction of Balance Streets of Shahpur Road With RMC in Ward No.90. |  |  |  | MC Funds / General Quota | MC |  |  |  | 2432 DT.05-01-2026 | [8 empty] | 23/EEA dt 28-01-2026 | M/s Neeraj Joshi | 21.65 | 02-10-2026 | 3 Months | 27-04-2026 |  |  |  |  | 0 |  | 0 | Delayed/Held Up |  | Inauguration Pending.
283 | MCL-0288 | B&R | A | A4 | North | 90 |  |  | Construction of Streets With RMC Backside JMD Mall in Ward No.90. |  |  |  | MC Funds / General Quota | MC |  |  |  | 2434 Dt.05-01-2026 | [8 empty] | 24/EEA dt 28-01-2026 | M/s Neeraj Joshi | 25.62 | 02-11-2026 | 3 Months | 27-04-2026 |  |  |  |  | 50 |  | 0 | In Progress |  | Work in Progress.
284 | MCL-0289 | B&R | A | A4 | North | 95 |  |  | Laying RMC M-30 in Streets of New Aman Nagar & Bhagat Singh Colony in Ward No.95. |  |  |  | MC Funds / General Quota | MC |  |  |  | 2281 Dt.21-11-2025 | [8 empty] | 26/EEA dt 28-01-2026 | M/s Navyug Company | 25.41 | 15-02-2026 | 3 Months | 27-04-2026 |  |  |  |  | 80 |  | 22.76 | In Progress |  | Work in Progress.
285 | MCL-0290 | B&R | A | A4 | North | 88 |  |  | Recarpeting of Road Along Budha Nallah from Chand Cinema Pully to Shivpuri Pully in Ward No. |  |  |  | MC Funds / General Quota | MC |  |  |  | 2285 Dt.21-11-2025 | [8 empty] | 49/EEA dt 20-02-2026 | M/s Maruti Construction Co. | 87.55 | 03-02-2026 | 6 Months | 19-08-2026 |  |  |  |  | 50 |  | 48.22 | In Progress |  | Work in Progress.
286 | MCL-0291 | B&R | A | A4 | North | 94 |  |  | P/L of RMC M-30 in Streets of Mahavir Homes Colony & Balance Streets of Rajauri Garden Colony in Ward No.94 (new Ward No.93) |  |  |  | MC Funds / General Quota | MC |  |  |  | 2273 Dt.21-11-2025 | [8 empty] | 50/EEA dt 20-02-2026 | M/s Navyug Company | 52.13 | 03-04-2026 | 6 Months | 19-08-2026 |  |  |  |  | 0 |  | 0 | Delayed/Held Up |  | Inauguration Pending.
287 | MCL-0292 | B&R | A | A4 | North | 88 |  |  | P/L of RMC -30 in Various Streets of Gandhi Nagar in Ward No.88. |  |  |  | MC Funds / General Quota | MC |  |  |  | 2469 Dt.05-01-2026 | [8 empty] | 51/EEA dt 20-02-2026 | M/s Varinder Singh Contractor | 59.52 | 03-03-2026 | 6 Months | 19-08-2026 |  |  |  |  | 40 |  | 0 | Delayed/Held Up |  | Delayed due to Water Supply Line.
288 | MCL-0293 | B&R | A | A4 | North | 88 |  |  | Construction of Retaining Wall along Budha Darya from Shivpuri Pully to Jain Nagar Pully (LHS) Ward No.88 (Old Ward No.85) |  |  |  | MC Funds / General Quota | MC |  |  |  | 2475 Dt.05-01-2026 | [8 empty] | 52/EEA dt 20-02-2026 | M/s Varinder Singh Contractor | 80.68 | 03-03-2026 | 9 Months | 19-11-2026 |  |  |  |  | 90 |  | 76.07 | In Progress |  | Work in Progress.
289 | MCL-0294 | B&R | A | A4 | North | 88 |  |  | Construction of Retaining Wall along Budha Darya from Jain Nagar Towards Basant Nagar in Ward No.88 |  |  |  | MC Funds / General Quota | MC |  |  |  | 2474 Dt.05-01-2026 | [8 empty] | 53/EEA dt 20-02-2026 | M/s Apex Developers | 77.2 | 04-05-2026 | 6 Months | 19-08-2026 |  |  |  |  | 60 |  | 0 | In Progress |  | Work in Progress.
290 | MCL-0295 | B&R | A | A4 | North | 94 |  |  | Laying RMC M-30 in Streets of Model Colony in Ward No.89.(New Ward No.94) |  |  |  | MC Funds / General Quota | MC |  |  |  | 2882 Dt.21-11-2025 | [8 empty] | 54/EEA dt 20-02-2026 | M/s K.S Constructions | 37.93 | 03-03-2026 | 4 Months | 19-06-2026 |  |  |  |  | 35 |  | 0 | In Progress |  | Work in Progress.
291 | MCL-0296 | B&R | A | A4 | North | 94 |  |  | P/L of RMC M-30 in Streets of Bhagwan Dass Colony in Ward No.89 (New Ward No.94) |  |  |  | MC Funds / General Quota | MC |  |  |  | 2284 Dt.21-11-2025 | [8 empty] | 55/EEA dt 20-02-2026 | M/s K.S Constructions | 56.42 | 03-07-2026 | 6 Months | 19-08-2026 |  |  |  |  | 40 |  | 0 | In Progress |  | Work in Progress.
292 | MCL-0297 | B&R | A | A4 | North | 86 |  |  | Laying RMC M-30 in Various Streets of Ward No.88 (New Ward No.86) |  |  |  | MC Funds / General Quota | MC |  |  |  | 2278 Dt.21-11-2025 | [8 empty] | 56/EEA dt 20-02-2026 | M/s Navyug Company | 46.06 | 03-12-2026 | 6 Months | 19-08-2026 |  |  |  |  | 75 |  | 22.61 | In Progress |  | Work in Progress.
293 | MCL-0298 | B&R | A | A4 | North | 1 |  |  | Construction of Metalled Road in adjoining streets of Nagesh Hosiery in Ward No.1. |  |  |  | MC Funds / General Quota | MC |  |  |  | 2463 Dt.05-01-2026 | [8 empty] | 57/EEA dt 20-02-2026 | M/s Somaya Infrastructures | 49.87 |  | 3 Months | 19-05-2026 |  |  |  |  | 0 |  | 0 | Delayed/Held Up |  | Inauguration Pending.
294 | MCL-0299 | B&R | A | A4 | North | 1 |  |  | Recarpeting of Akash Nagar Main Road in Ward No.1. |  |  |  | MC Funds / General Quota | MC |  |  |  | 2466 Dt.05-01-2026 | [8 empty] | 58/EEA dt 20-02-2026 | M/s Somaya Infrastructures | 41.25 | 04-04-2026 | 5 Months | 19-07-2026 |  |  |  |  | 60 |  | 25.34 | Delayed/Held Up |  | Work Held up due to Sewer Line.
295 | MCL-0300 | B&R | A | A4 | North | 89 |  |  | P/L of RMC M-30 in Kharbanda Chowk,Bohar Wala Gurudwara Nali Mohalla & Beli Ram Chowk Streets in Ward No.84.(New Ward No.89) |  |  |  | MC Funds / General Quota | MC |  |  |  | 2280 Dt.21-11-2025 | [8 empty] | 61/EEA dt 20-02-2026 | M/s Asis Builders | 51.35 | 03-09-2026 | 6 Months | 19-08-2026 |  |  |  |  | 40 |  | 26.31 | In Progress |  | Work in Progress.
296 | MCL-0301 | B&R | A | A4 | North | Gen |  |  | Development of Green Belt along Jalandhar Byepass upto MC Limit. |  |  |  | MC Funds / General Quota | MC |  |  |  | 2827 Dt.19-02-2026 | [8 empty] | 64/EEA dt 25-02-2026 | M/s Rajeev Enterprises | 68.49 | 03-12-2026 | 6 Months | 24-08-2026 |  |  |  |  | 95 |  | 67.89 | In Progress |  | Work in Progress.
297 | MCL-0302 | B&R | A | A4 | North | 88 |  |  | Construction of Retaining Wall Along Budha Darya From Basant Nagar Towards Gandhi Nagar in Ward No.88 |  |  |  | MC Funds / General Quota | MC |  |  |  | 2752 Dt.19-02-2026 | [8 empty] | 65/EEA dt 25-02-2026 | M/s Asis Builders | 78.49 | 04-04-2026 | 6 Months | 24-08-2026 |  |  |  |  | 50 |  | 0 | In Progress |  | Work in Progress.
298 | MCL-0303 | B&R | A | A4 | North | 88 |  |  | Construction of Joybox or Playground at Ward No.86 (New Ward No.88) |  |  |  | MC Funds / General Quota | MC |  |  |  | 2829 Dt.19-02-2026 | [8 empty] | 67/EEA dt 25-02-2026 | M/s Subodh Batish | 22.96 |  | 3 Months | 24-05-2026 |  |  |  |  | 0 |  | 0 | Delayed/Held Up |  | Held up due to Retaining Wall Work.
299 | MCL-0304 | B&R | A | A4 | North | 95 |  |  | Construction of Streets With RMC M-30 in Area Aman Vihar Colony Ward No.95. |  |  |  | MC Funds / General Quota | MC |  |  |  | 2739 Dt.19-02-2026 | [8 empty] | 68/EEA dt 25-02-2026 | M/s Navyug Company | 27.84 |  | 3 Months | 24-05-2026 |  |  |  |  | 0 |  | 0 | Delayed/Held Up |  | Inauguration Pending.
300 | MCL-0305 | B&R | A | A4 | North | 1 |  |  | Construction of Adjoining Streets of Guru Har Rai Nagar with RMC M-30 in Ward No.1 |  |  |  | MC Funds / General Quota | MC |  |  |  | 2740 Dt.19-02-2026 | [8 empty] | 71/EEA dt 25-02-2026 | M/s Asis Builders | 34.48 | 03-04-2026 | 3 Months | 24-05-2026 |  |  |  |  | 25 |  | 0 | In Progress |  | Work in Progress.
301 | MCL-0306 | B&R | A | A4 | North | 89 |  |  | P/Laying RMC M-30 in Various Streets of Naali Mohalla in Ward No.89, Ludhiana |  |  |  | MC Funds / General Quota | MC |  |  |  | 2849 Dt.19-02-2026 | [8 empty] | 72/EEA dt 25-02-2026 | M/s Asis Builders | 43.37 | 17-03-2026 | 3 Months | 24-05-2026 |  |  |  |  | 40 |  | 0 | In Progress |  | Work in Progress.
302 | MCL-0307 | B&R | A | A4 | North | 89 |  |  | Construction of Joybox or Playground at Ward No.89 |  |  |  | MC Funds / General Quota | MC |  |  |  | 2828 Dt.19-02-2026 | [8 empty] | 73/EEA dt 25-02-2026 | M/s Subodh Batish | 22.96 |  | 3 Months | 24-05-2026 |  |  |  |  | 0 |  | 0 | Delayed/Held Up |  | Inauguration pending.
303 | MCL-0308 | B&R | A | A4 | North | 94 |  |  | Construction of Joybox or Playground at Ward No.94 |  |  |  | MC Funds / General Quota | MC |  |  |  | Dt.19-02-2026 | [8 empty] | 75/EEA dt 25-02-2026 | M/s Subodh Batish | 22.96 |  | 3 Months | 24-05-2026 |  |  |  |  | 0 |  | 0 | Delayed/Held Up |  | Inauguration Pending.
304 | MCL-0309 | B&R | A | A4 | North | 86 |  |  | P/F of RMC M-30 in Streets B/S Ram Rai School & Sarvanand Colony in Ward No.86 |  |  |  | MC Funds / General Quota | MC |  |  |  | 2470 Dt.05-01-2026 | [8 empty] | 77/EEA dt 25-02-2026 | M/s Navdeep Gupta & Company | 30.44 | 06-01-2026 | 6 Months | 24-08-2026 |  |  |  |  | 10 |  | 0 | Delayed/Held Up |  | Work in Progress delayed due to laying of Water Supply & Sewer Lines.
305 | MCL-0310 | B&R | A | A4 | North | 90 |  |  | Construction of Main Kesar Ganj Mandi with RMC in Ward No.90, Ludhiana |  |  |  | MC Funds / General Quota | MC | [12 empty] | 94/EEA dt.05-05-2026 | M/S LRY Labour Contrator | 49.09 | 15-05-2026 | 4 Months | 09-04-2026 |  |  |  |  | 90 |  | 0 | In Progress |  | Work in Progress.
306 | MCL-0311 | B&R | A | A4 | North | 87 |  |  | P/L of RMC M-30 on streets of Vaishnu Colony in Ward No.87 |  |  |  | MC Funds / General Quota | MC | [12 empty] | 92/EEA dt.05-05-2026 | M/S GODWYN INFRA | 22.71 | 20-05-2026 | 3 Months | 08-04-2026 |  |  |  |  | 25 |  | 0 | Delayed/Held Up |  | Work in Progress delayed due to laying of Water Supply line.
307 | MCL-0312 | B&R | A | A4 | North | 90 |  |  | P/Laying RMC in adjoining streets of Bagh Wali Gali & Streets of Kutcha no 2-3-4 in Ward No.90, Ludhiana |  |  |  | MC Funds / General Quota | MC | [12 empty] | 88/EEA dt.05-05-2026 | M/S Capital Construction Co. | 18.82 | 18-05-2026 | 3 Months | 08-04-2026 |  |  |  |  | 30 |  | 0 | In Progress |  | Work in Progress.
308 | MCL-0313 | B&R | A | A4 | North | 1 |  |  | Laying RMC M-30 in streets of Gurbaksh Nagar & adjoining area in Ward No. 1 |  |  |  | MC Funds / General Quota | MC | [12 empty] | 90/EEA dt.05-05-2026 | M/S Capital Construction Co. | 49.14 | 24-05-2026 | 6 Months | 11-04-2026 |  |  |  |  | 60 |  | 23.26 | In Progress |  | Work in Progress.
309 | MCL-0314 | B&R | A | A4 | North | 1 |  |  | P/L of RMC M-30 in different streets of Geeta Colony & adjoining area in ward no 1 |  |  |  | MC Funds / General Quota | MC | [12 empty] | 87/EEA dt.05-05-2026 | M/S Capital Construction Co. | 53.38 | 20-05-2026 | 6 Months | 11-04-2026 |  |  |  |  | 50 |  | 22.65 | In Progress |  | Work in Progress.
310 | MCL-0315 | B&R | A | A4 | North | A4 |  |  | Upgradation of Road with RMC in Area Guru Har Rai Nagar Nagesh Hosiery Road Adjoining Jalandhar Byepass, Ludhiana |  |  |  | MDF / SASCI | SASCI | [12 empty] | 79/EEA dt 09/03/2026 | M/s NKC Construction Pvt. Ltd. | 501.26 | 20-03-2026 | 3 Months | 06-08-2026 |  |  |  |  | 20 |  | 83.19 | Delayed/Held Up |  | Delayed due to Payment Pending.
311 | MCL-0316 | B&R | A | A4 | North | A4 |  |  | Upgradation of Various Main Roads With RMC in North Constituency Zone-A,Ludhiana. |  |  |  | MDF / SASCI | MDF |  |  |  | 2898 Dt.19-02-2026 | [8 empty] | 81/EEA dt 25-03-2026 | M/s Gaanesh Kartikey | 858.33 | 04-04-2026 | 3 Months | 24-06-2026 |  |  |  |  | 50 |  | 182.88 | In Progress |  | Work in progress
312 | MCL-0317 | B&R | A | A4 | North | A4 |  |  | Upgradation of Elevated Road from Jagroan Bridge to Chand Cinema by Laying Mastic Asphalt |  |  |  | MDF / SASCI | MDF |  |  |  | 2678 Dt.11-02-2026 | [8 empty] | 82/EEA dt 25-03-2026 | M/s Dass Builders | 568.23 | 26-03-2026 | 3 Months | 24-06-2026 |  |  |  |  | 60 |  | 119.17 | In Progress |  | Work in progress
313 | MCL-0318 | B&R | A | A4 | North | A4 |  |  | Upgradation of Roads with RMC in Area Bharti Colony, Akash Nagar adjoining Jalandhar Byepass, Ludhiana |  |  |  | MDF / SASCI | MDF |  |  |  | 2677 Dt.11-02-2026 | [8 empty] | 80/EEA Dt.25-03-2026 | M/s Hitesh Aggarwal Cont | 571.5 | 04-04-2026 | [6 empty] | 35 |  | 195.5 | Delayed/Held Up |  | Held up due to Laying of Sewer Line.
314 | MCL-0319 | B&R | A | A4 | North | A4 |  |  | Upgradation of various Roads with RMC in Ward No.95, Ludhiana |  |  |  | MDF / SASCI | MDF |  |  |  | 2679 Dt.11-02-2026 | [8 empty] | 84/EEA Dt.25-03-2026 | M/s Ashok Kumar Sobti | 635.34 | 26-03-2026 | 3 Months | 24-06-2026 |  |  |  |  | 75 |  | 338.54 | In Progress |  | Work in progress
315 | MCL-0320 | B&R | A | A4 | North | A4 |  |  | Upgradation of various Roads with RMC in Ward No.1, Ludhiana |  |  |  | MDF / SASCI | MDF | [12 empty] | 85/EEA Dt.25-03-2026 | M/s Kabir Infra | 696.4 | 26-03-2026 | [6 empty] | 70 |  | 269.52 | Delayed/Held Up |  | Delayed due to Laying of Sewer Line.
316 | MCL-0321 | O&M | A | A2 | Central | 78 | Sewerage |  | Rough Cost Estimate Pro. Laying of Water Supply Line and Sewer Line in Mohar singh nagar st no 2-4 & 7 Ward No78. |  |  | 1 | Councillor Quota (CQ) | CQ | Awarded | 24.08 | -13.13% | 1442 Dt. 11/08/2025 | Yes | Yes | SDO |  |  |  | Yes | Yes | 45/G-33 Dt. 25/09/2025 | M/s Kohinoor Builders | 22.72 | 2025-01-10 | 3 | 07-10-2026 |  | Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN |  |  | 80 |  | 19.264 | In Progress |  | Work in Progress
317 | MCL-0322 | O&M | A | A2 | Central | 84 | Sewerage |  | Rough Cost Estimate Prov. Laying/Up-gradation and mtc. of Water Supply & Sewer Line At Different Localities of Ward No. 84. |  |  | 1 | Councillor Quota (CQ) | CQ | Awarded | 9.85 | -16% | 2201 Dt.21/11/2025 | Yes | Yes | SDO |  |  |  | Yes | Yes | 71/G-33 Dt. 22/11/2025 | M/s Brar Brothers | 8.36 | 23/11/2025 | 3 | 07-10-2026 |  | Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN |  |  | 85 |  | 7.106 | In Progress |  | Work in Progress
318 | MCL-0323 | O&M | A | A1 | Central | 10 | Sewerage |  | Rough Cost Estimate Prov. Laying/Up-gradation and mtc. of Water Supply & Sewer Line At Different Localities of Ward No. 10 |  |  | 1 | Councillor Quota (CQ) | CQ | Awarded |  |  | 2622 Dt. 11/02/2026 | Yes | Yes | SDO |  |  |  | Yes | Yes | 83/G-33 Dt. 24/02/2026 | As Contractor | 7.92 | 24/02/2026 | 3 | 07-10-2026 |  | Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN |  |  | 80 |  | 6.336 | In Progress |  | Work in Progress
319 | MCL-0324 | O&M | A | A1 | Central | 9 | Sewerage |  | Rough Cost Estimate Prov. Laying of Sewer Line and Water Supply Line in Basti Sheikh Mohammad Ward No. 9 |  |  | 1 | Councillor Quota (CQ) | CQ | Awarded | 21.05 | -12.65% | 2607 Dt.11/02/2026 | Yes | Yes | SDO |  |  |  | Yes | Yes | 100/G-33 Dt. 24/02/2026 | Surya Construction | 18.39 | 24/02/2026 | 3 | 30/10/2026 |  | Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN |  |  | 0 |  | 0 | Not Started |  | Narrow Streets work will start after monsoon
320 | MCL-0325 | O&M | A | A1 | Central | 83 | Sewerage |  | Rough Cost Estimate Prov. Laying of Sewer and Water Supply Line Mohalla Balmiki Ghatti Ward No. 83 |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 29.38 | -11.65% | 2608 Dt.11/02/2026 | Yes | Yes | XEN |  |  |  | Yes | Yes | 97/G-33 Dt. 24/02/2026 | Kohinoor Builders | 25.96 | 24/02/2026 | 3 | 30/8/2026 |  | Rajneesh Kumar JE Sandeep Sharma SDO Kamal Ram XEN |  |  | 50 |  | 12.98 | In Progress |  | Work in proress
321 | MCL-0326 | O&M | A | A2 | Central | 62 | Water Supply |  | Providing & Installation of 25 HP Straight Bore T/Well against failed T/Well in Bangru Mohalla, Ward no. 62. | NA | NA | 1 | MC Funds / General Quota | GQ | Awarded | 12.64 | -3.03% | 2367 Dt.23/08/2024 | Yes | Yes | SDO |  |  |  | Yes | Yes | 09/G-33 Dt. 18/09/2024 | The Ananda coop L&C Society Ltd. | 12.63 | 18/09/2024 | 3 | 30/8/2026 |  | Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN |  |  | 10 |  | 0 | In Progress |  | Work in proress, Delay due to site dispute
322 | MCL-0327 | O&M | A | A1 | Central | 60 | Water Supply |  | Providing and Installation of 12.5 HP Submersible T/well in Mohalla Nau Ghara Ward No. 60 | NA | NA | 1 | MC Funds / General Quota | GQ | Awarded | 6.53 | -16.01% | 2361 Dt.23/08/2024 | Yes | Yes | SDO |  |  |  | Yes | Yes | 17/G-33 Dt. 07/10/2024 | The Ananda coop L&C Society Ltd. | 5.48 | 10-07-2024 | 3 | 30/8/2026 |  | Rajneesh Kumar JE Sandeep Sharma SDO Kamal Ram XEN |  |  | 0 |  | 0 | Not Started |  | The streets at the site are narrow, so the machine couldn't be set up. Now, Mr. Thapar has said that they will open a new route, and the work can start after that
323 | MCL-0328 | O&M | A | A2 | Central | 84 | Water Supply |  | Providing & Installation of 12.5 HP Straight Bore T/Well Against Failed T/well Ktaira Norian Near Dal Bazar Ward No. 84 | NA | NA | 1 | Councillor Quota (CQ) | CQ | Awarded | 6.75 | -5.55% | 1724 Dt.13/10/2025 | Yes | Yes | SDO |  |  |  | Yes |  | 66G-33 Dt. 06/11/2025 | M/s Bedi Pump Store | 6.38 | 11-06-2025 | 2 | 30/7/2026 |  | Rajneesh Kumar JE Sandeep Sharma SDO Kamal Ram XEN |  |  | 70 |  | 0 | In Progress |  | Work in Progrss
324 | MCL-0329 | O&M | A | A2 | Central | 82 | Water Supply |  | Providing and Installation of 25 HP Straight Bore T/Well in Mohalla Harbanspura, Ward No. 82, Ludhiana. (MP Lad) | NA | NA | 1 | MPLAD Funds | MP LAD | Awarded | 13.5 | -18.89% | 2665 Dt.11/02/2026 | Yes | Yes | SDO | [5 empty] | 80/G-33 Dt. 24/02/2026 | JCS Electric Works | 10.96 | 24/02/2026 | 3 | 15/7/2026 |  |  |  |  | 100 |  | 10.96 | Delayed/Held Up |  | electrical meter pending
325 | MCL-0330 | O&M | A | A2 | Central | 78 |  |  | Providing & Installation of 25 HP Straight Bore T/Well Mohar Singh Nagar,Ward No. 78(new) |  |  |  | MC Funds / General Quota | GQ |  |  |  | 2614 Dt.11/02/2026 | [8 empty] | 79/G-33 Dt. 24/02/2026 | JCS Electric Works | 10.35 | 24/02/2026 | 3 | 30-06-2026 |  |  |  |  | 0 |  | 0 | Not Started |  | Notice issue to contactor
326 | MCL-0331 | O&M | A | A2 | Central | 78 |  |  | Providing and Installation of 25 HP Straight Bore T/Well Against Failed T/well Sadhu Sundar Singh Colony St No. 4 Issa Nagri Ward No. 78 |  |  |  | MC Funds / General Quota | GQ |  |  |  | 2786 Dt.19/02/2026 | [8 empty] | 103/G-33 Dt. 05/03/2026 | Rajdeep Enterprises | 10.87 | 03-05-2026 | 3 | 07-10-2026 |  |  |  |  | 80 |  | 8.696 | In Progress |  | Work in Progress
327 | MCL-0332 | O&M | A | A1 | Central | 83 |  |  | Providing & Installation of 25 HP Straight Bore T/Well Mohalla Balmik Ghatti Ward No. 83(new) |  |  |  | MC Funds / General Quota | GQ |  |  |  | 2785 Dt.19/02/2026 | [8 empty] | 104/G-33 Dt. 05/03/2026 | ESS Elechmech Enterprises | 11.84 | 03-05-2026 | 3 | 07-10-2026 |  |  |  |  | 100 |  | 11.84 | Delayed/Held Up |  | Electrical meter pending
328 | MCL-0333 | O&M | A | A4 | Central | 59 |  |  | Rough Cost Estimate Prov. Laying / Up-Gradation of Water Supply Line, Sewer line in Kohlu Wali Gali Qilla Mohalla Near Dispansary Petrol Pump Wali Gali & Mandir Wali Gali in Ward No. 59 |  |  |  | MC Funds / General Quota | GQ | [12 empty] | 61/G-33 Dt. 07/03/2024 | The Dynamic Coop. L&C Society Ltd. | 41.81 | 03-07-2024 | 3 | 30/9/2026 |  |  |  |  | 20 |  | 8.362 | In Progress |  | Machinary not entered at proposed site due to narrow streets/ Now contractor will arrange small machine and start the work
329 | MCL-0334 | O&M | A | A2 | Central | 56 |  |  | Rough Cost Estimate Prov. Laying / Up-Gradation of Water Supply Line, Sewer line in Dhoka Mohalla Street No. 1 and 2, Near Kalra Hospital, Ward No. 56 |  |  |  | MC Funds / General Quota | GQ |  |  |  | 351 Dt.26/03/2025 | [8 empty] | 05/G-33 Dt. 14/04/2025 | M/s Surya Const. | 33.24 | 14/04/2025 | 3 | 30/9/2026 |  |  |  |  | 60 |  | 19.944 | Delayed/Held Up |  | Low laying area pending work start to be done after monsoon
330 | MCL-0335 | O&M | A | A2 | Central | 54 |  |  | Rough Cost Estimate Prov. Laying of Water Supply Line and Sewer Line At Fatehganj Shanti Nikaten Wali Gali and Near Gurudwara Sahib Wali Gali, Ward No. 54 |  |  |  | MC Funds / General Quota | GQ |  |  |  | 558 Dt.09/04/2025 | [8 empty] | 15/G-33 Dt. 28/04/2025 | Dynamic Tiles | 23.12 | 28/04/2025 | 3 | 30/9/2026 |  |  |  |  | 50 |  | 11.56 | Delayed/Held Up |  | Pending Sewer work to be done after monsoon
331 | MCL-0336 | O&M | A | A2 | Central | 56 |  |  | Rough Cost Estimate Prov. Laying of Water Supply Line Gulchaman Gali and Its Branch line in Ward No. 56 |  |  |  | MC Funds / General Quota | GQ |  |  |  | 560 Dt.09/04/2025 | [8 empty] | 16/G-33 Dt. 28/04/2025 | ESS Elechmech Enterprises | 40.17 | 28/04/2025 | 3 | 30/7/2026 |  |  |  |  | 90 |  | 36.153 | In Progress |  | Work in Progress
332 | MCL-0337 | O&M | A | A1 | Central | 9 |  |  | Rough Cost Estimate Prov. Laying of Water Supply Line and Sewer Line From Sunder Nagar Pully to Bajwa Nagar Pully along Budha Dariya Ward No. 83 (old 61) |  |  |  | MC Funds / General Quota | GQ |  |  |  | 110 Dt.11/08/2025 | [8 empty] | 49/G-33 Dt. 25/09/2025 | Ess Elecmech Enterprises | 26.18 | 25/09/2025 | 3 | 30/9/2026 |  |  |  |  | 0 |  | 0 | Not Started |  | Work hold due to road level issue
333 | MCL-0338 | O&M | A | A1 | Central | 84 |  |  | Rough Cost Estmate Prov. Laying of Water Supply Line and Sewer Line in Maddi Bhature Wali Gali & Dr. Kheda wali Gali Ward No. 84 |  |  |  | Councillor Quota (CQ) | CQ |  |  |  | 2623 Dt.11/02/2026 | [8 empty] | 84/G-33 Dt. 24/02/2026 | ESS Elechmech Enterprises | 17.87 | 24/02/2026 | 3 | 30/7/2026 |  |  |  |  | 40 |  | 7.148 | In Progress |  | Work in Progress
334 | MCL-0339 | O&M | A | A1 | Central | 9 |  |  | Rough Cost Estimate Prov. Laying of Water Supply and Sewer Line at Basti Mani Singh Ward No. 9 |  |  |  | Councillor Quota (CQ) | CQ |  |  |  | 2606 Dt.11/02/2026 | [8 empty] | 99/G-33 Dt. 24/02/2026 | Surya Construction | 36.58 | 24/02/2026 | 3 | 30/9/2026 |  |  |  |  | 30 |  | 10.974 | In Progress |  | Work in Progress till 30-06-2026 & balance work will start after monsoon
335 | MCL-0340 | O&M | A | A2 | North | 90 | Roads - Bituminous |  | Rough Cost Estimate Pro. Laying / Up-Gradation of Water Supply line, sewer line IN Thaper PCO wali gali and Hanuman mandir wali gali Ward No.90 |  |  |  | Councillor Quota (CQ) | CQ | Awarded |  |  | 2478 Dt.05/01/2026 | Yes | Yes | XEN | N/A |  |  |  |  | 74/G-33 Dt. 30/01/2026 | Kohinoor Builders | 25.41 | 30/01/2026 | 3 | 30/9/2026 |  |  |  |  | 50 |  | 12.705 | In Progress |  | Work in Progress till 30-06-2026 & balance work will start after monsoon
336 | MCL-0341 | O&M | A | A2 | North | 90 |  |  | Rough Cost Estimate Prov. Laying/Up-gradation and mtc. of Water Supply & Sewer Line At Different Localities of Ward No. 90 |  |  |  | Councillor Quota (CQ) | CQ |  |  |  | 3285 Dt.25/02/2026 | [8 empty] | 107/G-33 Dt. 27/03/2026 | N.S Infra | 7.9 | 27/03/2026 | 3 | 31/8/2026 |  |  |  |  | 15 |  | 1.185 | In Progress |  | This work as per maintenance work
337 | MCL-0342 | O&M | A | A2 | North | 90 |  |  | Rough Cost Estimate Prov. Laying / Up-Gradation of Water Supply Line, Sewer line (Missing Link) in Kucha No. 5,6,7 Field Ganj, Fish Market, Tyre Market Ward No. 64 |  |  |  | Councillor Quota (CQ) | CQ | [12 empty] | 49/G-33 Dt. 29/02/2024 | The Rajowal Coop. L&C Society Ltd. | 45.71 | 29/02/2024 | 3 | 30-10-2026 |  |  |  |  | 65 |  | 29.7115 | In Progress |  | Work in Progress till 30-06-2026 & balance work will start after monsoon
338 | MCL-0343 | O&M | A | A2 | North | 90 |  |  | Rough Cost Estimate Pro. Laying of Water Supply Line and Sewer Line in Backside Local Adda Streets Ward no. 90 |  |  |  | Councillor Quota (CQ) | CQ |  |  |  | 1675 Dt.13/10/2025 | [8 empty] | 75/G-33 Dt. 30/01/2026 | Kohinoor Builders | 37.19 | 01-02-2026 | 3 | 30-10-2026 |  |  |  |  | 50 |  | 18.595 | In Progress |  | Work in Progress till 30-06-2026 & balance work will start after monsoon
339 | MCL-0344 | O&M | A | A3 | East | 2 |  |  | Providing, Laying / Up-Gradation of 16" & 24" dia. NP-3 HDPE pipe Sewer Line from Jivan Jyoti School to Phambran Disposal Ward No. 2 |  |  |  | MC Funds / General Quota | GQ |  |  |  | 2239 dt.21/11/2025 | [8 empty] | 05/G-33/XEN/Z-A dt. 01/06/2026 | M/s Deepak Madaan | 91.39 | 06-01-2026 | 3 | 31.12.2026 |  |  |  |  | 0 |  | 0 | Not Started |  | Work will be done after monsoon
340 | MCL-0345 | O&M | A | A3 | East | 2,3 |  |  | Providing, Laying /Up-gradation of 20" dia. NP=3 HDPE pipe Sewer Line from Phambran Disposal to Shivpuri Chownk. Ward No. 2 |  |  |  | MC Funds / General Quota | GQ |  |  |  | 2240 dt. 21/11/2025 | [8 empty] | 03/G-33/XEN/Z-A dt. 09/05/2026 | Kohinoor Builders | 109.42 | 05-09-2026 | 3 | 08-08-2026 |  |  |  |  | 50 |  | 54.71 | In Progress |  | Work is in Progress
341 | MCL-0346 | O&M | A | A3 | East | 3 |  |  | Providing, Laying Upgradation of 12'' dia UPVC Sewer Line and 4" dia. DI K7 water supply Line at Near Shani Dev Mandir, Extension Basant Vihar ward 3 |  |  |  | Councillor Quota (CQ) | CQ |  |  |  | 955 dt. 06/05/2025 | [8 empty] | 19/G-33 Dt. 15/05/2025 | ESS Elechmech Enterprises | 35.89 | 15/05/2025 | 3 | 20/7/2026 |  |  |  |  | 90 |  | 32.301 | In Progress |  | Earlier site issue. Now work start
342 | MCL-0347 | O&M | A | A3 | East | 4 |  |  | Providing, Laying 10'' dia UPVC Sewer Line at Vivek Dham and 4" dia. DI K7 water supply Line at Vivek Dham & Sant Cheema Singh Nagar ward 4 |  |  |  | Councillor Quota (CQ) | CQ |  |  |  | 1301 dt. 11/08/2025 | [8 empty] | 42/G-33 Dt. 25/09/2025 | Kohinoor Builders | 30.75 | 25/09/2025 | 3 | 30/7/2026 |  |  |  |  | 65 |  | 19.9875 | In Progress |  | Work is in Progress
343 | MCL-0348 | O&M | A | A3 | East | 5 |  |  | Providing Laying 10” UPVC SN-8 Sewer Line and 4” dia. DI K7 water supply Line at Beas Hosiery Complex at East Constituency. Ward 5 |  |  |  | Councillor Quota (CQ) | CQ |  |  |  | 2624 dt. 11/02/2026 | [8 empty] | 87/G-33/XEN/Z-A dt. 24/02/2026 | Friends & Company | 34.1 | 24/02/2026 | 3 | 20/7/2026 |  |  |  |  | 50 |  | 17.05 | In Progress |  | narrow streets manual work in progress
344 | MCL-0349 | O&M | A | A3 | East | 5 |  |  | Providing , Laying 10”dia. UPVC pipe Sewer Line at Flower Vally and 4” dia. DI K7 water supply Line at Flower Vally & Gagandeep colony at East Constituency. Ward No. 5 |  |  |  | Councillor Quota (CQ) | CQ |  |  |  | 2666 dt. 11/02/2026 | [8 empty] | 94/G-33/XEN/Z-A dt. 24/02/2026 | Friends & Company | 33.02 | 24/02/2026 | 3 | 30/7/2026 |  |  |  |  | 80 |  | 26.416 | In Progress |  | narrow streets manual work in progress
345 | MCL-0350 | O&M | A | A3 | East | 6 |  |  | Providing, Laying Upgradation of 12" dia. UPVC SN-8 pipe Sewer Line from Kuldeep Nagar St No. 4 to near Mohalla Clinic ward 6 |  |  |  | Councillor Quota (CQ) | CQ |  |  |  | 949 dt. 06/05/2025 | [8 empty] | 20/G-33 Dt. 15/05/2025 | ESS Elechmech Enterprises | 31.46 | 15/05/2025 | 3 | 30/7/2026 |  |  |  |  | 75 |  | 23.595 | In Progress |  | Work is in Progress
346 | MCL-0351 | O&M | A | A3 | East | 6 |  |  | Providing, Laying ,Upgradation of sewer line NP-3 16'' Shere punjab School to Kailash Nagar Road, 4" dia. DI K7 W/s Line at Janta Colony, 6" dia. DI K7 w/s Line at Lucky Enclave to Basti Jodhewal Chownk ward 6 |  |  |  | Councillor Quota (CQ) | CQ |  |  |  | 2027 dt. 13/10/2025 | [8 empty] | 55/XEN/Z-A Dt. 13/10/2025 | Kohinoor Builders | 39.15 | 13/10/2025 | 3 | 31.07.2026 |  |  |  |  | 90 |  | 35.235 | In Progress |  | Work is in Progress
347 | MCL-0352 | O&M | A | A3 | East | 6 |  |  | Providing laying Water Supply Line & Sewer Line at Kailash Nagar to Gehlewal and its Branch lines in East Constituency Zone-A |  |  |  | MC Funds / General Quota | GQ |  |  |  | 3386 dt. 05/12/2024 | [8 empty] | 66/G-33 Dt. 05/12/2024 | M/s Rajdeep Enterprises | 46.33 | 12-05-2024 | 3 | [5 empty] | 60 |  | 27.798 | In Progress |  | Balance work Case sent for site change. E.comp. No. 404820
348 | MCL-0353 | O&M | A | A4 | North | 86 |  |  | Construction of Storm Water Disposal Well in Near Shani Mandir, Shivpuri Pully Ward No. 86 |  |  |  | Councillor Quota (CQ) | CQ | [12 empty] | 43/G-33 Dt. 25/09/2025 | M/s Kohinoor Builders | 29.13 | 30/09/2025 | 3 | 30/7/2026 |  |  |  |  | 95 |  | 27.6735 | In Progress |  | Work in Progress
349 | MCL-0354 | O&M | A | A4 | North | 86 |  |  | Construction of Storm Water Disposal Well in Near Gandhi Nagar Pully Ward No. 86 |  |  |  | Councillor Quota (CQ) | CQ |  |  |  | 1445 11/08/2025 | [8 empty] | 46/G-33 Dt. 25/09/2025 | M/s Kohinoor Builders | 22.76 | 30/09/2025 | 3 | 30/6/2026 |  |  |  |  | 95 |  | 21.622 | In Progress |  | Work in Progress
350 | MCL-0355 | O&M | A | A4 | North | 88 |  |  | Making of Dispossal well at Shivpuri Pulli at ward no 88. |  |  |  | Councillor Quota (CQ) | CQ | [12 empty] | 61/G-33 Dt. 03/11/2025 | M/s Kohinoor Builders | 24.03 | 11-08-2025 | 1 | 30/6/2026 |  |  |  |  | 95 |  | 22.8285 | In Progress |  | Work in Progress
351 | MCL-0356 | O&M | A | A4 | North | 70,88,89 |  |  | Construction of Toilet Set in Ward No. 70,88,89 (under SBM 2.0) |  |  |  | SBM (Swachh Bharat Mission) | SBM | [12 empty] | 63/G-33 Dt. 03/11/2025 | M/s Ess Elecmech Enterprises | 28.7 | 11-10-2025 | 2 | 30/7/2026 |  |  |  |  | 45 |  | 12.915 | In Progress |  | site issue
352 | MCL-0357 | O&M | A | A4 | North | 89 |  |  | Rehabilitation/Diversion of Existing Sewer line with Dia 18" RCC HDPE Pipe at Janjh Ghar Road and Manna Singh Nagar to close the Dhakka colony outlet point fall in Buddah Daria in Ward no. 89 |  |  |  | Councillor Quota (CQ) | CQ | [12 empty] | 77/G-33 Dt. 30/01/2026 | M/s Joytee Builders | 55.86 | 02-05-2026 | 3 | 10-01-1900 |  |  |  |  | 60 |  | 33.516 | In Progress |  | balance work will be done after monsoon
353 | MCL-0358 | O&M | A | A4 | North | 89 |  |  | Prov. & Laying of Sewer Line at Nalli Mohalla Chowani Mohalla Shani Mandir Piru Banda Mohalla Ward No. 89 |  |  |  | MC Funds / General Quota | GQ | [12 empty] | 90/G-33 Dt. 24/02/2026 | Surya Construction | 30.63 | 28/02/2026 | 4 | 15/10/2026 |  |  |  |  | 20 |  | 6.126 | In Progress |  | narrow streets manual work in progress
354 | MCL-0359 | O&M | A | A4 | North | 88 |  |  | Rehablitation of sewer line at Surinder Nagar Chand Cinena Adjoining Petrol Pump & Noor Maszid Ward No. 88 |  |  |  | Councillor Quota (CQ) | CQ | [12 empty] | 93/G-33 Dt. 24/02/2026 | ESS Elechmech Enterprises | 39.63 | 28/02/2026 | 4 | 30/10/2026 |  |  |  |  | 15 |  | 5.9445 | In Progress |  | narrow streets manual work in progress
355 | MCL-0360 | O&M | A | A4 | North | 8,86 |  |  | Making of additional manhole scaver points others miscellaneous works in ward no. 8 & 86 |  |  |  | Councillor Quota (CQ) | CQ | [12 empty] | 82/G-33 Dt. 24/02/2026 | Prince Sharma | 29.03 | 30-02-2026 | 3 | 15/7/2026 |  |  |  |  | 35 |  | 10.1605 | In Progress |  | maintenance type work
356 | MCL-0361 | O&M | A | A4 | North | 86 |  |  | Rough Cost Estimate Prov. Laying/Up-gradation and mtc. of Water Supply & Sewer Line At Different Localities of Ward No. 8 and 86. |  |  |  | MC Funds / General Quota | GQ | [12 empty] | 98/G-33 Dt. 24/02/2026 | RS Builders | 23.59 | 03-03-2026 | 3 | 15/7/2026 |  |  |  |  | 10 |  | 2.359 | In Progress |  | Material is reached at site
357 | MCL-0362 | O&M | A | A4 | North | 8 |  |  | Rough Cost Estimate Prov. Laying of Sewer Line and Water Supply Line in Sarvanand Colony Ward No. 8 |  |  |  | MC Funds / General Quota | GQ | [12 empty] | 89/G-33 Dt. 24/02/2026 | Prince Sharma | 18.7 | 28/02/2026 | 3 | 07-05-2026 |  |  |  |  | 80 |  | 14.96 | In Progress |  | Work in Progress
358 | MCL-0363 | O&M | A | A4 | North | 88 |  |  | Up- Gradartion of Water Supply Line in Fatehgarh Mohalla Near Noori Maszid Ward No. 88 |  |  |  | MC Funds / General Quota | GQ | [12 empty] | 102/G-33 Dt. 02/03/2026 | Kohinoor Builders | 10.32 | 03-05-2026 | 3 | 15/11/2026 |  |  |  |  | 5 |  | 0.516 | In Progress |  | Work will be started after rain
359 | MCL-0364 | O&M | A | A4 | North | 95 |  |  | Providing & Installation of 25 HP Straight Bore T/Well Guru Har Rai Nagar Ward No. 95 |  |  |  | MC Funds / General Quota | GQ | [12 empty] | 92/G-33 Dt. 24/02/2026 | Rajdeep Enterprises | 12.09 |  | 3 | [7 empty] | 0 | Not Started |  | File sent for change of site
360 | MCL-0365 | O&M | A | A4 | North | 86 |  |  | Providing & Installation of 25 HP Straight Bore Tubewell against failed Tubewell In Dr. Ashwani Clinic Ward No. 86 |  |  |  | MC Funds / General Quota | GQ | [12 empty] | 91/G-33 Dt. 24/02/2026 | Rajdeep Enterprises | 10.74 |  | 3 | [7 empty] | 0 | Not Started |  | site issue
361 | MCL-0366 | O&M | A | A4 | North | 87 |  |  | Rehabilitation Missing Link of Water Supply line and Sewer line in Ward No. 87 |  |  |  | MC Funds / General Quota | GQ | [12 empty] | 58/G-33 Dt. 02/12/2024 | Rajdeep Enterprises | 26.46 | 15/12/2024 | 2 | [5 empty] | 95 |  | 25.137 | In Progress |  | File sent for 25% Enhancement
362 | MCL-0367 | O&M | A | A4 | North | 86 |  |  | Prov. Laying of Water Supply Line and Sewer Line in Bal Singh Nagar Gli No. 8 and Pritampuri, Ward No. 86. |  |  |  | Councillor Quota (CQ) | CQ | [12 empty] | 62/G-33 Dt. 05/12/2024 | surya contractor | 26.24 | 12-08-2024 | 3 | [5 empty] | 95 |  | 24.928 | In Progress |  | File sent for 25% Enhancement
363 | MCL-0368 | O&M | A | A4 | North | 85 |  |  | Providing & Laying 4" Water Supply Line at Gandhi Nagar, ward no.85. |  |  |  | Councillor Quota (CQ) | CQ | [12 empty] | 11/G-33 Dt. 28/04/2025 | Bedi Pump Store | 47.42 | 05-05-2025 | 3 | 15/7/2026 |  |  |  |  | 85 |  | 40.307 | In Progress |  | narrow streets manual work in progress
364 | MCL-0369 | O&M | A | A4 | North | 85 |  |  | Rehablitation of Water Supply line Due to Water Conteminations at Basant Nagar/ Gandhi Nagar, Ward no.85 |  |  |  | Councillor Quota (CQ) | CQ | [12 empty] | 48/G-33 Dt. 25/09/2025 | Bedi Pump Store | 47.11 | 30/09/2025 | 3 | 15/7/2026 |  |  |  |  | 80 |  | 37.688 | In Progress |  | narrow streets manual work in progress
365 | MCL-0370 | O&M | A | A4 | North | 1,95 |  |  | Rehabilitation/Missing link of Water Supply line and Sewer Line in Different Localities Ward No.1 & 95. |  |  |  | Councillor Quota (CQ) | CQ | [12 empty] | 62/G-33 Dt. 03/11/2025 | Dynamic Tiles | 26.96 | 11-08-2025 | 2 | 15/7/2026 |  |  |  |  | 80 |  | 21.568 | In Progress |  | Work in Progress
366 | MCL-0371 | O&M | A | A4 | North | 84 |  |  | Rehablitation of Water Supply line Due to Water Conteminations at Various Areas in North Consitituency Like Dakka Colony, Peeru Mohalla, Karabara Chownk & Badour House |  |  |  | Councillor Quota (CQ) | CQ | [12 empty] | 81/G-33 Dt. 24/02/2026 | Prince Sharma | 34.08 | 28/02/2026 | 3 | 15/7/2026 |  |  |  |  | 40 |  | 13.632 | In Progress |  | Work in Progress
367 | MCL-0372 | O&M | A | A4 | North | 88 |  |  | Rough Cost Estimate Prov. Laying Up-gradation of water supply line and sewer line at Sekhewal 60' Road, Ward No. 88. |  |  |  | Councillor Quota (CQ) | CQ | [12 empty] | 96/G-33 Dt. 24/02/2026 | Sushil Kumar Contractor | 30.03 | 03-07-2026 | 4 | 30/7/2026 |  |  |  |  | 10 |  | 3.003 | In Progress |  | Work in Progress
|  | O&M |  |  | East | 7 | Water Supply |  | Providing & Installation of 25 HP Straight Bore T/Well at Gujjar Colony, Jagirpur Road in Ward No. 7 (against failed tubewell) (Now Jain Colony) . |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 12.62
368 | MCL-0373 | O&M | B | B3 | East | 7 | Water Supply |  | Providing & Installing of 25 HP Deep straight Bore Tubewell at Atal Nagar in Ward No. 7 (MP LAD Scheme). |  |  | 1 | MPLAD Funds | MP LAD | Awarded | 13.5 | [10 empty] | 114/G33 06-03-2026 | Rajdeep Enterprises | 10.84 | 11-10-2025 | 3 | 07-10-2026 |  |  |  |  | 90 |  | 9.756 | In Progress |  | Work in progress
369 | MCL-0374 | O&M | B | B3 | East | 7 | Water Supply |  | Rough Cost Estimate for P/L of 4” dia DIK7 water supply line at Atal Nagar, St. No. 2,3,4 & 5 in W. No. 7. |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 61.99 | [10 empty] | 66/G33 07-11-2025 | CNC Precision Engineering | 60.82 | 10/11/1015 | 3 | 31/08/2026 |  |  |  |  | 25 |  | 15.205 | In Progress |  | Work in progress
370 | MCL-0375 | O&M | B | B3 | East | 11 | Water Supply |  | Rough Cost Estimate for Upgradation of 4” dia DIK7 water supply line in various areas of W. No. 9. |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 38.61 | [10 empty] | 257/G33 17-03-2025 | CNC Precision Engineering | 37.95 | 20/03/2025 | 3 | 07-10-2026 |  |  |  |  | 80 |  | 30.36 | In Progress |  | Work in progress
371 | MCL-0376 | O&M | B | B3 | East | 13 | Water Supply |  | Rough cost estimate for Up gradation of 4” dia DIK-7 water supply line and missing link of 8” UPVC sewer line in various areas of W. No. 13 |  |  | 2 | MC Funds / General Quota | GQ | Awarded | 95.16 | [10 empty] | 45/G33 14-05-2025 | A.B. Construction Co. | 75.93 | 15/05/2025 | 4 | 15/7/2026 |  |  |  |  | 90 |  | 68.337 | In Progress |  | Work in progress
372 | MCL-0377 | O&M | B | B3 | East | 13 | Water Supply |  | Rough cost estimate for Up gradation of 4” & 6” dia DIK-7 water supply line in various areas of W. No. 13 |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 20.17 | [10 empty] | 39/G33 14-05-2025 | CNC Precision Enginering | 17.07 | 15/05/2025 | 2 | 15/7/2026 |  |  |  |  | 90 |  | 15.363 | In Progress |  | Work in progress
373 | MCL-0378 | O&M | B | B3 | East | 14 | Water Supply |  | Upgradation of 4” dia DIK7 water supply line and 8” & 12” UPVC Sewer line at New Karamsar Colony in W. No. 14. |  |  | 1 | Councillor Quota (CQ) | CQ | Awarded | 81.01 | [10 empty] | 146/G33 07-05-2026 | Manmohan Singh Contractor | 60.76 | 05-10-2026 | 4 | 15/11/2026 |  |  |  |  | 50 |  | 30.38 | In Progress |  | Balance work will be done after rainy season
374 | MCL-0379 | O&M | B | B3 | East | 19 | Sewerage |  | Prov/Laying of 12” UPVC pipe at Kirti Nagar, St. No. 3&4, at W. No. 19 in East Constituency (Upgradation). |  |  | 1 | Councillor Quota (CQ) | CQ | Awarded | 13.94 | [10 empty] | 119/G33 06-03-2026 | Ess Elechmech Enterprises | 9.67 | 03-07-2026 | 2 | 31/07/2026 |  |  |  |  | 0 |  | 0 | Not Started |  | Material reached at site
375 | MCL-0380 | O&M | B | B3 | East | 14,15,18&29 | Water Supply |  | Rough Cost Estimate for P/L of 4” dia DIK7 water supply line in various wards of East Constituency (Missing Link). |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 18.72 | [10 empty] | 269/G33 17-03-2025 | CNC Precision Engineering | 18.4 | 20/3/2026 | 3 | 31/07/2026 |  |  |  |  | 80 |  | 14.72 | In Progress |  | Work in progress
376 | MCL-0381 | O&M | B | B3 | East | 17 | Water Supply |  | Providing & Installing of 25 HP Deep straight Bore Tubewell at Shiv Shankar Colony in Ward No. 17. |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 12.62 | [10 empty] | 125/G33 25-03-2026 | Bedi Pimp Store | 10.08 | 26/3/2026 | 3 | 15/7/2026 |  |  |  |  | 60 |  | 6.048 | In Progress |  | Work in progress
377 | MCL-0382 | O&M | B | B3 | East | 19 | Sewerage |  | Pro/Laying of 12” UPVC Pipe at 177 Welfare Society, Sector-39, Ward No-19 in East Constituency. (Upgradation). |  |  | 1 | Councillor Quota (CQ) | CQ | Awarded | 9.21 | [10 empty] | 136/G33 07-05-2026 | Bedi Pump Store | 6.53 | 05-09-2026 | 3 | 15/7/2026 |  |  |  |  | 90 |  | 5.877 | In Progress |  | Work in progress
378 | MCL-0383 | O&M | B | B3 | East | 20 | Water Supply |  | Providing & Installing of 12.5 HP Deep straight Bore Tubewell at Bhola Colony, Nr. Gurdwara Sahib in Ward No. 20. |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 5.82 | [10 empty] | 99/G33 06-03-2026 | Sai Enterprises | 4.82 | 03-10-2026 | 2 | 31/07/2026 |  |  |  |  | 0 |  | 0 | Not Started |  | Work will start next week
379 | MCL-0384 | O&M | B | B3 | East | 20 | Water Supply |  | Rough cost Estimate for providing & Installing of 25 HP Deep straight Bore Tubewell at Mahajan Vihar in Ward No. 20. |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 12.62 | [10 empty] | 101/G33 06-03-2026 | CNC Precision Engineering | 10.56 | 03-06-2026 | 3 | 07-10-2026 |  |  |  |  | 95 |  | 10.032 | In Progress |  | Work in progress
380 | MCL-0385 | O&M | B | B4 | East | 26 | Water Supply |  | Pro/Laying DIK-7 water supply line 6”, 4” at Focal Point, Phase-4A (Replace of old water supply line) W. No. 26, in East Constituency. |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 86.33 | [10 empty] | 92/G33 19-01-2026 | Baljit Singh Gill | 76.33 | 20/1/2026 | 3 | [7 empty] | 0 | Delayed/Held Up |  | Work stopped by MLA saab
381 | MCL-0386 | O&M | B | B4 | East | 26 | Water Supply |  | Providing & Installing of 25 HP Deep straight Bore Tubewell at Rajiv Gandhi Colony in Ward No. 26. |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 12.64 | [10 empty] | 105/G33 06-03-2026 | ESS Elechmech Enterprises | 10.46 | 03-06-2026 | 3 | 07-05-2026 |  |  |  |  | 90 |  | 9.414 | In Progress |  | Work in progress
382 | MCL-0387 | O&M | B | B4 | East | 26 | Water Supply |  | Rough Cost Estimate for Prov/Installation of New 25HP Deep Straight Bore Tubewell at Rajiv Gandhi Colony, HE Colony, Ward No. 26 (M.P Quota) in East Constituency. |  |  | 1 | MPLAD Funds | MP Quota | Awarded | 12.59 | [10 empty] | 135/G33 07-05-2026 | Rajdeep Enterprises | 9.89 | 05-10-2026 | 3 | 30/8/2026 |  |  |  |  | 0 |  | 0 | Not Started |  | Work will start by 1/7/2026
383 | MCL-0388 | O&M | B | B3 | East | 29 | Water Supply |  | Providing & Installing of 25 HP Deep straight Bore Tubewell at L.I.G Flat in Ward No. 29 (MP LAD Scheme). |  |  | 1 | MPLAD Funds | MP LAD | Awarded | 13.5 | [10 empty] | 102/G33 06-03-2026 | Rajdeep Enterprises | 10.84 | 03-07-2026 | 3 | [5 empty] | 0 |  | 0 | Delayed/Held Up |  | Delyed due to site dispute
384 | MCL-0389 | O&M | B | B3 | East | 29 | Water Supply |  | Providing & Installing of 25 HP Deep straight Bore Tubewell at Vishkarma Nagar, Nr. Baba Deep Singh Gurdwara in Ward No. 29 (against 25 HP failed tubewell) |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 12.62 | [10 empty] | 142/G33 07-05-2026 | Bedi Pump Store | 9.96 | 05-10-2026 | 4 | 30/8/2026 |  |  |  |  | 0 |  | 0 | Not Started |  | Work will start by 1/7/2026
385 | MCL-0390 | O&M | B | B3 | East | 7 | Sewerage |  | Rough Cost Estimate for Upgradation of 10" & 12” UPVC SN-8 sewer line at Indra Colony & Chanderlok Colony in W. No. 7. |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 87.88 | [10 empty] | 267/G33 17-03-2025 | CNC Precision Engg. | 65.92 | 20/3/2025 | 3 | 20/7/2026 |  |  |  |  | 70 |  | 46.144 | In Progress |  | Work in progress
386 | MCL-0391 | O&M | B | B3 | East | 7 | Sewerage |  | Rough Cost Estimate for Upgradation of 8” UPVC SN-8 sewer line at Golden Colony in W. No. 7. |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 70.1 | [10 empty] | 265/G33 17-03-2025 | CNC Precision Engg. | 52.58 | 20/3/2025 | 3 | 30/09/2026 |  |  |  |  | 25 |  | 13.145 | In Progress |  | Work in progress
|  | O&M | B | B3 | East | 11 | Sewerage |  | Upgradation of 8" UPVC SN-8 sewer line at Gulabi Bagh, Prem Vihar, Charan Nagar & Juneja Colony in W. No. 11, 12 & 13. |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 34.7
387 | MCL-0392 | O&M | B | B3 | East | 17 | Water Supply |  | Prov/Laying of 6" DIK7 water suplly line at Main Tibba Road Dump Site in W. No. 17 (GQ) |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 43.87 | [10 empty] | 143/G33 07-05-2026 | Friends and Company | 36.49 | 05-08-2026 | 3 | 15/11/2026 |  |  |  |  | 0 |  | 0 | Not Started |  | Work will start after monsoon
388 | MCL-0393 | O&M | B | B3 | East | 17 | Sewerage |  | Prov/Laying of 30" RCC NP3 sewer line at Mahavir jain (Puneet Nagar) in W. No. 17 (GQ) |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 52.54 | [10 empty] | 144/G33 07-05-2026 | Surya Construction | 38.35 | 05-08-2026 | 3 | 15/10/2026 |  |  |  |  | 0 |  | 0 | Not Started |  | Work will start after monsoon
389 | MCL-0394 | O&M | B | B3 | East | 17 | Sewerage |  | Prov/Laying of 18" RCC NP3 sewer line at Main Tibba Road Dump Site in W. No. 17 (GQ) |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 59.84 | [10 empty] | 140/G33 07-05-2026 | Surya Construction | 43.68 | 05-08-2026 | 4 | 15/11/2026 |  |  |  |  | 0 |  | 0 | Not Started |  | Work will start after monsoon
390 | MCL-0395 | O&M | B | B3 | East | 19 | Sewerage |  | Pro/Laying of 12” UPVC pipe at GRD Colony, Sector-39, W. No. 19, in East Constituency. (Upgaddation). |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 60.13 | [10 empty] | 91/G33 19-01-2026 | Glisten | 40.23 | 20/1/2026 | 3 | 20/7/2026 |  |  |  |  | 90 |  | 36.207 | In Progress |  | Work in progress
391 | MCL-0396 | O&M | B | B3 | East | 19 | Sewerage |  | Prov/Laying of 12” UPVC pipe at Sec-39, Back side Pal Petrol Pump in W. No. 19 in East Constituency (Upgradation). |  |  | 1 | Councillor Quota (CQ) | CQ | Awarded | 14.1 | [10 empty] | 106/G33 06-03-2026 | R.S. Builders | 10.17 | 03-09-2026 | 3 | 15/7/2026 |  |  |  |  | 60 |  | 6.102 | In Progress |  | Work in progress
392 | MCL-0397 | O&M | B | B3 | East | 20 | Sewerage |  | Rough Cost Estimate for Prov/Laying of 8" UPVC Sewer line at New GRD Nagar in Ward No. 16 (Site Changed) |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 16.35 | [10 empty] | 145/G33 9/18/2024 | The Sutlej Co-Op L&C Society Ltd. | 12.95 | 20/9/2024 | 3 | 30/10/2026 |  |  |  |  | 50 |  | 6.475 | In Progress |  | File Approved in F&CC dated:- 24/06/2026 for change of site now work started again
393 | MCL-0398 | O&M | B | B4 | East | 28 | Sewerage |  | Pro/Laying of 12” UPVC pipe at Street No. ¼, Heera Nagar, in W. No. 28 in East Constituency. |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 6.93 | [10 empty] | 84/G33 07-11-2025 | Rajdeep Enterprises | 4.95 | 11-10-2025 | 2 | 20/7/2026 |  |  |  |  | 20 |  | 0.99 | In Progress |  | Work held due to Super Suction work
394 | MCL-0399 | O&M | B | B4 | East | 26 | Sewerage |  | Construction of Additional Machine hole chamber at Vishkarma Colony in W. No. 26. |  |  | 1 | Councillor Quota (CQ) | CQ | Awarded | 1.92 | [10 empty] | 147/G33 07-05-2026 | K.B. Builders | 1.37 | 05-09-2026 | 2 | 31/7/2026 |  |  |  |  | 0 |  | 0 | Not Started
395 | MCL-0400 | O&M | B | B3 | East | 29 | Water Supply |  | Prov/Laying of 8” UPVC Sewer line and 4” dia DIK7 water supply line missing link at various streets of G.A.D Nagar in W. No. 29 (C.Q). |  |  | 2 | Councillor Quota (CQ) | CQ | Awarded | 7.02 | [10 empty] | 95/G33 27/1/2026 | Sushil Contractor | 5.27 | 30/1/2026 | 2 | 15/7/2026 |  |  |  |  | 80 |  | 4.216 | In Progress |  | Work in progress
396 | MCL-0401 | O&M | B | B3 | East | B | Sewerage |  | Upgradation of M/Hole Chamber of main 48” Sewer line at Dump Site (Tibba Road). |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 24.83 | [10 empty] | 124/G33 25-03-2026 | Kohinoor Builders | 18.33 | 25/3/2026 | 2 | 15/10/2026 |  |  |  |  | 40 |  | 7.332 | In Progress |  | Balance Work will start after monsoon
397 | MCL-0402 | O&M | B | B3 | East | B3 | Sewerage |  | Construction of Raising of manhole hole chambers and Prov and fixing of manhole cover sets i.e EHD, HD, MD sets in different localities of East Constituency (GQ) |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 36.65 | [10 empty] | 131/G33 07-05-2026 | Prince Sharma | 24.64 | 05-10-2026 | 3 | 15/11/2026 |  |  |  |  | 0 |  | 0 | Not Started |  | Work will start after monsoon
398 | MCL-0403 | O&M | B | B3 | East | B | Sewerage |  | Prov.& Laying Of 1100MM RCC NP-3 class Sewer line at Tajpur MPS chowk to Tajpur road Police Chonky Nr. Central Jail (G.Q) |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 191.28 | [10 empty] | 130/G33 07-05-2026 | Ludhiana Construction Company | 132.75 | 05-10-2026 | 6 | 07-10-2026 |  |  |  |  | 30 |  | 39.825 | In Progress |  | Work in progress
399 | MCL-0404 | O&M | B | B3 | East | B3 | Sewerage |  | Providing & Laying of 250mm, 300mm, 400mm & 600mm RCC NP3 HDPE Line & UPVC SN-8 Sewer line at Mahavir Jain Textile Colony. |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 177.32 | [10 empty] | 145/G33 07-05-2026 | Ludhiana Construction Company | 126.57 | 05-07-2026 | 6 | 28/2/2027 |  |  |  |  | 0 |  | 0 | Not Started |  | Work will start after monsoon
400 | MCL-0405 | O&M | B | B3 | East | B | Sewerage |  | Prov.& Laying Of 1000MM RCC NP-3 class Sewer line at Vardhman Chowk to MPS (Tajpur Road) in Sub Zone-B3. |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 256.39 | [10 empty] | 149/G33 21-05-2026 | Ludhiana Construction Company | 177.93 | 22/5/2026 | 6 | 31/12/2026 |  |  |  |  | 0 |  | 0 | Not Started |  | Work will start after work order no. 130
|  | O&M | B | B3 | East | B3 | Sewerage |  | Providing & Laying of 200mm, 400mm, 800mm & 900mm RCC NP3 Sewer line at Jaswal Complex. |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 305.62
|  | O&M | B | B3 | East | B3 | Sewerage |  | Providing & Laying of 200mm, 400mm & 450mm RCC NP3 HDPE Line & UPVC SN-8 Sewer line at Mahavir Jain Complex. |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 300.83
401 | MCL-0406 | O&M | B | B1 | Central | 75 | Water Supply |  | Providing & Installation of (200 mm) 25 HP Deep Straight Bore Tubewell at Gurdware wali gali in W. No.75 (Against Failed T/W) (Central Constituency) |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 12.45 | [10 empty] | 77/G33 07-11-2025 | Baljit Singh Gill | 10.91 | 11-10-2025 | 3 | [5 empty] | 0 |  | 0 | Not Started |  | Due to site issue (not adequate space)
|  | O&M | B | B1 | Central | 75 | Water Supply |  | Prov & Inst. of 12.5 HP straight bore tubewell at Arjan meet wali gali, islam ganj in ward No. 75. |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 6.41
402 | MCL-0407 | O&M | B | B1 | Central | 80 | Water Supply |  | Prov/Inst. of 12.5 HP Straight bore Tubewell at st no 10, Hargobind Nagar in W. No. 53 (Against Failed T/w) (Central Constituency). |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 6.53 | [10 empty] | 125/G33 9/18/2024 | Rana Electrical Works | 5.56 | 20/9/2024 | 2 | [5 empty] | 0 |  | 0 | Not Started |  | Due to site issue (not adequate space)
403 | MCL-0408 | O&M | B | B1 | Central | 80 | Water Supply |  | Prov/Inst. of 25 HP Straight bore Tubewell at Gabe wali Gali, Kidwai Nagar in W. No. 53 (Against Failed T/w) (Central Constituency). |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 12.34 | [10 empty] | 03/G33 11-04-2025 | Bedi Pump Store | 10.17 | 13/4/2025 | 3 | [5 empty] | 0 |  | 0 | Not Started |  | Due to site issue (not adequate space)
|  | O&M | B | B1 | Central | 63 | Sewerage |  | Raising of Slab of M/H in St. No. 6-1/2, Janakpuri in W. No. 63 (Old). |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 4.13
|  | O&M | B | B1 | Central | 76 | Sewerage |  | Prov & Laying of Additional Machine hole chamber in ward No. 76. |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 5.08
|  | O&M | B | B1 | Central | 79 | Sewerage |  | Prov & Laying of Additional Machine hole chamber in ward No. 79. |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 4.62
404 | MCL-0409 | O&M | B | B1 | Central | B1 | Sewerage |  | Repair & Upgaradation of Shingar Disposal. |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 27.24 | [10 empty] | 137/G33 07-05-2026 | G.K. Contractor | 20.2 | 05-10-2026 | 3 | 30/8/2026 |  |  |  |  | 40 |  | 8.08 | In Progress |  | Work in progress
405 | MCL-0410 | O&M | B | B2 | Sahnewal | 25 | Water Supply |  | Providing & Installing of 40 HP Rig Bore Tubewell at Phase-VII Focal Point Water Tanki Wala Park Near Marshell Kanda Ward No.28 (Against Failed Tubewell). |  |  | 1 | SIDBI | MDF/GQ (SIDBI) | Awarded | 23.99 | [10 empty] | 19/G33 11-04-2025 | CNC Precision Engineering | 21.03 | 04-11-2025 | 3 | 07-10-2026 |  |  |  |  | 90 |  | 18.927 | In Progress |  | Work in progress
406 | MCL-0411 | O&M | B | B2 | Sahnewal | 25 | Water Supply |  | Missing Links For 4" dia DIK-7 water supply at Different Areas Of Sub Zone-B2. |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 74.12 | [10 empty] | 16/G33 11-04-2025 | Friends & Co. | 71.64 | 04-12-2025 | 4 | 07-10-2026 |  |  |  |  | 85 |  | 60.894 | In Progress |  | Work in progress
407 | MCL-0412 | O&M | B | B2 | Sahnewal | 25 | Water Supply |  | Providing & Installing of 40 HP Rig Bore Tubewell at Phase-VIII Focal Point opp Perfect Dyeing. |  |  | 1 | SIDBI | MDF/GQ (SIDBI) | Awarded | 24 | [10 empty] | 116/G33 06-03-2026 | CNC Precision Engineering | 19.94 | 03-07-2026 | 3 | 07-10-2026 |  |  |  |  | 90 |  | 17.946 | In Progress |  | Work in progress
408 | MCL-0413 | O&M | B | B2 | Sahnewal | 25 | Water Supply |  | Providing & Installing of 40 HP Rig Bore Tubewell at Tikona park Near Metro Tyre Phase-V. |  |  | 1 | SIDBI | MDF/GQ (SIDBI) | Awarded | 24 | [10 empty] | 123/G33 25-03-2026 | CNC Precision Engineering | 19.94 | 25/3/2026 | 3 | 07-10-2026 |  |  |  |  | 90 |  | 17.946 | In Progress |  | Work in progress
409 | MCL-0414 | O&M | B | B2 | Sahnewal | 21 | Sewerage |  | Upgradation of sewer line in W. No. 24 and 25 (50% - 50% Work Alloted). |  |  | 1 | MC Funds / General Quota | GQ | [12 empty] | 25/G33 17-04-2025 | Deepak Madaan | 32.9 | 20/4/2025 | 4 | 07-10-2026 |  |  |  |  | 90 |  | 29.61 | In Progress |  | Work in progress
410 | MCL-0415 | O&M | B | B2 | Sahnewal | 23 | Sewerage |  | Upgradation of sewer line in W. No. 25, 26 and 27. |  |  | 1 | MC Funds / General Quota | GQ | [12 empty] | 11/G33 11-04-2025 | Friends & Co. | 73.8 | 04-11-2025 | 4 | 07-10-2026 |  |  |  |  | 90 |  | 66.42 | In Progress |  | Work in progress
411 | MCL-0416 | O&M | B | B2 | Sahnewal | 25 | Sewerage |  | Upgradation of 18” Sewer line from Shiv Colony to Devgan Kanda Sua Road in Sub Zone-B2 (Sahnewal Constituency). |  |  | 1 | Councillor Quota (CQ) | CQ | [12 empty] | 122/G33 06-03-2026 | Bharat Bhushan Contractor | 48.37 | 03-10-2026 | 4 | 15/8/2026 |  |  |  |  | 0 |  | 0 | Not Started |  | Material reached at site
412 | MCL-0417 | O&M | B | B2 | Sahnewal | B2 |  |  | Prov/Laying of RCC NP3 HDPE Lining UPVC SN-8 & HDPE Pipes of dia 250 MM, 300 MM, 400 MM & 450 MM From M.C Limit G.T Road (Ludhiana To Delhi NH) Near Eastman Cast and Forge Ltd. to UCO Bank Juginan Road Ldh. |  |  | 1 | MC Funds / General Quota | GQ | [12 empty] | 10/G33 11-04-2025 | Deepak Madaan | 130.3 | 04-11-2025 | 6 | [5 empty] | 0 |  | 0 | Delayed/Held Up |  | NOC Pending from NHAI
413 | MCL-0418 | O&M | B | B2 | Sahnewal | B2 | Sewerage |  | Providing & Laying Of 8",10",12" UPVC SN-8 & 16" RCC NP-3 HDPE Lining Sewer Line Missing Links at different places in sub zone B2. |  |  | 1 | MC Funds / General Quota | GQ | [12 empty] | 14/G33 11-04-2025 | Deepak Madaan | 53.38 | 04-11-2025 | 4 | 15/7/2026 |  |  |  |  | 90 |  | 48.042 | In Progress |  | Work in progress
414 | MCL-0419 | O&M | B | B2 | Sahnewal | B2 | Sewerage |  | Providing & Laying Of 8",10",12" UPVC SN-8 & 16" RCC NP-3 HDPE Lining Sewer Line Missing Links at different places in sub zone B2. |  |  | 1 | MC Funds / General Quota | GQ | [12 empty] | 15/G33 11-04-2025 | Friends & Co. | 68.47 | 04-11-2025 | 4 | 15/7/2026 |  |  |  |  | 85 |  | 58.1995 | In Progress |  | Work in progress
415 | MCL-0420 | O&M | B | B2 | Sahnewal | B2 | Sewerage |  | Prov./Laying of 900 mm dia RCC NP3 Sewer line at main chandigarh road near Police Colony Chowk. |  |  | 1 | MC Funds / General Quota | GQ | [12 empty] | 129/G33 07-05-2026 | Rajdeep Enterprises | 64.24 | 20/5/2026 | 4 | [5 empty] | 0 |  | 0 | Delayed/Held Up |  | NOC Pending from NHAI
416 | MCL-0421 | O&M | B | B4 | South | 32 | Water Supply |  | Rough Cost Estimate For Prov/Installation of 40 HP Straight Bore Tube well at Sherpur Khurd, Backside Kabristaan , Ward No- 22 in South Constituency (Against Failed T/Well Tanki wala). |  |  | 1 | MC Funds / General Quota | GQ | [12 empty] | 48/G33 20/05/2025 | Guru Kirpa & Co. | 21.05 |  | 3 | [7 empty] | 0 | Not Started |  | Not Started, Notice issued to contractor.
417 | MCL-0422 | O&M | B | B4 | South | 32 | Water Supply |  | Prov/Laying of DIK7 4" & 6" Water Supply line in various areas in W. No. 22. |  |  | 1 | MDF / SASCI | MDF | [12 empty] | 35/G33 05-05-2025 | Bedi Pump Store | 92.1 | 05-07-2025 | 3 | 15/7/2026 |  |  |  |  | 75 |  | 69.075 | In Progress |  | Work in progress
418 | MCL-0423 | O&M | B | B4 | South | 32 | Water Supply |  | Upgradation of 3” GI Pipe Water Supply Line at old Sherpur Village, Sherpur Khurd, Ward No-22 in South Constituency. |  |  | 1 | MC Funds / General Quota | GQ | [12 empty] | 32/G33 05-05-2025 | Surya Construction | 23.16 | 05-07-2025 | 3 | [7 empty] | 0 | Not Started |  | Work Shifted to Zone-A under CBD as funds not received work not started
419 | MCL-0424 | O&M | B | B4 | South | 32 | Water Supply |  | Prov/Inst. of 3000 ltr. water tanker in Sherpur ward no. 16 (old) 32 (new) under MP LAD Scheme. |  |  | 1 | MPLAD Funds | MP LAD | [12 empty] | 120/G33 06-03-2026 | Ram Parkash Kakar | 1.94 | 03-06-2026 | 2 | 07-05-2026 |  |  |  |  | 0 |  | 0 | Not Started |  | Supply will be provided by 05/7/2026
420 | MCL-0425 | O&M | B | B4 | South | 27 | Sewerage |  | Prov & Laying of 12” UPVC Pipe at Kailash Nagar, St. No. 3-1/2 (Cancer Road Sherpur) in W. No. 27 in South Constituency. |  |  | 1 | Councillor Quota (CQ) | CQ | [12 empty] | 117/G33 06-03-2026 | Ess Elechmech Enterprises | 8.67 | 03-07-2026 | 3 | 15/11/2026 |  |  |  |  | 0 |  | 0 | Not Started |  | Work will start after monsoon
421 | MCL-0426 | O&M | C |  | Atam Nagar | 44 |  |  | Prov./Laying 4” id DIK-7 Water Supply lines at street no.7 Partap Nagar Ward no. 41 old. MC Funds |  |  |  | MC Funds / General Quota | MCL |  |  |  | 518/09.04.2025 | [8 empty] | 1173/G/33 Dated 30-04-2025 | Bedi Pump Store | 8.99 | 30/4/2025 | 2 | 07-10-2026 |  |  |  |  | 60 |  | 5.394 | Delayed/Held Up |  | Work Has been delayed by Councillor
422 | MCL-0427 | O&M | C |  | Atam Nagar | 48 |  |  | Prov./Laying 4” id Dik-7 water supply lines at Bhai Himmat Singh Nagar (ward no. 48) MC Funds |  |  |  | MC Funds / General Quota | MCL |  |  |  | 520/09.04.2025 | [8 empty] | 1174/G/33 Dated 30-04-2025 | Bedi Pump Store | 47.31 | 30/4/2025 | 3 | [5 empty] | 60 |  | 28.386 | Delayed/Held Up |  | Work has been stopped by MLA Sir due to approval of road work
423 | MCL-0428 | O&M | C |  | Atam Nagar | C-1 |  |  | Prov./Installation of 3 nos. 25 hp Submersible T/wells and 2 nos. 12.5 hp Submersible T/wells in Sub Zone C-1 (AFT T/well) |  |  |  | MC Funds / General Quota | MCL |  |  |  | 2812/19.02.2026 | [8 empty] | 1243/G/33 Dated 29.04.2026 | Bedi pump Store | 40.38 | 30/4/2025 | 3 | [5 empty] | 20 |  | 8.076 | In Progress |  | T/well to be Installed Against failed as per requirment
424 | MCL-0429 | O&M | C |  | Atam Nagar | 40 |  |  | Prov./Laying 6" id Dik-7 water supply line at main Maya soap ward no. 40 |  |  |  | MC Funds / General Quota | MCL |  |  |  | 3390/21.04.2026 | [8 empty] | 1258/G/33 Dated 13.05.2026 | Shushil Kumar | 26.85 | 15/05/2026 | 3 | 10-10-2026 |  |  |  |  | 0 |  | 0 | Not Started |  | work to be start after monsoon
425 | MCL-0430 | O&M | C |  | Atam Nagar | 40 |  |  | Prov./Installation of 25 hp New Submersible T/well at street no. 12 1/2 chimeny road Shimlapuri ward no. 40 |  |  |  | MC Funds / General Quota | MCL |  |  |  | 2806/19.02.2026 | [8 empty] | 1269/G/33 Dated 20.05.2026 | JCS Electric works | 10.26 | 22/05/2026 | 3 | 25/08/2026 |  |  |  |  | 0 |  | 0 | Delayed/Held Up |  | Notice issued to contractor for delay in start
426 | MCL-0431 | O&M | C |  | Atam Nagar | 41 |  |  | Prov./Installation of 25 hp Submersible T/well at street no. 13 Shimlapuri (AFT 25 hp T/well)ward no. 41 |  |  |  | MC Funds / General Quota | MCL |  |  |  | 2814/19.02.2026 | [8 empty] | 1270/G/33 Dated 20.05.2026 | Ess Elechmec | 10.36 | 22/05/2026 | 3 | 20/08/2026 |  |  |  |  | 0 |  | 0 | Not Started |  | Material reached at site
427 | MCL-0432 | O&M | C |  | Atam Nagar | 44 |  |  | Upgradation of 10" id UPVC sewer line in SAS Nagar ward no. 44 |  |  |  | MC Funds / General Quota | MCL |  |  |  | 2808/19.02.2026 | [8 empty] | 1233/G/33 Dated 18.03.2026 | Joytee Builedrs | 16.97 |  | 3 | [5 empty] | 0 |  | 0 | Delayed/Held Up |  | Notice issued to contractor for delay in start
428 | MCL-0433 | O&M | C |  | Atam Nagar | 44 |  |  | Upgradation of 12" id UPVC sewer line in Miltary Camp ward no. 44 |  |  |  | MC Funds / General Quota | MCL |  |  |  | 2809/19.02.2026 | [8 empty] | 1234/G/33 Dated 18.03.2026 | ESS Elechmec | 16.42 | 20/03/2026 | 3 | 31/07/2026 |  |  |  |  | 60 |  | 9.852 | In Progress |  | Work in Progress
429 | MCL-0434 | O&M | C |  | Atam Nagar | 41 |  |  | Upgradation of 16" id RCC NP3 HDPE sewer line from Waheguru road to Daba road Dhand Palace ward no.41 |  |  |  | MC Funds / General Quota | MCL |  |  |  | 2781/19.02.2026 | [8 empty] | 1266/G/33 Dated 13.05.2026 | Bharat Bhushan | 68.39 | 13/5/2026 | 3 | 15/11/2026 |  |  |  |  | 60 |  | 41.034 | Delayed/Held Up |  | Work stopped and will start after monsoon
430 | MCL-0435 | O&M | C |  | South | 31 |  |  | Prov./Laying 4" id DIK-7 water supply lines at street no. 9,16,17 Bhagwan nagar ward no. 50 old |  |  |  | MC Funds / General Quota | MCL |  |  |  | 999/06.05.2025 | [8 empty] | 1189/G/33 Dated 14-05-2025 | APEX Developers | 9.9 | 15/05/2025 | 2 | 31/07/2026 |  |  |  |  | 60 |  | 5.94 | In Progress |  | work in progress
431 | MCL-0436 | O&M | C |  | South | 32 |  |  | Prov./Installation of 25 hp new Submersible T/well at street no.22 Makkar colony Dhandari kalan ward no.32 MC fund |  |  |  | MC Funds / General Quota | MCL |  |  |  | 2816/19.02.2026 | [8 empty] | 1238/G/33 Dated 09.04.2026 | Ess Elechmec | 10.61 | 04-10-2026 | 3 | 15/07/2026 |  |  |  |  | 40 |  | 4.244 | In Progress |  | work in progress
432 | MCL-0437 | O&M | C |  | South | C-3 |  |  | Prov./Installation of 4 nos. 25 hp submersible T/wells (AFT 25 hp t/wells) in South Constituency (MC funds.) |  |  |  | MC Funds / General Quota | MCL |  |  |  | 2036/13.10.2025 | [8 empty] | 1219/G/33 Dated 04-11-2025 | Bedi pump Store | 48.77 | 11-06-2025 | 3 | [5 empty] | 75 |  | 36.5775 | In Progress |  | T/well to be Installed Against failed as per requirment
433 | MCL-0438 | O&M | C |  | South | 29 |  |  | Providing Laying 4" i/d DIK-7 water supply line at Makkar Colony Ward No.29 |  |  |  | MC Funds / General Quota | MCL |  |  |  | 220/11.03.2025 | [8 empty] | 1161/G/33 Dated 11-04-2025 | APEX Developers | 35.84 | 15/4/2025 | 3 | 31/07/2026 |  |  |  |  | 80 |  | 28.672 | Delayed/Held Up |  | Work stopped by MLA, until road estimate to be approved
434 | MCL-0439 | O&M | C |  | South | 36 |  |  | Prov./Installation of 25 hp new Submersible T/well at street no.1 Chahal road Sukhdev Nagar ward no.36 MC fund |  |  |  | MC Funds / General Quota | MCL |  |  |  | 2538/05.02.2026 | [8 empty] | 1240/G/33 Dated 20.04.2026 | Amarpal Singh Bawa | 10.57 | 20/04/2026 | 3 | 20/7/2026 |  |  |  |  | 85 |  | 8.9845 | In Progress |  | Work in progress
435 | MCL-0440 | O&M | C |  | South | 37 |  |  | Prov./Installation of 25 hp new Submersible T/well at street no. 13 Guru Gobind singh nagar barota road ward no.37 MC fund |  |  |  | MC Funds / General Quota | MCL |  |  |  | 2810/19.02.2026 | [8 empty] | 1235/G/33 Dated 09.04.2026 | JCS Electric works | 10.26 |  | 3 | [5 empty] | 0 |  | 0 | Delayed/Held Up |  | Notice issued to contractor for delay in start
436 | MCL-0441 | O&M | C |  | South | 37 |  |  | Prov./Installation of 25 hp New Submersible T/well at Guru Gobind singh nagar street no. 10/3 ward no. 37 |  |  |  | MC Funds / General Quota | MCL |  |  |  | 2540/05.02.2026 | [8 empty] | 1236/G/33 Dated 09.04.2026 | Amarpal Singh Bawa | 10.58 | 04-10-2026 | 3 | 07-10-2026 |  |  |  |  | 85 |  | 8.993 | In Progress |  | Work In Progress
437 | MCL-0442 | O&M | C |  | South | 37 |  |  | Prov./Laying 4" id Dik-7 water supply lines at Barota road and Branch streets of Guru Gobind Singh Nagar ward no. 37 |  |  |  | MC Funds / General Quota | MCL |  |  |  | 2819/19.02.2026 | [8 empty] | 1242/G/33 Dated 27.04.2026 | Sushil Kumar contractor | 40.18 |  | 3 | [5 empty] | 0 |  | 0 | Delayed/Held Up |  | Work stopped by MLA, until road estimate to be approved
438 | MCL-0443 | O&M | C |  | South | 43 |  |  | Prov./Installation of 25 hp new Submersible t/well at New Amar nagar stret no. 10-B ward no. 43 |  |  |  | MC Funds / General Quota | MCL |  |  |  | 2818/19.02.2026 | [8 empty] | 1237/G/33 Dated 09.04.2026 | Ess Elechmec | 10.24 | 04-10-2026 | 3 | 15/7/2026 |  |  |  |  | 60 |  | 6.144 | In Progress |  | Work In Progress
439 | MCL-0444 | O&M | C |  | South | 44 |  |  | Prov./Laying 4” id DIK-7 Water Supply lines at street no.4 Kot Mangal Singh Ward no. 41 old. MC Funds |  |  |  | MC Funds / General Quota | MCL |  |  |  | 517/09.04.2025 | [8 empty] | 1168/G/33 Dated 30-04-2025 | The Boha Co.op L&C Society ltd. | 9.73 |  | 2 | [5 empty] | 0 |  | 0 | Delayed/Held Up |  | Due To road dispute of Public work not started
440 | MCL-0445 | O&M | C |  | South | 45 |  |  | Prov./Laying 4" id Dik-7 water supply lines in street no. 11, 14 & 15 at Vishkarma colony ward no. 50 old |  |  |  | MC Funds / General Quota | MCL |  |  |  | 516/09.04.2025 | [8 empty] | 1169/G/33/30.04.2025 | Bedi pump store | 9.37 | 30/4/2025 | 2 | [5 empty] | 70 |  | 6.559 | Delayed/Held Up |  | Work Held up due to political dispute
441 | MCL-0446 | O&M | C |  | South | 31 |  |  | Upgradation of 4" id DIK water supply lines & 12" UPVC sewer line at street no 3,4,5,6 Hargobind Nagar ward no. 31 |  |  |  | MC Funds / General Quota | MCL |  |  |  | 2890/19.02.2026 | [8 empty] | 1247/G/33 Dated 11.05.2026 | APEX Developers | 72.24 | 15/05/2026 | 3 | 15/10/2026 |  |  |  |  | 0 |  | 0 | Not Started |  | work to be start after monsoon
442 | MCL-0447 | O&M | C |  | South | 34 |  |  | Prov./Laying missing links 4" id DIK-7 water supply lines & 10" id UPVC sewer lines at Lachman nagar & Ajit Colony ward no. 34 |  |  |  | MC Funds / General Quota | MCL |  |  |  | 2811/19.02.2026 | [8 empty] | 1250/G/33 Dated 11.05.2026 | GK Contractor | 6.5 | 15/05/2026 | 2 | 08-10-2026 |  |  |  |  | 25 |  | 1.625 | In Progress |  | Work in Progress
443 | MCL-0448 | O&M | C |  | South | 33 |  |  | Prov./Laying missing links 4" id DIK-7 water supply lines for missing links & 10" id UPVC sewer lines at Mahadev nagar, Samrat Colony & Laxmi Nagar ward no. 33 |  |  |  | MC Funds / General Quota | MCL |  |  |  | 2807/19.02.2026 | [8 empty] | 1251/G/33 Dated 11.05.2026 | NS Infra | 14.37 | 13/05/2026 | 3 | 15/08/2026 |  |  |  |  | 25 |  | 3.5925 | In Progress |  | Work in Progress
444 | MCL-0449 | O&M | C |  | South | 36 |  |  | Upgradation of 4" id DIK water supply lines & 12" id UPVC sewer line at Gill colony Sappan wala mandir ward no. 36 |  |  |  | MC Funds / General Quota | MCL |  |  |  | 2891/19.02.2026 | [8 empty] | 1249/G/33 Dated 11.05.2026 | Friennds & company | 67.85 | 15/05/2026 | 3 | 31/08/2026 |  |  |  |  | 20 |  | 13.57 | In Progress |  | Work in Progress
445 | MCL-0450 | O&M | C |  | South | 32 |  |  | Purchase of 3000 litters water tanker for ward no. 16 old new ward no. 32 MP Quota |  |  |  | MPLAD Funds | MP Lad |  |  |  | 3386/21.04.2026 | [8 empty] | 1252/G/33 Dated 13.05.2026 | Ram Parkash Kakkar | 1.94 | 15/05/2026 | 2 | 07-12-2026 |  |  |  |  | 0 |  | 0 | Not Started |  | Manufacturing under process
446 | MCL-0451 | O&M | C |  | South | 32 |  |  | Purchase of 3000 litters water tanker for ward no. 30 old new ward no. 32 MP Quota |  |  |  | MPLAD Funds | MP Lad |  |  |  | 3382/21.04.2026 | [8 empty] | 1253/G/33 Dated 13.05.2026 | Ram Parkash Kakkar | 1.94 | 15/05/2026 | 2 | 07-12-2026 |  |  |  |  | 0 |  | 0 | Not Started |  | Manufacturing under process
447 | MCL-0452 | O&M | C |  | South | 34 |  |  | Prov./Installation of 25 hp New Submersible T/well at street no. 8 Gagan Nagar ward no. 34 |  |  |  | MC Funds / General Quota | MCL |  |  |  | 3524/21.04.2026 | [8 empty] | 1254/G/33 Dated 13.05.2026 | Bedi pump Store | 10.11 | 13/05/2026 | 3 | 15/08/2026 |  |  |  |  | 0 |  | 0 | Not Started |  | Work not done. Need to be expedited in view of monsoon.
448 | MCL-0453 | O&M | C |  | South | 43 |  |  | Prov./Installation of 25 hp New Submersible T/well at street no. 33 Kot Mangal Singh Nagar ward no. 43 |  |  |  | MC Funds / General Quota | MCL |  |  |  | 3388/21.04.2026 | [8 empty] | 1256/G/33 Dated 13.05.2026 | Bedi pump Store | 10.11 | 13/05/2026 | 3 | 15/08/2026 |  |  |  |  | 0 |  | 0 | Not Started
449 | MCL-0454 | O&M | C |  | South | 32 & 33 old |  |  | Prov./Suction tanker for desilting of sewer in various area of ward no. 32 & 33 old sub Zone C-2 |  |  |  | MC Funds / General Quota | MCL |  |  |  | 3379/21.04.2026 | [8 empty] | 1257/G/33 Dated 13.05.2026 | Sai Enterprises | 5.95 | 13/05/2026 | 3 | 15/08/2026 |  |  |  |  | 50 |  | 2.975 | Not Started
450 | MCL-0455 | O&M | C |  | South | 36 |  |  | Prov./Laying 4" id DIK-7 water supply lines & 10" id UPVC sewer lines at Dhillon nagar ward no. 36 |  |  |  | MC Funds / General Quota | MCL |  |  |  | 2892/19.02.2026 | [8 empty] | 1267/G/33 Dated 13.05.2026 | Apex Developers | 56.03 | 13/05/2026 | 3 | 30/11/2026 |  |  |  |  | 0 |  | 0 | Not Started |  | Work will start after monsoon
451 | MCL-0456 | O&M | C |  | South | 31 |  |  | Upgradation of 10" id UPVC sewer line in Gandhi Nagar Ward no. 50 |  |  |  | MC Funds / General Quota | MCL |  |  |  | 3408/05.12.2024 | [8 empty] | 1143/G/33 Dated 05-12-2024 | M/S Kohinoor Builders | 29.05 | 12-07-2024 | 3 | [5 empty] | 85 |  | 24.6925 | In Progress |  | As per original contract work is completed. File sent for change of site for balance fund.
452 | MCL-0457 | O&M | C |  | South | 34 |  |  | Providing Laying 10" UPVC Sewer line & 4" i/d DIK-7 water supply line Near BSUP Flats Ward No.31 |  |  |  | MC Funds / General Quota | MCL |  |  |  | 332/26.03.2025 | [8 empty] | 1162/G/33 Dated 11-04-2025 | The Sarabha Co. Op. L&C Society Ltd. | 7.52 | 13/04/2025 | 2 | 31/07/2026 |  |  |  |  | 70 |  | 5.264 | Delayed/Held Up |  | Work in Progress, delay due to clearance from building branch
453 | MCL-0458 | O&M | C |  | South | 34 |  |  | Upgradation of 4" id DIK water supply lines & 10" UPVC sewer line at City Garden colony ward no. 34 |  |  |  | MC Funds / General Quota | MCL |  |  |  | 3381/21.04.2026 | [8 empty] | 1245/G/33 Dated 11.05.2026 | APEX Developers | 69.37 | 05-12-2026 | 3 | 15/09/2026 |  |  |  |  | 20 |  | 13.874 | In Progress |  | Work in Progress
454 | MCL-0459 | O&M | C |  | South | 32 |  |  | Upgradation of 24" id RCC NP3 HDPE sewer line at Singla Cycle road ward no. 32 |  |  |  | MC Funds / General Quota | MCL |  |  |  | 3383/21.04.2026 | [8 empty] | 1246/G/33 Dated 11.05.2026 | Rajdeep Enterprises | 70.06 | 20/04/2026 | 4 | 30/09/2026 |  |  |  |  | 20 |  | 14.012 | In Progress |  | Work in Progress
455 | MCL-0460 | O&M | C |  | South | 32 |  |  | Prov./Laying 12" id UPVC sewer lines at Mittal kanda Dhandari Kalan near Skoda showroom ward no. 32 |  |  |  | MC Funds / General Quota | MCL |  |  |  | 2813/19.02.2026 | [8 empty] | 1248/G/33 Dated 11.05.2026 | Prince Sharma | 19.01 | 14/5/2026 | 3 | [5 empty] | 0 |  | 0 | Delayed/Held Up |  | Delayed due to earth filling has to done by B&R
456 | MCL-0461 | O&M | C |  | South | 39 |  |  | Upgradation of 12" id UPVC sewer line at street no. 8 Harkrishan nagar ward no. 39 |  |  |  | MC Funds / General Quota | MCL |  |  |  | 2815/19.02.2026 | [8 empty] | 1268/G/33 Dated 13.05.2026 | Prince Sharma | 22.04 | 14/05/2026 | 3 | 15/09/2026 |  |  |  |  | 0 |  | 0 | Not Started
457 | MCL-0462 | O&M | C |  | Central | 74 |  |  | Raising & Construction of M/H Slabs & Additional M/H Chambers , Prov./Laying 8" id sewer line for missing links in ward no. 74 |  |  |  | MC Funds / General Quota | MCL |  |  |  | 3380/21.04.2026 | [8 empty] | 1260/G/33 Dated 13.05.2026 | Kohinoor Builders | 7.66 | 14/05/2026 | 3 | 30/07/2026 |  |  |  |  | 50 |  | 3.83 | Not Started
458 | MCL-0463 | O&M | C |  | Central | 74 |  |  | Upgradation of 10" id UPVC storm sewer line from Gill road to Loha Mandi Indra market opp. Indra market ward no. 74 |  |  |  | MC Funds / General Quota | MCL |  |  |  | 3547/21.04.2026 | [8 empty] | 1263/G/33 Dated 13.05.2026 | Friennds & company | 19.86 | 14/05/2026 | 3 | 15/11/2026 |  |  |  |  | 0 |  | 0 | Not Started |  | Work will be start after monsoon
459 | MCL-0464 | O&M | C |  | Central | 74 |  |  | Raising & Constyruction of M/H slabs and construction of add. M/H chambers in Ward no. 74 |  |  |  | MC Funds / General Quota | MCL |  |  |  | 3387/21.04.2026 | [8 empty] | 1264/G/33 Dated 13.05.2026 | Bharat Nirman Infracon | 5.84 | 14/05/2026 | 2 | 30/07/2026 |  |  |  |  | 20 |  | 1.168 | Not Started
460 | MCL-0465 | O&M | C |  | Central | 74 |  |  | Upgradation of 10" id UPVC sewer lines in Industrial Estate ward no. 74 |  |  |  | MC Funds / General Quota | MCL |  |  |  | 3578/21.04.2026 | [8 empty] | 1265/G/33 Dated 13.05.2026 | Friennds & company | 24.9 | 14/05/2026 | 3 | 15/11/2026 |  |  |  |  | 0 |  | 0 | Not Started |  | Work will start after monsoon
461 | MCL-0466 | O&M | D |  | North | North |  |  | Rehabitation/Missing links of 8" and 12"UPVC Sewer line and 2" G.I & 4" water supply line at Various wards of North Constituency |  |  |  | MC Funds / General Quota | G.Q |  |  |  | 242 26-03-2025 & 2233 21/11/2026 | [8 empty] | 03/G-33 Dt. 15/04/2025 & 358/XEN/D 10/09/2025 | M/s Rajdeep Enterprises | 49.38 | 20/04/2025 | (upto 10/11/2025) | 07-10-2026 |  |  |  |  | 95 |  | 46.911 | Delayed/Held Up |  | Work was delayed due to road work was not approved. now work under progress
462 | MCL-0467 | O&M | D |  | North | 91 | Sewerage | 385246 | P/Laying 12” id storm sewer line at on the road outside the park, near Silver Spoon, New Deep Nagar, Ward No. 91. (G.Q) (E Comp No. 385246) |  | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 11.83 | -24.99% | 256 26-03-2025 | Yes | Yes | SDO | N/A | 2026-04-01 | 2026-04-16 | Yes | Yes | 6/g/33 11-05-2026 | M/S Sushil Kumar Contractor, Ludhiana | 9.31 | 2026-05-15 | 2 months | 2026-07-14 | 2026-08-10 | Sh. Gurinder Singh JE, Sh. Anshul Garcha SDO, Sh. RAndeep SIngh XEN | N/A | N/A | 80% |  | 0 | 80% |  | Work in Progress
463 | MCL-0468 | O&M | D |  | North | D1 | Water Supply | NA | Rehablitation/Missing link of 4" Water Supply line at various wards of Subzone-D1 |  | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 74.45 | -7.07% | 2025-11-06 | Yes | Yes | Chief Engineer | N/A | 2025-03-11 | 2025-04-05 | Yes | Yes | 104/G-33 Dt. 06/11/2025 | M/S ESS Elecmech Enterprises | 69.18 | 10-11-2025 | 3 Months | 2026-02-08 | 15/07/2026 | Sh. Gurinder Singh JE, Sh. Anshul Garcha SDO, Sh. RAndeep SIngh XEN | N/A | N/A | 95 |  | 65.721 | Delayed/Held Up |  | Work is delayed Due to rehablitation work
464 | MCL-0469 | O&M | D |  | North | 66 |  |  | Providing & Installation of 12.5 HP submersible T/well at Gaganpreet Vihar in Ward No-66. (G.Q) |  |  |  | MC Funds / General Quota | G.Q | Awarded | 5.29 | -15.7% | 2627 11-02-2026 | Yes | Yes | JE | N/A | 2025-03-11 | 2025-04-05 | Yes | Yes | 107/G/33 20-02-2026 | M/s JCS Electric Works | 4.45 | 20-05-2026 | 2 months | 15/07/2026 | 15/07/2026 | Sh. Gurinder Singh JE, Sh. Anshul Garcha SDO, Sh. RAndeep SIngh XEN | N/A | N/A | 60 |  | 0.445 | In Progress |  | Work in Progress
465 | MCL-0470 | O&M | D |  | North | 93 |  |  | Making of Disposal Well at new Kundanpuri (PeeruBanda) Railway bridge Sandhu Showroom in ward no-93 . (G.Q) |  |  |  | MC Funds / General Quota | G.Q | Awarded | 28.73 | -11.86% | 2615 11-02-2026 | Yes | Yes | SE | N/A | 2025-03-11 | 2025-04-05 | Yes | Yes | 108/G/33 20-02-2026 | M/s Bedi Pump Srore | 25.12 | 21/02/2026 | 3 months | 30/06/2026 | 15/07/2026 | Sh. Gurinder Singh JE, Sh. Anshul Garcha SDO, Sh. RAndeep SIngh XEN | N/A | N/A | 95 |  | 21.6032 | Delayed/Held Up |  | Only Gen set pending
466 | MCL-0471 | O&M | D |  | North | 66,68,92 |  |  | Rehablition of water supply & Sewer line at Gokul Vihar, Tersem Colony, Jaganath Purm, Preet Vihar, Civil City, New Sant Nagar in Ward no. 66, 68, 92(C.Q) |  |  |  | Councillor Quota (CQ) | C.Q |  |  |  | 2625 11-02-2026 | [8 empty] | 110/G/33 20-02-2026 | M/s Sushil Kumar Contractor | 27.38 | 15-04-2026 | 3 months | 30/07/2026 |  |  |  |  | 25 |  | 6.845 | Not Started
467 | MCL-0472 | O&M | D |  | North | 93 |  |  | Rehablition of water supply line at sunil nagar in ward no 93. |  |  |  | Councillor Quota (CQ) | C.Q |  |  |  | 2867 19-02-2026 | [8 empty] | 123/g/33 26-02-2026 | M/s Sushil Kumar Contractor | 40.33 | 27/02/2026 | 3 months | 07-05-2026 |  |  |  |  | 95 |  | 38.3135 | Not Started
468 | MCL-0473 | O&M | D |  | North | - |  |  | Providing & Installing of 2nos.12.5 HP, 1 nos. 25 HP & 1 nos. 40 HP Tubewells in place of against failed tubewells and water shortage in Emergency Situations in various areas under North Constituency. (G.Q) (E Comp No. 376246) |  |  |  | MC Funds / General Quota | G.Q |  |  |  | 3378 21-04-2026 | [8 empty] | 1/g/33 08-05-2026 | M/S Rana Electrical Works, Ludhiana. | 43.37 | 05-11-2026 | 12 months | 05-10-2027 |  |  |  |  | 90 |  | 39.033 | Not Started
469 | MCL-0474 | O&M | D |  | North | 70 |  |  | Providing & Installation of 25 HP submersible T/well in Pahwa dharamshala against failed T/well in Ward no- 70.. (G.Q) (E Comp No. 374186) |  |  |  | MC Funds / General Quota | G.Q |  |  |  | 3346 21-04-2026 | [8 empty] | 4/g/33 11-05-2026 | M/S Bharat Nirman Infracon, Ludhiana. | 8.2 | 05-12-2026 | 3 months | 08-10-2026 |  |  |  |  | 0 |  | 0 | Not Started |  | Notice Issued
470 | MCL-0475 | O&M | D |  | North | 93 |  |  | Rehablition of water supply line at Kehar Singh Nagar in ward no 93. (C.Q) (E Comp No. 377250) |  |  |  | Councillor Quota (CQ) | C.Q |  |  |  | 3573 21-04-2026 | [8 empty] | 7/g/33 11-05-2026 | M/S Friends and Company, Ludhiana.. | 61.12 | 05-12-2026 | 4 months | 09-10-2026 |  |  |  |  | 0 |  | 0 | Not Started |  | Notice Issued
471 | MCL-0476 | O&M | D |  | Atam Nagar | 47 |  |  | Providing and Laying 4"dia DIK-7 water supply line at the area of Kartar Nagar in Ward No-49 |  |  |  | MC Funds / General Quota | G.Q |  |  |  | 241 03-12-2024 | [8 empty] | 4/G/33 11-04-2025 | M/S ESS Elecmech Enterprices, Ludhiana.. | 31.49 | 20/4/2026 | 3 months | [5 empty] | 55 |  | 17.3195 | Delayed/Held Up |  | Work stopped by MLA saab and work to be done after road work allotment
472 | MCL-0477 | O&M | D |  | Atam Nagar | 47 |  |  | Providing and Laying 4"dia DIK-7 water supply line at the area of Ambedker Nagar, street no-9, in Ward No-48 |  |  |  | MC Funds / General Quota | G.Q |  |  |  | 543 09-04-2025 | [8 empty] | 40/G/33 25-04-2025 | M/S Bedi Pump Store , Ludhiana | 31.83 | 25/04/2025 | 3 months | [5 empty] | 0 |  | 0 | Delayed/Held Up |  | Work stopped by MLA saab and work to be done after road work allotment
473 | MCL-0478 | O&M | D |  | Atam Nagar | 47 |  |  | Providing and Laying 4"dia DIK-7 water supply line at the area of Anbedker Nagar in Ward No-48 |  |  |  | MC Funds / General Quota | G.Q |  |  |  | 540 09-04-2025 | [8 empty] | 42/G/33 25-04-2025 | M/S ESS Elecmech Enterprises, Ludhiana | 22.06 | 25/04/2025 | 2 months | [5 empty] | 0 |  | 0 | Delayed/Held Up |  | Work stopped by MLA saab and work to be done after road work allotment
474 | MCL-0479 | O&M | D |  | Atam Nagar | 52 |  |  | Providing and Laying 4"dia DIK-7 water supply line at the area of Abdulapur Basti in Ward No-47. |  |  |  | MC Funds / General Quota | G.Q |  |  |  | 541 09-04-2025 | [8 empty] | 41/G/33 25-04-2025 | M/S ESS Elecmech Enterprises, Ludhiana | 22.95 | 30-04-2025 | 3 months | 15/7/2026 |  |  |  |  | 60 |  | 13.77 | In Progress |  | Area is conjusted and there was sewer issue due to which excavation was not possible work started after sewer is cleared
475 | MCL-0480 | O&M | D |  | Atam Nagar | 52 |  |  | Prov/Inst. of 25 HP Straight bore T/well at Abdulapur basti Vikas dharamshalla in W. No. 52 (against failed t/well 40 HP) |  |  |  | MC Funds / General Quota | G.Q |  |  |  | 1458 13-10-2025 | [8 empty] | 97/G/33 03-11-2025 | M/S Rajdeep Enterprises | 10.06 | 11-10-2025 | 3 months | 15/7/2026 |  |  |  |  | 95 |  | 9.557 | Not Started
476 | MCL-0481 | O&M | D |  | Atam Nagar | 51 |  |  | Prov/Inst. of 2 No. New 25 HP Straight bore Tube wells in Ward No. 51. |  |  |  | MC Funds / General Quota | G.Q |  |  |  | 2379 05-01-2026 | [8 empty] | 106/G/33 27-01-2026 | M/S Rajdeep Enterprises | 20.29 | 02-04-2026 | 3 months | 15/7/2026 |  |  |  |  | 90 |  | 18.261 | Not Started
477 | MCL-0482 | O&M | D |  | Atam Nagar | 50 |  |  | Providing and Installation of 25 HP Straight Bore Submersible Tubewell at 200 ft. road, Urban Estate, Ph-3 in Ward No 50.(C.Q) |  |  |  | Councillor Quota (CQ) | C.Q |  |  |  | 2631 11-02-2026 | [8 empty] | 116/G/33 20-02-2026 | M/s ESS Elechmech Enterprises | 10.31 | 25/2/26 | 3 months | 15/7/2026 |  |  |  |  | 65 |  | 6.7015 | Not Started
478 | MCL-0483 | O&M | D |  | Atam Nagar | 49 |  |  | Providing and Installation of 25 HP Straight Bore Submersible Tubewell at Ph-1, Near Dr. Grewal Park in Ward No 49 (against 12.5HP failed tubewell )(G.Q). |  |  |  | MC Funds / General Quota | G.Q |  |  |  | 2636 110-2-2026 | [8 empty] | 117/G/33 20-02-2026 | M/s ESS Elechmech Enterprises | 10.31 | 25-02-2026 | 3 months | 07-05-2026 |  |  |  |  | 80 |  | 8.248 | Not Started
479 | MCL-0484 | O&M | D |  | Atam Nagar | 50 |  |  | Providing and Installation of 25 HP Straight Bore Submersible Tubewell at L.I.G Flat, Urban Estate, Ph-3, Near Army Flat in Ward No 50.(C.Q) |  |  |  | Councillor Quota (CQ) | C.Q |  |  |  | 2633 11-02-2026 | [8 empty] | 120/G/33 20-02-2026 | M/s JCS Electric Works | 10.3 | 21/02/2026 | 3 months | 15/7/2026 |  |  |  |  | 0 |  | 0 | Not Started |  | Notice Issued
480 | MCL-0485 | O&M | D |  | Atam Nagar | 47 |  |  | Providing and Installation of 25 HP Straight Bore Submersible Tubewell at Kartar Nagar (Apna Park), in Ward No 47 (against 40HP failed tubewell). (G.Q). |  |  |  | MC Funds / General Quota | G.Q |  |  |  | 2637 11-02-2026 | [8 empty] | 121/G/33 20-02-2026 | M/s JCS Electric Works | 10.18 | 25/2/26 | 3 months | 15/7/2026 |  |  |  |  | 95 |  | 9.671 | Delayed/Held Up |  | only electric connection pending
481 | MCL-0486 | O&M | D |  | Atam Nagar | 50 |  |  | Providing and Installation of 25 HP Straight Bore Submersible Tubewell at Chhoti Jawaddi in Ward No 50. (C.Q) |  |  |  | Councillor Quota (CQ) | C.Q |  |  |  | 2638 11-02-2026 | [8 empty] | 122/G/33 20-02-2026 | M/s JCS Electric Works | 10.17 | 25/02/2026 | 3 months | 31/7/2026 |  |  |  |  | 0 |  | 0 | Not Started |  | Notice Issued
482 | MCL-0487 | O&M | D |  | Atam Nagar | D2 |  |  | Prepare of Foundation of 100 HP Motor Pump at Water Works Plant, Ph1, Dugri in Sub Zone D2. (C.Q) (E Comp No. 375948) |  |  |  | MC Funds / General Quota | G.Q |  |  |  | 3347 21-4-02026 | [8 empty] | 9/g/33 11-05-2026 | M/S G.K Contractor, Ludhiana | 1.96 | 05-12-2026 | 2 months | 07-11-2026 |  |  |  |  | 0 |  | 0 | Not Started
483 | MCL-0488 | O&M | D |  | Atam Nagar | 47 |  |  | Prov/Laying of Sewer line (missing links) in W. No. 47..(C.Q) |  |  |  | MC Funds / General Quota | G.Q |  |  |  | 2632 11-02-2026 | [8 empty] | 119/G/33 20-02-2026 | M/s G.K. Contractor | 7.36 | 25/2/2026 | 2 months | 15/7/2026 |  |  |  |  | 50 |  | 3.68 | In Progress |  | Mannual work is being done
484 | MCL-0489 | O&M | D | D3 | West | 59 | Water Supply | NA | P/I or New Sub. 40 HP Tubewell at Big Park, Chhpar wali park, Ward No-74. |  | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 28.87 | 7.81 | 255 & 26-03-2025 | Yes | Yes | XEN | N/A | 2024-11-14 | 2024-12-03 | Yes | Yes | 15/G/33 11-04-2025 | CNC Precision Engineering | 26.62 |  | 3 months |  |  | Naresh kumar JE, Jatinder Sodhi SDO, Randeep SIngh Xen | N/A | N/A | 0 |  | 0 | Not Started | Stata of site is not suitable. New site requirement | Stata of site is not suitable. New site requirement
485 | MCL-0490 | O&M | D |  | West | 60 | Water Supply | NA | Rough Cost Estimate For Prov. & Laying of 4” DIK-7 Water Supply lines & 8” SN-8 UPVC sewer lines at Sargodha Colony &Gurdev Nagar, Backside Silver Arc Mall in Ward No.60 |  |  | 1 | MC Funds / General Quota | G.Q | Awarded | 29.14 | -20.1% | 973 06-05-2025 | Yes | Yes | SE | N/A | 2025-04-11 | 2025-04-28 | Yes | Yes | 67/G/33 14-05-2025 | M/s Bharat Bhushan Contractor | 29.14 | 2025-05-20 | 3 months | 2025-08-15 | 15/7/2026 | Naresh kumar JE and Harkesh kumar JE, Jatinder Sodhi SDO, Randeep SIngh Xen | N/A | N/A | 60% |  | 17.484 | 75 |  | Work In Progress
486 | MCL-0491 | O&M | D |  | West | Gen. | Water Supply | NA | Rough cost of Estimate For Providing & Installation of 40 HP. Rig Bore Tubewell at against failed T/well) Ward General T/well West |  | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 20.54 | -17.79% | 961 06-05-2025 | Yes | Yes | XEN | N/A | 2025-04-11 | 2025-04-28 | Yes | Yes | 72/G/33 14-05-2025 | M/s Guru Kirpa & Co | 20.54 | not Started | 3 months | 2025-08-30 | not Started | Naresh kumar JE and Harkesh kumar JE, Jatinder Sodhi SDO, Randeep SIngh Xen | N/A | N/A | not Started |  | 0 | 0 | Notice Issued | Notice Issued
487 | MCL-0492 | O&M | D |  | West | 72 | Water Supply | NA | Prov. & Laying of 4” DIK-7 Water Supply Line at Jawahar Nagar Camp Ward No-72. |  | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 43.41 | -12.3% | 1871 13-10-2025 | Yes | Yes | SE | N/A | 2025-08-04 | 2025-08-12 | Yes | Yes | 89/G/33 03-11-2025 | M/S Bharat Bhushan Contractor | 43.41 | 11-10-2025 | 3 months | 2026-01-15 | 15/7/2026 | Naresh kumar JE and Harkesh kumar JE, Jatinder Sodhi SDO, Randeep SIngh Xen | N/A | N/A | 95 |  | 41.2395 | 95 |  | Only one street pending mannual work in being done
488 | MCL-0493 | O&M | D |  | West | 72 | Water Supply | NA | Rough Cost Estimate For 4" DIK-7 Water Supply Line at Bus Stand to Bharat Nagar chowk Ward No-72. |  | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 29.16 | -0.04% | 1870 13-10-2025 | Yes | Yes | SE | N/A | 2025-08-04 | 2025-08-12 | Yes | Yes | 90/G/33 03-11-2025 | 1 Apex Devlopers, Ludhiana. 2. M/S Kohinoor Builders, Ludhiana. | 29.16 | 11-08-2025 | 3 months | 2025-11-11 | 15/7/2026 | Naresh kumar JE and Harkesh kumar JE, Jatinder Sodhi SDO, Randeep SIngh Xen | N/A | N/A | 70% |  | 14.58 | 50 |  | Not further work required in this file
489 | MCL-0494 | O&M | D |  | West | 54 | Water Supply | NA | Providing & Installation of 25 HP. Submersible new Tubewell at J- Block, Sarabha Nagar (Against Failed Tubewell) Ward No-55. shifted to karnail singh nagar |  | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 13.13 | -1.25% | 1460 13-10-2025 | Yes | Yes | SDO | N/A | 2025-08-04 | 2025-08-12 | Yes | Yes | 95/G/33 03-11-2025 | M/S Amarpal Singh Bawa | 12.96 | 10-11-2025 | 2 months | 15/7/2026 | 15/7/2026 | Naresh kumar JE and Harkesh kumar JE, Jatinder Sodhi SDO, Randeep SIngh Xen | N/A | N/A | 85 |  | 11.016 | Not Started
490 | MCL-0495 | O&M | D |  | West | 59 | Water Supply | 373959 | Upgradaiton of 4" DIK7 Water Supply line at Indra Colony, Barewal Road, Ward No-59. (C.Q) (E Comp No. 373959) |  | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 13.8 | -16.1% | 3371 21-04-2026 | Yes | Yes | SDO | N/A | 2025-12-26 | 2026-01-15 | Yes | Yes | 5/g/33 11-05-2026 | M/S Sushil Kumar Contractor, Ludhiana | 11.57 | not Started | 3 months | 2026-08-08 | not Started | Naresh kumar JE and Harkesh kumar JE, Jatinder Sodhi SDO, Randeep SIngh Xen | N/A | N/A | not Started |  | 0 | Not Started
491 | MCL-0496 | O&M | D |  | West | 55 | Sewerage | NA | Estimate For Prov. & Laying of 10” UPVC SN-8 Pipe Sewer Line at H. No.-22 Block-K, Sarabha Nagar in Ward No-75, Ludhiana |  | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 6.95 | -23..50% | 3250 29-11-2024 | Yes | Yes | SDO | N/A | 2024-08-26 | 20-82024 | Yes | Yes | 52/G/33 02-12-2024 | Bharat Bhusan Contractor | 5.31 | not started | 2 months | 2025-02-10 | not Started | Naresh kumar JE and Harkesh kumar JE, Jatinder Sodhi SDO, Randeep SIngh Xen | N/A | N/A | not Started |  | 0 | In Progress | New Road constucted so hold up | New Road constucted
492 | MCL-0497 | O&M | D |  | West | 59 | Sewerage | NA | Rough Cost Estimate For Upgradation of 315mm UPVC SN-8 Pipe Sewer Line at Barewal Shamshan Ghat Road in Ward No-74, Ludhiana. |  | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 9.95 | -26% | 3248 29-11-2024 | Yes | Yes | SDO | N/A | 2024-08-26 | 20-82024 | Yes | Yes | 50/G/33 02-12-2024 | Bedi Pump Store., Ludhiana. | 7.37 | not started | 2 months | [7 empty] | 0 | Not Started |  | New Road constucted
493 | MCL-0498 | O&M | D |  | West | 56 | Sewerage | NA | Up-gradation of 12” SN-8 UPVC Sewer line at House No.-3H to Opp. Key Hotel Wd. No.-71. |  | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 42.28 | -31.31% | 976 06-05-2026 | Yes | Yes | XEN | N/A | 2025-04-11 | 2025-04-28 | Yes | Yes | 66/G/33 14-05-2025 | M/s Anmol Katyal Contractor | 29.04 | not started | 3 months | [7 empty] | 0 | Not Started |  | road level issue so hold up.
494 | MCL-0499 | O&M | D |  | West | 56 |  |  | Providing & Laying of 8” SN-8 UPVC Sewer Line at keys Hotel back side, S.B.S Nagar in Ward No- 56, Ludhiana.(C.Q) |  |  |  | Councillor Quota (CQ) | C.Q |  |  |  | 2634 11-02-2026 | [8 empty] | 112/G/33 20-02-2026 | M/s N.S. Infra | 17.21 | 25/2/2026 | 3 months | 15/7/2026 |  |  |  |  | 90 |  | 15.489 | In Progress |  | Notice Issued
495 | MCL-0500 | O&M | D |  | West | 55 |  |  | Providing & Laying 12" UPVC SN-8 Storm Sewer Line at Block-G, B.R.S Nagar in Ward No-55, Ludhiana. (G.Q) (E Comp No. 379488) | 1 |  |  | MC Funds / General Quota | G.Q |  |  |  | 3408 21-04-2026 | [8 empty] | 8/g/33 11-05-2026 | M/S Friends and Company, Ludhiana.. | 58.95 | 15/5/2026 | 4 months | 14/08/2026 |  |  |  |  | 50 |  | 29.475 | In Progress | Colony residents informed that work is very slow and of poor quality | Concerned officials to visit. ZC to visit as well and report on status
496 | MCL-0501 | O&M | D |  | West | 61 |  |  | Providing & installation of a new tubewell (against failure) of 40 HP in Rose Garden-2 (inside the park) under Ward No.-61. |  |  |  | MC Funds / General Quota | G.Q |  |  |  | 962 06-05-2025 | [8 empty] | 54/G/33 14-05-2025 | M/s Guru Kirpa & Co | 22.54 | not started | 3 months | - | [6 empty] | 0 | Not Started |  | Notice Issued
497 | MCL-0502 | O&M | D |  | West | Gen. |  |  | Purchase of Wate Tankerof 15 no. of S.S. for west constituency, Municipal Corporation Ludhiana. (15th Finance Commmission Drinking Water Head). |  |  |  | MC Funds / General Quota | G.Q |  |  |  | 2503 23-08-2024 | [8 empty] | 43/G/33 26-11-2024 | M/s Kakar Fabricators, Ludhiana | 34.02 | 30/11/2024 | 3 months | 07-04-2026 |  |  |  |  | 75 |  | 25.515 | Not Started
498 | MCL-0503 | O&M | D |  | West | West |  |  | Annual rate contract of Prov. and installation of 25 HP & 12.5 HP Tubewells for West Constituency. (G.Q) |  |  |  | MC Funds / General Quota | G.Q |  |  |  | 2585 11-02-2026 | [8 empty] | 114/G/33 20-02-2026 | M/s ESS Elechmech Enterprises | 68.67 | 25/2/2026 | 12 months | 02-10-2027 |  |  |  |  | 80 |  | 54.936 | Not Started
499 | MCL-0504 | O&M | D |  | West | 53 |  |  | Rough Cost Estimate For Prov. & Laying of 4” DIK-7 Water Supply line,8” & 10”UPVC Sewer lines at A-Block, Model Town Extension in ward No-53. |  |  |  | MC Funds / General Quota | G.Q |  |  |  | 3279 25-02-2026 | [8 empty] | 125/g/33 10-03-2026 | M/S Rajdeep Enterprises | 45.94 | 15/3/2026 | 3 months | 15/7/2026 |  |  |  |  | 70 |  | 32.158 | Not Started
500 | MCL-0505 | O&M | D |  | West | 65 |  |  | Providing & Installation of 12.5 HP. Submersible Tubewell at St. No. 13, Jain Colony in Ward No-65(E.Comp. No 398855) |  |  |  | MC Funds / General Quota | G.Q |  |  |  | 12-06-2025 | [8 empty] | 11/g/33 15-06-2026 | Ess Elecmech Enterprises | 5.58 | 16/06/2026 | 2 months | 15/08/2026 |  |  |  |  | 0 |  | 0 | Not Started
501 | MCL-0506 | O&M | D |  | West | D4 |  |  | Estimate for P/I of 12" i/d SN-8 Sewer Line at Hambran Road, MC limit to B&R Store (right side) and Hambran Road, Onkar Autos to outside World Diabetes (left side), sub zone-D4. (E Comp No. 384878) |  |  |  | MC Funds / General Quota | G.Q |  |  |  | 04-0 5-02026 | [8 empty] | 10/g/33 11-05-2026 | M/s Bedi Pump Store, | 40.49 | 15/05/2026 | 3 months | 14/08/2026 |  |  |  |  | 75 |  | 30.3675 | Not Started
502 | MCL-0507 | B&R | D |  | West | 53 |  |  | Providing Zebra Crossong & Road Marking work at Various Streets of Ward no. 53 |  |  |  | MC Funds / General Quota | MC Funds |  | 9.95 | 25 | 2090 13-10-2025 | [8 empty] | 83/EED 04-11-2025 | M/s Dhindsa Enterprises | 7.46 |  | 2 | [5 empty] | 10 |  |  | In Progress |  | Work in Progress
503 | MCL-0508 | B&R | D |  | West | 54 |  |  | Laying BM & OGPC in various streets of Punjab Mata Nagar |  |  |  | MC Funds / General Quota | MC Funds |  | 38.39 | 2 | 1171 15-11-2023 | [8 empty] | 123/EED 16-01-2024 | M/s VKBS Const (P) Ltd | 37.6222 |  | 3 | [5 empty] | 85 |  |  | Delayed/Held Up |  | Premix Work Completed, Only road furniture Pending
504 | MCL-0509 | B&R | D |  | West | 54 |  |  | Laying BM & OGPC in Various Streets of Karnail Singh Nagar Ph-2 |  |  |  | MC Funds / General Quota | MC Funds |  | 153.1 | 35.88 | 2332 23-08-2024 | [8 empty] | 01/EED 01-04-2025 | M/s SK Const. Co. | 98.1677 |  | 3 | [5 empty] | 95 |  |  | Delayed/Held Up |  | Premix Work Completed, Only road furniture Pending
505 | MCL-0510 | B&R | D |  | West | 54 |  |  | Providing and Laying OGPC in various streets of Punjab Mata Nagar Opposite Dhami Property Dealer |  |  |  | MC Funds / General Quota | MC Funds |  | 36.84 | 24.99 | 3496 21-04-2026 | [8 empty] | 05/EED 07-05-2026 | M/s Somaya Infrastructures | 27.6337 |  | 3 | [5 empty] | 95 |  |  | Delayed/Held Up |  | Premix Work Completed, Only road furniture Pending
506 | MCL-0511 | B&R | D |  | West | 55 |  |  | P/L BM & OGPC in J Block Sarabha Nagar |  |  |  | MC Funds / General Quota | MC Funds |  | 83.03 | 27.9 | 2999 Dt. 8-11-2024 | [8 empty] | 18/EED 09-04-2025 | M/s IHR Associates | 59.8646 |  | 3 | [5 empty] | 85 |  |  | In Progress |  | Work in Progress
507 | MCL-0512 | B&R | D |  | West | 55 |  |  | Laying SDBC on Main Road from Zone-D Office to FZR Road Ward No.55 |  |  |  | N-CAP | N-CAP |  | 73.08 | 26.09 | 1861 13-10-2025 | [8 empty] | 141/EED 25-03-2026 | Maruti Construction Co. | 54.01 |  | 5 | [5 empty] | 95 |  |  | In Progress |  | Work in progress
508 | MCL-0513 | B&R | D |  | West | 55 |  |  | Laying SDBC on Roads of BRS Nagar Block-B W.No.55 |  |  |  | MC Funds / General Quota | MC Funds |  | 77.54 | 28.65 | 1772 13-10-2025 | [8 empty] | 136/EED 25-03-2026 | M/s Somaya Infrastructure | 55.3248 |  | 5 | [5 empty] | 95 |  |  | In Progress |  | Work in progress
509 | MCL-0514 | B&R | D |  | West | 55 |  |  | Laying SDBC on Roads of BRS Nagar Block-C W.No.55 |  |  |  | MC Funds / General Quota | MC Funds |  | 90.57 | 25.2 | 1770 13-10-2025 | [8 empty] | 142/EED 25-03-2026 | Maruti Construction Co. | 67.7464 |  | 5 | [5 empty] | 90 |  |  | In Progress |  | Work in progress
510 | MCL-0515 | B&R | D |  | West | 56 |  |  | Laying OGPC in Various Streets of Gobind Nagar W. No. - 56 |  |  |  | MC Funds / General Quota | MC Funds |  | 41.21 | 7.7 | 2602 11-02-2026 | [8 empty] | 128/EED 18-03-2026 & 129/EED 18-03-2026 | Soham Construction Company & CH Builders Pvt. Ltd | 38.0368 |  | 3 | [5 empty] | 0 |  |  | Not Started |  | Not Started
511 | MCL-0516 | B&R | D |  | West | 56 |  |  | Laying OGPC in Streets of New BRS Nagar, Sham Nagar and New Sham Nagar W. No. - 56 |  |  |  | MC Funds / General Quota | MC Funds |  | 71 | 17.36 | 2597 11-02-2026 | [8 empty] | 121/EED 18-03-2026 | Ganpati Infra | 58.6744 |  | 4 | [5 empty] | 20 |  |  | In Progress |  | Work in progress
512 | MCL-0517 | B&R | D |  | West | 57 |  |  | Laying BM & OGPC in Various Streets of Sunet W.No.72 |  |  |  | MC Funds / General Quota | MC Funds |  | 66.04 | 33.63 | 2329 23-08-2024 | [8 empty] | 101/EED 12-02-2025 | SK Const. Co. | 43.8307 |  | 3 | [5 empty] | 20 |  |  | In Progress |  | Work in Progress
513 | MCL-0518 | B&R | D |  | West | 57 |  |  | Laying OGPC in Streets of Sunet Village W. No. 57 |  |  |  | MC Funds / General Quota | MC Funds |  | 47.84 | 7.7 | 2590 11-02-2026 | [8 empty] | 130/EED 18-03-2026 & 131/EED 18-03-2026 | Soham Construction Company & CH Builders Pvt. Ltd | 44.1563 |  | 3 | [5 empty] | 0 |  |  | Not Started |  | work not started
514 | MCL-0519 | B&R | D |  | West | 57 & 55 |  |  | Laying SDBC on Main Road From Durga Mata Mandir to CFC School W. No. 57 & 55 |  |  |  | MC Funds / General Quota | MC Funds |  | 25.34 | 7.7 | 2529 11-02-2026 | [8 empty] | 132/EED 18-03-2026 | Soham Construction Company | 23.3888 |  | 2 | [5 empty] | 0 |  |  | Not Started |  | work not started
515 | MCL-0520 | B&R | D |  | West | 57 |  |  | Laying OGPC in Streets of E - Block Near Lodhi Club W. No. 57 |  |  |  | MC Funds / General Quota | MC Funds |  | 55.77 | 24.54 | 2598 11-02-2026 | [8 empty] | 117/EED 18-03-2026 | Somaya Infrastructure | 42.084 |  | 3 | [5 empty] | 95 |  |  | In Progress |  | Work in Progress
516 | MCL-0521 | B&R | D |  | West | 57 |  |  | Laying OGPC in Streets of BRS Nagar I - Block Near Cremation Ground W. No. 57 |  |  |  | MC Funds / General Quota | MC Funds |  | 80.56 | 18.36 | 2600 11-02-2026 | [8 empty] | 120/EED 18-03-2026 | Ganpati Infra | 65.7692 |  | 3 | [5 empty] | 0 |  |  | Not Started |  | Work Order Issued
517 | MCL-0522 | B&R | D |  | West | 57 |  |  | Laying OGPC in Streets of BRS Nagar I - Block Near Lodhi Club W. No. 57 |  |  |  | MC Funds / General Quota | MC Funds |  | 85.26 | 15.1 | 2599 11-02-2026 | [8 empty] | 119/EED 18-03-2026 | Soham Construction Company | 72.3857 |  | 3 | [5 empty] | 0 |  |  | Not Started |  | Not started
518 | MCL-0523 | B&R | D |  | West | 57 |  |  | Laying SDBC Main Sunet Road from Orient Market to Post Office Sunet. W. No. 57 |  |  |  | MC Funds / General Quota | MC Funds |  | 48.42 | 18.08 | 3221 25-02-2026 | [8 empty] | 139/EED 25/03/2026 | Maruti Construction Co. | 39.6657 |  | 3 | [5 empty] | 10 |  |  | In Progress |  | Work in Progress
519 | MCL-0524 | B&R | D |  | West | 58 |  |  | Laying OGPC in Various Streets of Rajouri garden and Gill Avenue W.No.58 |  |  |  | MC Funds / General Quota | MC Funds |  | 86.85 | 24.55 | 2048 13-10-2025 | [8 empty] | 148/EED 25/03/2026 | M/s Somaya Infrastructure | 65.5283 |  | 5 | [5 empty] | 95 |  |  | In Progress |  | Work in Progress
520 | MCL-0525 | B&R | D |  | West | 58 |  |  | Milling Laying BM & SDBC on Main Roads of J-Block, HJ Block, Lodhi Club to Namdev Chownk and under bridge side Slipway W.No.58 |  |  |  | MC Funds / General Quota | MC Funds |  | 96.89 | 25.2 | 2049 13-10-2025 | [8 empty] | 149/EED 25/03/2026 | M/s Durga Construction Company | 72.4737 |  | 5 | [5 empty] | 95 |  |  | In Progress |  | Work in Progress
521 | MCL-0526 | B&R | D |  | West | 58 |  |  | Laying OGPC in Various Streets of Flower Dale, Good Friend Colony and Bhai Daya Singh Nagar on Barewal Main Road W.No.58 |  |  |  | MC Funds / General Quota | MC Funds |  | 45.79 | 25.2 | 2047 13-10-2025 | [8 empty] | 147/EED 25/03/2026 | M/s Durga Construction Company | 34.2509 |  | 3 | [5 empty] | 5 |  |  | In Progress |  | Work in Progress
522 | MCL-0527 | B&R | D |  | West | 58 |  |  | Laying OGPC in Streets of Malkeet Avenue on Barewal Road Ward No. 58 |  |  |  | MC Funds / General Quota | MC Funds |  | 49.87 | 12.7 | 3567 21-04-2026 | [8 empty] | 06/EED 07-05-2026 | M/s Soham Construction | 43.5365 |  | 3 | [8 empty] | Not Started |  | Work Order Issued
523 | MCL-0528 | B&R | D |  | West | 58 |  |  | Laying OGPC in Various Streets of Pink Park and Raja Garden W.No.58 |  |  |  | MC Funds / General Quota | MC Funds |  | 45.43 | 26.41 | 3568 21-04-2026 | [8 empty] | 04/EED 07-05-2026 | M/s Somaya Infrastructure | 33.4319 |  | 3 | [5 empty] | 95 |  |  | In Progress |  | Work in Progress
524 | MCL-0529 | B&R | D |  | West | 59 |  |  | Providing & laying BM & OGPC in various streets of Mahaveer Enclave Barewal |  |  |  | MC Funds / General Quota | MC Funds |  | 174.71 | 34.26 | 3162 22-11-2024 | [8 empty] | 03/EED 01-04-2025 | SK Const. Co. | 114.8544 |  | 3 | [5 empty] | 85 |  |  | In Progress |  | Work in Progress
525 | MCL-0530 | B&R | D |  | West | 59 |  |  | P/L OGPC in Various Streets of Ajit Villa South City |  |  |  | MC Funds / General Quota | MC Funds |  | 118.16 | 2.51 | 871 06-05-2025 | [8 empty] | 53/EED 16-05-2024 | M/s Apex Builder | 115.1942 |  | 4 | [5 empty] | 60 |  |  | In Progress |  | Work in Progress
526 | MCL-0531 | B&R | D |  | West | 59 |  |  | Laying OGPC in various Streets of Parkash Colony W.No.-59 |  |  |  | MC Funds / General Quota | MC Funds |  | 25.07 | 7.7 | 2592 11-02-2026 | [8 empty] | 133/EED 18-03-2026 | Soham Construction Company | 23.1396 |  | 4 | [5 empty] | 0 |  |  | Not Started |  | Not Started
527 | MCL-0532 | B&R | D |  | West | 59 |  |  | Laying SDBC on Main Road From Environmental Friendly Park to Mahaveer Enclave. W. No. 59 |  |  |  | N-CAP | N-CAP |  | 30.55 | 18.08 | 1771 13-10-2025 | [8 empty] | 138/EED 25/03/2026 | Maruti Construction Co. | 25.0266 |  | 3 | [5 empty] | 95 |  |  | In Progress |  | Work in progress
528 | MCL-0533 | B&R | D |  | West | 60 |  |  | Laying BM & OGPC in Various Streets of Gurdev Nagar Adjoining Pakhowal Road and Ferozepur Road |  |  |  | MC Funds / General Quota | MC Funds |  | 154.77 | -1.09 | 2654 Dt. 11-02-2026 | [8 empty] | 94/EED 05-12-2025 | Vansh Engineers | 153.08 |  | 4 | [5 empty] | 30 |  |  | In Progress |  | Ongoing Work
529 | MCL-0534 | B&R | D |  | West | 60 |  |  | Laying BM & OGPC in Various Streets of New Lajpat Nagar |  |  |  | MC Funds / General Quota | MC Funds |  | 66.87 | 0.24 | 3505 Dt. 21-04-2026 | [8 empty] | 07/EED 07-05-2026 | S.K Construction | 66.7 |  | 5 | [5 empty] | 0 |  |  | Not Started |  | Work Order Issued
530 | MCL-0535 | B&R | D |  | West | 65 |  |  | Laying BM & OGPC in various streets of Pavittar nagar ward no 65. |  |  |  | MC Funds / General Quota | MC Funds |  | 70.58 | 1.5 | 1215 11-08-25 | [8 empty] | 100/EED 09-02-2026 | M/s Rajeev enterprises | 69.52 |  | 3 | [5 empty] | 0 |  |  | Delayed/Held Up |  | inauguration pending
531 | MCL-0536 | B&R | D |  | West | 65 |  |  | Laying BM & OGPC in various streets of Prem Nagar,Haqiqat Nagar and New patel Nagar. |  |  |  | MC Funds / General Quota | MC Funds |  | 96.18 | 7 | 692 Dt. 09-04-2025 | [8 empty] | 152/EED 25/03/2026 | M/s Somaya Infrastructure | 89.44 |  | 3 | [5 empty] | 90 |  |  | In Progress |  | Work in Progress
532 | MCL-0537 | B&R | D |  | West | 65 |  |  | Const of metaled roads in Joshi Nagar Part-1 W.No.81 |  |  |  | MC Funds / General Quota | MC Funds |  | 95.63 | [10 empty] | 37/EED 28-04-2025 | M/s Somaya Infrastructure | 64.88 |  | 4 | [5 empty] | 90 |  |  | In Progress |  | Work in progress
533 | MCL-0538 | B&R | D |  | West | 65 |  |  | Const of metaled roads in Joshi Nagar Part-2 W.No.81 |  |  |  | MC Funds / General Quota | MC Funds |  | 99.31 | [10 empty] | 37/EED 28-04-2025 | M/s Somaya Infrastructure | 67.38 |  | 4 | [5 empty] | 90 |  |  | In Progress |  | Work in progress
534 | MCL-0539 | B&R | D |  | West | 81 |  |  | Const. of metalled roads in ranjodh park, Haibowal Nagar and New Patel Nagar |  |  |  | MC Funds / General Quota | MC Funds |  | 94.66 | [10 empty] | 146/EED 25-03-2026 | M/s Durga Construction Company | 88.03 |  | 3 | [5 empty] | 0 |  |  | Not Started
535 | MCL-0540 | B&R | D |  | West | 69 |  |  | Providing and Laying OGPC in Green Park Society adjoining Prince Hostel. Ward no. 82 |  |  |  | MC Funds / General Quota | MC Funds |  | 89.49 | 7 | 3497 Dt. 21-04-2026 | [8 empty] | 10/EED 07/05/2026 | Anil Kumar and Sons | 83.22 |  | 4 | [8 empty] | Not Started |  | Work Order Issued
536 | MCL-0541 | B&R | D |  | West | 69 |  |  | Laying BM & SDBC on Saggu Chowk to Humbran Road |  |  |  | MC Funds / General Quota | MC Funds |  | 152.59 | 21.6 | 629 Dt. 09-04-2025 | [8 empty] | 162/EED 25/03/2026 | M/s NKC Construction Pvt. Ltd | 119.63 |  | 3 | [5 empty] | 90 |  |  | Delayed/Held Up |  | Premix Work Completed, Only road furniture Pending
537 | MCL-0542 | B&R | D |  | West | 71 |  |  | Laying OGPC in streets of Officer colony and adjoining Rakh Bagh |  |  |  | MC Funds / General Quota | MC Funds |  | 113.35 | 26.5 | 3009 Dt. 08-11-2024 | [8 empty] | 43/EED 08-05-2025 | Durga Construction | 83.31 |  | 3 | [5 empty] | 20 |  |  | In Progress |  | Ongoing Work
538 | MCL-0543 | B&R | D |  | West | 71 |  |  | P/l BM and OGPC In various streets of Ghumar Mandi. |  |  |  | MC Funds / General Quota | MC Funds |  | 66.92 | 7 | 3494 Dt. 21-04-2026 | [8 empty] | 09/EED 07-05-2026 | S.K Construction Co | 62.23 |  | 3 | [8 empty] | Not Started |  | Work Order Issued
539 | MCL-0544 | B&R | D |  | West | 72 |  |  | Laying BM & OGPC in Various Streets of Friends Colony, Partap Colony and Kartar Nagar in Ward no. 72 |  |  |  | MC Funds / General Quota | MC Funds |  | 68.43 | 7 | 3491 Dt. 21-04-2026 | [8 empty] | 08/EED 07-05-2026 | Global Construction | 63.64 |  | 3 | [8 empty] | Not Started |  | Work order Issued
540 | MCL-0545 | B&R | D |  | West | 72 |  |  | Laying BM & OGPC in Various Streets of Model Gram Ward no. 72 |  |  |  | MC Funds / General Quota | MC Funds |  | 234.39 | 7 | 3492 Dt. 21-04-2026 | [8 empty] | 11/EED 07-05-2026 | Ganpati Infra | 217.98 |  | 3 | [8 empty] | Not Started |  | Work order Issued
541 | MCL-0546 | B&R | D |  | West | 53 |  |  | Repair and Renovation of park Nehru Nagar & Shastri Nagar Ward no. 53 |  |  |  | MC Funds / General Quota | MC Funds |  | 20.22 | 25.02 | 2108 13-10-2025 | [8 empty] | 86/EED 04-11-2025 | M/s Dynamic Tiles | 15.16 |  | 3 | [5 empty] | 60 |  |  | In Progress |  | Work in Progress
542 | MCL-0547 | B&R | D |  | West | 55 |  |  | Repair and Renovation of Parks (7 No.s) in Block-C BRS Nagar in Ward no 55. |  |  |  | MC Funds / General Quota | MC Funds |  | 68.48 | 22.92 | 1206 11-08-2025 | [8 empty] | 79/EED 08-10-2025 | T & G Construction Co. | 52.7844 |  | 5 | [5 empty] | 95 |  |  | In Progress |  | Work in Progress
543 | MCL-0548 | B&R | D |  | West | 55 |  |  | Repair and Renovation of Parks (5 No.s) in Block -A and Block-B BRS Nagar in Ward no 55. |  |  |  | MC Funds / General Quota | MC Funds |  | 39.9 | 21 | 1205 11-08-2025 | [8 empty] | 82/EED 04-11-2025 | GLISTEN | 31.521 |  | 5 | [5 empty] | 70 |  |  | In Progress |  | Work in Progress
544 | MCL-0549 | B&R | D |  | West | 55 |  |  | Development of Green Belt outside Canal view apartments HIG Flats W.No.75 |  |  |  | MC Funds / General Quota | MC Funds |  | 47.49 | 35.36 | 864 06-05-2025 | [8 empty] | 57/EED 16-05-2025 | T&G Const.Co | 30.6975 |  | 3 | [5 empty] | 0 |  |  | Not Started |  | Not Started
545 | MCL-0550 | B&R | D |  | West | 55 |  |  | Repair and Renovation of Various Parks in Sarabha Nagar & BRS Nagar. W. No. 55. |  |  |  | MC Funds / General Quota | MC Funds |  | 39.98 | 6.66 | 1203 11-08-2025 | [8 empty] | 143&144/EED 25-03-2026 | M/s Apex Developers & K. S. Constructions | 37.3173 |  | 3 | [5 empty] | 10 |  |  | In Progress |  | Work in progress
546 | MCL-0551 | B&R | D |  | West | 55 |  |  | Providing and Fixing of Children Playing Equipments and Garden Gyms in Various Parks W. No. 55. |  |  |  | MC Funds / General Quota | MC Funds |  | 26.93 | 34.2 | 753 09-04-2025 | [8 empty] | 137/EED 25-03-2026 | M/s Ram Parkash kakkar | 17.7199 |  | 3 | [5 empty] | 0 |  |  | Not Started |  | Not Started
547 | MCL-0552 | B&R | D |  | West | 55 |  |  | Civil work in Rose Valley on sidhwan Canal Near Jawaddi Bridge |  |  |  | MC Funds / General Quota | MC Funds |  | 27.67 | 33.99 | 1512 18-01-2024 | [8 empty] | 88/EED 29-11-2024 | The Boha Co op L&C society ltd | 18.265 |  | 3 | [5 empty] | 90 |  |  | In Progress |  | Work in Progress
548 | MCL-0553 | B&R | D |  | West | 56 |  |  | P/F Cemented Benches in Various Parks of Ward No 56. |  |  |  | MC Funds / General Quota | MC Funds |  | 2.79 | 36.13 | 1204 11-08-2025 | [8 empty] | 76/EED 08-10-2025 | Rakesh Kumar Contractor | 1.782 |  | 2 | [5 empty] | 25 |  |  | In Progress |  | Work in Progress
549 | MCL-0554 | B&R | D |  | West | 57 |  |  | Repair & Renovation of Park near railway line D Block BRS Nagar |  |  |  | MC Funds / General Quota | MC Funds |  | 18.2 | 25.52 | 2547 24-09-2024 | [8 empty] | 33/EED 24-10-2024 | The Civil Engineers & Builders Co op L&C society ltd | 13.5554 |  | 3 | [5 empty] | 50 |  |  | In Progress |  | Work in Progress
550 | MCL-0555 | B&R | D |  | West | 57 |  |  | Construction of New Park in F Block BRS Nagar Near Ravidas Shamshan Ghat Ward No 72 |  |  |  | MC Funds / General Quota | MC Funds |  | 24.32 | 24.99 | 2541 05-02-2026 | [8 empty] | 154/EED 25/03/2026 | Varinder Singh Govt. Cont. | 18.2424 |  | 4 | [5 empty] | 0 |  |  | Not Started |  | Not started
551 | MCL-0556 | B&R | D |  | West | 57 |  |  | P/F Cemented Benches in Various Parks of Ward No 57. |  |  |  | MC Funds / General Quota | MC Funds |  | 9.77 | 36.13 | 1369 11-08-2025 | [8 empty] | 74/EED 08-10-2025 | Rakesh Kumar Contractor | 6.2401 |  | 2 | [5 empty] | 30 |  |  | In Progress |  | Work in Progress
552 | MCL-0557 | B&R | D |  | West | 58 |  |  | P/F Cemented Benches in Various Parks of Ward No 58. |  |  |  | MC Funds / General Quota | MC Funds |  | 8.37 | 36.13 | 1207 11-08-2025 | [8 empty] | 77/EED 08-10-2025 | Rakesh Kumar Contractor | 5.3459 |  | 2 | [5 empty] | 25 |  |  | In Progress |  | Work in Progress
553 | MCL-0558 | B&R | D |  | West | 58 |  |  | Construction & Various Works of Sports Court in Parks of BRS J-Block, Near RUB. W. No. 58 |  |  |  | MC Funds / General Quota | MC Funds |  | 8.84 | 17.77 | 634 09-04-2025 | [8 empty] | 85/EED 04-11-2025 | Subodh Batish | 7.2691 |  | 3 | [5 empty] | 95 |  |  | In Progress |  | Work in Progress
554 | MCL-0559 | B&R | D |  | West | 58 |  |  | Repair & Renovation of Various Parks in River Dale Colony in Barewal W.No. 58 |  |  |  | MC Funds / General Quota | MC Funds |  | 9.79 | 21.88 | 638 09-04-2025 | [8 empty] | 84/EED 04-11-2025 | Subodh Batish | 7.6479 |  | 5 | [5 empty] | 25 |  |  | In Progress |  | Work in Progress
555 | MCL-0560 | B&R | D |  | West | 58 |  |  | P/F Garden Gym in Various Parks of W. No. 58 |  |  |  | MC Funds / General Quota | MC Funds |  | 9.96 | 21.99 | 642 09-04-2025 | [8 empty] | 145/EED 25/03/2026 | M/s Khalsa Export Private Limited | 7.7698 |  | 2 | [5 empty] | 0 |  |  | Not Started |  | Not Started
556 | MCL-0561 | B&R | D |  | West | 58 |  |  | Repair & Renovation of Various Parks in J Block 64 Yards W.No.58 |  |  |  | MC Funds / General Quota | MC Funds |  | 46.7 | 32.26 | 2051 13-10-2025 | [8 empty] | 150/EED 25/03/2026 | M/s Varinder Singh Govt. Contractor | 31.6346 |  | 5 | [5 empty] | 25 |  |  | In Progress |  | Work in Progress
557 | MCL-0562 | B&R | D |  | West | 59 |  |  | Const. of Canopies, Gym Garden, Swings in various parks W.No.74 |  |  |  | MC Funds / General Quota | MC Funds |  | 48.93 | 31.99 | 2439 23-08-2024 | [8 empty] | 32/EED 24-10-2024 | The Akal Co op L&C Society Ltd | 33.2773 |  | 3 | [5 empty] | 60 |  |  | Delayed/Held Up |  | Work in Progress, 859 Dt. 6-5-25 PENDING
558 | MCL-0563 | B&R | D |  | West | 59 |  |  | Repair and Renvoation of various parks of sunil park, Flower Date Park, Citizen Enclave. Professor colony in Ward no 74. |  |  |  | MC Funds / General Quota | MC Funds |  | 35.07 | 25.71 | 2657 24-09-2024 | [8 empty] | 49/EED 29-10-2024 | M/s The Saharan Majra Co-op LC Society Ltd | 26.0535 |  | 5 | [5 empty] | 90 |  |  | In Progress |  | Work in Progress
559 | MCL-0564 | B&R | D |  | West | 59 |  |  | Repair & Renovation of Eco Friendly Park in Barewal Awana W. No. 59 |  |  |  | MC Funds / General Quota | MC Funds |  | 6.19 | 17.66 | 2601 11-02-2026 | [8 empty] | 122/EED 18-03-2026 | Varinder Singh Govt. Contractor | 5.0968 |  | 3 | [5 empty] | 0 |  |  | Not Started |  | Not Started
560 | MCL-0565 | B&R | D |  | West | 59 |  |  | Repair & Renovation of Various Parks in Parkash Colony & Madhuvan Enclave on Barewal Road W. No. 59 |  |  |  | MC Funds / General Quota | MC Funds |  | 11.28 | 30.1 | 1381 11-08-2025 | [8 empty] | 151/EED 25/03/2026 | M/s Dynamic tiles | 7.8847 |  | 2 | [5 empty] | 10 |  |  | In Progress |  | Work in progress
561 | MCL-0566 | B&R | D |  | West | 60 |  |  | Repari and Renovation of different parks of new Lajpat Nagar in Ward no 67 (2 nos. parks) |  |  |  | MC Funds / General Quota | MC Funds |  | 35.92 | 23.19 | 1169 15-11-2023 | [8 empty] | 113/EED 21-12-2023 | M/s The Civil Engineer & Builders Co-op L/C Society Ltd | 27.59 |  | 3 | [5 empty] | 80 |  |  | In Progress |  | Ongoing Work
562 | MCL-0567 | B&R | D |  | West | 60 |  |  | Repair & Renovation of parks (4 nos.) in Gurdev nagar (4 nos. parks) |  |  |  | MC Funds / General Quota | MC Funds |  | 49.28 | 37.5 | 3004 Dt. 08-11-2024 | [8 empty] | 34/EED 25-4-2025 | Ram Parkash Kakar | 30.8 |  | 3 | [5 empty] | 95 |  |  | In Progress | Sprinkler needs to be fixed in Kartar Park, New Lajpat Nagar, Gurdev Nagar | Ongoing Work
563 | MCL-0568 | B&R | D |  | West | 60 |  |  | Repair and Renovation of Park in Ghumar Mandi (1 No. park) |  |  |  | MC Funds / General Quota | MC Funds |  | 21.76 | 32 | 618 Dt. 09-04-2025 | [8 empty] | 47/EED 28-10-2024 | Dynamic Tiles | 14.79 |  | 2 | [5 empty] | 20 |  |  | In Progress |  | Ongoing Work
564 | MCL-0569 | B&R | D |  | West | 60 |  |  | Reapir and renovation of Murgi Farm Park and other parks of Gurdev Nagar w-60 |  |  |  | MC Funds / General Quota | MC Funds |  | 36.94 | -33.6 | 1860 Dt.13-10-2025 | [8 empty] | 125/EED 18-03-2026 | Ram Parkash Kakkar | 24.52 |  | 3 | [5 empty] | 20 |  |  | In Progress |  | Work in progress
565 | MCL-0570 | B&R | D |  | West | 61 |  |  | Repair and Renovation of various Parks in Ward no 61. (3 Nos. parks) |  |  |  | MC Funds / General Quota | MC Funds |  | 48.87 | 33.5 | 616 Dt. 09-04-2025 | [8 empty] | 63/EED 19-05-2025 | Dynamic Tiles | 32.49 |  | 3 | [5 empty] | 50 |  |  | In Progress |  | work in progress
566 | MCL-0571 | B&R | D |  | West | 62 |  |  | Construction of 2 new parks & Repair of other Parks in Ward No 78 |  |  |  | MC Funds / General Quota | MC Funds |  | 48.19 | 41.01 | 1662 Dt. 14-02-2024 | [8 empty] | 46/EED 15-05-2025 | M/s Dynamic tiles | 64.88 |  | 3 | [5 empty] | 60 |  |  | In Progress |  | Work in progress
567 | MCL-0572 | B&R | D |  | West | 63 |  |  | Repair and Renovation of various parks in ward no 63. |  |  |  | MC Funds / General Quota | MC Funds |  | 85.5 | 32.5 | 685 Dt. 09-04-2025 | [8 empty] | 105/EED 16-02-2026 | M/s Dynamic tiles | 57.71 |  | 3 | [5 empty] | 45 |  |  | In Progress |  | Work in progress
568 | MCL-0573 | B&R | D |  | West | 64 |  |  | Repair and renovation of corporation colony parks (2 nos.) in ward no. 78 |  |  |  | Other / Unspecified |  |  | 57.55 | 32.59 | 323 dt 26.03.25 | [8 empty] | 36/EED 28-04-2025 | M/S JP Builders | 38.79 |  | 3 | [5 empty] | 95 |  |  | In Progress |  | Work in progress
569 | MCL-0574 | B&R | D |  | West | 65 |  |  | Repair and Renovation of various parks in ward no 65. |  |  |  | MC Funds / General Quota | MC Funds |  | 83.28 | 35.88 | 1202 Dt. 11-08-2025 | [8 empty] | 153/EED 25/03/2026 | M/s Naresh kumar contractor | 53.4 |  | 3 | [5 empty] | 25 |  |  | In Progress |  | Work in progress
570 | MCL-0575 | B&R | D |  | West | 69 |  |  | Repair & renovation of various parks adjoining Cementry road W-82 (3 Nos. parks) |  |  |  | MC Funds / General Quota | MC Funds |  | 28.05 | 23.46 | 3010 Dt. 08-11-2024 | [8 empty] | 17/EED 09.04.2025 | M/s Smridhi Constructions | 21.46 |  | 3 | [5 empty] | 90 |  |  | In Progress |  | Ongoing Work
571 | MCL-0576 | B&R | D |  | West | 71 |  |  | Repair and renovation of Rajaram park in Mall Enclave. (1 No. park) |  |  |  | MC Funds / General Quota | MC Funds |  | 22.82 | 24.99 | 2671 Dt. 24-09-2024 | [8 empty] | 41/EED 28-10-2024 | The Sunet Co op L&C society ltd | 17.11 |  | 3 | [5 empty] | 95 |  |  | In Progress |  | Ongoing Work
572 | MCL-0577 | B&R | D |  | West | 71 |  |  | P/L Perforated interlocking tiles on side berms of various streets in Mall Enclave |  |  |  | MC Funds / General Quota | MC Funds |  | 32.81 | 41 | 652 Dt. 09-04-2025 | [8 empty] | 61/EED 19-05-2025 | Dynamic Tiles | 19.35 |  | 3 | [5 empty] | 60 |  |  | In Progress |  | Ongoing Work
573 | MCL-0578 | B&R | D |  | West | 72 |  |  | Repair & Renovation of Park in Kochar Market and Jawahar Camp (2 Nos. parks) |  |  |  | MC Funds / General Quota | MC Funds |  | 49.76 | 24.99 | 2672 Dt. 24-09-2024 | [8 empty] | 45/EED 28-10-2024 | The Sunet Co op L&C society ltd | 37.32 |  | 3 | [5 empty] | 95 |  |  | In Progress |  | Work in progress
574 | MCL-0579 | B&R | D |  | West | 72 |  |  | Repair and Renovation of park near potohari Gurudwara and Batra Park. (2 Nos. parks) |  |  |  | MC Funds / General Quota | MC Funds |  | 40.33 | 24.99 | 2670 24-09-2024 | [8 empty] | 51/EED 06-11-2024 | M/s The Sunet L/C Society Ltd | 30.25 |  | 3 | [5 empty] | 95 |  |  | In Progress |  | Work in progress
575 | MCL-0580 | B&R | D |  | West | 72 |  |  | Repair and renovation of parks (6 Nos.) In Model Gram Partap Colony & Friends Colony in Ward no. 72 (6 Nos. parks) |  |  |  | MC Funds / General Quota | MC Funds |  | 47.41 | 33 | Dt. 09-04-2025 | [8 empty] | 59/EED 19-05-2025 | Dynamic Tiles | 31.76 |  | 3 | [5 empty] | 30 |  |  | In Progress |  | Work in progress
576 | MCL-0581 | B&R | D |  | West | 72 |  |  | Construction of an entrance gate in jawahar nagar camp |  |  |  | MC Funds / General Quota | MC Funds |  | 18.37 | 5.2 | 2672 Dt. 11-02-2026 | [8 empty] | 106/EED 03-03-2026 | Asis Builders | 17.41 |  | 3 | [5 empty] | 30 |  |  | In Progress |  | Work in progress
577 | MCL-0582 | B&R | D |  | West | 73 |  |  | Repair and Renovation of Various Parks in Ward No 65 (3 Nos. parks) |  |  |  | MC Funds / General Quota | MC Funds |  | 48.97 | 35.88 | 321 26-03-2025 | [8 empty] | 13/EED 09-04-2024 | M/s Naresh Kumar Contarctor | 31.39 |  | 3 | [5 empty] | 30 | 0 |  | In Progress | Pavement done (concrete), canopies, benches done in 1 park. Gym area, jhule pending. | Ongoing Work
578 | MCL-0583 | B&R | D |  | West | 53 |  |  | Providing and Laying of 60mm thick interlocking tiles on side berms of Model Town Extension (Ishmeet Singh road) |  |  |  | MC Funds / General Quota | MC Funds |  | 43.03 | 35.66 | 2660 24-09-2024 | [8 empty] | 55/EED 06-11-2024 | M/s The Boha Co-op | 27.68 |  | 5 | [5 empty] | 75 |  |  | In Progress |  | Work in Progress
579 | MCL-0584 | B&R | D |  | West | 54 |  |  | P/L interlocking tiles on side berms of road in New Punjab Mata Nagar W.No.70 |  |  |  | MC Funds / General Quota | MC Funds |  | 56.96 | 41.01 | 2331 23-08-2024 | [8 empty] | 27/EED 11-04-2025 | M/s Dynamic Tiles | 33.6007 |  | 5 | [5 empty] | 5 |  |  | Delayed/Held Up |  | Work Held up due to NGT Guidelines
580 | MCL-0585 | B&R | D |  | West | 54 |  |  | P/Laying interlocking tiles on side berms of roads in Karnail Singh Nagar Ph-II |  |  |  | MC Funds / General Quota | MC Funds |  | 95.93 | 32.25 | 1288 20-11-2023 | [8 empty] | 118/EED 05-01-2024 | M/s J.P Builders | 64.9926 |  | 5 | [5 empty] | 30 |  |  | Delayed/Held Up |  | Work Held up due to NGT Guidelines, Moreover Case Sent to F&CC for Change of Site - PENDING 858 Dt. 6-5-25
581 | MCL-0586 | B&R | D |  | West | 56 |  |  | P/Laying Inter-locking tiles on side berms of roads in Vikas Nagar & Gobind Nagar Ward No 71 |  |  |  | MC Funds / General Quota | MC Funds |  | 223.68 | 13.85 | 6869 07-09-2022 | [8 empty] | 10/EED 26-12-2022 | M/s Aglow Builders | 192.7003 |  | 5 | [5 empty] | 95 |  |  | In Progress |  | Work in Progress, Revised vide F&CC Res. no. 880 dt. 06.05.2025
582 | MCL-0587 | B&R | D |  | West | 56 |  |  | P/L 80mm Thick Interlocking Tiles in Victoria Colony on 200' Road W. No. 56 |  |  |  | MC Funds / General Quota | MC Funds |  | 52.38 | 30.44 | 2850 19-02-2026 | [8 empty] | 134/EED 18-03-2026 | T&G Construction | 36.4355 |  | 4 | [5 empty] | 70 |  |  | In Progress |  | Work in progress
583 | MCL-0588 | B&R | D |  | West | 57 |  |  | P & Laying Interlocking Tiles on side Berms In D Block BRS Nagar Ward No 72 |  |  |  | MC Funds / General Quota | MC Funds |  | 98.63 | 42.88 | 1660 14-02-2024 | [8 empty] | 25/EED 11-04-2025 | Varinder Singh Govt. Cont. | 56.3375 |  | 4 | [5 empty] | 80 |  |  | In Progress |  | Work in Progress
584 | MCL-0589 | B&R | D |  | West | 57 |  |  | P/L 80mm thick interlocking tiles in village Sunet |  |  |  | MC Funds / General Quota | MC Funds |  | 17.33 | 40.88 | 419 26-03-2025 | [8 empty] | 11/EED 09-04-2025 | Varinder Singh Govt. Cont. | 10.2455 |  | 4 | [5 empty] | 70 |  |  | In Progress |  | Work in Progress
585 | MCL-0590 | B&R | D |  | West | 57 |  |  | P & Laying Interlocking Tiles on side Berms In L Block BRS Nagar Ward No 72 |  |  |  | MC Funds / General Quota | MC Funds |  | 62.66 | 42.88 | 1624 14-02-2024 | [8 empty] | 24/EED 11-04-2025 | Varinder Singh Govt. Cont. | 35.7914 |  | 3 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Work Held up due to Upgradation of Sewer Line
586 | MCL-0591 | B&R | D |  | West | 57 |  |  | P/L 80mm Thick Interlocking Tiles in Various Streets of Sunet. W. No. 57 |  |  |  | MC Funds / General Quota | MC Funds |  | 35.18 | 39.13 | 1202 11-08-2025 | [8 empty] | 75/EED 08-10-2025 | Rakesh Kumar Contractor | 21.4141 |  | 5 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Work Held up due to Upgradation of Sewer Line
587 | MCL-0592 | B&R | D |  | West | 57 |  |  | P/L 60mm thick relaying tiles in streets of village Sunet near Shitla Mata Mandir W.No. 57 |  |  |  | MC Funds / General Quota | MC Funds |  | 23.06 | 42.66 | 2587 11-02-2026 | [8 empty] | 135/EED 18-03-2026 | Navdeep Gupta and Company | 13.2226 |  | 3 | [5 empty] | 0 |  |  | Not Started |  | work not started
588 | MCL-0593 | B&R | D |  | West | 58 |  |  | P/L 60mm Thick Perforated Interlocking Tiles on Side Berms of Barewal Sua Road W. No. 58 |  |  |  | MC Funds / General Quota | MC Funds |  | 62.29 | 33.99 | 1200 11-08-2025 | [8 empty] | 78/EED 08-10-2025 | Dynamic Tiles | 41.1176 |  | 5 | [5 empty] | 5 |  |  | In Progress |  | Work in Progress
589 | MCL-0594 | B&R | D |  | West | 58 |  |  | P/L 60mm Thick Perforated Interlocking Tiles on Side Berms of Magnet Resort Road W. No. 58 |  |  |  | MC Funds / General Quota | MC Funds |  | 82.56 | 36.96 | 1773 13-10-2025 | [8 empty] | 93/EED 02-12-2025 | R. K. Construction Co. | 52.0458 |  | 5 | [5 empty] | 5 |  |  | In Progress |  | Work in Progress
590 | MCL-0595 | B&R | D |  | West | 59 |  |  | Providing and Laying interlocking tiles on side berms of road in Mahaveer nagar Ward no 74. |  |  |  | MC Funds / General Quota | MC Funds |  | 65.29 | 37.99 | 860 06-05-2025 | [8 empty] | 48/EED 29-10-2024 | M/s Apex Developers | 40.4863 |  | 3 | [5 empty] | 80 |  |  | In Progress |  | Work in Progress & Case Approved by F&CC Res. no.860 Dt. 6-5-25 for Change of Site for Motar Wali Gali
591 | MCL-0596 | B&R | D |  | West | 61 |  |  | Prov. and laying perforated interlocking tiles in various streets of w. no. 76 |  |  |  | MC Funds / General Quota | MC Funds |  | 69.54 | 32 | 3006 Dt. 08-11-2024 | [8 empty] | 42//EED 08-05-2025 | Glisten | 47.22 |  | 3 | [5 empty] | 30 |  |  | In Progress |  | work in progress
592 | MCL-0597 | B&R | D |  | West | 63 |  |  | Prov. and fixing of 60mm thick interlocking tiles on side berms of different area Kitchlu Nagar Block E, F and G W. No. 77 |  |  |  | MC Funds / General Quota | MC Funds |  | 80.08 | 37 | 2386 Dt. 23-08-2024 | [8 empty] | 35/EED 28-04-2025 | M/s Dynamic tiles | 50.45 |  | 4 | [5 empty] | 40 |  |  | In Progress |  | Work in progress
593 | MCL-0598 | B&R | D |  | West | 65 |  |  | P/F of 60mm Interlocking Tiles in various streets of Prem Nagar ward no 65. |  |  |  | MC Funds / General Quota | MC Funds |  | 66.54 | 36.99 | 1216 Dt. 11-08-2025 | [8 empty] | 99/EED 09-02-2026 | M/s Apex developers | 41.93 |  | 3 | [5 empty] | 0 |  |  | Not Started |  | Work in Progress
594 | MCL-0599 | B&R | D |  | West | 71 |  |  | P/L Perforated interlocking tiles on side berms of Collage Road and Hira Singh Road |  |  |  | MC Funds / General Quota | MC Funds |  | 49.62 | 35 | 651 Dt. 09-04-2025 | [8 empty] | 62/EED 19-05-2025 | Dynamic Tiles | 32.25 |  | 3 | [5 empty] | 90 |  |  | In Progress |  | Ongoing Work
595 | MCL-0600 | B&R | D |  | West | 71 |  |  | P/L Perforated interlocking tiles on side berms of various streets in Mall Enclave |  |  |  | MC Funds / General Quota | MC Funds |  | 32.81 | 41 | 652 Dt. 09-04-2025 | [8 empty] | 61/EED 19-05-2025 | Dynamic Tiles | 19.35 |  | 3 | [5 empty] | 60 |  |  | In Progress |  | Ongoing Work
596 | MCL-0601 | B&R | D |  | West | 57 |  |  | P/L RMC (M-30) in Various Streets of Sunet. W. No. 57 |  |  |  | MC Funds / General Quota | MC Funds |  | 49.89 | 42.66 | 2591 11-02-2026 | [8 empty] | 118/EED 18-03-2026 | M/s Navdeep gupta & company | 28.6069 |  | 3 | [5 empty] | 60 |  |  | In Progress |  | Work in Progress
597 | MCL-0602 | B&R | D |  | West | 62 |  |  | P/Laying of RMC M-30 in streets of Mandeep Nagar ward no 62 |  |  |  | MC Funds / General Quota | MC Funds |  | 99.3 | 41.68 | 840 06.05.2025 | [8 empty] | 98/EED 05.02.2026 | M/s Navdeep gupta & company | 57.91 |  | 4 | [5 empty] | 80 |  |  | In Progress |  | Work in progress
598 | MCL-0603 | B&R | D |  | West | 62 |  |  | P/L of RMC M-30 in balance streets of Punj Peer road ward no 62 |  |  |  | MC Funds / General Quota | MC Funds |  | 30.31 | 41.82 | 839 06.05.2025 | [8 empty] | 97/EED 05.02.2026 | M/s Navdeep gupta & company | 17.63 |  | 3 | [5 empty] | 5 |  |  | In Progress |  | Work in progress
599 | MCL-0604 | B&R | D |  | West | 63 |  |  | P/L of RMC M-30 in Haqiqat nagar ward no 63. |  |  |  | MC Funds / General Quota | MC Funds |  | 33.67 | 34.51 | 690 Dt. 09-04-2025 | [8 empty] | 58/EED 19-05-2025 | M/s K.S Constructions | 22.05 |  | 3 | [5 empty] | 80 |  |  | In Progress |  | Work in progress
600 | MCL-0605 | B&R | D |  | West | 55 |  |  | Repair and renovation of various parks and sprinkler system in parks w. no. 55 |  |  |  | Rangla Punjab | Rangla Punjab |  | 20 | 7.77 | In Anticipation | [8 empty] | 28/EED 13-05-2026 | M/s Subodh Batish | 18.45 |  | 3 | [5 empty] | 10 |  |  | In Progress |  | Work Order Issued
601 | MCL-0606 | B&R | D |  | West | 59 |  |  | Repair and renovation by laying 60mm Thick Interlocking Tiles in streets of sanjha sahib gurudwara to village barewal T point of W. no. 59 |  |  |  | Rangla Punjab | Rangla Punjab |  | 10 | 12.12 | In Anticipation | [8 empty] | 29/EED 13-05-2026 | M/s Kohinoor Builders | 8.79 |  | 1 | [5 empty] | 50 |  |  | In Progress |  | Work in Progress
602 | MCL-0607 | B&R | D |  | West | 60 |  |  | Construction of Public Library in Gurdev Nagar in W. no. 60 |  |  |  | Rangla Punjab | Rangla Punjab |  | 12 | -2.05 | In Anticipation | [8 empty] | 27/EED 13-05-2025 | M/s Kohinoor Builders | 11.75 |  | 2 | [8 empty] | Not Started | Site not clear, Councillor ro provide clear land. SE/Xen to follow up and finalise. Proposed to be made in ward. | Work Order Issued
603 | MCL-0608 | B&R | D |  | West | 60 |  |  | Construction of Cricket Play ground Gurdev Nagar in W. no. 60 |  |  |  | Rangla Punjab | Rangla Punjab |  | 5 | -3.99 | In Anticipation | [8 empty] | 24/EED 13-05-2025 | MAA Chintpurani Construction | 4.8 |  | 2 | [8 empty] | Not Started | Land Issue, Councillor to provide land by 10/07/26 | Work Order Issued
604 | MCL-0609 | B&R | D |  | West | 63 |  |  | Construction of Joybox or Playground at Green Belt opp. Polytechnic College ward no 63. |  |  |  | Rangla Punjab | Rangla Punjab Scheme |  | 27.23 | 16.89 | In Anticipation | [8 empty] | 26/EED 13-05-2026 | M/s Teg Builders | 22.63 |  | 3 | [5 empty] | 5 |  |  | In Progress |  | Work in progress
605 | MCL-0610 | B&R | D |  | West | 72 |  |  | Construction of additional rooms at Ayurvedic Dispensary jawahar nagar camp near bus stand in W. no. 72 |  |  |  | Rangla Punjab | Rangla Punjab-1 |  | 15 | 8.77 | In Anticipation | [8 empty] | 25/EED 13-05-2026 | M/s Smridhi Construction | 13.68 |  | 2 | [5 empty] | 10 |  |  | In Progress |  | Work in progress
606 | MCL-0611 | B&R | D |  | West | New Ward No |  |  | Name of Work |  |  |  | Viveki Funds | Head |  | Est. Amount (In Lacs) | OAS (%) | TAC/F&CC resolution no. | [8 empty] | Work Order No. & Date | Name of Agency | Tender Amount (In Lacs) |  | Time Limit (in Months) | [8 empty] | Not Started |  | Remarks/Status
607 | MCL-0612 | B&R | D |  | West | 54 |  |  | Repair & Renovation of Jawaddi Dharmshalla |  |  |  | Viveki Funds | Viveki Funds |  | 16.66 | 20.1 | 2548 24-09-2024 | [8 empty] | 22/EED 11-04-2025 | M/s Smridhi Const. | 13.3113 |  | 6 | [5 empty] | 90 |  |  | In Progress |  | Work in Progress
608 | MCL-0613 | B&R | D |  | West | 57 |  |  | Repair & Renovation of Ravidass Dharmshalla Village Sunet |  |  |  | Viveki Funds | Viveki Funds |  | 16.67 | 20.1 | 2548 24-09-2024 | [8 empty] | 20/EED 11-04-2025 | M/s Smridhi Const. | 13.3193 |  | 2 | [5 empty] | 90 |  |  | In Progress |  | Work in Progress
609 | MCL-0614 | B&R | D |  | West | 57 |  |  | Repair & Renovation of Dharmshalla Near Masjid |  |  |  | Viveki Funds | Viveki Funds |  | 16.67 | 18.78 | 274 26-03-2025 | [8 empty] | 21/EED 11-04-2025 | M/s Smridhi Const. | 13.5394 |  | 2 | [5 empty] | 60 |  |  | In Progress |  | Work in Progress
610 | MCL-0615 | B&R | D |  | West | 55 |  |  | Laying SDBC on Main Road from Zone-D Office to FZR Road Ward No.55 |  |  |  | N-CAP | N-CAP |  | 73.08 | 26.09 | 1861 13-10-2025 | [8 empty] | 141/EED 25-03-2026 | Maruti Construction Co. | 54.01 |  | 5 | [5 empty] | 95 |  |  | In Progress |  | Work in progress
611 | MCL-0616 | B&R | D |  | West | 59 |  |  | Laying SDBC on Main Road From Environmental Friendly Park to Mahaveer Enclave. W. No. 59 |  |  |  | N-CAP | N-CAP |  | 30.55 | 18.08 | 1771 13-10-2025 | [8 empty] | 138/EED 25/03/2026 | Maruti Construction Co. | 25.0266 |  | 3 | [5 empty] | 95 |  |  | In Progress |  | Work in progress
612 | MCL-0617 | B&R | D | D2 | West | 53 |  |  | Construction Old Rooms In Guru Teg Bahadur Hospital,Shastri Nagar,Model Town,Ludhiana |  |  |  | MPLAD Funds | MPLAD Funds |  | 10 | 4.44 | [9 empty] | 15/EED 07/05/2026 | M/s Kohinoor Builders | 9.56 | [10 empty] | Not Started |  | Work Order Issue
613 | MCL-0618 | B&R | D | D3 | West | 55 |  |  | Installation of Swings & Development of Parks in GEE Green Welfare Society Park, 97-G BRS Nagar W. No. 55 |  |  |  | MPLAD Funds | MPLAD Funds |  | 5 | 5.12 | [9 empty] | 107/EED 05/03/2026 | M/s Kohinoor Builders | 4.744 | [7 empty] | 15 |  |  | In Progress |  | Work Order Issue
614 | MCL-0619 | B&R | D | D3 | West | 55 |  |  | Construction of Canopy and Benches in Flowerdale Park, B-Block BRS Nagar W. No. 55 |  |  |  | MPLAD Funds | MPLAD Funds |  | 5 | 1.13 | [9 empty] | 108/EED 05/03/2026 | M/s Varinder Singh Govt. Contractor | 4.9435 | [7 empty] | 70 |  |  | In Progress |  | Work Order Issue
615 | MCL-0620 | B&R | D | D3 | West | 55 |  |  | Development of Public Parks with Swings, Foothpath, Benches & Grills W. No. 55 (E, F, H, I, J Blocks of Sarabha Nagar and C Block of BRS Nagar) |  |  |  | MPLAD Funds | MPLAD Funds |  | 10 | 11 | [9 empty] | 109/EED 05/03/2026 | M/s Ram Parkash kakkar | 8.9 | [10 empty] | Not Started |  | Work Order Issue
616 | MCL-0621 | B&R | D | D3 | West | 55 |  |  | Development of Public Parks with Installation of Swings & Benches etc. in Park No. 245 BRS Nagar W. No. 55 |  |  |  | MPLAD Funds | MPLAD Funds |  | 3 | 4.55 | [9 empty] | 110/EED 05/03/2026 | M/s Kohinoor Builders | 2.8635 | [7 empty] | 100 |  |  | Completed |  | Work Order Issue
617 | MCL-0622 | B&R | D | D3 | West | 56 |  |  | Development of Public Parks with Installation of Steel Benches & Swings W. No. 56 (Vikas & SBS Nagar, G & D Block SBS Nagar, Housefed Flats) |  |  |  | MPLAD Funds | MPLAD Funds |  | 10 | 11 | [9 empty] | 111/EED 05/03/2026 | M/s Ram Parkash kakkar | 8.9 | [7 empty] | 60 |  |  | In Progress |  | Work Order Issue
618 | MCL-0623 | B&R | D | D3 | West | 56 |  |  | Installation of Swings and Steel (Cast Iron) Benches in F-Block SBS Nagar W. No. 56 |  |  |  | MPLAD Funds | MPLAD Funds |  | 3 | 15.99 | [9 empty] | 112/EED 05/03/2026 | M/s Maa Chintpurni Construction | 2.5203 | [7 empty] | 30 |  |  | In Progress |  | Work Order Issue
619 | MCL-0624 | B&R | D | D3 | West | 58 |  |  | Development of Public Parks with Installation of Swings W. No. 58 (A to D Blocks of Rajguru Nagar and J Block of BRS Nagar, Housing Board, B Block Aggar Nagar) |  |  |  | MPLAD Funds | MPLAD Funds |  | 10 | 11 | [9 empty] | 113/EED 05/03/2026 | M/s Ram Parkash kakkar | 8.9 | [7 empty] | 10 |  |  | In Progress |  | Work Order Issue
620 | MCL-0625 | B&R | D | D3 | West | 58 |  |  | Development of Public Parks with Swings, Foothpath, Canopy, Benches, Boundary Wall W. No. 58 (J Block Park Opp. Lodhi Club) |  |  |  | MPLAD Funds | MPLAD Funds |  | 10 | 7.12 | [9 empty] | 114/EED 05/03/2026 | M/s Kohinoor Builders | 9.288 | [7 empty] | 30 |  |  | In Progress |  | Work Order Issue
621 | MCL-0626 | B&R | D | D3 | West | 58 |  |  | Installation of Cement Benches and Construction of Shed (10' x 8') in Public Places, Gate No. 1 Verka Plant W. No. 58 |  |  |  | MPLAD Funds | MPLAD Funds |  | 1 | 6.66 | [9 empty] | 14/EED 07/05/2026 | M/s Kohinoor Builders | 0.93 | [10 empty] | Not Started |  | Work Order Issue
622 | MCL-0627 | B&R | D | D3 | West | 58 |  |  | Installation of Swings & Benches in B-Block Aggar Nagar W. No. 58 |  |  |  | MPLAD Funds | MPLAD Funds |  | 1.5 | 3.1 | [9 empty] | 115/EED 05/03/2026 | M/s Kohinoor Builders | 1.4535 | [7 empty] | 100 |  |  | Completed |  | Work Order Issue
623 | MCL-0628 | B&R | D | D3 | West | 58 |  |  | Construction of Badminton Court in B-Block Aggar Nagar, 524 - B W. No. 58 |  |  |  | MPLAD Funds | MPLAD Funds |  | 4 | 7.17 | [9 empty] | 17/EED 07/05/2026 | M/s Kohinoor Builders | 3.71 | [7 empty] | 40 |  |  | In Progress |  | Work Order Issue
624 | MCL-0629 | B&R | D | D3 | West | 58 |  |  | Installation of Cement Benches W. No. 58 |  |  |  | MPLAD Funds | MPLAD Funds |  | 0.29 | 7.77 | [9 empty] | 13/EED 07/05/2026 | M/s Kohinoor Builders | 0.27 | [10 empty] | Not Started |  | Work Order Issue
625 | MCL-0630 | B&R | D | D3 | West | 59 |  |  | Installation of Swings & Benches in Parks A-Block Aggar Nagar W. No. 59 |  |  |  | MPLAD Funds | MPLAD Funds |  | 1.5 | 3.12 | [9 empty] | 116/EED 05/03/2026 | M/s Kohinoor Builders | 1.4532 | [7 empty] | 100 |  |  | Completed |  | Work Order Issue
626 | MCL-0631 | B&R | D | D4 | West | 60 |  |  | Repair & Renovation of Kumra Park in Gurdev Nagar w no 60 |  |  |  | MPLAD Funds | MPLAD Funds |  | 3 | 7.77 | [9 empty] | 16/EED 07/05/2026 | M/s Kohinoor Builders | 2.77 | 2026-06-29 | [6 empty] | 20 |  |  | In Progress |  | Work Order Issue
627 | MCL-0632 | B&R | D | D1 | West | 62 |  |  | (Installation of swings, open gym and jogging tracks, construction of boundary wall, installation of 25 benches.) Develpoment of different public parks in W. no. 62 |  |  |  | MPLAD Funds | MPLAD Funds |  | 10 | 22.41 | [9 empty] | 158/EED 25/03/2026 | Bharat Nirman Infracon | 7.76 | [7 empty] | 10 |  |  | In Progress |  | Work Order Issue
628 | MCL-0633 | B&R | D | D1 | West | 63 |  |  | Development of public park w.no.63. |  |  |  | MPLAD Funds | MPLAD Funds |  | 10 | 24.93 | [9 empty] | 159/EED 25/03/2026 | Bharat Nirman Infracon | 7.5 | [7 empty] | 10 |  |  | In Progress |  | Work Order Issue
629 | MCL-0634 | B&R | D | D1 | West | 64 |  |  | Development of different public park W. no. 64.(Providing open Gym and benches.) |  |  |  | MPLAD Funds | MPLAD Funds |  | 4 | 24.99 | [9 empty] | 160/EED 25/03/2026 | Bharat Nirman Infracon | 3 | [7 empty] | 100 |  |  | Completed |  | Work Order Issue
630 | MCL-0635 | B&R | D | D1 | West | 64 |  |  | Construction of rooms at Adarsh Public school Kapil Park W no 64 |  |  |  | MPLAD Funds | MPLAD Funds |  | 15 | 5.15 | [9 empty] | 21/EED 07/05/2026 | M/s Kohinoor Builders | 14.23 | [10 empty] | Not Started |  | Work Order Issue
631 | MCL-0636 | B&R | D | D1 | West | 65 |  |  | Development of different public parks in w.no.65.(P/F mini mast lights and swings, footpath, benches, boundry walls, open gym, w.no. 65) |  |  |  | MPLAD Funds | MPLAD Funds |  | 10 | 23.49 | [9 empty] | 161/EED 25/03/2026 | Bharat Nirman Infracon | 7.65 | [7 empty] | 10 |  |  | In Progress |  | Work Order Issue
632 | MCL-0637 | B&R | D | D4 | West | 69 |  |  | P& Fixing Benches and Open Gym equipment in parks of Officer colony, Tagore Nagar, Kitchlu Nagar, Malerkotla House, Green Park, Police Line and Rajpura Pind W.No.69 |  |  |  | MPLAD Funds | MPLAD Funds |  | 10 | 24.8 | [9 empty] | 157/EED 25/03/2026 | M/s Ram Parkash kakkar | 7.52 | [7 empty] | 10 |  |  | In Progress |  | Work Order Issue
633 | MCL-0638 | B&R | D | D4 | West | 71 |  |  | Construction of Rooms at Goverment Collage for Girls Fzr Road Ldh |  |  |  | MPLAD Funds | MPLAD Funds |  | 25 | 7.26 | [9 empty] | 18/EED 07/05/2026 | M/s Kohinoor Builders | 23.18 | [10 empty] | Not Started |  | Work Order Issue
634 | MCL-0639 | B&R | D | D4 | West | 71 |  |  | Repair & Renovation of Park in Park Streets Collage Road W no 71 |  |  |  | MPLAD Funds | MPLAD Funds |  | 1 | 5.55 | [9 empty] | 19/EED 07/05/2026 | M/s Kohinoor Builders | 0.944 | [7 empty] | 40 |  |  | In Progress |  | Work Order Issue
635 | MCL-0640 | B&R | D | D4 | West | 71 |  |  | Repair & Renovation of park on Sangat road Backside Church Yard |  |  |  | MPLAD Funds | MPLAD Funds |  | 1 | 5.66 | [9 empty] | 20/EED 07/05/2026 | M/s Kohinoor Builders | 0.943 | [7 empty] | 40 |  |  | In Progress |  | Work Order Issue
636 | MCL-0641 | B&R | D | D4 | West | 73 |  |  | Providing Water Tanker in w no 73 of west Constituency Ludhiana |  |  |  | MPLAD Funds | MPLAD Funds |  | 2 | 8.88 | [9 empty] | 12/EED 07/05/2026 | M/s Kohinoor Builders | 1.82 | [10 empty] | Not Started |  | Work Order Issue
637 | MCL-0642 | B&R | D | D4 | West | 73 |  |  | P & Fixing Benches and open Gym Equipment in parks of Ashok Nagar,Sham Nagar W.No.73 |  |  |  | MPLAD Funds | MPLAD Funds |  | 8 | 2.89 | [9 empty] | 156/EED 25/03/2026 | M/s Varinder Singh Govt. Contractor | 7.77 | [10 empty] | Not Started |  | Work Order Issue

## B&R
| Project ID | Branch | Zone | Sub-Zone | Assembly Constituency | Ward | Nature of Work | E office number | Name of Work / Description | Length (Rmt) | Road Width (Ft) | No. of Units | Fund / Quota Type | Quota (as recorded) | Current Status | Est./Vetted Cost (Lacs) | OAS % | Resolution No. & Date | Administrative Approval (Y/N) | Technical Sanction (Y/N) | TS Accorded By | Accounts / SE Certificate (Y/N) | Tender Float Date | Tender End Date | Technical Evaluation (Y/N) | Financial Evaluation (Y/N) | Work Order No. & Date | Executing Agency | Tender Cost (Lacs) | Start Date | Time Limit (Months) | Scheduled End Date | Actual Completion Date | Supervising Officer (SE) | Third Party Inspection (Y/N) | Completion Certificate (Y/N) | Physical Progress % | Financial Progress % | Expenditure / Payment (Lacs) | Status | Issues / Bottlenecks | Remarks / Status Notes | Geo-tagged Photograph (Link) | Last Updated On
1 | MCL-0001 | B&R | B | B4 | East | 19 | Parks & Green Belts |  | Repair & Renovation of various parks in LIG W No.19 |  |  |  | MC Funds / General Quota | General |  | 62.03 | 39.99 | 3189 22.11.2024 | [8 empty] | 82 dt 04.12.2024 | M/s Prince Sharma | 37.22 | 04.12.2024 | 6 | 03.06.2025 |  |  |  |  | 80 |  | 24.61 | In Progress |  | Work is in Progress
2 | MCL-0002 | B&R | B | B3 | East | 12 | Roads - Interlocking Tiles |  | P/F I/tiles in various streets of W No.12 | 2100 | 11 |  | MC Funds / General Quota | General |  | 93.51 | 42.99 | 3190 22.11.2024 | [8 empty] | 83 dt 04.12.2024 | M/s Apex Developers | 53.31 | 04.12.2024 | 5 | 03.05.2025 |  |  |  |  | 60 |  | 30.00 | Delayed/Held Up |  | Work was held up due to non-laying of W/s line in Guru Nanak Estate . Now same has been laid. Work is in progress
3 | MCL-0003 | B&R | B | B2 | East | 17 & 19 | Roads - Interlocking Tiles |  | P/F I/tiles in streets of Guru Arjun Dev Nagar, Jaswant Nagar and Indrapuri St No.4 W No.17 & 19 | 430.49 | 11 |  | MC Funds / General Quota | General |  | 20.81 | 41.65 | 3141 22.11.2024 | [8 empty] | 86 dt 04.12.2024 | Capital Const Co. | 12.14 | 04.12.2024 | 3 | 03.03.2025 |  |  |  |  | 25 |  | 5.00 | Delayed/Held Up |  | Heldup due to Dispute at site for the balance work
4 | MCL-0004 | B&R | B | B2 | East | 16 | Parks & Green Belts |  | Const of Park on Bhamian Road Near Football Ground W No.16 | 0 |  |  | MC Funds / General Quota | General |  | 50 | 31.89 | 355 dt 26.03.2025 | [8 empty] | 01 16.04.2025 | M/s Teg Builders | 34.06 | 16.04.2025 | 6 | 15.10.2025 |  |  |  |  | 10 |  | 0.0 | In Progress |  | Heldup due to construction of water tank by O&M Cell
5 | MCL-0005 | B&R | B | B3 | East | 12 | Roads - Interlocking Tiles |  | P/F I/tiles in streets of Juneja Colony and Karamsar Colony W No.12 | 1022.87 | 11 |  | MC Funds / General Quota | General |  | 50 | 41.99 | 177 dt 26.03.2025 | [8 empty] | 9 16.04.2025 | Apex Developers | 29 | 16.04.2025 | 4 | 15.08.2025 |  |  |  |  | 15 |  | 0 | In Progress |  | Work is in Progress
6 | MCL-0006 | B&R | B | B3 | East | East | Roads - Interlocking Tiles |  | P/F 80mm thick Interlocking tiles in streets of Mohalla New Subhash Nagar on Towerline No. 2 & 5 and St No.10 & St No.2/10 & 2/11 of Subhash Nagar W No.10 | 679.27 | 11 |  | MC Funds / General Quota | General |  | 29.69 | 41.55 | 179 dt 26.03.2025 | [8 empty] | 10 16.04.2025 | Capital Const Co. | 17.35 | 16.04.2025 | 3 | 15.07.2025 |  |  |  |  | 30 |  | 0 | In Progress |  | Work heldup due to upgradation of W/s lines, Now same has been completed. Work is in progress now.
7 | MCL-0007 | B&R | B | B3 | East | 9 | Roads - Interlocking Tiles |  | P/F I/tiles in remaining streets of Shastri Nagar and link of New Shakti Nagar W No.09 | 656.71 | 11 |  | MC Funds / General Quota | General |  | 34.61 | 42.61 | 180 dt 26.03.2025 | [8 empty] | 11 16.04.2025 | T&G Const Co. | 19.86 | 16.04.2025 | 3 | 15.07.2025 |  |  |  |  | 70 |  | 8.78 | In Progress |  | Work heldup due to upgradation of W/s lines in the balance area
8 | MCL-0008 | B&R | B | B4 | East | 21 | Roads - Interlocking Tiles |  | P/F I/tiles in streets No.2 of Hargobindpura & Links W No.21 | 733.54 | 11 |  | MC Funds / General Quota | General |  | 34.21 | 41.55 | 185 dt 26.03.2025 | [8 empty] | 13 16.04.2025 | Capital Const Co. | 19.99 | 16.04.2025 | 3 | 15.07.2025 |  |  |  |  | 90 |  | 13.50 | In Progress |  | Balance work was heldup due to upgradation of W/S line in the balance area, now same has been laid. Work is in Progress now.
9 | MCL-0009 | B&R | B | B3 | East | 11 | Roads - Interlocking Tiles |  | P/F I/tiles in streets of Sandhu Colony | 3484.15 | 11 |  | MC Funds / General Quota | General |  | 145.87 | 44.09 | 1483 dt 13.10.2025 | [8 empty] | 20 11.07.2025 | T&G Const Co. | 81.55 | 11.07.2025 | 6 | 10.01.2026 |  |  |  |  | 90 |  | 75.64 | In Progress |  | Work is in Progress
10 | MCL-0010 | B&R | B | B2 | East |  | Others |  | Providing & Fixing of Sign Boards in different areas of Sub Zone B2 | 0 | 0 |  | MC Funds / General Quota | General |  | 34.03 | 32 | Approved inanticipation of F&CC | [8 empty] | 22 14.08.2025 | Glisten | 23.14 | 14.08.2025 | 3 | 13.11.2025 |  |  |  |  | 50 |  | 13.62 | In Progress |  | Work is in Progress
11 | MCL-0011 | B&R | B | B3 | East |  | Others |  | Providing & Fixing of Sign Boards in different areas of Sub Zone B3 | 0 | 0 |  | MC Funds / General Quota | General |  | 43.13 | 32 | Approved inanticipation of F&CC, | [8 empty] | 23 14.08.2025 | Glisten | 29.33 | 14.08.2025 | 4 | 13.12.2025 |  |  |  |  | 60 |  | 17.43 | In Progress |  | Work is in Progress
12 | MCL-0012 | B&R | B | B3 | East | 12 | Parks & Green Belts |  | Development of Green Belt on Towerline No.2 and 5 | 0 | 0 |  | MC Funds / General Quota | General |  | 309.16 | 29.99 | 1787 dt 13.10.2025 | [8 empty] | 24 27.08.2025 | RK Const Co. | 216.44 | 27.08.2025 | 6 | 26.02.2026 |  |  |  |  | 60 |  | 70.00 | In Progress |  | Work is in Progress |  | As per councillor, work is extremely slow.
13 | MCL-0013 | B&R | B | B3 | East | 16,18,20 &29 | Others |  | Construction of Central Verge on Tajpur raod . | 0 | 0 |  | MC Funds / General Quota | General |  | 217.47 | 14.15 | 1786 dt 13.10.2025 | [8 empty] | 25 27.08.2025 | Navyug Comapany | 186.7 | 27.08.2025 | 6 | 26.02.2026 |  |  |  |  | 40 |  | 82.88 | In Progress |  | Work is in Progress
14 | MCL-0014 | B&R | B | B4 | East | 19 | Parks & Green Belts |  | P/F different type of Open garden gym machines in ward no 19. | 0 | 0 |  | MC Funds / General Quota | General |  | 16.03 | 36.99 | 1669 dt 13.10.2025 | [8 empty] | 27 15.01.2026 | Khalsa Exports Pvt Ltd. | 10.1 | 15.01.2026 | 2 | 14.03.2026 | [6 empty] | 0 | Not Started |  | Inauguration is to be done
15 | MCL-0015 | B&R | B | B4 | East | 19 | Parks & Green Belts |  | Repair & Renovation of various Park in Sec 39 Block-I | 0 | 0 |  | MC Funds / General Quota | General |  | 36.2 | 28.59 | 1666 dt 13.10.2025 | [8 empty] | 32 15.01.2026 | RK Const Co. | 25.85 | 15.01.2026 | 3 | 14.04.2026 |  |  |  |  | 75 |  | 14.68 | In Progress |  | Work is in Progress
16 | MCL-0016 | B&R | B | B4 | East | 19 | Parks & Green Belts |  | Repair & Renovation of various Park in Sec 39 Block-II | 0 | 0 |  | MC Funds / General Quota | General |  | 38.85 | 28.59 | 1667 dt 13.10.2025 | [8 empty] | 33 15.01.2026 | RK Const Co. | 27.74 | 15.01.2026 | 3 | 14.04.2026 |  |  |  |  | 75 |  | 19.77 | In Progress |  | Work is in Progress
17 | MCL-0017 | B&R | B | B4 | East | 19 | Others |  | Renovation of Disposal site and Fixing of Information Board at enterance of Sec-39 near Vardhman Chowk W No.19 | 0 | 0 |  | Councillor Quota (CQ) | Councillor |  | 20.7 | 5.89 | 2493 dt 05.01.2026 Workorder to be issued | [8 empty] | 43 15.01.2026 | Teg Builders | 19.48 | 15.01.2026 | 2 | 14.03.2026 |  |  |  |  | 80 |  | 10.10 | In Progress |  | Work is in Progress
18 | MCL-0018 | B&R | B | B3 | East | 16 | Roads - RMC / Cement Concrete |  | Const of Road by laying RMC from Gita Nagar Pully to Vijay Nagar Pully W No.16 | 1085.06 | 11 |  | MC Funds / General Quota | General |  | 66.47 | 36.69 | 2488 dt 05.01.2026 | [8 empty] | 44 15.01.2026 | RK Const Co. | 42.08 | 15.01.2026 | 4 | 14.05.2026 |  |  |  |  | 5 |  | 0 | In Progress |  | Work heldup due to upgradation of Sewer line
19 | MCL-0019 | B&R | B | B4 | Sahnewal |  | Others |  | Providing & Fixing of Sign Boards in different areas of Sub Zone B4 | 0 | 0 |  | MC Funds / General Quota | General |  | 36.92 | 32 | 1571 dt 13.10.2025 | [8 empty] | 46 29.01.2026 | Glisten | 25.11 | 46 29.01.2026 | 3 | 28.04.2026 |  |  |  |  | 50 |  | 2.49 | In Progress |  | Work is in Progress
20 | MCL-0020 | B&R | B | B4 | East | 19 | Parks & Green Belts |  | P/F of Garden Benches in various park of W No.19 | 0 | 0 |  | MC Funds / General Quota | General |  | 7.91 | 18.5 | 1668 dt 13.10.2025 | [8 empty] | 48 29.01.2026 | Glisten | 6.45 | 48 29.01.2026 | 1 | 28.02.2026 | [6 empty] | 0 | Not Started |  | Inauguration is to be done
21 | MCL-0021 | B&R | B | B4 | East | 28 | Parks & Green Belts |  | P/F Garden Benches, Open Gym Machines & Children Playing Equipments in W No.28 | 0 | 0 |  | MC Funds / General Quota | General |  | 12.92 | 20.5 | 1671 dt 13.10.2025 | [8 empty] | 49 16.02.2026 | Glisten | 10.27 | 49 16.02.2026 | 1 | 15.03.2026 | [6 empty] | 0 | Not Started |  | Inauguration is to be done
22 | MCL-0022 | B&R | B | B3 | East | 13 | Others |  | Development of Badminton Court in Banda Bhadur Colony near Shamshanghat W No.13 | 0 | 0 |  | MC Funds / General Quota | General |  | 7.92 | 2.22 | Approved inanticipation by W/Mayor vide dt 21.01.2026 & Regular approval by F&CC 2779 dt 19.02.2026 | [8 empty] | 50 16.02.2026 | Sachdeva Art Gallery | 7.74 | 16.02.2026 | 1 | 15.03.2026 |  |  |  |  | 70 |  | 4.00 | In Progress |  | Work is in Progress
23 | MCL-0023 | B&R | B | B4 | East | 21 | Roads - Bituminous |  | Const.of bituminous road in GRD colony | 2329.27 | 11 |  | MC Funds / General Quota | General |  | 49.88 | 19.05 | 2522 dt 05.02.2026 | [8 empty] | 52 16.02.2026 | Somaya Infrastructure | 40.38 | 16.02.2026 | 5 | 15.07.2026 | [6 empty] | 0 | Not Started |  | Work heldup due to upgradation of W/S lines
24 | MCL-0024 | B&R | B | B3 | East | 11 | Parks & Green Belts |  | Re-devlopment of New Shastri Nagar Park W No.11 | 0 |  |  | MC Funds / General Quota | General |  | 4.7 | 7.89 | 2520 dt 05.02.2026 | [8 empty] | 54 16.02.2026 | Teg Builders | 4.33 | 16.02.2026 | 3 | 15.05.2026 |  |  |  |  | 90 |  | 0 | In Progress |  | Work is in Progress
25 | MCL-0025 | B&R | B | B4 | East | 19 | Roads - Interlocking Tiles |  | P/F Perforated I/tiles on side berms of GRD Colony W NO.19 | 2329.27 | 11 |  | Councillor Quota (CQ) | Councillor |  | 24.53 | 30.35 | 2518 dt 05.02.2026 | [8 empty] | 55 16.02.2026 | Navyug Company | 17.08 | 16.02.2026 | 3 | 15.05.2026 |  |  |  |  | 5 |  | 0 | In Progress |  | Work heldup due to upgradation of sewerline.
26 | MCL-0026 | B&R |  |  | East |  | Roads - Bituminous |  | Upgradation of Gurudwara road urban estate phase 1&2 from Metro road to Jeewan Nagar chowk, Road along budha nallah from NHAI to MC limit , Main Bhadur Ke Road from Sabji Mandi upto MC Limit, Main New Azad Nagar 30' Road from Kainth Property Dealer upto Gaur Property Dealer and Roads of Onkar Vihar. | 14377.74 | 11 |  | SASCI | Special Assistance Scheme |  | 535.05 | 3.25 | 2675 dt 11.02.2026 | [8 empty] | 60 18.02.2026 | CH Builders Pvt. Ltd. | 517.66 | 18.02.2026 | 3 | 17.05.2026 |  |  |  |  | 10 |  | 0 | In Progress |  | Work is in Progress
27 | MCL-0027 | B&R |  |  | East |  | Roads - Bituminous |  | Upgradation of Main Metro Road from Jamalpur Chowk to Kangaroo Industry, Jaswant Singh Dental College to Delhi road via Sethi Sweets, Internal Roads of Sec-39, Road from Primary Govt School to NRI Police Station in Sec-39, Main Jain Colony road from Rahon Road to Swastik Enclave and Main Road of Guru Arjun Dev Nagar from GT Road upto Greenland School, Sabji Mandi Road from Chd road to Puda road, EWS colony main road from Jacha Bacha Hospital upto Tajpur road. | 28676.52 | 11 |  | SASCI | Special Assistance Scheme |  | 718.12 | 4.25 | 2873 dt 19.02.2026 | [8 empty] | 61 20.02.2026 | Kabir Infra Pvt. Ltd. | 687.6 | 20.02.2026 | 3 | 19.05.2026 |  |  |  |  | 25 |  | 0 | In Progress |  | Work is in Progress
28 | MCL-0028 | B&R | B | B2 | East | 20 | Roads - Bituminous |  | Const.of bituminous road in Sukhdev Nagar | 2009.45 | 11 |  | MC Funds / General Quota | General |  | 49.95 | 19.05 | 2769 dt 19.02.2026 | [8 empty] | 66 09.03.2026 | Somaya Infrastructure | 40.43 | 09.03.2026 | 5 | 08.08.2026 |  |  |  |  | 0 |  | 0 | Not Started |  | Heldup due to non avaiability of Bitumen
29 | MCL-0029 | B&R | B | B3 | East | 7 | Roads - Interlocking Tiles |  | P/F I/tiles in street No.5/1 to 5/6 & Links of New Subhash Nagar on Towerline No.5 W No.7 | 2015.85 | 11 |  | MC Funds / General Quota | General |  | 78.55 | 35.39 | 2771 dt 19.02.2026 | [8 empty] | 67 09.03.2026 | Navyug Company | 50.75 | 09.03.2026 | 5 | 08.08.2026 |  |  |  |  | 50 |  | 0 | In Progress |  | Work is in Progress
30 | MCL-0030 | B&R | B | B4 | East | 19 | Parks & Green Belts |  | Renovation of remaining Parks in Sec-39 Block- II W No.19 | 0 | 0 |  | Councillor Quota (CQ) | Councillor |  | 97.59 | 30.66 | 2761 dt 19.02.2026 | [8 empty] | 71 09.03.2026 | Apex Developers | 67.67 | 09.03.2026 | 5 | 08.08.2026 |  |  |  |  | 5 |  | 0 | In Progress |  | Work is in Progress
31 | MCL-0031 | B&R | B | B3 | East | 12 | Parks & Green Belts |  | Repair & Renovation of Sawtantar Nagar Park in W No.12 | 0 | 0 |  | MC Funds / General Quota | General |  | 18.99 | 13.89 | 2878 dt 19.02.2026 | [8 empty] | 72 09.03.2026 | Teg Builders & Varinder Singh Govt Contractor | 16.35 | 09.03.2026 | 3 | 08.06.2026 |  |  |  |  | 70 |  | 9.00 | In Progress |  | Work is in Progress
32 | MCL-0032 | B&R | B | B3 | East | 13 | Others |  | Development of Box Cricket in Banda Bhadur Colony near Shamshanghat W No.13 | 0 | 0 |  | MC Funds / General Quota | General |  | 30.16 | 5.89 | 2760 dt 19.02.2026 | [8 empty] | 75 09.03.2026 | Teg Builders & Varinder Singh Govt Contractor | 28.38 | 09.03.2026 | 4 | 08.07.2026 |  |  |  |  | 50 |  | 15.00 | In Progress |  | Work is in Progress
33 | MCL-0033 | B&R | B | B3 | East | 13 | Others |  | Construction of Entrance Gates for Karamsar Colony & Sutantar Nagar in w no.13. | 0 | 0 |  | MC Funds / General Quota | General |  | 26.34 | 2.89 | 2791dt 19.02.2026 | [8 empty] | 76 09.03.2026 | Teg Builders & Varinder Singh Govt Contractor | 25.58 | 09.03.2026 | 4 | 08.07.2026 | [6 empty] | 0 | Not Started |  | Inauguration is to be done
34 | MCL-0034 | B&R | B | B3 | East | 13 | Roads - Interlocking Tiles |  | P/Fixing I/tiles in Karamsar Colony & Nalwa Coloiny W No.13 | 2099.7 | 11 |  | Councillor Quota (CQ) | Councillor |  | 83.89 | 36.99 | 2770 dt 19.02.2026 | [8 empty] | 77 12.03.2026 | Apex Developers | 52.86 | 12.03.2026 | 4 | 11.07.2026 |  |  |  |  | 20 |  | 0 | In Progress |  | Work is in Progress
35 | MCL-0035 | B&R | B | B3 | East | 13 | Roads - Interlocking Tiles |  | P/Fixing I/tiles in streets of Grewal Colony & Raju Colony W No.13 | 1330.18 | 11 |  | Councillor Quota (CQ) | Councillor |  | 49.53 | 11.89 | 3436 dt 21.04.2026 | [8 empty] | 09 13.05.2026 | Teg Builders | 43.64 | 13.05.2026 | 4 | 12.09.2026 | [6 empty] | 0 | Not Started |  | Inauguration is to be done
36 | MCL-0036 | B&R | B | B3 | East | 13 | Roads - Interlocking Tiles |  | P/Fixing I/tiles in streets of Heera Vihar & Sutantar Nagar W No.13 | 1102.44 | 11 |  | Councillor Quota (CQ) | Councillor |  | 49.8 | 11.89 | 3435 dt 21.04.2026 | [8 empty] | 10 13.05.2026 | Varinder Singh Govt Contractor | 43.88 | 13.05.2026 | 4 | 12.09.2026 |  |  |  |  | 25 |  | 0 | In Progress |  | Work is in Progress
37 | MCL-0037 | B&R | B | B4 | East | 19 | Roads - RMC / Cement Concrete |  | Laying RMC in streets of New Kirti Nagar W No.19 | 222.87 | 11 |  | MC Funds / General Quota | General |  | 18.07 | 15.89 | 3434 dt 21.04.2026 | [8 empty] | 11 13.05.2026 | Teg Builders | 15.2 | 13.05.2026 | 3 | 12.08.2026 |  |  |  |  | 25 |  | 0 | In Progress |  | Work is in Progress
38 | MCL-0038 | B&R | B | B4 | East | 28 | Roads - Interlocking Tiles |  | P/F I/tiles in street of Saini Colony W No.28 | 1640.24 | 11 |  | Councillor Quota (CQ) | Councillor |  | 88.68 | 28.89 | 3433 dt 21.04.2026 | [8 empty] | 12 13.05.2026 | Teg Builders | 63.06 | 13.05.2026 | 5 | 12.10.2026 | [6 empty] | 0 | Not Started |  | Work heldup due to W/s Line
39 | MCL-0039 | B&R | B | B4 | East | 19 | Others |  | Const of RCC Boundary wall adj GRD Colony Sec-39 W No.19 | 0 |  |  | MC Funds / General Quota | General |  | 24.65 | 5.89 | 3432 dt 21.04.2026 | [8 empty] | 13 13.05.2026 | Varinder Singh Govt Contractor | 23.5 | 13.05.2026 | 3 | 12.08.2026 |  |  |  |  | 10 |  | 0 | In Progress |  | Work is in Progress
40 | MCL-0040 | B&R | B | B4 | East | 28 | Roads - Bituminous |  | Const.of bituminous road of Moti Nagar Block-C W No.28 | 1776.52 | 11 |  | Councillor Quota (CQ) | Councillor |  | 65.52 | 5 | 3431 dt 21.04.2026 | [8 empty] | 14 13.05.2026 | Shiva Construction | 62.24 | 13.05.2026 | 5 | 12.10.2026 | [6 empty] | 0 | Not Started |  | Inauguration is to be done
41 | MCL-0041 | B&R | B | B3 | East | 13 | Roads - Interlocking Tiles |  | P/Fixing I/tiles in left side streets of Banda Singh Bhadur Colony W No.13 | 1812.5 | 11 |  | MC Funds / General Quota | General |  | 88.4 | 39.99 | 3429 dt 21.04.2026 | [8 empty] | 16 13.05.2026 | Varinder Singh Govt Contractor | 53.05 | 13.05.2026 | 6 | 12.11.2026 |  |  |  |  | 10 |  | 0 | In Progress |  | Work is in Progress
42 | MCL-0042 | B&R | B | B3 | East | 13 | Roads - Interlocking Tiles |  | P/Fixing I/tiles in right side streets of Banda Singh Bhadur Colony W No.13 | 1513.72 | 11 |  | MC Funds / General Quota | General |  | 68.69 | 39.99 | 3428 dt 21.04.2026 | [8 empty] | 17 13.05.2026 | Varinder Singh Govt Contractor | 41.22 | 13.05.2026 | 5 | 12.10.2026 | [6 empty] | 0 | Not Started |  | Inauguration is to be done
43 | MCL-0043 | B&R | B | B3 | East | 13 | Roads - Interlocking Tiles |  | P/Fixing I/tiles in various Streets of juneja colony W No.13 | 2386.28 | 11 |  | MC Funds / General Quota | General |  | 76.4 | 28.64 | 3427 dt 21.04.2026 | [8 empty] | 18 13.05.2026 | Varinder Singh Govt Contractor | 54.52 | 13.05.2026 | 5 | 12.10.2026 | [6 empty] | 0 | Not Started |  | Inauguration is to be done
44 | MCL-0044 | B&R | B | B2 | East | 20 | Roads - Bituminous |  | Const.of bituminous road Guru Nanak Nagar Bhamian 27' Road | 698.48 | 11 |  | MC Funds / General Quota | General |  | 35.74 | 8.35 | Approved by W/Mayor dt 14.05.2026 inanticipation of F&CC, | [8 empty] | 23 27.05.2026 | Shiva Construction | 32.76 | 27.05.2026 | 5 | 26.10.2026 |  |  |  |  | 80 |  | 0 | In Progress |  | Work is in Progress
45 | MCL-0045 | B&R | B | B4 | Sahnewal | 28 | Roads - RMC / Cement Concrete |  | Const of road by laying RMC (M-30) in Ishwar colony W No.28 | 1298.17 | 11 |  | MC Funds / General Quota | General |  | 52 | 41.65 | 3205 29.11.2024 | [8 empty] | 75 dt 04.12.2024 | Capital Const Co. | 30.34 | 04.12.2024 | 4 | 03.05.2025 |  |  |  |  | 0 |  | 0 | Not Started |  | Heldup due to non laying of Sewerline
46 | MCL-0046 | B&R | B | B4 | Sahnewal | 28 | Roads - Interlocking Tiles |  | P/F 80mm thick I/Tiles in Balance streets of Prem Nagar & New Durga Colony W No.28 | 1578.96 | 11 |  | MC Funds / General Quota | General |  | 71.89 | 42.89 | 361 dt 26.03.2025 | [8 empty] | 15 16.04.2025 | T&G Const Co. | 41.06 | 16.04.2025 | 5 | 15.09.2025 |  |  |  |  | 50 |  | 20.66 | In Progress |  | Work was heldup due to upgradation of W/S Line, now same has been laid. Work is in Progress
47 | MCL-0047 | B&R | B | B4 | Sahnewal | 24 | Parks & Green Belts |  | Re-Development of Main Jeevan Nagar Park W No.24 | 0 |  |  | MC Funds / General Quota | General |  | 26.72 | 30.4 | 186 dt 26.03.2025 | [8 empty] | 16 16.04.2025 | Asis Builders | 18.6 | 16.04.2025 | 3 | 15.07.2025 |  |  |  |  | 80 |  | 17.46 | In Progress |  | Work is in Progress
48 | MCL-0048 | B&R | B | B4 | Sahnewal | 28 | Parks & Green Belts |  | Re-Development of Park Backside Gov.Sen.Sec School Dhandari Khurd Ludhiana W No.28 | 0 |  |  | MC Funds / General Quota | General |  | 25.74 | 33.99 | 188 dt 26.03.2025 | [8 empty] | 17 16.04.2025 | Apex Developers | 16.99 | 16.04.2025 | 3 | 15.07.2025 |  |  |  |  | 70 |  | 8.77 | In Progress |  | Work is in Progress
49 | MCL-0049 | B&R | B | B2 | Sahnewal | 22 | Roads - Interlocking Tiles |  | P/F I/tiles in streets of Jyoti Colony | 603.05 | 11 |  | MC Funds / General Quota | General |  | 23.07 | 34.4 | 1670 dt 13.10.2025 | [8 empty] | 26 15.01.2026 | Capital Const Co. | 15 | 15.01.2026 | 2 | 14.03.2026 |  |  |  |  | 5 |  | 0 | In Progress |  | Work is in Progress
50 | MCL-0050 | B&R | B | B2 | Sahnewal | 22 | Parks & Green Belts |  | Renovation of Tikoni park | 0 |  |  | MC Funds / General Quota | General |  | 15.02 | 24.99 | 2524 dt 05.02.2026 | [8 empty] | 57 16.02.2026 | Varinder Singh Govt Contractor and Maa Chintpurni Const | 11.27 | 16.02.2026 | 3 | 15.05.2026 | [6 empty] | 0 | Not Started |  | Inauguration is to be done
51 | MCL-0051 | B&R | B | B4 | Sahnewal | 21 | Parks & Green Belts |  | Renovation of park in Urban Estate Phase-II on Chd Road | 0 |  |  | MC Funds / General Quota | General |  | 105.91 | 34.1 | 2582 dt 11.02.2026 | [8 empty] | 59 16.02.2026 | Ram Parkash Kakkar | 69.79 | 16.02.2026 | 6 | 15.08.2026 |  |  |  |  | 30 |  | 0 | In Progress |  | Work is in Progress
52 | MCL-0052 | B&R | B | B2 | Sahnewal | 22 | Roads - RMC / Cement Concrete |  | Laying RMC in streets of Village Kuliewal W No.22 | 828.35 | 11 |  | Councillor Quota (CQ) | Councillor |  | 86.8 | 38.7 | 2763 dt 19.02.2026 | [8 empty] | 74 09.03.2026 | KS Constructions | 53.21 | 09.03.2026 | 5 | 08.08.2026 |  |  |  |  | 30 |  | 0 | In Progress |  | Heldup due to non laying of W/s line
53 | MCL-0053 | B&R | B | B2 | Sahnewal | 22 | Roads - RMC / Cement Concrete |  | Laying RMC in streets of Jamalpur Awana W No.22 | 621.95 | 11 |  | Councillor Quota (CQ) | Councillor |  | 69.91 | 39.99 | 2762 dt 19.02.2026 | [8 empty] | 78 12.03.2026 | Apex Developers | 41.95 | 12.03.2026 | 5 | 11.08.2026 |  |  |  |  | 45 |  | 0 | In Progress |  | Work is in Progress
54 | MCL-0054 | B&R | B | B2 | Sahnewal | 24 | Roads - Bituminous |  | Const of Bituminous roads in GK Estate main Road | 5382.01 | 11 |  | MC Funds / General Quota | General |  | 117.76 | 5 | 3309, dt 25.02.2026 | [8 empty] | 80 20.03.2026 | CH Builders Pvt. Ltd. | 111.87 | 20.03.2026 | 6 | 19.09.2026 |  |  |  |  | 15 |  | 0 | In Progress |  | Work is in Progress
55 | MCL-0055 | B&R | B | B4 | Sahnewal | 25 | Roads - Interlocking Tiles |  | P/F 80mm thick I/Tiles in Shiv colony | 2596.65 | 11 |  | MC Funds / General Quota | General |  | 112.48 | 41.72 | 3324 dt 25.02.2026 | [8 empty] | 85 24.03.2026 | T&G Const Co. | 65.55 | 24.03.2026 | 6 | 23.09.2026 |  |  |  |  | 40 |  | 26.2 | In Progress |  | Work is in Progress
56 | MCL-0056 | B&R | B | B4 | Sahnewal | 21 | Roads - Bituminous |  | Const of Bituminous Road of Jeewan Nagar & Guru Bag Colony Main Road of W No.21 | 1719.51 | 11 |  | MC Funds / General Quota | General |  | 48.52 | 5.3 | 3438 dt 21.04.2026 | [8 empty] | 20 13.05.2026 | Maruti Const Co. | 45.95 | 13.05.2026 | 4 | 12.09.2026 | [6 empty] | 0 | Not Started |  | Inauguration to be done
57 | MCL-0057 | B&R | B | B4 | Sahnewal | 21 | Parks & Green Belts |  | Renovation and Development of various parks Urban Estate Phase-II, Jamalpur of W No.21 | 0 |  |  | Councillor Quota (CQ) | Councillor |  | 78.46 | 24.9 | 3437 dt 21.04.2026 | [8 empty] | 21 13.05.2026 | Ram Parkash Kakkar | 58.92 | 13.05.2026 | 5 | 12.10.2026 | [6 empty] | 0 | Not Started |  | Inauguration to be done
58 | MCL-0058 | B&R | B | B2 | Sahnewal | 24 | Roads - Bituminous |  | Const of Bituminous Road from Chandigarh Road to GTB Nagar Near Jassal Factory | 745.12 | 11 |  | MC Funds / General Quota | General |  | 15.02 | 8.35 | Approved by W/Mayor dt 14.05.2026 inanticipation of F&CC, workorder to be issued | [8 empty] | 24 27.05.2026 | Shiva Construction | 13.77 | 27.05.2026 | 3 | 26.08.2026 |  |  |  |  | 10 |  | 0 | In Progress |  | Work is in Progress
59 | MCL-0059 | B&R | B | B2 | Sahnewal | 22 | Roads - RMC / Cement Concrete |  | P/L RMC(M-30) in Streets of Bank Colony W. No. 22 | 1493.9 | 11 |  | MC Funds / General Quota | General |  | 65.95 | 38.7 | Approved by W/Mayor dt 14.05.2026 inanticipation of F&CC, | [8 empty] | 25 27.05.2026 | LRY Labour Contractor | 40.43 | 27.05.2026 | 6 | 26.11.2026 | [6 empty] | 0 | Not Started |  | Inauguration to be done
60 | MCL-0060 | B&R | B | B4 | Sahnewal | 21 | Roads - Bituminous |  | Const of Bituminous Road of Guru Bag Colony W No.21 | 5132.62 | 11 |  | MC Funds / General Quota | General |  | 99.8 | 17.27 | Approved by W/ Mayor dt 28.05.2026 inanticipation approval by F&CC | [8 empty] | 26 01.06.2026 | Rajesh Kumar Sood | 82.56 | 01.06.2026 | 5 | 30.11.2026 |  |  |  |  | 5 |  | 0 | In Progress |  | Just Started
61 | MCL-0061 | B&R | B | B3 | East | 17 | Roads - RMC / Cement Concrete |  | Laying RMC from Main Tibba road upto Mahavir Jain Colony W No.17 | 1144.82 | 11 |  | MC Funds / General Quota | General |  | 114.55 | 33 | Inanticipation approval by W Mayor dt 16.06.2026 | [8 empty] | 27 19.06.2026 | Capital const Co. | 76.75 | 19.06.2026 | 6 | 18.12.2026 | [6 empty] | 0 | Not Started |  | Heldup due to laying of Sewerline
62 | MCL-0062 | B&R | B | B4 | Sahnewal | 28 | Roads - RMC / Cement Concrete |  | Const of Road by laying RMC in Prem Nagar W No.28 | 4964.33 | 11 |  | MDF | MDF |  | 191.52 | 32.87 | 1005 13.10.2023 | [8 empty] | 23 dt 20.10.2023 | M/s Capital Const Co. | 128.57 | 20.10.2023 | 6 | 19.04.2024 |  |  |  |  | 55 |  | 45.64 | In Progress |  | Work heldup due to upgradation of W/s & Sewer lines in the balance streets
63 | MCL-0063 | B&R | B | B4 | Sahnewal | 28 | Roads - RMC / Cement Concrete |  | Laying RMC in street of New Durga Colony W No.28 | 4287.8 | 11 |  | MDF | MDF |  | 196.63 | 8.05 | 1321 20.11.2023 | [8 empty] | 44A & 44B dt 20.11.2023 | M/s Glisten and Ashok Kumar Sobti (50%-50% allotted) | 180.8 | 20.11.2023 | 6 | 19.05.2024 |  |  |  |  | 55 |  | 40.48 | In Progress |  | Work heldup due to upgradation of W/s lines in the balance streets
64 | MCL-0064 | B&R | B | B3 | East | 15 | Roads - Bituminous |  | Const of Bituminous Road on Mata Karam Kaur Road W No.15 | 1205.79 | 11 |  | MDF | MDF |  | 25 | 1.5 | 1324 20.11.2023 | [8 empty] | 47 dt 20.11.2023 | Shiva Construction | 24.62 | 20.11.2023 | 3 | 19.02.2024 |  |  |  |  | 20 |  | 0 | In Progress |  | Work is in Progress
65 | MCL-0065 | B&R | B | B4 | East | Focal Point | Parks & Green Belts |  | Development of Green Belt along Surpal cycle Road Phase-I Focal Point | 0 |  |  | MDF | 50%MDF &50%MC |  | 146.06 | 18.2 | 3307, dt 25.02.2026 | [8 empty] | 01 10.04.2026 | Navyug Company | 119.48 | 10.04.2026 | 6 | 9.10.2026 |  |  |  |  | 10 |  | 0 | In Progress |  | Work is in Progress
66 | MCL-0066 | B&R | B | B4 | East | Focal Point | Parks & Green Belts |  | Const of Green Belt on Sanatan Dharam Mandir Road Phase-III Focal Point Ludhiana | 0 |  |  | MDF | 50%MDF &50%MC |  | 79.02 | 32.2 | 2481 dt 05.01.2026 | [8 empty] | 40 15.01.2026 | Ram Parkash Kakkar | 53.58 | 15.01.2026 | 4 | 14.07.2026 |  |  |  |  | 20 |  | 0 | In Progress |  | Work is in Progress
67 | MCL-0067 | B&R | B | B4 | East | Focal Point | Parks & Green Belts |  | Re-Development of Green Belts & Parks near E-76 to E-92, E-93 to E-106, E-107 to E-145 & E-21, E-173 & E-190 in Phase-IV Focal Point Ludhiana | 0 |  |  | MDF | 50%MDF &50%MC |  | 99.85 | 27.99 | 2482 dt 05.01.2026 | [8 empty] | 41 15.01.2026 | Apex Developers | 71.9 | 15.01.2026 | 5 | 14.07.2026 |  |  |  |  | 5 |  | 0 | In Progress |  | Work is in Progress
68 | MCL-0068 | B&R | B | B4 | East | Focal Point | Roads - RMC / Cement Concrete |  | Laying RMC along Kangaroo Industry & Upgradation of Junction Near BJ Computer Kanda on Metro Road Phase-IV Focal Point Ludhiana | 1495.12 | 11 |  | MDF | 50%MDF &50%MC |  | 117.69 | 37.8 | 2773 dt 19.02.2026 | [8 empty] | 02 10.04.2026 | LRY Labour Contractor | 73.2 | 10.04.2026 | 5 | 09.10.2026 |  |  |  |  | 80 |  | 0 | In Progress |  | Work is in Progress
69 | MCL-0069 | B&R | B | B4 | Sahnewal | Focal Point | Roads - RMC / Cement Concrete |  | Const of road by laying RMC from Rishi Raj D-40 to Udehra Mechanical Works and other various locations in Focal Point Phase V, Ludhiana . | 2263.41 | 11 |  | MDF | 50%MDF &50%MC |  | 151.9 | 37.8 | 2775 dt 19.02.2026 | [8 empty] | 03 10.04.2026 | LRY Labour Contractor | 94.48 | 10.04.2026 | 6 | 09.10.2026 |  |  |  |  | 10 |  | 0 | In Progress |  | Work is in Progress
70 | MCL-0070 | B&R | B | B4 | Sahnewal | Focal Point | Roads - Bituminous |  | Widening of Road from Jeewan Nagar Chowk upto Junction of Akal Spring Road, Phase-V and laying RMC in links between C-215 & C-216 near Dainik Jagran Road and Rectification of level at various Junctions in Focal Point, Ludhiana. | 1542.68 | 11 |  | MDF | 50%MDF &50%MC |  | 169.46 | 37.8 | 2772 dt 19.02.2026 | [8 empty] | 04 10.04.2026 | LRY Labour Contractor | 105.4 | 10.04.2026 | 6 | 09.10.2026 |  |  |  |  | 20 |  | 0 | In Progress |  | Work is in Progress
71 | MCL-0071 | B&R | B | B4 | Sahnewal | Focal Point | Parks & Green Belts |  | Development of Green Belt From Jeewan Nagar Road to Rotar Kanda Phase-V Focal Point Ludhiana (Park No.1,2,3, 4,5 & 6) | 0 | 0 |  | MDF | 50%MDF &50%MC |  | 173.65 | 21.89 | 2774 dt 19.02.2026 | [8 empty] | 62 09.03.2026 | Navyug Co. | 135.64 | 09.03.2026 | 7 | 08.10.2026 |  |  |  |  | 5 |  | 0 | In Progress |  | Work is in Progress
72 | MCL-0072 | B&R | B | B4 | Sahnewal | Focal Point | Parks & Green Belts |  | Re-Development of Green Belts & Parks near D-119, C-207 C-82, B-37, D-42 D-51 & D-70 in Phase-V Focal Point Ludhiana (Park No.12,13,15,18,21 & 22) | 0 | 0 |  | MDF | 50%MDF &50%MC |  | 215.85 | 18.83 | 3305, dt 25.02.2026 | [8 empty] | 05 10.04.2026 | Navyug Company | 175.21 | 10.04.2026 | 6 | 09.10.2026 |  |  |  |  | 5 |  | 0 | In Progress |  | Work is in Progress
73 | MCL-0073 | B&R | B | B4 | Sahnewal | Focal Point | Parks & Green Belts |  | Re-Development of Green Belts & Parks near D-190d, E-362 & E-393 in Phase-VI Focal Point Ludhiana (Park No.9,10,11 & 12) | 0 | 0 |  | MDF | 50%MDF &50%MC |  | 99.41 | 31.6 | 2483 dt 05.01.2026 | [8 empty] | 42 15.01.2026 | Ram Parkash Kakkar | 68 | 15.01.2026 | 4 | 14.07.2026 |  |  |  |  | 5 |  | 0 | In Progress |  | Work is in Progress
74 | MCL-0074 | B&R | B | B4 | Sahnewal | Focal Point | Parks & Green Belts |  | Re-Development of Green Belts & Parks near E-581, E-626 & C-202A in Phase-VII Focal Point Ludhiana (Park No.2 & 3) | 0 | 0 |  | MDF | 50%MDF &50%MC |  | 198.84 | 19.59 | 2777 dt 19.02.2026 | [8 empty] | 79 12.03.2026 | RK Const Co. | 159.89 | 12.03.2026 | 8 | 11.10.2026 |  |  |  |  | 65 |  | 66.25 | In Progress |  | Work is in Progress
75 | MCL-0075 | B&R | B | B4 | Sahnewal | Focal Point | Roads - Bituminous |  | Const of mettaled Road Opp ESI Dispensery Phase - V and Residential pocket Phase VIII Focal Point, Ludhiana. | 3159.76 | 11 |  | MDF | 50%MDF &50%MC |  | 147.05 | 29.5 | 2776 dt 19.02.2026 | [8 empty] | 06 10.04.2026 | Somaya Infrastructures | 103.67 | 10.04.2026 | 6 | 09.10.2026 |  |  |  |  | 80 |  | 73.46 | In Progress |  | Work is in Progress
76 | MCL-0076 | B&R | B | B4 | Sahnewal | Focal Point | Parks & Green Belts |  | Re-Development of Parks near C-246, C-256, 164 & 241 & Residential Pocket in Phase-VIII (Park No.2,3,6 & 9) & Parks in 34 Acre Scheme Focal Point Ludhiana (Park No.2) | 0 |  |  | MDF | 50%MDF &50%MC |  | 113.02 | 9 | 3308, dt 25.02.2026 | [8 empty] | 07 10.04.2026 | Ashok Kumar Sobti | 102.85 | 10.04.2026 | 8 | 09.10.2026 |  |  |  |  | 5 |  | 0 | In Progress |  | Work is in Progress
77 | MCL-0077 | B&R | B | B4 | Sahnewal | Focal Point | Roads - Bituminous |  | Const of Various Bituminous Roads in Phase - V & VII Focal Point Ludhiana (Roter Kanda towards Jiwan Nagar Chown, Disposal Rd.and E-654) & (E-773 to E-778 and Roter Kanda Rd to Fortis Hospital Chd Rd) | 7056.4 | 11 |  | SIDBI | SIDBI |  | 158.55 | 7.19 | 3439 dt 21.04.2026 | [8 empty] | 08 13.05.2026 | Maruti Const Co. | 147.15 | 08 13.05.2026 | 6 | [5 empty] | 15 |  | 0 | In Progress |  | Work is in Progress
78 | MCL-0078 | B&R | B | B4 | Sahnewal | Focal Point | Roads - RMC / Cement Concrete |  | Const of Various Roads by laying RMC(M-40) in Phase-V,VI,VII & VIII Focal Point Ludhiana (Satya Industry Phase 5, D-51 to D-58 )(A13E & A13A) (Opp. RCJ Auto Forge E-756 and C-202 A to C-203 C(E-701 to E-706 | 1876.52 | 11 |  | SIDBI | SIDBI |  | 136.09 | 41.99 | 1484 dt 13.10.2025 | [8 empty] | 30 15.01.2026 | Apex Developers | 78.95 | 30 15.01.2026 | 6 | 14.07.2026 |  |  |  |  | 45 |  | 34.43 | In Progress |  | Work is in Progress
79 | MCL-0079 | B&R | B | B4 | East | Focal Point | Parks & Green Belts |  | Development of various Parks in Phase-I Focal Point (OPP Kay Jay Forjing and Opp E-2) | 0 | 0 |  | SIDBI | SIDBI |  | 53.25 | 28.89 | 2486 dt 05.01.2026 | [8 empty] | 34 15.01.2026 | Teg Builders | 37.87 | 34 15.01.2026 | 5 | 14.06.2026 |  |  |  |  | 60 |  | 0 | In Progress |  | Work is in Progress
80 | MCL-0080 | B&R | B | B4 | East | Focal Point | Parks & Green Belts |  | Development of various Parks in Phase-IV Focal Point (OPP E-90 and Opp E-132) | 0 | 0 |  | SIDBI | SIDBI |  | 78.08 | 28.89 | 2485 dt 05.01.2026 | [8 empty] | 35 15.01.2026 | Teg Builders | 55.52 | 35 15.01.2026 | 5 | 14.06.2026 |  |  |  |  | 90 |  | 40.34 | In Progress |  | Work is in Progress
81 | MCL-0081 | B&R | B | B4 | East | Focal Point | Parks & Green Belts |  | Development of various Parks in Phase-IVA Focal Point (Opp D-145, Opp D-148 and Opp D-152) | 0 | 0 |  | SIDBI | SIDBI |  | 8.05 | 21.26 | 2263, dt 21.11.2025 | [8 empty] | 29 15.01.2026 | Varinder Singh Contractor | 6.34 | 29 15.01.2026 | 3 | 14.05.2026 |  |  |  |  | 80 |  | 0 | In Progress |  | Work is in Progress
82 | MCL-0082 | B&R | B | B4 | Sahnewal | Focal Point | Parks & Green Belts |  | Construction of Various Parks of Focal Point Phase-V , Ludhiana (D-114, C-86,B-37, C-115, D-130) | 0 | 0 |  | SIDBI | SIDBI |  | 217.72 | 28.1 | 2484 dt 05.01.2026 | [8 empty] | 36 15.01.2026 | RK Const Co. | 156.54 | 36 15.01.2026 | 6 | 14.07.2026 |  |  |  |  | 30 |  | 35.75 | In Progress |  | Work is in Progress
83 | MCL-0083 | B&R | B | B4 | Sahnewal | Focal Point | Parks & Green Belts |  | Construction of Various Parks of Focal Point Phase-VI , Ludhiana (Park No.1,2,4,6,7 & 8) | 0 | 0 |  | SIDBI | SIDBI |  | 348.82 | 18.2 | 2487 dt 05.01.2026 | [8 empty] | 37 15.01.2026 | Navyug Company | 285.33 | 37 15.01.2026 | 6 | 14.07.2026 |  |  |  |  | 5 |  | 0 | In Progress |  | Work is in Progress
84 | MCL-0084 | B&R | B | B4 | Sahnewal | Focal Point | Parks & Green Belts |  | Construction of Various Parks of Focal Point Phase-VII Ludhiana (Park No.2,3,4,5 & 6) | 0 | 0 |  | SIDBI | SIDBI |  | 123.11 | 28.99 | 2492 dt 05.01.2026 | [8 empty] | 38 15.01.2026 | RK Const Co. | 87.42 | 38 15.01.2026 | 6 | 14.07.2026 |  |  |  |  | 25 |  | 19.95 | In Progress |  | Work is in Progress
85 | MCL-0085 | B&R | B | B4 | Sahnewal | Focal Point | Parks & Green Belts |  | Development of various Parks in Phase-VIII Focal Point (Adj F-170 & F171,Adj F-155 & F156 , Adj F-179 & F176, Adj F-194 & F195 and Opp F-251) | 0 | 0 |  | SIDBI | SIDBI |  | 168.7 | 23.51 | 2489 dt 05.01.2026 | [8 empty] | 39 15.01.2026 | KS Constructions | 129.04 | 39 15.01.2026 | 6 | 14.07.2026 |  |  |  |  | 30 |  | 0 | In Progress |  | Work is in Progress
86 | MCL-0086 | B&R | B | B4 | Sahnewal | Focal Point | Parks & Green Belts |  | Repair & Renovation of various Parks in 34 Acre Scheme Focal Point (Park Opp F-309, Opp K-312) | 0 | 0 |  | SIDBI | SIDBI |  | 25.32 | 31.26 | 2172 dt 13.10.2025 | [8 empty] | 31 15.01.2026 | Varinder Singh Contractor | 17.4 | 31 15.01.2026 | 4 | 14.05.2026 |  |  |  |  | 90 |  | 15.99 | In Progress |  | Work is in Progress
87 | MCL-0087 | B&R | A | A1 | Central | 83 | Retaining Wall |  | Construction Of Retaining Wall And Road Along Budha Nallah From Madhopuri Pulli To Sunder Nagar Pulli, Ludhiana. | NA | NA |  | MC Funds / General Quota | MC Funds | Work in progress | 366.48 | -17.86% | 931 dt. 06-05-2025 | Y | Y | Y | N |  |  | Y | Y | 88/EEA dt. 15-05-2025 | Gaaneshkartikey Construction Pvt. Ltd. | 301.02 | 15-05-2025 | 18 months | 14-11-2026 |  | Er. Ranjit Singh |  |  | 60 |  | 90 | Delayed/Held Up |  | Work delayed due to shortage of bitumen. Notice issue to Contractor
88 | MCL-0088 | B&R | A | A1 | Central | 9 & 10 | Bituminous |  | Construction of Main 70' Road Sunder Nagar in w.no.8 & 58. | 1250 | 40 |  | MC Funds / General Quota | MC Funds | Not Started | 57.19 | -24.99% | 102 dt. 26-03-2025 | Y | Y | Y | N |  |  | Y | Y | 83/EEA dt. 21-04-2025 | M/s C.H Builders Pvt. Ltd. | 42.89 | 21-04-2025 | 6 months | 22-10-2025 | Not Started | Er. Ranjit Singh | NA | NA | 0 | 0 | NIL | Delayed/Held Up |  | Work delayed due to shortage of bitumen. Final Notice issued to Contractor
89 | MCL-0089 | B&R | B | B1 | Central | 81 | Building Work |  | Repair and Maintenance of Zone-B Main Building of Municipal Corporation Ludhiana. | NA | NA |  | MC Funds / General Quota | MC Funds | Work in progress | 123.69 | -21.13% | 124 dt. 26-03-2025 | Y | Y | Y | N |  |  | Y | Y | 91/EEA dt. 15-05-2025 | Teg Builders (Govt. Contractor) | 97.55 | 15-05-2025 | 6 months | 16-10-2025 |  | Er. Ranjit Singh |  |  | 95 |  | 86.12 | In Progress |  | Revised est. has been prepared due to increase of electrical item, sanitation items.
90 | MCL-0090 | B&R | A | A1 | Central | 83 & 85 | RMC M-30 |  | Laying RMC M-30 in various streets in vakilla Mohalla & Krishana Gali in ward no.59 & 61.(New w.no. 83 & 85) | 410 | 15 |  | MC Funds / General Quota | MC Funds | Work in progress | 25.19 | -44.55% | Tender F&CC Reso.no. 97 dt. 26-03-2025 | Y | Y | Y | N |  |  | Y | Y | 94/EEA dt. 01-08-2025 | Capital Construction Co. | 13.96 | 01-08-2025 | 6 months | 02-01-2026 | Work in progress | Er. Ranjit Singh |  |  | 75 | 60% | 8.36 | In Progress |  | Work in progress
91 | MCL-0091 | B&R | B | B1 | Central | 76 | Bituminous |  | Laying 30mm thick SDBC Kucha no.16 adjoining Janj Ghar w.no.63. (New w.no.76) | 242 | 16 |  | MC Funds / General Quota | MC Funds | Work in progress | 20.32 | -35.10% | Tender F&CC Reso.no. 100 dt. 26-03-2025 | Y | Y | Y | N |  |  | Y | Y | 95/EEA dt. 01-08-2025 | Capital Construction Co. | 13.18 | 01-08-2025 | 6 months | 02-01-2026 | Work in progress | Er. Ranjit Singh |  |  | 10 | - | NIL | Delayed/Held Up |  | Work delayed due to shortage of bitumen.
92 | MCL-0092 | B&R | C | C | Central | 74 | Bituminous |  | Laying BM&PC on various streets of Industrial Area B adjoining overlock road in w.no.51. |  |  |  | MC Funds / General Quota | MC Funds |  | 175.23 |  | Tender F&CC Reso.no. 761 dt. 09-04-2025 | [8 empty] | 101/EEA dt. 01-08-2025 | Hitesh Aggarwal Cont. | 110.39 | 01-08-2025 | 6 months | 02-01-2026 |  |  |  |  | 10 |  | NIL | Delayed/Held Up |  | Work delayed due to shortage of bitumen.
93 | MCL-0093 | B&R | A | A2 | Central | 78 | Park |  | Renovation of various parks in ward no. 78, Ludhiana. | NA | NA |  | MC Funds / General Quota | MC Funds | Work in progress | 37.41 | -21.00% | Tender F&CC reso.no. 1821 dt. 13-10-2025 | Y | Y | Y | N |  |  | Y | Y | 103/EEA dt. 19-11-2025 | M/s Dynamic tiles | 29.55 | 19-11-2025 | 6 months | 20-06-2026 | Work in progress | Er. Ranjit Singh |  |  | 50 | - | NIL | In Progress |  | The work of one park has been completed balance work in progress Notice issued to contractor
94 | MCL-0094 | B&R | B | B1 | Central | 80 | Bituminous |  | Laying SDBC in streets of Janakpuri Part-I in w.no.80. | 1134 | 20 |  | MC Funds / General Quota | MC Funds | Not Started | 39.89 | -7.70% | Tender F&CC reso.no. 2147 dt. 13-10-2025 | Y | Y | Y | N |  |  | Y | Y | 105/EEA dt. 19-11-2025 | M/s Soham Construction Company | 36.81 | 19-11-2025 | 6 months | 20-06-2026 | Not Started | Er. Ranjit Singh |  |  | 0 |  | NIL | Delayed/Held Up |  | Work delayed due to shortage of bitumen.
95 | MCL-0095 | B&R | A | A1 | Central | 9 | Building Work |  | Construction of New Toilets and Repair & Renovation of Sunder Nagar Fire Station. | NA | NA |  | MC Funds / General Quota | MC Funds | Work in progress | 24.33 | -20.58% | Tender F&CC reso.no. 1811 dt. 13-10-2025 | Y | Y | Y | N |  |  | Y | Y | 106/EEA dt. 19-11-2025 | M/s Prince Sharma | 19.32 | 19-11-2025 | 6 months | 20-06-2026 |  | Er. Ranjit Singh |  |  | 60 | 65% | 12.61 | In Progress |  | Work will be completed 30-07-2026 Work in progress
96 | MCL-0096 | B&R | A | A2 | Central | 78 | RMC M-30 |  | Laying RMC M30 In Streets No.1,2,3,4 & Links of Mohar Singh Nagar, W.No.78, Ludhiana. | 1237 | 20 |  | MC Funds / General Quota | MC Funds | Work in progress | 93.11 | -42.70% | Tender F&CC reso.no. 1823 dt. 13-10-2025 | Y | Y | Y | N |  |  | Y | Y | 108/EEA dt. 19-11-2025 | K.S Constructions | 53.35 | 19-11-2025 | 6 months | 20-06-2026 |  | Er. Ranjit Singh |  |  | 80 | 95% | 50.7 | Delayed/Held Up |  | Work delayed due to laying Water supply line by O&M Cell.
97 | MCL-0097 | B&R | A | A1 | Central | 10 | RMC M-30 |  | Laying RMC in street of Mohalla New Madho Puri in w.no.58 (New w.no.10) Part-II. | 371 | 20 |  | MC Funds / General Quota | MC Funds | Work in progress | 83.72 | -42.7% | Tender F&CC reso.no. 1819 dt. 13-10-2025 | Y | Y | Y | N |  |  | Y | Y | 110/EEA dt. 19-11-2025 | K.S Constructions | 47.97 | 19-11-2025 | 7 months | 20-05-2026 |  | Er. Ranjit Singh |  |  | 60 | 39% | 18.75 | In Progress |  | Work in progress
98 | MCL-0098 | B&R | A | A1 | Central | 83 | RMC M-30 |  | Laying RMC M-30 in street of Mohalla Mehmoodpura in w.no.61. (New w.no.83) | 896 | 15 |  | MC Funds / General Quota | GQ | Work in progress | 71.84 | -42.70% | Tender F&CC reso.no. 1814 dt. 13-10-2025 | Y | Y | Y | N |  |  | Y | Y | 111/EEA dt. 19-11-2025 | K.S. Constructions | 41.16 | 19-11-2025 | 6 months | 20-05-2026 | Work in progress | Er. Ranjit Singh |  |  | 30 | 19% | 7.89 | In Progress |  | Work in progress
99 | MCL-0099 | B&R | B | B1 | Central | 81 | RMC M-30 |  | Laying RMC M-30 in streets of Harcharan Nagar in w.no.57. | 810 | 20 |  | MC Funds / General Quota | MC Funds | Work in progress | 56.74 | -45.56% | Tender F&CC reso.no.758 dt. 09-04-2025 | Y | Y | Y | N |  |  | Y | Y | 114/EEA dt.19-11-2025 | Varinder Singh Govt. Contractor | 30.88 | 19-11-2025 | 4 months | 20-02-2026 | Work in progress | Er. Ranjit Singh |  |  | 10 | 0 | NIL | Delayed/Held Up |  | Work stopped due to upgradation of water supply line.
100 | MCL-0100 | B&R | A | A2 | Central | 82 | 60/80mm I/Tiles |  | P/F 60/80mm I/Tiles on RMC in Streets of Dhoka Mohalla, Ludhiana. (Rs. 33,89,445.15 Only (1/2 of total Tender Cost: 67,78,890.30) ) | 1270 | 4165 |  | MC Funds / General Quota | MC Funds | Work in progress | 121.03 | -43.99% | Tender F&CC reso.no. 1795 dt. 13-10-2025 | Y | Y | Y | N |  |  | Y | Y | 115/EEA dt.19-11-2025 & 116/EEA dt.19-11-2025 | M/s Apex Devlopers & M/s K.S. Constructions | 67.78 | 19-11-2025 | 7 months | 20-05-2026 |  | Er. Ranjit Singh |  |  | 40 |  | 13.72 | Delayed/Held Up |  | Work delayed due to laying Water supply line by O&M Cell.
101 | MCL-0101 | B&R | A | A1 | Central | 83 | RMC M-30 |  | Laying RMC M-30 in street of Bharam Puri in w.no.83. | 533 | 15 |  | MC Funds / General Quota | MC Funds | Not Started | 24.93 | -43.05% | Tender F&CC reso.no. 2153 dt. 13-10-2025 | Y | Y | Y | N |  |  | Y | Y | 124/EEA dt.18-02-2026 | Godwyn Infra | 14.19 | 18-02-2026 | 6 months | 17-07-2026 | Not Started | Er. Ranjit Singh |  |  | 0 |  | NIL | Not Started |  | Work not started Notice issued
102 | MCL-0102 | B&R | A | A2 | Central | 78 | RMC M-30 |  | Laying RMC M30 In Streets No. 5,6 & Links of Mohar Singh Nagar, W.No.78, Ludhiana. | 850 | 2788 |  | MC Funds / General Quota | GQ | Work in progress | 73.03 | -42.30% | Tender F&CC reso.no. 1809 dt. 13-10-2025 | Y | Y | Y | N |  |  | Y | Y | 127/EEA dt.18-02-2026 | LRY Labour Contractor | 42.13 | 18-02-2026 | 6 months | 17-07-2026 |  | Er. Ranjit Singh |  |  | 60 |  | NIL | Delayed/Held Up |  | Work delayed due to laying Water supply line by O&M Cell.
103 | MCL-0103 | B&R | A | A2 | Central | 78 | RMC M-30 |  | Laying RMC M30 In Streets No.7, 8 & Links of Mohar Singh Nagar, W.No.78, Ludhiana. | 1410 | 4624 |  | Councillor Quota (CQ) | CQ | Work in progress | 99.68 | -42.30% | Tender F&CC reso.no. 1890 dt. 13-10-2025 | Y | Y | Y | N |  |  | Y | Y | 128/EEA dt.18-02-2026 | LRY Labour Contractor | 57.51 | 18-02-2026 | 6 months | 17-07-2026 |  | Er. Ranjit Singh |  |  | 50 |  | NIL | Delayed/Held Up |  | Work delayed due to laying Water supply line by O&M Cell.
104 | MCL-0104 | B&R | A | A1 | Central | 85 | Building Work |  | Repair & Renovation of Sub Zone-A1 Office at Daresi. W. No. 85. | NA | NA |  | MC Funds / General Quota | GQ | Work in progress | 35.53 | -19.99% | Tender F&CC reso.no. 3266 dt. 25-02-2026 | Y | Y | Y | N |  |  | Y | Y | 131/EEA dt.18-03-2026 & 132/EEA dt.18-03-2026 | The Sobha Gram Co Operative Labour and Construction Society Ltd. & Apex Devlopers | 28.42 | 18-03-2026 | 7 months | 17-09-2026 |  | Er. Ranjit Singh |  |  | 10 |  | NIL | In Progress |  | Work in progress
105 | MCL-0105 | B&R | B | B1 | Central | 75 | Bituminous |  | Laying 30mm thick SDBC on Kidwai Nagar Main Road & Road from Suffian Chowk to Janakpuri in w.no.75. | 710 | 2328 |  | MC Funds / General Quota | GQ | Work in progress | 38.33 | -10.99% | Tender F&CC reso.no. 3263 dt. 25-02-2026 | Y | Y | Y | N |  |  | Y | Y | 133/EEA dt. 18-03-2026 | Capital Construction Co. | 34.11 | 18-03-2026 | 6 months | 17-08-2026 |  | Er. Ranjit Singh |  |  | 10 |  | NIL | Delayed/Held Up |  | Work delayed due to shortage of bitumen.
106 | MCL-0106 | B&R | A | A1 | Central | 83 | RMC M-30 |  | Laying RMC M-30 in St.no.1 Madhopuri & Links in w.no.83. | 670 | 2197 |  | MC Funds / General Quota | GQ | Not Started | 46.89 | -44.99% | Tender F&CC reso.no. 3267 dt. 25-02-2026 | Y | Y | Y | N |  |  | Y | Y | 135/EEA dt. 18-03-2026 | N.S. Infra | 25.79 | 18-03-2026 | 6 months | 17-08-2026 |  | Er. Ranjit Singh | N |  | 0 |  | NIL | Delayed/Held Up |  | Inaguration pending
107 | MCL-0107 | B&R | A | A1 | Central | 83 | RMC M-30 |  | Laying RMC M-30 in street of Ghati Mohalla in ward no. 83. | 270 | 885 |  | Councillor Quota (CQ) | CQ | Work in progress | 11.4 | -40.99% | Tender F&CC reso.no. 3265 dt. 25-02-2026 | Y | Y | Y | N |  |  | Y | Y | 137/EEA dt. 18-03-2026 | K.S. Constructions | 6.72 | 18-03-2026 | 6 months | 17-08-2026 |  | Er. Ranjit Singh |  |  | 10 |  | NIL | Delayed/Held Up |  | Work stopped due to laying of water supply line.
108 | MCL-0108 | B&R | A | A2 | Central | 82 | RMC M-30 |  | Laying RMC M-30 in street of Mohalla Taj Ganj in ward no.82. | 290 | 951 |  | Councillor Quota (CQ) | CQ | Work in progress | 24.65 | -43.31% | Tender F&CC reso.no. 3264 dt. 25-02-2026 | Y | Y | Y | N |  |  | Y | Y | 139/EEA dt. 18-03-2026 | K.S. Constructions | 13.97 | 18-03-2026 | 3 months | 17-05-2026 |  | Er. Ranjit Singh |  |  | 20 |  | NIL | In Progress |  | Work in progress Work will be completed within 20 days.
109 | MCL-0109 | B&R | A | A2 | Central | 75 | RMC M-30 |  | Laying RMC (M-30) in various streets of ward no.75. | 1010 | 3312 |  | Councillor Quota (CQ) | CQ | Work in progress | 63.32 | -45.13% | Tender F&CC reso.no. 3268 dt. 25-02-2026 | Y | Y | Y | N |  |  | Y | Y | 141/EEA dt. 18-03-2026 | K.S. Constructions | 34.74 | 18-03-2026 | 6 months | 17-08-2026 |  | Er. Ranjit Singh |  |  | 65 |  | 14.62 | In Progress |  | Work in progress
110 | MCL-0110 | B&R | A | A2 | Central | 78 | Park |  | Re-Development of Children Friendly Park on Old Jail Road, Ludhiana. | NA | NA |  | MC Funds / General Quota | GQ | Work in progress | 66.68 | -35.99% | Tender F&CC reso.no. 2788 dt. 19-02-2026 | Y | Y | Y | N |  |  | Y | Y | 142/EEA dt. 18-03-2026 | Navdeep Gupta and Company | 42.68 | 18-03-2026 | 6 months | 17-08-2026 |  | Er. Ranjit Singh |  |  | 40 |  | NIL | In Progress |  | Repair work of Satpal prasher park has been completed work in progress.
111 | MCL-0111 | B&R | B | B1 | Central | 80 | RMC M-30 |  | Laying RMC M-30 in St.no.1,2,3 & 4 of Janakpuri w.no.80. | 1580 | 5182 |  | MC Funds / General Quota | GQ |  | 69.55 | -45.51% | Tender F&CC reso.no. 2794 dt. 19-02-2026 | Y | Y | Y | N |  |  | Y | Y | 143/EEA dt. 18-03-2026 | Vansh Engineers | 37.89 | 18-03-2026 | 7 months | 17-09-2026 |  | Er. Ranjit Singh |  |  | 0 |  | NIL | Delayed/Held Up |  | Inaguration pending
112 | MCL-0112 | B&R | A | A2 | Central | 77 | RMC M-30 |  | Laying RMC streets in internal streets of Mochpura Bazar. | 220 | 721 |  | SASCI | Under Special Central Assistance Scheme |  | 26.98 |  | Tender F&CC reso.no. 2574 dt. 11-02-2026 | Y | Y | Y | N |  |  | Y | Y | 144/EEA dt. 20-03-2026 | Maa Chintpurni Construction | 14.84 | 20-03-2026 | 3 months | 21-05-2026 |  | Er. Ranjit Singh |  |  | 45 |  | 14.51 | Delayed/Held Up |  | Work delayed due to core area. Work in progress.
113 | MCL-0113 | B&R | B | B1 | Central | 80 | Bituminous |  | Laying SDBC in streets of Janakpuri Part-II in w.no.80. | 660 | 2164 |  | MC Funds / General Quota | GQ/MLA |  | 24.15 | -21.59% | Tender F&CC reso.no. 3578 dt. 21-04-2026 | Y | Y | Y | N |  |  | Y | Y | 151/EEA dt. 06-05-2026 | Capital Construction Co. | 18.93 | 06-05-2026 | 6 months | 07-10-2026 |  | Er. Ranjit Singh |  |  | 10 |  | NIL | Delayed/Held Up |  | Work delayed due to shortage of bitumen. Notice issue
114 | MCL-0114 | B&R | A | A1 | Central | 85 | RMC M-30 | E 388259 | Laying RMC M-30 in street of Mohalla Shankar Puri, Veer Nagar & SDP College Quilla Mohalla in w.no.85. | 1390 |  |  | Rangla Punjab | Under Rangla Punjab Vikas Scheme Ph-I | Work in progress | 85.9 | -45.99% | 3196 dt. 25-02-2026 | Y | Y | Y | N |  |  | Y | Y | 150/EEA dt. 05-05-2026 | Maa Chintpurni Construction | 46.39 | 05-05-2026 | 7 months | 06-11-2026 |  | Er. Ranjit Singh |  |  | 45 |  | NIL | In Progress |  | Work in progress. Work will be completed upto 15-07-2026
115 | MCL-0115 | B&R | A | A2 | Central | 82 | RMC M-30 | E 388261 | Laying RMC M-30 in Shanti Niketen School St & Links Streets of Mohalla Fateh Ganj in Ward No-82. |  |  |  | Rangla Punjab | Under Rangla Punjab Vikas Scheme Ph-I | Work in progress | 43.22 | -38.70% | 3271 dt. 25-02-2026 | Y | Y | Y | N |  |  | Y | Y | 148/EEA dt. 05-05-2026 | LRY Labour Contractor | 26.49 | 05-05-2026 | 3 months | 06-07-2026 |  | Er. Ranjit Singh |  |  | 10 |  | NIL | In Progress |  | Work in progress. Work will be completed upto 15-07-2026
116 | MCL-0116 | B&R | A | A2 | Central | 82 | RMC M-30 | E 388263 | Laying RMC M-30 in streets near Gajja Jain Mandir in Tilak Nagar w.no.82. |  |  |  | Rangla Punjab | Under Rangla Punjab Vikas Scheme Ph-I | Work in progress | 27.91 | -38.70% | 3274 dt. 25-02-2026 | Y | Y | Y | N |  |  | Y | Y | 147/EEA dt. 05-05-2026 | LRY Labour Contractor | 17.1 | 05-05-2026 | 4 months | 06-08-2026 |  | Er. Ranjit Singh |  |  | 25 |  | NIL | In Progress |  | Work in progress. Work will be completed upto 15-07-2026
117 | MCL-0117 | B&R | B | B1 | Central | 79 | RMC M-30 | E 388264 | Laying RMC M-30 in Hargobind Nagar & its adjoining streets of w.no.79. |  |  |  | Rangla Punjab | Under Rangla Punjab Vikas Scheme Ph-I | Work in progress | 53.15 | -43.17% | 3273 dt. 25-02-2026 | Y | Y | Y | N |  |  | Y | Y | 149/EEA dt. 05-05-2026 | Capital Construction Co. | 30.2 | 05-05-2026 | 4 months | 06-08-2026 |  | Er. Ranjit Singh |  |  | 10 |  | NIL | In Progress |  | Work in progress. Work will be completed upto 15-07-2026
118 | MCL-0118 | B&R | B | B1 | Central | 80 | RMC M-30 | E 388266 | Laying RMC M-30 in streets of New Kidwai Nagar in w.no. 80. |  |  |  | Rangla Punjab | Under Rangla Punjab Vikas Scheme Ph-I | Work in progress | 39.8 | -43.17% | 3272 dt. 25-02-2026 | Y | Y | Y | N |  |  | Y | Y | 146/EEA dt. 05-05-2026 | Godwyn Infra | 22.61 | 05-05-2026 | 7 months | 06-11-2026 |  | Er. Ranjit Singh |  |  | 10 |  | NIL | In Progress |  | Work in progress. Work will be completed upto 15-07-2026
119 | MCL-0119 | B&R |  |  | Central | Gen. |  |  | Remodeling of Nallah & Constructions of roads from Shingar Cinema Bridge to Shamshan Ghat Bridge. |  |  |  | MC Funds / General Quota | PUEIP Ph-III |  |  |  | 26-11-2021 | [8 empty] | 153/EEA/LOA dt. 13-12-2021 | M/s Kabir Infra | 939.21 | 13-12-2021 | 12 months | 14-12-2021 |  |  |  |  | 60 |  | 300.62 | Delayed/Held Up |  | Work delayed because of pending IPS construction work causing obstruction at the site. Work in progress (Amt. approved from under PUEIP PH-III 600 lacs) but Orginal Est. Cost is 948.70 & vetted Est. amt. 942.05 lacs
120 | MCL-0121 | B&R | A |  | Central | Gen. |  |  | Laying SDBC Links between Vijay Nagar Road & Suffian Chowk Road, Links Nearby Night Shelter Moti Nagar, Main Road from Basti Jodhewal to Sunder Nagar Pulley Both Sides, Gaushalla Main Road, Ghora Colony & Links and Links between RK Road & Kabir Road in central Constituency. |  |  |  | MDF | MDF Funds |  | 877.87 | [23 empty] | Not Started |  | Under technical evaluation
121 | MCL-0122 | B&R | A |  | Central | Gen. |  |  | Laying RMC M-30 in streets of Old Madho Puri Part-I & II, Janakpuri, Hargobind Nagar Road, Ambedkar Nagar & Ram Nagar, Industrial area, Basti Sheikh Mohamadh, Mohalla Vijay Nagar & New Shiva Ji Nagar of Central Constituency. |  |  |  | MDF | MDF Funds |  | 601.4 | [23 empty] | Not Started |  | Under technical evaluation
122 | MCL-0123 | B&R | A |  | Central | Gen. |  |  | Laying RMC M-40 in Various Streets of Transport Nagar Part-II Ward No.30. |  |  |  | MDF | MDF Funds |  | 701.92 | [23 empty] | Not Started |  | Under technical evaluation
123 | MCL-0124 | B&R | A |  | Central | Gen. |  |  | Laying BM & SDBC on Guru Nanak Dev Market, Main Hargobind Marg, Main Textile Colony Road and Brown Road & Islamia School Road and Main Road from 3 No. Division to CMC Chowk. |  |  |  | MDF | MDF Funds |  | 553.56 | [23 empty] | Not Started |  | Under technical evaluation
124 | MCL-0125 | B&R | A |  | Central | Gen. |  |  | Laying RMC M-30 in streets of Mohalla Islam Ganj, Mustak Ganj and Ucha Tibba in w.no.75, Various Kuchas in w.no.76, Various Streets of Shivaji Nagar in w.no.79, Streets of Kashmir Nagar & Narinder Nagar in w.no.81 and Main Road of Dal Bazar, Hindi Bazar & Chawal Bazar and Main Hosiery Road. |  |  |  | MDF | MDF Funds |  | 652.17 | [23 empty] | Not Started |  | Under technical evaluation
125 | MCL-0126 | B&R | B | B1 | Central | 30 | RMC M-30 |  | Laying RMC M-30 in Various Streets of Bihari Colony in ward no.30. |  |  |  | Rangla Punjab | Rangla Punjab-II |  | 73.82 |  |  | Y | Y | Y | N |  |  | Y | Y | [7 empty] | Er. Ranjit Singh | [5 empty] | Not Started |  | F&CC approved in anticipation Tender to be called
126 | MCL-0127 | B&R | B | B1 | Central | 79 | RMC M-30 |  | Laying RMC M-30 in Street No.1,2,3 & Links Hari Kartar Colony in ward no.79. |  |  |  | Rangla Punjab | Rangla Punjab-II |  | 53.46 |  |  | Y | Y | Y | N |  |  | Y | Y | [7 empty] | Er. Ranjit Singh | [5 empty] | Not Started |  | F&CC approved in anticipation Tender to be called
127 | MCL-0128 | B&R | B | B1 | Central | 76 | RMC M-30 |  | Laying RMC M-30 in link Streets of Kusht Ashram Road in ward no.76. |  |  |  | Rangla Punjab | Rangla Punjab-II |  | 72.81 |  |  | Y | Y | Y | N |  |  | Y | Y | [13 empty] | Not Started |  | F&CC approved in anticipation Tender to be called
128 | MCL-0129 | B&R | B | B1 | Central | 76 | RMC M-30 |  | Laying RMC M-30 in Different Streets of Prem Nagar Part-II in ward no.76. |  |  |  | Rangla Punjab | Rangla Punjab-II |  | 49.81 |  |  | Y | Y | Y | N | [17 empty] | Not Started |  | F&CC approved in anticipation Tender to be called
129 | MCL-0130 | B&R |  |  | Central | Gen. |  |  | Upgradation of RMC Roads in various wards of Central Constituency. |  |  |  | SASCI | Special Central Assistance Scheme |  |  |  | 2676 dt. 11-02-2026 | [8 empty] | 123/EEA dt. 18-02-2026 | M/s J.K.Infocon Pvt. Ltd | 741.93 | 18-02-2026 | [6 empty] | 90 |  |  | In Progress |  | Work will be completed upto 30-06-2026
130 | MCL-0132 | B&R | D | D1 | North | 68 | Roads - RMC / Cement Concrete | Old File/Offline | P/Laying RMC M-30 in streets of Chander nagar & Jagan nath puram road ward no. 68. | 750 | 20 |  | MC Funds / General Quota | MC Funds | In Progress | 55.3 | -42.54% | 2639 dt 11.02.2026 | Y | Y | SE | N |  |  | Y | Y | 29/EED dt 23.02.2026 | M/s Prince Sharma | 31.78 | 23.02.2026 | 4 | 25.06.2026 |  | Er. Ranjit Singh | No | No | 90% | 0 | 0 | In Progress |  | Work in Progress
131 | MCL-0133 | B&R | D | D1 | North | 70 | Roads - RMC / Cement Concrete | Old File/Offline | P/Laying RMC M-30 in streets of Wadhwa street, Gandhi street , Prem nagar & kundanpuri ward no. 70. | 930 | 20 |  | Councillor Quota (CQ) | CQ | In Progress | 57.3 | -42.85% | 2648 dt 11.02.2026 | Y | Y | SE | N |  |  | Y | Y | 27/EED dt 23.02.2026 | M/s Navdeep Gupta & Company | 32.75 | 23.02.2026 | 4 | 25.06.2026 | 31.08.2026 | Er. Ranjit Singh | No | No | 70 | 64.855 | 21.24 | In Progress |  | Work in Progress | https://drive.google.com/file/d/12RCLpHR9xsoaF6dzJVf5GGwwNsKw_Et4/view?usp=sharing
132 | MCL-0134 | B&R | D | D1 | North | 70 | Perforated Tiles | Old File/Offline | P/L 60mm thick Perforated tiles on side berms of Pavillion chowk to Kailash chowk , Petrol pump street w.no.70. | 670 |  |  | MC Funds / General Quota | MC Funds | Not started | 18.72 | -38.99% | 2641 dt 11.02.2026 | Y | Y | XEN | N |  |  | Y | Y | 25/EED dt 23.02.2026 | M/s Navdeep Gupta & Company | 11.42 | 23.02.2026 | 2 | 25.04.2026 |  | Er. Ranjit Singh | No | No |  |  | NiL | Delayed/Held Up |  | Inauguration pending
133 | MCL-0135 | B&R | D | D1 | North | 70 | Parks & Green Belts | Old File/Offline | Repair & Renovation of Tanki wala park (prem nagar), Park lane & Gol park in ward no. 70. | NA | NA |  | Councillor Quota (CQ) | CQ | In Progress | 27.82 | -32.99% | 2640 dt 11.02.2026 | Y | Y | XEN | N |  |  | Y | Y | 26/EED dt 23.02.2026 | M/s Deepak Madaan | 18.64 | 23.02.2026 | 3 | 26.05.2026 | 31.08.2026 | Er. Ranjit Singh | No | No | 50% |  | NiL | In Progress |  | Work in Progress | https://drive.google.com/file/d/1XhqdEARm7B2rRcpXp-rH_RoWejvF4lNR/view?usp=sharing
134 | MCL-0136 | B&R | D | D1 | North | 66 | Roads - Bituminous | Old File/Offline | P/Laying Bm & Pc from Lal Kothi chowk to Sheller road, main road Bank colony w.no. 66. | 1130 | 14 |  | MC Funds / General Quota | GQ | Not started | 46.64 | -15.1% | 2643 dt 11.02.2026 | Y | Y | XEN | N |  |  | Y | Y | 23/EED dt 23.02.2026 | M/s Soham Construction Co. | 39.59 | 23.02.2026 | 3 | 26.05.2026 |  | Er. Ranjit Singh | No | No |  |  | NiL | Delayed/Held Up |  | Inauguration pending
135 | MCL-0137 | B&R | D | D1 | North | 91 | Roads - RMC / Cement Concrete | Old File/Offline | P/Laying RMC M-30 in streets of Guru Nanak pura ward no. 91. | 575 |  |  | Councillor Quota (CQ) | CQ | In Progress | 31.5 | -40.61% | 2647 dt 11.02.2026 | Y | Y | XEN | N |  |  | Y | Y | 28/EED dt 23.02.2026 | M/s Navdeep Gupta & Company | 18.71 | 23.02.2026 | 3 | 15.07.2026 | 31.08.2026 | Er. Ranjit Singh | No | No | 70 | 76.4297 | 14.3 | In Progress |  | Work in progress | https://drive.google.com/file/d/1vfsf5ItZPYfFe027qgW6vCWnygTdPhkx/view?usp=sharing
136 | MCL-0138 | B&R | D | D1 | North | 66 | Roads - RMC / Cement Concrete | Old File/Offline | P/Laying RMC M-30 in New Deep Nagar ward no. 66. | 118 | 30 |  | MC Funds / General Quota | MC Funds | Not started | 11.81 | -42.66% | 2644 dt 11.02.2026 | Y | Y | SDO | N |  |  | Y | Y | 21/EED dt 23.02.2026 | M/s Prince Sharma | 6.77 | 23.02.2026 | 2 | 25.04.2026 |  | Er. Ranjit Singh | No | No |  |  | NiL | Delayed/Held Up |  | Inauguration pending (council. Quota)
137 | MCL-0139 | B&R | D | D1 | North | 66 | Roads - RMC / Cement Concrete | Old File/Offline | P/Laying RMC M-30 in streets of Om Park Part -I ward no. 66. | 822 | 20 |  | MC Funds / General Quota | GQ | Not started | 50.15 | -43.4% | 2642 dt 11.02.2026 | Y | Y | SE | N |  |  | Y | Y | 22/EED dt 23.02.2026 | M/s Navdeep Gupta & Company | 28.38 | 23.02.2026 | 4 | 25.06.2026 |  | Er. Ranjit Singh | No | No |  |  | NiL | Delayed/Held Up |  | Inauguration pending
138 | MCL-0140 | B&R | D | D1 | North | 66 | Roads - RMC / Cement Concrete | Old File/Offline | P/Laying RMC M-30 in streets of Om Park Part -II ward no. 66. | 870 | 20 |  | MC Funds / General Quota | GQ | In Progress | 52.76 | -44.23% | 2646 dt 11.02.2026 | Y | Y | SE | N |  |  | Y | Y | 24/EED dt 23.02.2026 | M/s Prince Sharma | 29.42 | 23.02.2026 | 4 | 10.07.2026 | 15.08.2026 | Er. Ranjit Singh | No | No | 95 | 99.966 | 29.41 | Delayed/Held Up |  | only 300 feet length of sts. pending due to W/S supply Work in Progress
139 | MCL-0141 | B&R | D | D1 | North | 70 | Roads - RMC / Cement Concrete | Old File/Offline | P/Laying RMC M-30 in Bhandari street ward no. 70. | 440 | 20 |  | Councillor Quota (CQ) | CQ | Not started | 27.91 | -42.85% | 2645 dt 11.02.2026 | Y | Y | XEN | N |  |  | Y | Y | 30/EED dt 23.02.2026 | M/s Navdeep Gupta & Company | 15.95 | 23.02.2026 | 3 | 25.05.2026 |  | Er. Ranjit Singh | No | No |  |  | NiL | Delayed/Held Up |  | Inauguration pending (Council. Quota)
140 | MCL-0142 | B&R | D | D1 | North | 68 | Roads - RMC / Cement Concrete | Old File/Offline | P/Laying RMC M-30 in streets of Jagannath puram ward no. 68. | 610 | 20 |  | MC Funds / General Quota | MC Funds | In Progress | 36.79 | -39.59% | 1876 dt 13.10.2025 | Y | Y | XEN | N |  |  | Y | Y | 15/EED dt 23.12.2025 | M/s Prince Sharma | 22.22 | 23.12.2025 | 3 | 25.03.2026 |  | Er. Ranjit Singh | No | No | 60% |  | NiL | In Progress |  | Work in progress | https://drive.google.com/file/d/1uyzo9_h4oyyaisoHvO1b5fkM8bqjBtIA/view?usp=sharing
141 | MCL-0143 | B&R | D | D1 | North | 68 | Perforated Tiles | Old File/Offline | P/L 60mm thick Perforated tiles on both side berms of Malhi road ward no. 68. | 2700 |  |  | MC Funds / General Quota | MC Funds | In Progress | 47.6 | -35.99% | 1877 dt 13.10.2025 | Y | Y | XEN | N |  |  | Y | Y | 14/EED dt 23.12.2025 | M/s Navdeep Gupta & Company | 30.47 | 23.12.2025 | 3 | 25.03.2026 |  | Er. Ranjit Singh | No | No | 10% |  | NiL | In Progress |  | Work just started
142 | MCL-0144 | B&R | D | D1 | North | 92 | Parks & Green Belts | Old File/Offline | Repair & Renovation of Parks in Pritam Nagar ward no. 92. | NA | NA |  | MC Funds / General Quota | MC Funds | In Progress | 18.62 | -28% | 2671 dt 11.02.2026 | Y | Y | SDO | N |  |  | Y | Y | 19/EED dt 16.01.2026 | M/s Dynamic tiles | 13.41 | 16.01.2026 | 3 | 20.04.2026 |  | Er. Ranjit Singh | No | No | 70% |  | NiL | In Progress |  | Work in Progress | https://drive.google.com/file/d/11Bo11_9DFd2wgGQRp8kPi-9TqeZ4CWc-/view?usp=sharing
143 | MCL-0145 | B&R | D | D1 | North | 68 | Others | Old File/Offline | PROVIDING AND FIXING M.S.SIGN BOARDS IN WARD NO 68 LUDHIANA | NA | NA |  | MC Funds / General Quota | MC Funds | In Progress | 15.66 | -31.15% | 2670 dt 11.02.2026 | Y | Y | SDO | N |  |  | Y | Y | 18/EED dt 16.01.2026 | M/s Dynamic tiles | 10.78 | 16.01.2026 | 3 | 20.04.2026 |  | Er. Ranjit Singh | No | No | 10 |  | NiL | In Progress |  | Work in Progress
144 | MCL-0146 | B&R | D | D1 | North | 70 | Others | Old File/Offline | Repair & Renovation of Govt. Primary school, kundan puri ward no. 70. | NA | NA |  | Viveki Funds | Un-tied/ Viveki Funds | Held up | 10 | -13.1% | 298 dt 26-03-2025 | Y | Y | SDO | N |  |  | Y | Y | 9/EED/D1-N dt 25/04/2025 | M/s Prince Sharma | 8.62 | 25.04.2025 | 2 | 26.06.2026 |  | Er. Ranjit Singh | No | No | 40% |  | NiL | Delayed/Held Up | The work was sanctioned under the viveki funds. However, private individuals have claimed ownership of the land at the site. As the matter is sub judice and a court stay order is in force, the work has been stopped. | Work held Up
145 | MCL-0147 | B&R | D | D1 | North | 91 | Others | Old File/Offline | Construction of Retainnig wall from Budha Nallah towards Baba Balak Nath Mandir in New Kundanpuri ward no. 91. | NA | NA |  | MC Funds / General Quota | MC Funds | In Progress | 125.95 | -25.2% | 843 dt 06-05-2025 | Y | Y | SE | N |  |  | Y | Y | 11/EED dt 22.05.2025 | M/S LRY Contractor | 94.21 | 22.05.2025 | 6 | 25.11.2025 |  | Er. Ranjit Singh | No | No | 85% | 82.125 | 77.37 | In Progress |  | Work in Progress
146 | MCL-0148 | B&R | D | D1 | North | 91 | Others | Old File/Offline | Construction of Volleyball Ground in Dusshera ground Upkar nagar ward no. 91. | NA | NA |  | MC Funds / General Quota | General quota | In Progress | 17.68 | -12.15% | 2823 dt 19.02.2026 | Y | Y | SDO | N |  |  | Y | Y | 33/EED dt 15.03.2026 | M/s Subodh Batish | 15.53 | 15.03.2026 | 3 | 16.06.2026 |  | Er. Ranjit Singh | No | No | 90% |  | NiL | In Progress |  | Work in Progress | https://drive.google.com/file/d/1VIdwUeSkRv8OjFfjUFJyIHFtGq7A_DRg/view?usp=sharing
147 | MCL-0149 | B&R | D | D1 | North | 93 | Roads - RMC / Cement Concrete | Old File/Offline | Prov. and laying of RMC M-30 in L.H.S streets of Mohalla Smart City in ward no. 94.(site change P//L of RMC M-30 at Main Haibowal puli upto MLA Office via Bhuriwala Gurudwara road & streets of Pahalwan colony ) | 650 |  |  | MC Funds / General Quota | MC funds | Completed | 75.76 | -42.5% | 3094 dt 22-11-2024 | Y | Y | SE | N |  |  | Y | Y | 35/EEA dt 27-11-2024 | Navdeep Gupta & Company | 43.56 | 27.11.2024 | 6 | 28.06.2026 |  | Er. Ranjit Singh | No | No | 100% | 63.5216 | 27.67 | Completed |  | Work completed
148 | MCL-0150 | B&R | D | D1 | North | 93 | Roads - RMC / Cement Concrete | Old File/Offline | Prov. and laying of RMC M-30 in streets of Sunil Nagar and balance streets of New Friends colony in ward no. 93. | 1540 |  |  | MC Funds / General Quota | MC funds | Held up | 95.63 | [9 empty] | Y | 66/EEA dt 05-12-2024 | Neeraj Joshi | 53.4 | 05.12.2024 |  |  |  | Er. Ranjit Singh | No | No | 50% |  | NiL | Delayed/Held Up |  | work held up due to original file missing | https://drive.google.com/file/d/1MLBjTsO7vifaHpDTWB_UYvERvKhT0zU9/view?usp=sharing
149 | MCL-0151 | B&R | D | D1 | North | 93 | Roads - RMC / Cement Concrete | Old File/Offline | Prov. and laying of RMC M-30 in R.H.S streets of Mohalla Smart City in ward no. 93. | 1380 |  |  | MC Funds / General Quota | MC funds | In Progress | 70.65 | -42.5% | 3093 dt 22-11-2024 | Y | Y | SE | N |  |  | Y | Y | 34/EEA dt 27-11-2024 | Navdeep Gupta & Company | 40.62 | 27.11.2024 | 6 | 28.05.2026 |  | Er. Ranjit Singh | No | No | 50% |  | NiL | In Progress |  | Work in Progress | https://drive.google.com/file/d/1NSazfmSHJxcgLvFaUX_G0HGsFhiSV6Xj/view?usp=sharing
150 | MCL-0152 | B&R | D | D1 | North | 68 | Roads - RMC / Cement Concrete | 374653 | P/Laying RMC M-30 in various streets of Hargobind nagar w.no 68. | 470 | 20 |  | MC Funds / General Quota | MC Funds | In Progress | 35.43 | -36.15% | 3328 dt 21.04.2026 | Y | Y | XEN | N |  |  | Y | Y | 03/EED dt 07.05.2026 | R.K Construction | 22.62 | 07.05.2026 | 4 | 10.09.2026 |  | Er. Ranjit Singh | No | No | 40% |  | NiL | In Progress |  | Work in Progress | https://drive.google.com/file/d/1uAM9W7QD7p4xXNuz6Q2XTuKxvNL2Mqre/view?usp=sharing
151 | MCL-0153 | B&R | D | D1 | North | 68 | Roads - RMC / Cement Concrete | 374646 | P/Laying RMC M-30 in remaining streets of Chander nagar ward no. 68. | 1610 | 20 |  | Councillor Quota (CQ) | CQ | In Progress | 93.29 | -15.15% | 3329 dt 21.04.2026 | Y | Y | SE | N |  |  | Y | Y | 04/EED dt 07.05.2026 | Neeraj Joshi | 79.16 | 07.05.2026 | 6 | 10.11.2026 |  | Er. Ranjit Singh | No | No | 60% |  | NiL | In Progress |  | Work in Progress | https://drive.google.com/file/d/1ytIxf_jUGjQV_WjCXK_RZGHWjeXdGUeU/view?usp=sharing
152 | MCL-0154 | B&R | D | D1 | North | 68 | Retaining Wall | 375142 | Construction of Retaining wall at Malhi puli existing bitumen road side. | NA | NA |  | MC Funds / General Quota | GQ | In Progress | 23.28 | -13.5% | 3326 dt 21.04.2026 | Y | Y | SDO | N |  |  | Y | Y | 06/EED dt 07.05.2026 | Rajesh Kumar Sood | 20.13 | 07.05.2026 | 3 | 10.08.2026 |  | Er. Ranjit Singh | No | No | 100% |  | NiL | In Progress |  | Work in Progress
153 | MCL-0155 | B&R | D | D1 | North | 67 | Retaining Wall | 375139 | Construction of Retainnig wall at Main haibowal puli to life line puli existing bitumen road side. | NA | NA |  | MC Funds / General Quota | GQ | In Progress | 27.91 | -12.04% | 3333 dt 21.04.2026 | Y | Y | XEN | N |  |  | Y | Y | 05/EED dt 07.05.2026 | Rajesh Kumar Sood | 24.55 | 07.05.2026 | 2 | 10.07.2026 |  | Er. Ranjit Singh | No | No | 100% |  | NiL | In Progress |  | Work in Progress
154 | MCL-0156 | B&R | D | D1 | North | 70 | Parks & Green Belts | 374746 | Repair & Renovation of Shahi Mohalla park in ward no. 70. | NA | NA |  | MC Funds / General Quota | GQ | In Progress | 26.07 | -28.95% | 3330 dt 21.04.2026 | Y | Y | XEN | N |  |  | Y | Y | 10/EED dt 07.05.2026 | Navdeep Gupta & Company | 18.52 | 07.05.2026 | 3 | 10.08.2026 |  | Er. Ranjit Singh | No | No | 80% | 80.7775 | 14.96 | In Progress |  | Work in Progress | https://drive.google.com/file/d/1M2_pDhwlY3Fy2ts-J0z5FgdG8HqNFbQF/view?usp=sharing
155 | MCL-0157 | B&R | D | D1 | North | 91 | Parks & Green Belts | 374725 | Repair & Renovation of Park 1 & Park 2 in New Deep Nagar ward no. 91. | NA | NA |  | Councillor Quota (CQ) | CQ | In Progress | 17.81 | -27.65% | 3335 dt 21.04.2026 | Y | Y | SDO | N |  |  | Y | Y | 08/EED dt 07.05.2026 | Navdeep Gupta & Company | 12.88 | 07.05.2026 | 3 | 10.08.2026 |  | Er. Ranjit Singh | No | No | 90 | 66.5373 | 8.57 | In Progress |  | Work in Progress
156 | MCL-0158 | B&R | D | D1 | North | 91 | Parks & Green Belts | 375161 | Repair & renovation of Parks along with Road Dusshera ground to damoria chowk in ward no. 91. | NA | NA |  | Councillor Quota (CQ) | CQ | In Progress | 43.8 | -34.8% | 3336 dt 21.04.2026 | Y | Y | XEN | N |  |  | Y | Y | 09/EED dt 07.05.2026 | M/s Prince Sharma | 28.56 | 07.05.2026 | 4 | 10.09.2026 |  | Er. Ranjit Singh | No | No | 30% |  | NiL | In Progress |  | Work just started | https://drive.google.com/file/d/1M3rviajyPYUqGRCrLTPvzlslvbZsMXtV/view?usp=sharing
157 | MCL-0159 | B&R | D | D1 | North | D1 | Roads - Bituminous | 375168 | Scrapping by Cold Milling Machine and P/L BM & SDBC in Haibowal Main road (hambran road to churpur road ) | 1680 | 32 |  | MC Funds / General Quota | MC Funds | Held up | 130.41 | -10.28% | 3334 dt 21.04.2026 | Y | Y | SE | N |  |  | Y | Y | 07/EED dt 07.05.2026 | Vansh Engineers | 117 | 07.05.2026 | 6 | 10.11.2026 |  | Er. Ranjit Singh | No | No |  |  | NiL | Delayed/Held Up |  | Work held up due to world bank project
158 | MCL-0160 | B&R | D | D1 | North | 91 | Roads - Bituminous | Offline | Upgradation of Road From Shamshan Ghat Puli & Malhi Pulli backside New Deep nagar ward no. 91. | 1500 |  |  | SASCI | Special Assistenace scheme | In Progress | 674.61 | -7.75% | 2674 dt 11.02.2026 | Y | Y | CE | N |  |  | Y | Y | 35/EED dt 25.03.2026 | M/s J.K Infcon Pvt. Ltd | 622.32 | 25.03.2026 | 3 | 26.06.2026 | 31.08.2026 | Er. Ranjit Singh | No | No | 97 | 24.1082 | 150.03 | In Progress |  | Work in progress | https://drive.google.com/file/d/1IFu9aUNI6ipIafexkp4mITEfkB8NXawK/view?usp=sharing
159 | MCL-0161 | B&R | D | D1 | North | D1 | Roads - Bituminous | Offline | Upgradation of various roads in different wards with RMC & Bitumen roads in sub zone D1 North Constituency. | 9110 | 22 |  | MDF | MDF | In Progress | 564.8 | -21.16% | 3288 dt 25.02.2026 | Y | Y | CE | N |  |  | Y | Y | 36/EED dt 25.03.2026 | M/s Dass Builders Pvt. Ltd | 445.29 | 25.03.2026 | 3 | 26.06.2026 | 31.08.2026 | Er. Ranjit Singh | No | No | 50% | 17.9793 | 80.06 | In Progress |  | Work in progress | https://drive.google.com/file/d/1imwQ0AYHXvrrLZUFIpelJetDhyJzhtKY/view?usp=sharing
160 | MCL-0162 | B&R | D | D1 | North | 93,67&92,91 | Roads - Bituminous | Offline | P/Laying 40mm BC at Sangam chowk towards Jassian road, Dusshera ground to shahi mohalla park road, Luxmi nagar main road in subzone D1 North Constituency. | 2256 | 21 |  | MDF | MDF-3 | Awarded | 171.24 |  |  | Y | Y | SE | N | [11 empty] | Er. Ranjit Singh | No | No |  |  |  | Not started |  | Estimate approval in anticipation. Tender has been called which is under Technical Evalution.
161 | MCL-0163 | B&R | D | D1 | North | 93,92,66,70, 91,68 | Roads - RMC / Cement Concrete | Offline | P/Laying RMC in streets of Kesari Enclave, Mohalla Smart City, Jagat Nagar, Luxmi nagar st no. 5,7,9 & Links & st.s of Kehar singh nagar road, Durgapuri st no. 8,9,10 & Mandir st, Piara singh chakki main road & Links, Mohini resort road to damoria chowk along dusshera ground, st no. 10 & Links & Garg optical shop humbran road to shamshanghat chowk,Bassi hospital to Lifeline puli road, Chander nagar councillor off to shakti nagar roads in subzone D1 North Constituency. | 8534 | 20' |  | MDF | MDF-3 | Awarded | 672.05 |  |  | Y | Y | CE | N | [11 empty] | Er. Ranjit Singh | No | No |  |  |  | Not Started |  | Estimate approval in anticipation. Tender has been called which is under Technical Evalution.
162 | MCL-0164 | B&R | D | D1 | North | 66 | Parks & Green Belts | 396353 | Construction of Playground/JoyBox opp. Bhatia School, Bank Colony ward no. 66. | NA | NA |  | Rangla Punjab | Rangla punjab Ph-I | In Progress | 25 | -12.1% | Approved in anticipation | Y | Y | XEN | N |  |  | Y | Y | 11/EED dt 25.02.2026 | M/s Subodh Batish | 21.96 | 25.02.2026 | 3 | 26.05.2026 | 30.08.2026 | Er. Ranjit Singh | No | No | 40% |  |  | In Progress |  | work in progress | https://drive.google.com/drive/folders/1dAGrq_8BKHHwseBfxxEdg3pB-Q95pS37?usp=sharing
163 | MCL-0165 | B&R | D | D1 | North | 70 | Building / Community Centre | 416819 | Construction of Room & Shed in Community Health Center in North Consitutency. Ward no. 70. | NA | NA |  | Rangla Punjab | Rangla punjab Ph-I | Not started | 20 | -4.61% | Approved in anticipation | Y | Y | SDO | N |  |  | Y | Y |  | M/s Samridhi construction | 19.07 |  | 3 |  |  | Er. Ranjit Singh | No | No |  |  |  | Not Started |  | Tender received allotment pending
164 | MCL-0166 | B&R | D | D1 | North | 67 | Roads - RMC / Cement Concrete | 404313 | Construction of Road with RMC from Karanvir hospital to Jassian chowk (22 ft road) w.no. 67. | 417.68 | 20 |  | Rangla Punjab | Rangla punjab Ph-II | Not started | 35 | -5.66% | 3331 dt 21.04.2026 | Y | Y | XEN | N |  |  | Y | Y |  | M/S Apex Developers | 33.01 |  | 3 |  |  | Er. Ranjit Singh | No | No |  |  |  | Not Started |  | File sent to F&CC for approval of tender.
165 | MCL-0167 | B&R | D | D1 | North | 68 | Roads - RMC / Cement Concrete | 376456 | Construction of Road with RMC from Lala Jagat Narain chowk to B.K Building Material store w.no. 68 | 365.85 | 27 |  | Rangla Punjab | Rangla punjab Ph-II | Awarded | 30 |  | 3332 dt 21.04.2026 | Y | Y | XEN | N |  |  | Y | Y |  |  |  |  | 3 |  |  | Er. Ranjit Singh | No | No |  |  |  | Not Started |  | 2nd time tender recalled
166 | MCL-0168 | B&R | A | A3 | East | 5 | RMC M-30 in roads |  | Laying RMC M-30 in roads between from Kakowal Road via MD Factory to Kailash Nagar Main Road w.no.5. |  |  |  | MC Funds / General Quota | GQ |  | 59.25 |  | 2709 dt. 24-09-2024 | Y | Y | [6 empty] | 3 16.04.2025 | Capital Const Co. | 32.85 | 16-04-2025 | 5 |  |  | Er. Ranjit Singh |  |  | 50 |  | 12.85 | Delayed/Held Up |  | Work was heldup due to non upgradation of Water supply lines, now same has been laid by 30/04/26 & 1100 Feet Completed & 2000 Feet Is pending. work is in progress now.
167 | MCL-0169 | B&R | A | A3 | East | 3 & 4 | RMC M-30 |  | Laying RMC M-30 in Mohalla Inder Vihar, New Basant Vihar, Basant Vihar Ext., Anand Puri in w.no.3 & 4. |  |  |  | MC Funds / General Quota | GQ |  | 37.09 |  | 2708 dt. 24-09-2024 | Y | Y | [6 empty] | 4 16.04.2025 | Capital Const Co. | 20.57 | 16-04-2025 | 4 |  |  | Er. Ranjit Singh |  |  | 85 |  | 4.58 | Delayed/Held Up |  | The work of streets of new basant vihar,Basant vihar ext. is completed and inder vihar and anandpuri streets work in process which is delayed due to water supply line now balance work will be completed by 10/07/26 350 Feet Completed & 1190 Feet Is pending. Work In progress
168 | MCL-0170 | B&R | A | A3 | East | 5 | P/Fixing I/tiles |  | P/Fixing I/tiles in Mohalla Royal Estate, Green City W No.5 |  |  |  | MC Funds / General Quota | GQ |  | 99.88 |  | 1518 dt. 13-10-2025 | Y | Y | [6 empty] | 51 16.02.2026 | M/s T&G Const Co. | 61.31 | 16-02-2026 | 6 |  |  | Er. Ranjit Singh |  |  | 25 |  | NIL | Delayed/Held Up |  | Initally work was stopped by area councillor due to upgradation of sewer line but now work is in progress which will be completed within time limit upto 15/8/26
169 | MCL-0171 | B&R | A | A3 | East | 2 | P/Fixing I/tiles |  | P/Fixing I/tiles in Golden Vihar W.No.02. |  |  |  | Councillor Quota (CQ) | CQ |  | 37.62 |  | 1624 dt. 13-10-2025 | Y | Y | [6 empty] | 53 16.02.2026 | Varinder Singh Govt Contractor | 23.33 | 16-02-2026 | 4 |  |  | Er. Ranjit Singh |  |  | 0 |  | NIL | Delayed/Held Up |  | Work was delayed due to inauguration pending by worthy MLA .Now worthy MLA has directed to start the work.
170 | MCL-0172 | B&R | A | A3 | East | 5 | Laying RMC |  | Laying RMC in street of Mohalla New Shimla Colony and Jaiswal Colony in W No.05 |  |  |  | Councillor Quota (CQ) | CQ |  | 44.22 |  | 1946 dt. 13-10-2025 | Y | Y | [6 empty] | 56 16.02.2026 | NS Infra | 27.42 | 16-02-2026 | 5 |  |  | Er. Ranjit Singh |  |  | 0 |  | NIL | Delayed/Held Up |  | Work is held up due to pending of laying W/S lines to be laid by o&m cell street has been katcha at site.
171 | MCL-0173 | B&R | A | A3 | East | 2 | P/Fixing I/tiles |  | P/Fixing I/tiles in Ekjot Nagar & Banda Bahadur Nagar in W No.02 |  |  |  | MC Funds / General Quota | GQ |  | 70.15 |  | 3268 dt. 29-11-2024 | Y | Y | [6 empty] | 58 16.02.2026 | Varinder Singh Govt Contractor | 43.64 | 16-02-2026 | 6 |  |  | Er. Ranjit Singh |  |  | 0 |  | NIL | Delayed/Held Up |  | Work was delayed due to inauguration pending by worthy MLA .Now worthy MLA has directed to start the work.
172 | MCL-0174 | B&R | A | A3 | East | 2 | P/Fixing I/tiles |  | P/Fixing I/tiles in Banda Bhadur Colony, New Azad Nagar & Masjid Wali Gali Ward No.02. |  |  |  | Councillor Quota (CQ) | CQ |  | 85.43 |  | 1663 dt. 13-10-2025 | Y | Y | [6 empty] | 68 09.03.2026 | Apex Developers | 53.83 | 09-03-2026 | 5 |  |  | Er. Ranjit Singh |  |  | 15 |  | NIL | Delayed/Held Up |  | Work was delayed due to inauguration pending by worthy MLA .Now worthy MLA has directed to start the work. work In progress
173 | MCL-0175 | B&R | A | A3 | East | 3 | P/F of I/tiles |  | P/F of I/tiles in Guru Gobind Singh Nagar, Panchsheel Colony & Basant Valley W No.03 |  |  |  | Councillor Quota (CQ) | CQ |  | 71.71 |  | 1893 dt. 13-10-2025 | Y | Y | [6 empty] | 69 09.03.2026 | Varinder Singh Govt Contractor | 44.37 | 09-03-2026 | 5 |  |  | Er. Ranjit Singh |  |  | 60 |  | 12.75 | Delayed/Held Up |  | The panchsheel colony streets completed and basant balley streets is in progress and the work of the work of guru gobind nagar streests will be started after completion of water supply lines to be laid by O&M cell . 1646 Feet Completed & 3075 Is Pending. Work In Progress
174 | MCL-0176 | B&R | A | A3 | East | 5 | P/fixing I/tiles |  | P/fixing I/tiles in Amrit Vihar in ward no.5. |  |  |  | Councillor Quota (CQ) | CQ |  | 65.29 |  | 1936 dt. 13-10-2025 | Y | Y | [6 empty] | 70 09.03.2026 | Varinder Singh Govt Contractor | 40.39 | 09-03-2026 | 4 |  |  | Er. Ranjit Singh |  |  | 80 |  | 24.46 | Delayed/Held Up |  | Work is in Progress. 2418 Feet completed & 1645 Is pending. Work in progress
175 | MCL-0177 | B&R | A | A3 | East | 3&4 | OGPC |  | Construction of bituminious roads between Main Noorwala Road & Kakowal Road via Raghunath Mandir & DVM School Road |  |  |  | MC Funds / General Quota | GQ |  | 40.42 |  | 2710 dt. 24-09-2024 | Y | Y | [6 empty] | 73 09.03.2026 | Maruti Const Co. | 33.18 | 09-03-2026 | 3 |  |  | Er. Ranjit Singh |  |  | 20 |  |  | Delayed/Held Up |  | Road gully work completed bitumen work pending due to shortage of bitumen
176 | MCL-0178 | B&R | A | A3 | East | 4&5 | OGPC |  | Construction of Main Kakowal Road w.no.4& 5 |  |  |  | MC Funds / General Quota | GQ |  | 80.2 |  | 813 dt. 09-04-2025 | Y | Y | [6 empty] | 85 10.04.2026 | Apex Builders | 76.19 | 10-04-2026 | 4 |  |  | Er. Ranjit Singh |  |  | 0 |  | NIL | Not Started |  | Work heldup due to upgradation of w/s Lines , (24/7)
177 | MCL-0179 | B&R | A | A3 | East | 3&4 | OGPC |  | Construction of Main Noorwala Road |  |  |  | MC Funds / General Quota | GQ |  | 72.8 |  | 814 dt. 09-04-2025 | Y | Y | [6 empty] | 86 10.04.2026 | VKBS Constructions Pvt. Ltd. | 69.16 | 10-04-2026 | 4 |  |  | Er. Ranjit Singh |  |  | 20 |  | NIL | In Progress |  | R/G work in progress & Work will start after rainy season
178 | MCL-0180 | B&R | A | A3 | East | 3 | Civil Work |  | Beautification of Lajpat Nagar Entry Point on Noorwala Road. |  |  |  | MC Funds / General Quota | GQ |  | 6.62 |  | 1973 dt. 13-10-2025 | [8 empty] | 87 10.04.2026 | Teg Builders | 6.36 | 10-04-2026 | 2 |  |  | Er. Ranjit Singh |  |  | 80 |  | NIL | In Progress |  | Work is in Progress
179 | MCL-0181 | B&R | A | A3 | East | 4 | P/Fixing I/tiles |  | P/Fixing I/tiles in Prem Vihar, Pink City, Vivek Dham & Sant Singh Cheema Nagar W No.04 |  |  |  | Councillor Quota (CQ) | CQ |  | 77.89 |  | 1958 dt. 13-10-2025 | [8 empty] | 87 10.04.2026 | Varinder Singh Govt Contractor | 55.39 | 10-04-2026 |  |  |  | Er. Ranjit Singh |  |  | 20 |  | NIL | In Progress |  | Work is in Progress
180 | MCL-0182 | B&R | A | A3 | East | 5&6 | OGPC |  | Construction of Main Kailash Nagar Road w.no.5 |  |  |  | MC Funds / General Quota | GQ |  | 102.73 |  | 463 dt. 09-04-2025 | [8 empty] | 15 13.05.2026 | Somaya Infrastructure | 73.3 | 13-05-2026 | 6 |  |  | Er. Ranjit Singh |  |  | 90 |  | NIL | In Progress |  | Work in progress. 7200 feet completed.
181 | MCL-0184 | B&R | C |  | Atam Nagar | 48 |  |  | Laying SDBC on various roads of W.No.43 |  |  |  | MC Funds / General Quota | MC |  | 106.79 |  | 2269 dt 24.07.24 | [8 empty] | 140/EEC DT 11.10.24 | Rajesh Kumar Sood | 75.83 |  | 6 | [5 empty] | 65 |  |  | Delayed/Held Up |  | Work stopped due to 24X7 W/S
182 | MCL-0185 | B&R | C |  | Atam Nagar | 46 |  |  | Development of Green Belt Dhuri Line to Gill Bridge along Sidhwan Canal |  |  |  | MC Funds / General Quota | MC |  | 137.66 |  | 1452 dt 22.02.23 | [8 empty] | 116/EEC DT 15.02.24 | Glisten | 95.09 |  | 6 | [5 empty] | 70 |  |  | In Progress |  | Work not completed due to enchroachment at site.
183 | MCL-0186 | B&R | C |  | Atam Nagar | 45 |  |  | Renovation of Municipal Corporation Ludhiana Zone C Main Office Gill Road. |  |  |  | MC Funds / General Quota | MC |  | 45.56 |  | 1664 dt 14.02.24 | [8 empty] | 124/EEC DT 20.02.24 | The Gill Co Op Diploma Holder Society Ltd | 34.17 |  | 6 | [5 empty] | 80 |  |  | In Progress |  | Work in progress.
184 | MCL-0187 | B&R | C |  | Atam Nagar | 41& 42 |  |  | Construction of RCC road from Labour chowk to Harkrishan Sahib School. |  |  |  | MC Funds / General Quota | MC |  | 118.84 |  | 721 dt 09.04.25 | [8 empty] | 169/EEC dt 28.04.25 | M/S Ashok Kumar Sobti | 84.78 |  | 6 | [5 empty] | 55 |  |  | Delayed/Held Up |  | Work held up due to upgradation of s/w line.
185 | MCL-0188 | B&R | C |  | Atam Nagar | 40 |  |  | Laying RMC in link of Kwality Road & Link of Maya Soap. |  |  |  | MC Funds / General Quota | MC |  | 43.73 |  | 1982 dt 13.10.25 | [8 empty] | 196/EEC dt 11.11.25 | N.S.Infra | 25.07 |  | 3 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Work held up due to upgradation of w/s line.
186 | MCL-0189 | B&R | C |  | Atam Nagar | 40 |  |  | P/F of Informatory Sign Board in various streets of W.No.40 |  |  |  | MC Funds / General Quota | MC |  | 4.06 |  | 1839 dt 13.10.25 | [8 empty] | 197/EEC dt 11.11.25 | Glisten | 3.57 |  | 1 | [5 empty] | 10 |  |  | Delayed/Held Up |  | work stopped due to dispute
187 | MCL-0190 | B&R | C |  | Atam Nagar | 45 |  |  | Laying RMC in main street Ram nagar market ,mohalla parbhat nagar and labour colony ward no.45 |  |  |  | MC Funds / General Quota | MC |  | 64.56 |  | 1840 dt 13.10.25 | [8 empty] | 199/EEC dt 11.11.25 | K.S.Constructions | 37.83 |  | 3 | [5 empty] | 25 |  |  | Delayed/Held Up |  | work stopped due to dispute
188 | MCL-0191 | B&R | C |  | Atam Nagar | 42 |  |  | P/F of Informatory Sign Board in various streets of W.No.42 |  |  |  | MC Funds / General Quota | MC |  | 7.6 |  | 1951 dt 13.10.25 | [8 empty] | 200/EEC dt 11.11.25 | Ram Parkash Kakar | 5.42 |  | 1 | [5 empty] | 0 |  |  | Not Started |  | Not Started
189 | MCL-0192 | B&R | C |  | Atam Nagar | 41 |  |  | Laying RMC in Streets of daba colony and new janta nagar ward no.41 |  |  |  | MC Funds / General Quota | MC |  | 88.55 |  | 1802 dt 13.10.25 | [8 empty] | 203/EEC dt 11.11.25 | Apex Devlopers | 51.36 |  | 4 | [5 empty] | 80 |  |  | In Progress |  | Work in progress.
190 | MCL-0193 | B&R | C |  | Atam Nagar | 40 |  |  | Laying RMC in Main Streets of Maya Soap W.No.40 |  |  |  | MC Funds / General Quota | MC |  | 76.67 |  | 1801 dt 13.10.25 | [8 empty] | 204/EEC dt 11.11.25 | K.S.Constructions | 44.92 |  | 3 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Work held up due to upgradation of water supply.
191 | MCL-0194 | B&R | C |  | Atam Nagar | 45 |  |  | Laying RMC in streets of mohalla parbhat nagar and vishvakarma colony ward no.45 |  |  |  | MC Funds / General Quota | MC |  | 29.51 |  | 1804 dt 13.10.25 | [8 empty] | 206/EEC dt 11.11.25 | R.K.Construction Co. | 18.07 |  | 3 | [5 empty] | 50 |  |  | In Progress |  | Work in progress.
192 | MCL-0195 | B&R | C |  | Atam Nagar | 40 |  |  | Laying BM&PC on Seerat Hospital Road upto Gurudwara Sahib. Site Change Lappar Paint Main Street & Links. |  |  |  | MC Funds / General Quota | MC |  | 57.13 |  | 2085 dt 13.10.25 | [8 empty] | 208/EEC dt 21.11.25 | Apex Builders | 36.07 |  | 5 | [8 empty] | Delayed/Held Up |  | Inaugration pending
193 | MCL-0196 | B&R | C |  | Atam Nagar |  | Roads - Bituminous |  | Upgradation of various roads of Atam Nagar constituency Zone C. |  |  |  | CSAG | CSAG |  | 522.08 |  | 2683 dt 11.02.2026 | [8 empty] | 03/EEC dt 20.02.26 | M/S VKBS Construction Pvt Ltd. | 498.58 |  | 3 | [5 empty] | 30 |  |  | In Progress |  | Work in progress.
194 | MCL-0197 | B&R | C |  | Atam Nagar |  | Roads - RMC / Cement Concrete |  | Upgradation of various roads of Atam Nagar constituency Zone C. |  |  |  | CSAG | CSAG |  | 511.6 |  | 2865 dt 19.02.2026 | [8 empty] | 04/EEC dt 20.02.26 | M/S Dass Builders | 434.66 |  | 3 | [5 empty] | 30 |  |  | In Progress |  | Work in progress.
195 | MCL-0198 | B&R | C |  | Atam Nagar | 40 |  |  | Laying RMC from Gill Road to Gurudwara Sahib (Seerat Hospital Road) |  |  |  | MC Funds / General Quota | MC |  | 96.65 |  | 2423 dt 05.01.2026 | [8 empty] | 11/EEC dt 27.02.2026 | LRY Labour Contractor | 62.73 |  | 4 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Inaugration pending
196 | MCL-0199 | B&R | C |  | Atam Nagar | 40 |  |  | P/F of cat eyes & laying Thermoplastic lines in different streets of W.No.40 |  |  |  | MC Funds / General Quota | MC |  | 13.9 |  | 2352 dt 05.01.26 | [8 empty] | 07/EEC dt 27.02.2026 | Anand Sales | 9.93 |  | 2 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Decision pending
197 | MCL-0200 | B&R | C |  | Atam Nagar | 40 |  |  | Laying RMC in Nippy Public School Street W.No.40 |  |  |  | MC Funds / General Quota | MC |  | 49.15 |  | 2440 dt 05.01.2026 | [8 empty] | 08/EEC dt 27.02.2026 | M/S Ashok Kumar Sobti | 33.59 |  | 3 | [5 empty] | 75 |  |  | In Progress |  | Work in progress.
198 | MCL-0201 | B&R | C |  | Atam Nagar | 40 |  |  | Laying RMC in various streets of mohalla Shimlapuri W.No.40. |  |  |  | MC Funds / General Quota | MC |  | 84.21 |  | 2441 dt 05.01.26 | [8 empty] | 09/EEC dt 27.02.2026 | M/S Ashok Kumar Sobti | 57.55 |  | 4 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Inaugration pending
199 | MCL-0202 | B&R | C |  | Atam Nagar | 41 |  |  | Construction of Road by Laying RMC from Bedi Chowk to Harkrishan Chowk. (GQ) |  |  |  | MC Funds / General Quota | MC Funds(GQ) |  | 76.1 |  | 2842 dt 19.02.2026 | [8 empty] | 20/EEC dt 02.03.2026 | The Gill Co Op Diploma Holder Society Ltd | 46.64 |  | 4 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Work held up due to upgradation of sewer line.
200 | MCL-0203 | B&R | C |  | Atam Nagar | 42 |  |  | Laying RMC in Streets of New Janta Nagar W.No.42 |  |  |  | Councillor Quota (CQ) | MC Funds (CQ) |  | 98.29 |  | 2838 dt 19.02.2026 | [8 empty] | 17/EEC dt 02.03.2026 | Capital Const.Co. | 57.22 |  | 5 | [5 empty] | 5 |  |  | In Progress |  | Work in progress.
201 | MCL-0204 | B&R | C |  | Atam Nagar | 45 |  |  | Providing and Laying Perforated interlocking tiles adjoining Road from Sangeet Cinema to Gabria Office Road, W.No.45 |  |  |  | Councillor Quota (CQ) | MC Funds (CQ) |  | 14.6 |  | 2730 dt 19.02.26 | [8 empty] | 21/EEC dt 02.03.2026 | Dynamic Tiles | 9.93 |  | 2 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Inaugration pending
202 | MCL-0205 | B&R | C |  | Atam Nagar | 45 |  |  | Construction of new park near Partap Chowk, W.No.45. |  |  |  | Councillor Quota (CQ) | MC Funds (CQ) |  | 64.41 |  | 2820 dt 19.02.2026 | [8 empty] | 28/EEC dt 02.03.2026 | Ram Parkash Kakar | 44.31 |  | 5 | [5 empty] | 35 |  |  | In Progress |  | Work in progress.
203 | MCL-0206 | B&R | C |  | Atam Nagar | 45 |  |  | Providing and Laying Perforated interlocking tiles adjoining Road Vishkarma Park. |  |  |  | N-CAP | NCAP Funds |  | 21.84 |  | 2729 dt 19.02.2026 | [8 empty] | 23/EEC dt 02.03.2026 | T and G Construction Co. | 16.38 |  | 2 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Inaugration pending
204 | MCL-0207 | B&R | C |  | Atam Nagar | 45 |  |  | Providing and Laying Perforated interlocking tiles adjoining Road Basant Park. |  |  |  | MC Funds / General Quota | MC Funds |  | 13.51 |  | 2735 dt 19.02.2026 | [8 empty] | 19/EEC dt 02.03.2026 & 29/EEC dt 02.03.2026 | Dynamic Tiles & T and G Construction Co. | 10.13 |  | 2 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Inaugration pending
205 | MCL-0208 | B&R | C |  | Atam Nagar | 48 |  |  | Laying RMC in various streets of mohalla Himmat Singh Nagar, Shaheed Karnail Singh Nagar & Guru nanak Colony W No. 48 |  |  |  | Councillor Quota (CQ) | CQ |  | 89.41 |  | 2863 dt 19.02.2026 | [8 empty] | 26/EEC dt 02.03.2026 | V.S.Infra | 48.28 |  | 5 | [5 empty] | 45 |  |  | In Progress |  | work in progress.
206 | MCL-0209 | B&R | C |  | Atam Nagar | 42 |  |  | Construction of Road by Laying RMC from Jeet Sweet Shop to Itta Wala Chowk Halka Atam Nagar. (Rangla Punjab Vikas Scheme). |  |  |  | RPVS | RPVS |  | 60.95 |  | 3463 dt 21.04.2026 | [8 empty] | 54/EEC dt 30.04.2026 | Apex Devlopers | 42.67 |  | 4 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Inaugration pending
207 | MCL-0210 | B&R | C |  | Atam Nagar | 46 |  |  | P/F of Informatory Sign Board in various streets of W.No.46 |  |  |  | Councillor Quota (CQ) | MC Funds (CQ) |  | 7.61 |  | 3409 dt 21.04.2026 | [8 empty] | 58/EEC dt 08.05.2026 | Glisten | 6.21 |  | 2 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Decision pending
208 | MCL-0211 | B&R | C |  | Atam Nagar | 44 |  |  | Laying RMC in street no 3,4,5 & Links of SAS Nagar W.No.44 |  |  |  | Councillor Quota (CQ) | MC Funds (CQ) |  | 75.05 |  | 3482 dt 21.04.2026 | [8 empty] | 60/EEC dt 08.05.2026 | Capital Const.Co. | 43.69 |  | 4 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Inaugration pending
209 | MCL-0212 | B&R | C |  | Atam Nagar | 46 |  |  | Laying RMC in streets of super cycle market & mohalla chet singh nagar W.No.46 |  |  |  | Councillor Quota (CQ) | MC Funds (CQ) |  | 41.51 |  | 3417 dt 21.04.2026 | [8 empty] | 62/EEC dt 08.05.2026 | Capital construction Co. | 24.16 |  | 3 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Inaugration pending
210 | MCL-0213 | B&R | C |  | Atam Nagar | 40 |  |  | P/F of Stainless Steel Sign boards in ward no.40 |  |  |  | MC Funds / General Quota | MC Funds(GQ) |  | 12.31 |  | 3414 dt 21.04.2026 | [8 empty] | 66/EEC dt 08.05.2026 | Glisten | 10.58 |  | 2 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Decision pending
211 | MCL-0214 | B&R | C |  | Atam Nagar | 46 |  |  | Laying RMC in Streets No 5, 7 New Janta Nagar( Gill Road) , Street No.20 Janta Nagar, W.No 46 |  |  |  | Councillor Quota (CQ) | MC Funds (CQ) |  | 44.3 |  | 3418 dt 21.04.2026 | [8 empty] | 71/EEC dt 08.05.2026 | Capital construction Co. | 25.79 |  | 3 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Inaugration pending
212 | MCL-0215 | B&R | C |  | Atam Nagar | 46 |  |  | Repair & Renovation of Central Verge of Gill Road from Gill Chowk to Gill Canal.(GQ) |  |  |  | MC Funds / General Quota | GQ |  | 19.76 |  | 3410 dt 21.04.2026 | [8 empty] | 73/EEC dt 08.05.2026 | Teg Builders | 19.18 |  | 3 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Inaugration pending
213 | MCL-0216 | B&R | C |  | Atam Nagar | 40 |  |  | Repair & Renovation of Green belt from gill road to Guru Arjun Dev Gurudwara Sahib and Const. of Canopies in ward no 40 |  |  |  | MC Funds / General Quota | MC Funds(GQ) |  | 39.75 |  | 3420 dt 21.04.2026 | [8 empty] | 74/EEC dt 08.05.2026 | Teg Builders | 37.43 |  | 5 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Inaugration pending
214 | MCL-0217 | B&R | C |  | Atam Nagar | 44 |  |  | Laying RMC in street no. 01 & 04 of mohalla Partap Nagar ward no.44. |  |  |  | Councillor Quota (CQ) | MC Funds (CQ) |  | 25.83 |  | 3483 dt 21.04.2026 | [8 empty] | 75/EEC dt 08.05.2026 | Capital Const.Co. | 15.04 |  | 2 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Inaugration pending
215 | MCL-0218 | B&R | C |  | Atam Nagar | 44 |  |  | Laying RMC in streets no.2 & Links of SAS Nagar W.No.44. |  |  |  | Councillor Quota (CQ) | MC Funds (CQ) |  | 40.88 |  | 3481 dt 21.04.2026 | [8 empty] | 76/EEC dt 08.05.2026 | Capital Const.Co. | 23.8 |  | 3 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Inaugration pending
216 | MCL-0220 | B&R | C |  | South | 35 |  |  | Construction of Stadium at Village Daba |  |  |  | MDF | MDF |  | 323.39 |  | 931 dt 12.10.23 | [8 empty] | 100/EEC dt 13.10.23 | Asis Builders | 290.89 |  | 12 | [5 empty] | 95 |  |  | In Progress |  | File sent for revision of work
217 | MCL-0221 | B&R | C |  | South |  |  |  | Relocation and construction of Lohara Bridge in alignment with the Missing Link-2 Part C with Southern Bye Pass Project Ludhiana |  |  |  | MC Funds / General Quota | MC |  | 1194.48 |  | 3333 dt 05.12.24 | [8 empty] | 145/EEC DT 26.11.24 | M/s Tarmac Road and Roof Builders. | 1194.48 |  | 12 | [5 empty] | 80 |  |  | In Progress |  | Work will start after Canal Closure
218 | MCL-0222 | B&R | C |  | South | 43 |  |  | Laying RMC in st.no.19,20 and link of Mohalla Kot Mangal and St.No.1 Mohalla Gurpal Nagar. |  |  |  | MC Funds / General Quota | MC |  | 51.92 |  | 3341 dt 05.12.24 | [8 empty] | 156/EEC dt 24.12.24 | M/s Capital Construction Co. | 28.01 |  | 4 | [5 empty] | 90 |  |  | Delayed/Held Up |  | Work held up due to 24X7 W/S line.
219 | MCL-0223 | B&R | C |  | South | 43 |  |  | Laying RMC in St.No.2, St.No. 7 ½ and Main street of Mohalla Hargobind Nagar. |  |  |  | MC Funds / General Quota | MC |  | 75.15 |  | 3335 dt 05.12.24 | [8 empty] | 157/EEC dt 24.12.24 | M/s Capital Construction Co. | 40.54 |  | 5 | [5 empty] | 30 |  |  | Delayed/Held Up |  | Work stopped due to dispute
220 | MCL-0224 | B&R | C |  | South | 38 |  |  | Construction of Road from Shamshan Ghat to Bapu market via Radha Swami Satsang Ghar Lohara. |  |  |  | MC Funds / General Quota | MC |  | 84.28 |  | 720 dt 09.04.25 | [8 empty] | 165/EEC dt 28.04.25 | Apex Builders | 57.07 |  | 3 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Work held up due to 24X7 W/S line.
221 | MCL-0225 | B&R | C |  | South | 34 |  |  | Construction of 33' road from Giaspura Park to Pippal Chowk. |  |  |  | MC Funds / General Quota | MC |  | 172.89 |  | 726 dt 09.04.25 | [8 empty] | 166/EEC dt 28.04.25 | M/s Hitesh aggarwal contractor | 107.19 |  | 6 | [5 empty] | 95 |  |  | In Progress |  | File sent for revision of work
222 | MCL-0226 | B&R | C |  | South |  |  |  | Construction of RCC road from wine shop to Giaspura Chowk |  |  |  | MC Funds / General Quota | MC |  | 124.53 |  | 820 dt 06.05.25 | [8 empty] | 181/EEC dt 22.05.25 | Apex Devlopers | 74.73 |  | 8 | [5 empty] | 85 |  |  | In Progress |  | Work in progress
223 | MCL-0227 | B&R | C |  | South | 38 |  |  | Construction of road from Simran palace to Morgan crossing. |  |  |  | MC Funds / General Quota | MC |  | 99.94 |  | 729 dt 09.04.25 | [8 empty] | 182/EEC dt 22.05.25 | Hitesh Aggarwal | 61.96 |  | 8 | [5 empty] | 30 |  |  | Delayed/Held Up |  | Work held up due to 24X7 W/S line.
224 | MCL-0228 | B&R | C |  | South | 35 |  |  | Laying 80mm thick I/tiles balance streets mohalla Maha Singh Nagar. |  |  |  | MC Funds / General Quota | MC |  | 67.42 |  | 830 dt 06.05.25 | [8 empty] | 189/EEC dt 26.06.25 | Apex Devlopers | 38.44 |  | 5 | [5 empty] | 95 |  |  | In Progress |  | Work in progress.
225 | MCL-0229 | B&R | C |  | South | 31 |  |  | Construction of RCC roads from NPC upto Daba road and link on GT road. |  |  |  | MC Funds / General Quota | MC |  | 179.36 |  | 1021 dt 06.05.25 | [8 empty] | 195/EEC dt 20.08.25 | LRY labour Contractor. | 97.84 |  | 8 | [5 empty] | 20 |  |  | In Progress |  | Work in progress.
226 | MCL-0230 | B&R | C |  | South | 32 |  |  | Construction of RCC road from Giaspura Chowk to Eastman Chowk. |  |  |  | MC Funds / General Quota | MC |  | 326.57 |  | 1020 dt 06.05.25 | [8 empty] | 192/EEC dt 20.08.25 | LRY labour Contractor. | 178.14 |  | 12 | [5 empty] | 60 |  |  | In Progress |  | Work in progress.
227 | MCL-0231 | B&R | C |  | South | 32 |  |  | P/ Fixing 80mm thick I/Tiles in Mohalla Makkar Colony, Dhandari Kalan & Shanti Nagar, W. No. 32. |  |  |  | Councillor Quota (CQ) | MC Funds (CQ) |  | 76.48 |  | 1033 dt 06.05.2025 | [8 empty] | 05/EEC dt 27.02.2026 | Navyug Company | 42.66 |  | 3 | [5 empty] | 30 |  |  | In Progress |  | Work in progress
228 | MCL-0232 | B&R | C |  | South | 27 |  |  | Construction Of Rooms, Boundary wall and I/ Tiles adjoining Sewa Kendra Water Tank Sherpur |  |  |  | MC Funds / General Quota | GQ |  | 49.73 |  | 1027 dt 06.05.25 | [8 empty] | 10/EEC dt 27.02.2026 | Teg Builders | 42.82 |  | 6 | [5 empty] | 25 |  |  | In Progress |  | Work in progress
229 | MCL-0233 | B&R | C |  | South | 35 |  |  | Laying RMC in St.No. 2,3 & 5 of Mohalla Fateh Singh Nagar W.No.35 |  |  |  | Councillor Quota (CQ) | MC FUNDS (CQ) |  | 19.37 |  | 2721 dt 19.02.2026 | [8 empty] | 27/EEC dt 02.03.2026 | Varinder Singh Govt. Contractor | 11.62 |  | 2 | [5 empty] | 10 |  |  | In Progress |  | work in progress
230 | MCL-0234 | B&R | C |  | South | 36 |  |  | Laying RMC in various streets of Lohara Village and Basant Nagar W.No.36 |  |  |  | Councillor Quota (CQ) | MC FUNDS (CQ) |  | 54.86 |  | 2840 dt 19.02.26 | [8 empty] | 30/EEC dt 02.03.2026 | T And G Construction Co | 35.7 |  | 3 | [5 empty] | 30 |  |  | In Progress |  | work in progress
231 | MCL-0235 | B&R | C |  | South | 38 |  |  | Laying RMC in various streets of Ishar Nagar W.No-38 |  |  |  | Councillor Quota (CQ) | MC FUNDS (CQ) |  | 21.21 |  | 2722 dt 19.02.26 | [8 empty] | 15/EEC dt 02.03.2026 | Neeraj Joshi | 12.17 |  | 2 | [5 empty] | 60 |  |  | In Progress |  | work in progress
232 | MCL-0236 | B&R | C |  | South | 31 |  |  | Laying RMC in Streets of Mohalla Bhagwan Nagar W. No.31 |  |  |  | Councillor Quota (CQ) | MC FUNDS (CQ) |  | 72.79 |  | 2841 dt 19.02.2026 | [8 empty] | 18/EEC dt 02.03.2026 | Capital Const.Co. | 44 |  | 4 | [5 empty] | 0 |  |  | Delayed/Held Up |  | inaugration pending.
233 | MCL-0237 | B&R | C |  | South | 27 |  |  | Construction of central Verge HP Dharam Kanda, upto Opp Govt.High School Sherpur W.No.27 |  |  |  | MC Funds / General Quota | MC |  | 98.83 |  | 2727 dt 19.02.2026 | [8 empty] | 37/EEC dt 02.03.2026 | M/S Apex Devlopers | 69.19 |  | 5 | [5 empty] | 10 |  |  | In Progress |  | work in progress
234 | MCL-0238 | B&R | C |  | South | 27 |  |  | Laying RMC in various streets of baba gajjamall Jain Colony & Mohindra Colony, W.No.27 |  |  |  | Councillor Quota (CQ) | MC Funds (CQ) |  | 16.48 |  | 2708 dt 19.02.2026 | [8 empty] | 33/EEC dt 02.03.2026 | Asis Builders | 9.7 |  | 2 | [5 empty] | 20 |  |  | In Progress |  | work in progress
235 | MCL-0239 | B&R | C |  | South | 37 |  |  | Laying RMC Balance Streets of Basant Nagar Halka South, W.No.37 |  |  |  | Councillor Quota (CQ) | MC Funds (CQ) |  | 24.96 |  | 2726 dt 19.02.26 | [8 empty] | 34/EEC dt 02.03.2026 | Asis Builders | 14.69 |  | 2 | [5 empty] | 0 |  |  | Delayed/Held Up |  | inaugration pending.
236 | MCL-0240 | B&R | C |  | South | 32& 34 |  |  | Laying RMC in Asian Bike Street Dhandari Kalan Sua Road w.no. 32 and various streets of Guru Nanak Nagar W.No. 34 |  |  |  | MC Funds / General Quota | MC Funds (GQ) |  | 63.73 |  | 2757 dt 19.02.26 | [8 empty] | 36/EEC dt 02.03.2026 | Neeraj Joshi | 36.56 |  | 4 | [5 empty] | 60 |  |  | In Progress |  | work in progress
237 | MCL-0241 | B&R | C |  | South | 34 & 35 |  |  | Laying RMC in St. no. 2,3 & links of Captain Sewa Singh Nagar W.No. 34 and various roads of Daba Village adjoining Nanka Darbar Gurudwara Sahib and JB Karyana Store in W. no. 35 |  |  |  | MC Funds / General Quota | MC Funds (GQ) |  | 93.65 |  | 2846 dt 19.02.26 | [8 empty] | 41/EEC dt 02.03.2026 | The Gill Co op Diploma Holder Society. | 57.4 |  | 5 | [5 empty] | 0 |  |  | Delayed/Held Up |  | inaugration pending.
238 | MCL-0242 | B&R | C |  | South | 32 & 39 |  |  | Laying RMC in street no. 5 of Guru Gobind Singh Nagar in W.No. 39 and Street near Mini Rose Garden W.No. 32 |  |  |  | Councillor Quota (CQ) | MC Funds (CQ) |  | 49.87 |  | 2724 dt 19.02.26 | [8 empty] | 31/EEC dt 02.03.2026 | T And G Construction Co | 33.67 |  | 3 | [5 empty] | 20 |  |  | In Progress |  | work in progress
239 | MCL-0243 | B&R | C |  | South | 32 |  |  | Laying RMC in Dhandari Kalan road W.No. 32 |  |  |  | MC Funds / General Quota | MC Funds (GQ) |  | 57.6 |  | 2710 dt 19.02.2026 | [8 empty] | 40/EEC dt 02.03.2026 | M/S Apex Devlopers | 33.41 |  | 3 | [5 empty] | 0 |  |  | Delayed/Held Up |  | inaugration pending.
240 | MCL-0244 | B&R | C |  | South | 33 |  |  | Laying RMC in various streets of Makkar Colony W.No. 33 |  |  |  | MC Funds / General Quota | MC Funds (GQ) |  | 76.08 |  | 2758 dt 19.02.26 | [8 empty] | 35/EEC dt 02.03.26 | Neeraj Joshi. | 43.64 |  | 4 | [5 empty] | 20 |  |  | In Progress |  | work in progress
241 | MCL-0245 | B&R | C |  | South | 32 |  |  | Laying RMC near PSPCL road street and Mohalla Shanti Nagar Link in W.No. 32 |  |  |  | MC Funds / General Quota | MC Funds (GQ) |  | 59.95 |  | 2711 dt 19.02.26 | [8 empty] | 39/EEC dt 02.03.2026 | M/S Apex Devlopers | 34.77 |  | 3 | [5 empty] | 40 |  |  | In Progress |  | work in progress
242 | MCL-0246 | B&R | C |  | South | 32 |  |  | Reconstruction of Road Dhandari Phirni W.No.32.(NCAP Funds). |  |  |  | MC Funds / General Quota | MC Funds (GQ) |  | 94.37 |  | 2837 dt 19.02.26 | [8 empty] | 38/EEC dt 02.03.2026 | Dugra Construction Co. | 70.58 |  | 5 | [5 empty] | 10 |  |  | In Progress |  | work in progress
243 | MCL-0247 | B&R | C |  | South | 38 |  |  | Laying RMC in Various street of Captain Nagar W.No. 38, St. no. 9 link and Isher Nagar Block-C streets in w. no. 38 and Various Streets of Mohalla Ishar Nagar And begoana Street |  |  |  | Councillor Quota (CQ) | MC Funds (CQ) |  | 67.18 |  | 2728 dt 19.02.2026 | [8 empty] | 50/EEc dt 09.04.2026 | M/S Apex Devlopers | 40.31 |  | 4 | [5 empty] | 0 |  |  | Delayed/Held Up |  | inaugration pending.
244 | MCL-0248 | B&R | C |  | South | 37 |  |  | Laying RMC in street no. 8 of Guru Gobind Singh Nagar W. no. 37 |  |  |  | Rangla Punjab | Rangla Punjab |  | 32.43 |  | 3448 dt 21.04.2026 | [8 empty] | 51/EEC dt 30.04.2026 | K.S. Constructions | 21.37 |  | 3 | [5 empty] | 40 |  |  | In Progress |  | work in progress
245 | MCL-0249 | B&R | C |  | South | 32 |  |  | Providing and Installation of Open air Gym Equipments Dhandari Kalan W.no. 32 |  |  |  | Rangla Punjab | Rangla Punjab |  | 8 |  | 3455 dt 21.04.26 | [8 empty] | 52/EEC dt 30.04.2026 | Aggarwal Builders | 4.64 |  | 2 | [5 empty] | 20 |  |  | In Progress |  | work in progress
246 | MCL-0250 | B&R | C |  | South | 33 |  |  | Laying RMC in various streets of Satguru Nagar & Karamjit Nagar Halka South W. no. 33 |  |  |  | Rangla Punjab | Rangla Punjab |  | 76.57 |  | 3450 dt 21.04.2026 | [8 empty] | 55/EEC dt 30.04.2026 | M/S Ashok Kumar Sobti | 49.77 |  | 4 | [5 empty] | 20 |  |  | In Progress |  | work in progress
247 | MCL-0251 | B&R | C |  | South | 35 |  |  | Laying RMC in Streets No-1 & 5 of Mohalla Guru Gobid Singh Nagar w. No-35 |  |  |  | MC Funds / General Quota | MC FUNDS |  | 35.91 |  | 3465 dt 21.04.2026 | [8 empty] | 56/EEC dt 08.05.2026 | Godwyn | 20.02 |  | 1.5 | [5 empty] | 0 |  |  | Delayed/Held Up |  | inaugration pending.
248 | MCL-0252 | B&R | C |  | South | 33 |  |  | Construction of Bathrooms in Shamshan Ghat Lohara W.no.33 |  |  |  | MPLAD Funds | MP LAD |  | 4.5 |  | 3461 dt 21.04.2026 | [8 empty] | 57/EEC dt 08.05.2026 | Kohinoor Builders | 4.39 |  | 3 | [5 empty] | 0 |  |  | Delayed/Held Up |  | inaugration pending.
249 | MCL-0253 | B&R | C |  | South | 35 |  |  | P/F 80MM Thick I/Tiles Streets No-18,1 and Links Mohalla Fateh Singh Nagar W. No-35 |  |  |  | MC Funds / General Quota | MC FUNDS |  | 38.14 |  | 3464 dt 21.04.2026 | [8 empty] | 59/EEC dt 08.05.2026 | Godwyn | 21.26 |  | 1.5 | [5 empty] | 0 |  |  | Delayed/Held Up |  | inaugration pending.
250 | MCL-0254 | B&R | C |  | South | 36 |  |  | Laying RMC in Streets of Mohalla Gurmail Nagar Dhillon Nagar and Basatn Nagar in W. No-36 |  |  |  | Councillor Quota (CQ) | MC FUNDS (CQ) |  | 27.63 |  | 3413 dt 21.04.2026 | [8 empty] | 61/EEC dt 08.05.2026 | Godwyn infra | 18.42 |  | 2 | [5 empty] | 0 |  |  | Delayed/Held Up |  | inaugration pending.
251 | MCL-0255 | B&R | C |  | South | 50 |  |  | Construction of Bathrooms in Shamshan Ghat Dholewal W.no.50 |  |  |  | MPLAD Funds | MP LAD |  | 4.5 |  | 3456 dt 21.04.2026 | [8 empty] | 63/EEC dt 08.05.2026 | Kohinoor Builders | 4.44 |  | 3 | [5 empty] | 0 |  |  | Delayed/Held Up |  | inaugration pending.
252 | MCL-0256 | B&R | C |  | South | 35 |  |  | P/F of informatory sign board in various streets of W.No.35 |  |  |  | Councillor Quota (CQ) | MC FUNDS (CQ) |  | 8.5 |  | 3421 dt 21.04.2026 | [8 empty] | 64/EEC dt 08.05.2026 | Glisten | 6.94 |  | 2 | [5 empty] | 0 |  |  | Delayed/Held Up |  | inaugration pending.
253 | MCL-0257 | B&R | C |  | South | 43 |  |  | Laying RMC in street no. 11/5,11/6 and 11/7 of Kabir Nagar in W.No. 43 |  |  |  | MC Funds / General Quota | MC Funds (GQ) |  | 49.99 |  | 3416 dt 21.04.2026 | [8 empty] | 65/EEC dt 08.05.2026 | Prince Sharma | 29.66 |  | 3 | [5 empty] | 0 |  |  | Delayed/Held Up |  | inaugration pending.
254 | MCL-0258 | B&R | C |  | South | 37 |  |  | P/F 80MM thick I/Tiles in Streets of Mohalla Gobind Nagar and Azad Nagar in W. No-37 |  |  |  | MC Funds / General Quota | MC Funds (GQ) |  | 39.71 |  | 3415 dt 21.04.2026 | [8 empty] | 67/EEC dt 08.05.2026 | N.S.Infra | 26.21 |  | 3 | [5 empty] | 0 |  |  | Delayed/Held Up |  | inaugration pending.
255 | MCL-0259 | B&R | C |  | South | 32 |  |  | P/F 80mm thick I/Tiles in various streets Shanti Nagar in W.No. 32 |  |  |  | Councillor Quota (CQ) | MC Funds (CQ) |  | 48.65 |  | 3411 dt 21.04.2026 | [8 empty] | 68/EEC dt 08.05.2026 | N.S.Infra | 31.63 |  | 3 | [5 empty] | 0 |  |  | Delayed/Held Up |  | inaugration pending.
256 | MCL-0260 | B&R | C |  | South | 38 |  |  | P/F 60MM I/Tiles in Streets 5L, 6L, 13R & Links of Mohalla Isher Nagar W. No.38 |  |  |  | MC Funds / General Quota | MC FUNDS |  | 31.45 |  | 3480 dt 21.04.2026 | [8 empty] | 70/EEC dt 08.05.2026 | Godwyn | 17.53 |  | 1.5 | [5 empty] | 0 |  |  | Delayed/Held Up |  | inaugration pending.
257 | MCL-0261 | B&R | C |  | South | 35 |  |  | P/F 60mm I/Tiles Streets of 6 to 12 & St No. 17 in Mohalla Fateh Singh Nagar W. No. 35 |  |  |  | MC Funds / General Quota | MC FUNDS |  | 87.31 |  | 3474 dt 21.04.2026 | [8 empty] | 72/EEC dt 08.05.2026 | M/S Apex Devlopers | 50.65 |  | 3 | [5 empty] | 0 |  |  | Delayed/Held Up |  | inaugration pending.
258 | MCL-0262 | B&R | C |  | South |  |  |  | Construction of various roads in South Constituency Zone C. |  |  |  | SASCI | SASCI Funds |  | 564.33 |  | 2681 dt 11.02.2026 | [8 empty] | 77/EEC dt 08.05.2026 | M/S Hitesh Aggarwal Cont. | 537.8 |  | 3 | [5 empty] | 25 |  |  | In Progress |  | Work in progress.
259 | MCL-0263 | B&R | C |  | South | Gen |  |  | Construction of Fire Station at Dhandari Kalan in South Constituency. |  |  |  | MC Funds / General Quota | MC Funds (GQ) |  | 189.77 |  | in-anticipation by Worthy Mayor on dt 21.05.2026 | [8 empty] | 78/EEC dt 21.05.2026 | M/S Parveen Sehgal | 187.68 |  | 8 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Dispute at Site
260 | MCL-0264 | B&R | C |  | South | 35 |  |  | Construction of RCC road from Mair Di Chakki Chowk to Near Daba Village W. No. 35 |  |  |  | Rangla Punjab | Rangla Punjab |  | 61.02 |  | 3110 dt 25.02.26 | [8 empty] | 79/EEC dt 22.06.26 | Varinder Singh Govt Contractor | 51.46 |  | 4 | [5 empty] | 20 |  |  | In Progress |  | Work in progress.
261 | MCL-0265 | B&R | C |  | South | 38 |  |  | Construction of Dispensary on Shamshan Ghat road Lohara W. NO. 38 |  |  |  | Rangla Punjab | Rangla Punjab |  | 14.99 |  | in-anticipation by Worthy Mayor on dt 13.06.26 | [8 empty] | 80/EEC dt 22.06.26 | Smridhi Construction | 13.67 |  | 4 | [5 empty] | 5 |  |  | In Progress |  | Work in progress.
262 | MCL-0266 | B&R | C |  | South | 32 |  |  | Reconstruction of community centre on Campa Cola road in village Dhandari kalan. W. no. 32 |  |  |  | Rangla Punjab | Rangla Punjab |  | 25 |  | 3472 dt 21.04.26 | [8 empty] | 81/EEC dt 22.06.26 | Smridhi Construction | 22.61 |  | 4 | [5 empty] | 5 |  |  | In Progress |  | Work in progress.
263 | MCL-0268 | B&R | A | A4 | North | 86&88 | Bridge | Old file / Offline | Estimate for Bridge across Budha Naala Near Shivpuri Ludhina | 25.91 | 34 |  | MC Funds / General Quota | MC | Awarded | 204.76 | 0% | 03 Dt.26-03-2025 | Y | Y | SE | No | Work Alloted |  | Y | Y | 72/LOA dt. 28-01-2025 | M/s Hitesh Aggarwal | 204.76 | 02-05-2026 | 9 Months | 27-10-2025 |  | JE Vikas Kumar | No | No | 95 |  | 252.71 | In Progress |  | Work in Progress. | WhatsApp Image 2026-08-04 at 7.02.47 PM.jpeg | 2026-08-04
264 | MCL-0269 | B&R | A | A4 | North | Gen | Bridge | Old file / Offline | Estimate for Bridge across Budha Naala Near Manna Singh Nagar Ludhina | 40.85 | 35 |  | MC Funds / General Quota | MC | Awarded | 275.94 | 0% | 04 Dt.26-03-2025 | Y | Y | SE | No | Work Alloted | 31.07.2024 | Y | Y | 73/LOA dt. 28-01-2025 | J.K. Infocon Pvt. Ltd | 275.94 | 18-02-2025 | 9 Months | 27-10-2025 | 2026-09-15 | JE Vikas Kumar | No | No | 85 |  | 214.71 | In Progress |  | Work in Progress. | WhatsApp Image 2026-08-04 at 6.51.00 PM.jpeg | 2026-08-04
265 | MCL-0270 | B&R | A | A4 | North | 89 | Building | Old file / Offline | Construction of Senior Citizen Home cum Community Center in Peeru Banda in Ward No.84. | 15.24 | 26 |  | MC Funds / General Quota | MC | Awarded | 28.39 | 17.11 | 3099 Dt.22-11-2024 | Y | Y | SE | No | Work Alloted |  | Y | Y | 40/EEA dt. 27-11-2024 | M/s Smridhi Constructions | 23.53 | 13-12-2024 | 3 Months | 2025-03-13 | 2026-09-15 | JE Vikas Kumar | No | No | 90 |  | 20.93 | In Progress |  | Work in Progress. | WhatsApp Image 2026-08-04 at 3.56.52 PM.jpeg | 2026-08-04
266 | MCL-0271 | B&R | A | A4 | North | 89 | Building | - | Construction of Senior Citizen Home cum Community Center in ward no.84. | 16.76 | 34 |  | MC Funds / General Quota | MC | Awarded | 21.92 | 14.11% | 2645 Dt.24-09-2024 | Y | Y | SE | No | Work Alloted |  | Y | Y | 168/EEA dt. 23-10-2024 | The Saharan Majra Co-op | 18.83 | 11-11-2024 | 3 Months | 22-01-2025 | 2026-09-15 | JE Vikas Kumar | No | No | 80 |  | 0 | In Progress |  | Work in Progress. |  | 2026-08-04
267 | MCL-0272 | B&R | A | A4 | North | 95 | Building | Old file/ Offline | Construction of Badminton Indoor Stadium Backside Duke factory near Jalandhar Byepass Ludhiana. | 39.63 | 60 |  | MC Funds / General Quota | MC | Awarded | 83.36 | 16.15 | 3097 Dt.22-11-2024 | Y | Y | SE | No | Work Alloted |  | Y | Y | 38/EEA dt. 27-11-2024 | M/s Apurva Inc | 69.9 | 14-12-2025 | 6 Months | 26-05-2025 | 2026-11-15 | JE Vikas Kumar | No | No | 20 |  | 0 | In Progress |  | Work in Progress. | WhatsApp Image 2026-08-04 at No.5.jpeg | 2026-08-04
268 | MCL-0273 | B&R | A | A4 | North | 87 | Bituminous/tiles | Old file/ Offline | Construction of Metailed Road to Join Missing Link of Service Lane Backside Petrol Pump in Ward No.87. | 792.68 | 18 |  | MC Funds / General Quota | MC | Awarded | 49.67 | 5 | 1741 Dt.13-10-2025 | Y | Y | SE | No | Work Alloted | 2025-07-22 | Y | Y | 01/EEA dt 25-08-2025 | M/s Soham Construction Company | 47.18 | 15-09-2025 | 3 Months | 24-11-2025 | 2026-09-15 | JE Vikas Kumar | No | No | 85 |  | 42.08 | In Progress |  | Work in Progress. | Whatsapp Image 2026- NO 23.jpeg | 2026-08-04
269 | MCL-0274 | B&R | A | A4 | North | 90 | RMC | - | Construction of Bijli Market Main Road & Streets Near Lakkar Bazar With RMC in Field Ganj Ward No.90. | 832.37 | 15.5 |  | MC Funds / General Quota | MC | Awarded | 84.09 | 41. 55% | 1747 Dt.13-10-2025 | Y | Y | SE | No | Work Alloted |  | Y | Y | 06/EEA dt 24-10-2025 | M/S Capital Construction Co. | 49.15 | 15-11-2025 | 6 Months | 23-04-2026 |  | JE Vikas Kumar | No | No | 40 |  | 27.67 | Delayed/Held Up |  | Work in Progress delayed due to internal city area. |  | 2026-08-04
270 | MCL-0275 | B&R | A | A4 | North | 90 | Road Furniture | Old file/Offline | P/F of Painting Road Marking & Cat Eyes at Various Main Roads of Ward No.90. | 609.75 | 0.5 |  | MC Funds / General Quota | MC | Awarded | 28.23 | 35.79 | 1830 Dt.13-10-2025 | Y | Y | SE | No | Work Alloted |  | Y | Y | 07/EEA dt 24-10-2025 | M/S Capital Construction Co. | 18.13 | 18-11-2025 | 3 Months | 23-01-2026 | 2026-09-15 | JE Karan Pathak | No | No | 40 |  | 9.96 | Delayed/Held Up |  | Work in Progress delayed due to bitumen Work. |  | 2026-08-04
271 | MCL-0276 | B&R | A | A4 | North | 90 | RMC | Old file/Offline | Construction of Lekhi Vehra With RMC in Ward No.90. | 215.54 | 12.4 |  | MC Funds / General Quota | MC | Awarded | 23 | 41.99 | 1744 Dt.13-10-2025 | Y | Y | SE | No | Work Alloted |  | Y | Y | 08/EEA dt 24-10-2025 | M/s Godwyn Infra | 13.34 | 19-11-2025 | 3 Months | 23-01-2026 |  | JE Vikas Kumar | No | No | 25 |  | 0 | In Progress |  | Work in Progress. |  | 2026-08-04
272 | MCL-0277 | B&R | A | A4 | North | 90 | RMC | - | Construction of Side Berms With RMC of Main Gurudwara Dukhniwaran Sahib Road Ward No.90. | 932.92 | 9.75 |  | MC Funds / General Quota | MC | Awarded | 42.76 | 41. 99% | 1746 Dt.13-10-2025 | Y | Y | SE | No | Work Alloted | 2025-07-22 | Y | Y | 09/EEA dt 24-10-2025 | M/s Godwyn Infra | 24.81 | 11-11-2025 | 3 Months | 23-01-2026 |  | JE Vikas Kumar | No | No | 50 |  | 9.91 | In Progress |  | Work in Progress.
273 | MCL-0278 | B&R | A | A4 | North | 88 | RMC | Old file/ Offline | P/L of RMC M-30 in Damage Streets of Mohalla Shivpuri in Ward No.88. | 621.95 | 20.5 |  | MC Funds / General Quota | MC | Awarded | 63.03 | 43.62 | 1832 Dt.13-10-2025 | Y | Y | SE | No | Work Alloted |  | Y | Y | 10/EEA dt 24-10-2025 | M/s Neeraj Joshi | 35.54 | 13-11-2025 | 4 Months | 23-02-2026 | 2026-09-15 | JE Vikas Kumar | No | No | 50 |  | 0 | In Progress |  | Work in Progress. | WhatsApp Image 2026-08-04 at 6.58.37 PM.jpeg | 2026-08-04
274 | MCL-0279 | B&R | A | A4 | North | 84 | RMC | - | Laying RMC M-30 in Streets of Near Guru Ravidass Mandir of Main Peeru Banda Ward No 84.(New Ward No.89) | 767.07 | 13.55 |  | MC Funds / General Quota | MC | Awarded | 47.59 | 43.62 | 1749 Dt.13-10-2025 | Y | Y | SE | No | Work Alloted | 2025-07-22 | Y | Y | 12/EEA dt 24-10- 2025 | M/s Neeraj Joshi | 26.83 | 11-12-2025 | 3 Months | 23-01-2026 | 2026-10-15 | JE Vikas Kumar | No | No | 35 |  | 8.41 | In Progress |  | Laying of Water Supply Line Work in Progress. | WhatsApp Image 2026-08-04 at 7.01.52 PM.jpeg | 2026-08-04
275 | MCL-0280 | B&R | A | A4 | North | 95 | RMC | - | P/L of RMC M-30 in Streets of New Ashok Nagar in Ward No.95 |  |  |  | MC Funds / General Quota | MC | Awarded | 99.83 | 42. 30% | 1748 Dt.13-10-2025 | Y | Y | SE | No | Work Alloted |  | Y | Y | 13/EEA dt 24-10-2025 | M/s LRY Labour Constractor | 57.6 | 13-11-2025 | 6 Months | 22-04-2026 | 2026-08-15 | JE Vikas Kumar | No | No | 90 |  | 0 | In Progress |  | Work in Progress. | WhatsApp Image 2026-08-04 at 6.56.30 PM.jpeg
276 | MCL-0281 | B&R | A | A4 | North | 94 | RMC | - | P/L of RMC M-30 in Streets of Mohalla Saroop Nagar New Janak Puri & Suiyan Wala Hospital Road in Ward No.89. (New Ward no.94) | 1396 | 17.5 |  | MC Funds / General Quota | MC | Awarded | 88.86 | 40.5 | 1745 Dt.13-10-2025 | Y | Y | SE | No | Work Alloted |  | Y | Y | 14/EEA dt 24-10-2025 | M/s LRY Labour Constractor | 52.87 | 11-11-2025 | 6 Months | 22-04-2026 | 2026-08-31 | JE Vikas Kumar | No | No | 35 |  | 0 | In Progress |  | Work in Progress. | WhatsApp Image 2026-08-04 at No14.jpeg | 2026-08-04
277 | MCL-0282 | B&R | A | A4 | North | 85 | RMC | Old file/ Offline | Laying RMC M-30 in Streets of Mohalla Gandhi Nagar & Mohalla Basant Nagar St no.6 in Ward No.85. (New Ward No.88) | 1150.91 | 12.45 |  | MC Funds / General Quota | MC | Awarded | 70.51 | 41.68 | 1742 Dt.13-10-2025 | Y | Y | SE | No | Work Alloted |  | Y | Y | 16/EEA dt 24-10-2025 | M/s Navdeep Gupta & Company | 41.12 | 13-11-2025 | 4 Months | 23-02-2026 | 2026-10-15 | JE Vikas Kumar | No | No | 25 |  | 0 | Delayed/Held Up |  | Delayed due to Water Supply Line. | WhatsApp Image 2026-08-04 at No.15.jpeg | 2026-08-04
278 | MCL-0283 | B&R | A | A4 | North | Gen | Painting | Old file/ Offline | Painting of Elevated Road Deck Slab Roof,Jagroan Bridge,Ludhiana. | 2134 | 55 |  | MC Funds / General Quota | MC | Awarded | 49.9 | -13.13 | 2751 Dt.19-02-2026 | Y | Y | SE | No | Work Alloted |  | Y | Y | 18/EEA dt 12-12-2025 | M/s K.S Constructions | 43.35 | 2026-03-25 | 3 Months | 03-11-2026 | 2026-10-15 | JE Vikas Kumar | No | No | 0 |  | 0 | Delayed/Held Up |  | Inauguration Pending. Will start after Elevated road work. | WhatsApp Image 2026-08-05 at No. deck slab.jpeg | 2026-08-04
279 | MCL-0284 | B&R | A | A4 | North | Gen | Petty Works | Old file/ Offline | Painting of Kerb Stone Elevated Road Pillars & Walls Below Elevated Road Jagroan Bridge,Ludhiana. | 2286 | 3 |  | MC Funds / General Quota | MC | Awarded | 20.33 | 15.66 | 2744 Dt.19-02-2026 | Y | Y | SE | No | Work Alloted |  | Y | Y | 19/EEA dt 12-12-2025 | M/s N.S Infra | 17.15 | 01-05-2026 | 3 Months | 03-11-2026 | 2026-09-15 | JE Vikas Kumar | No | No | 5 |  | 0 | In Progress |  | Work in Progress. | WhatsApp Image 2026-08-04 at No.15.jpeg | 2026-08-04
280 | MCL-0285 | B&R | A | A4 | North | 86 | RMC | - | Laying RMC M-30 in Streets of Farid Nagar in Ward No.86. (New Wrad No.8). | 436.95 | 20 |  | MC Funds / General Quota | MC | Awarded | 46.09 | 45.6 | 2274 DT.21-11-2025 | Y | Y | SE | No | Work Alloted | 2025-09-24 | Y | Y | 20/EEA dt 22-12-2025 | M/s Neeraj Joshi | 25.07 | 13-01-2026 | 3 Months | 21-03-2026 | 2026-09-15 | JE Vikas Kumar | No | No | 60 |  | 19.81 | In Progress |  | Work in Progress. | Farid Nagar.jpeg
281 | MCL-0286 | B&R | A | A4 | North | 87 | RMC | - | Laying RMC M-30 in Streets of Arjun Nagar & Vai Kunth Nagar in Ward No.87 | 565.54 | 19 |  | MC Funds / General Quota | MC | Awarded | 48.51 | 45.6 | 2272 Dt.21-11-2025 | Y | Y | SE | No | Work Alloted | 2025-09-24 | Y | Y | 21/EEA dt 22-12-2025 | M/s Neeraj Joshi | 26.39 | 14-01-2026 | 5 Months | 21-05-2026 | 2026-09-15 | JE Vikas Kumar | No | No | 90 |  | 26.03 | In Progress |  | Work in Progress. | WhatsApp Image 2026-08-05 at Arjun nagar.jpeg | 2026-08-04
282 | MCL-0287 | B&R | A | A4 | North | 90 | RMC | Old file/ Offline | Construction of Balance Streets of Shahpur Road With RMC in Ward No.90. | 675.6 | 16 |  | MC Funds / General Quota | MC | Awarded | 40.34 | 46.32 | 2432 DT.05-01-2026 | Y | Y | SE | No | Work Alloted |  | Y | Y | 23/EEA dt 28-01-2026 | M/s Neeraj Joshi | 21.65 | 02-10-2026 | 3 Months | 27-04-2026 |  | JE Karan Pathak | No | No | 0 |  | 0 | Delayed/Held Up |  | Inauguration Pending. |  | 2026-08-04
283 | MCL-0288 | B&R | A | A4 | North | 90 | RMC | - | Construction of Streets With RMC Backside JMD Mall in Ward No.90. | 799.3902 | 11.69 |  | MC Funds / General Quota | MC | Awarded | 47.72 | 46.32 | 2434 Dt.05-01-2026 | Y | Y | SE | No | Work Alloted |  | Y | Y | 24/EEA dt 28-01-2026 | M/s Neeraj Joshi | 25.62 | 02-11-2026 | 3 Months | 27-04-2026 | 2026-09-15 | JE Karan Pathak | No | No | 50 |  | 0 | In Progress |  | Work in Progress.
284 | MCL-0289 | B&R | A | A4 | North | 95 | RMC | Old file/ Offline | Laying RMC M-30 in Streets of New Aman Nagar & Bhagat Singh Colony in Ward No.95. | 368.9 | 20.5 |  | MC Funds / General Quota | MC | Awarded | 46.25 | 45.06 | 2281 Dt.21-11-2025 | Y | Y | SE | No | Work Alloted | 2025-09-24 | Y | Y | 26/EEA dt 28-01-2026 | M/s Navyug Company | 25.41 | 15-02-2026 | 3 Months | 27-04-2026 | 2026-09-15 | JE Vikas Kumar | No | No | 80 |  | 22.76 | In Progress |  | Work in Progress. | WhatsApp Image 2026-08-04 at No 22.jpeg | 2026-08-04
285 | MCL-0290 | B&R | A | A4 | North | 88 | Bituminous | Old file/ Offline | Recarpeting of Road Along Budha Nallah from Chand Cinema Pully to Shivpuri Pully in Ward No.85 | 1341 | 26 |  | MC Funds / General Quota | MC | Awarded | 92.16 | 5 | 2285 Dt.21-11-2025 | Y | Y | SE | No | Work Alloted |  | Y | Y | 49/EEA dt 20-02-2026 | M/s Maruti Construction Co. | 87.55 | 03-02-2026 | 6 Months | 19-08-2026 | 2026-09-15 | JE Vikas Kumar | No | No | 50 |  | 48.22 | In Progress |  | Work in Progress. | WhatsApp Image 2026-08-04 at Chand cinema pully ro shiv puri pully.jpeg | 2026-08-04
286 | MCL-0291 | B&R | A | A4 | North | 94 | RMC | - | P/L of RMC M-30 in Streets of Mahavir Homes Colony & Balance Streets of Rajauri Garden Colony in Ward No.94 (new Ward No.93) |  |  |  | MC Funds / General Quota | MC | Awarded | 96.31 | 45. 87% | 2273 Dt.21-11-2025 | Y | Y | SE | No | Work Alloted |  | Y | Y | 50/EEA dt 20-02-2026 | M/s Navyug Company | 52.13 | 03-04-2026 | 6 Months | 19-08-2026 | 2026-10-30 | JE Vikas Kumar | No | No | 0 |  | 0 | Delayed/Held Up |  | Inauguration Pending.
287 | MCL-0292 | B&R | A | A4 | North | 88 | RMC | Old file/ Offline | P/L of RMC -30 in Various Streets of Gandhi Nagar in Ward No.88. | 1309.45 | 19.3 |  | MC Funds / General Quota | MC | Awarded | 99.64 | 40.26 | 2469 Dt.05-01-2026 | Y | Y | SE | No | Work Alloted |  | Y | Y | 51/EEA dt 20-02-2026 | M/s Varinder Singh Contractor | 59.52 | 03-03-2026 | 6 Months | 19-08-2026 | 2026-10-15 | JE Vikas Kumar | No | No | 40 |  | 0 | Delayed/Held Up |  | Delayed due to Water Supply Line. | WhatsApp Image 2026-08-07 at Gandhi nagar.jpeg | 2026-08-04
288 | MCL-0293 | B&R | A | A4 | North | 88 | Retaining Wall | - | Construction of Retaining Wall along Budha Darya from Shivpuri Pully to Jain Nagar Pully (LHS) Ward No.88 (Old Ward No.85) | 116 | 12 |  | MC Funds / General Quota | MC | Awarded | 95.53 | 15.54 | 2475 Dt.05-01-2026 | Y | Y | SE | No | Work Alloted |  | Y | Y | 52/EEA dt 20-02-2026 | M/s Varinder Singh Contractor | 80.68 | 03-03-2026 | 9 Months | 19-11-2026 | 2026-08-15 | JE Vikas Kumar | No | No | 90 |  | 76.07 | In Progress |  | Work in Progress. | WhatsApp Image 2026-08-04 at 7.05.46 PM.jpeg | 2026-08-04
289 | MCL-0294 | B&R | A | A4 | North | 88 | Retaining Wall | - | Construction of Retaining Wall along Budha Darya from Jain Nagar Towards Basant Nagar in Ward No.88 | 92 | 3.9 |  | MC Funds / General Quota | MC | Awarded | 99.83 | 22. 66% | 2474 Dt.05-01-2026 | Y | Y | SE | No | Work Alloted |  | Y | Y | 53/EEA dt 20-02-2026 | M/s Apex Developers | 77.2 | 04-05-2026 | 6 Months | 19-08-2026 | 2026-09-15 | JE Vikas Kumar | No | No | 60 |  | 0 | In Progress |  | Work in Progress. | WhatsApp Image 2026-08-04 at 7.04.47 PM.jpeg | 2026-08-04
290 | MCL-0295 | B&R | A | A4 | North | 94 | RMC | Old file/ Offline | Laying RMC M-30 in Streets of Model Colony in Ward No.89.(New Ward No.94) | 748.47 | 20.5 |  | MC Funds / General Quota | MC | Awarded | 60.73 | 37.55 | 2882 Dt.21-11-2025 | Y | Y | SE | No | work Alloted | 2026-09-24 | Y | Y | 54/EEA dt 20-02-2026 | M/s K.S Constructions | 37.93 | 03-03-2026 | 4 Months | 19-06-2026 | 2026-10-15 | JE Vikas Kumar | No | No | 35 |  | 0 | In Progress |  | Work in Progress. |  | 2026-08-04
291 | MCL-0296 | B&R | A | A4 | North | 94 | RMC | Old file/Offline | P/L of RMC M-30 in Streets of Bhagwan Dass Colony in Ward No.89 (New Ward No.94) | 634.14 | 19 |  | MC Funds / General Quota | MC | Awarded | 90.35 | 37.55% | 2284 Dt.21-11-2025 | Y | Y | SE | No | work Alloted | 2025-09-24 | Y | Y | 55/EEA dt 20-02-2026 | M/s K.S Constructions | 56.42 | 03-07-2026 | 6 Months | 19-08-2026 | 2026-08-15 | JE Vikas Kumar | No | No | 40 |  | 0 | In Progress |  | Work in Progress. | WhatsApp Image 2026-08-04 at Bhagwan dass colony.jpeg | 2026-08-04
292 | MCL-0297 | B&R | A | A4 | North | 86 | RMC | Old file/Offline | Laying RMC M-30 in Various Streets of Ward No.88 (New Ward No.86) | 1018.29 | 18.75 |  | MC Funds / General Quota | MC | Awarded | 84.96 | 45.78 | 2278 Dt.21-11-2025 | Y | Y | SE | No | Work Alloted | 2025-09-24 | Y | Y | 56/EEA dt 20-02-2026 | M/s Navyug Company | 46.06 | 03-12-2026 | 6 Months | 19-08-2026 | 2026-10-15 | JE Vikas Kumar | No | No | 75 |  | 22.61 | In Progress |  | Work in Progress. | WhatsApp Image 2026-08-04 at various streets ward no 88.jpeg | 2026-08-04
293 | MCL-0298 | B&R | A | A4 | North | 1 | Bituminous | Old file/Offline | Construction of Metalled Road in adjoining streets of Nagesh Hosiery in Ward No.1. | 609.75 | 22.33 |  | MC Funds / General Quota | MC | Awarded | 70.29 | 29.05% | 2463 Dt.05-01-2026 | Y | Y | SE | No | Work Alloted | 2025-09-24 | Y | Y | 57/EEA dt 20-02-2026 | M/s Somaya Infrastructures | 49.87 | 2026-02-20 | 3 Months | 19-05-2026 |  | JE Vikas Kumar | No | No | 0 |  | 0 | Delayed/Held Up |  | Inauguration Pending. | WhatsApp Image 2026-08-05 at Nagesh Hosiery.jpeg | 2026-08-04
294 | MCL-0299 | B&R | A | A4 | North | 1 | Bituminous | Old file/ Offline | Recarpeting of Akash Nagar Main Road in Ward No.1. | 853.65 | 30 |  | MC Funds / General Quota | MC | Awarded | 58.1 | 29 | 2466 Dt.05-01-2026 | Y | Y | SE | No | Work Alloted |  | Y | Y | 58/EEA dt 20-02-2026 | M/s Somaya Infrastructures | 41.25 | 04-04-2026 | 5 Months | 19-07-2026 | 2026-09-15 | JE Vikas Kumar | No | No | 60 |  | 25.34 | Delayed/Held Up |  | Work Held up due to Sewer Line. | WhatsApp Image 2026-08-05 at Akash nagar.jpeg | 2026-08-04
295 | MCL-0300 | B&R | A | A4 | North | 89 | RMC | - | P/L of RMC M-30 in Kharbanda Chowk,Bohar Wala Gurudwara Nali Mohalla & Beli Ram Chowk Streets in Ward No.84.(New Ward No.89) |  |  |  | MC Funds / General Quota | MC | Awarded | 96.87 | 46. 99% | 2280 Dt.21-11-2025 | Y | Y | SE | No | Work Alloted |  | Y | Y | 61/EEA dt 20-02-2026 | M/s Asis Builders | 51.35 | 03-09-2026 | 6 Months | 19-08-2026 | 2026-10-15 | JE Vikas Kumar | No | No | 40 |  | 26.31 | In Progress |  | Work in Progress. | WhatsApp Image 2026-08-04 at Beli ram.jpeg | 2026-08-04
296 | MCL-0301 | B&R | A | A4 | North | Gen | Park | - | Development of Green Belt along Jalandhar Byepass upto MC Limit. | 762.19 | 14 |  | MC Funds / General Quota | MC | Awarded | 97.85 | 30 | 2827 Dt.19-02-2026 | Y | Y | SE | No | Work Alloted | 2024-11-29 | Y | Y | 64/EEA dt 25-02-2026 | M/s Rajeev Enterprises | 68.49 | 03-12-2026 | 6 Months | 24-08-2026 | 2026-09-15 | JE Vikas Kumar | No | No | 95 |  | 67.89 | In Progress |  | Work in Progress. | WhatsApp Image 2026-08-04 at Green belt along jalandhar byepass.jpeg
297 | MCL-0302 | B&R | A | A4 | North | 88 | Retaining Wall | - | Construction of Retaining Wall Along Budha Darya From Basant Nagar Towards Gandhi Nagar in Ward No.88 | 92 | 3.9 |  | MC Funds / General Quota | MC | Awarded | 99.53 | 21.13 | 2752 Dt.19-02-2026 | Y | Y | SE | No | Work Alloted |  | Y | Y | 65/EEA dt 25-02-2026 | M/s Asis Builders | 78.49 | 04-04-2026 | 6 Months | 24-08-2026 | 2026-09-15 | JE Vikas Kumar | No | No | 50 |  | 0 | In Progress |  | Work in Progress. | WhatsApp Image 2026-08-04 at Basant nagar towards gandhi nagar.jpeg | 2026-08-04
298 | MCL-0303 | B&R | A | A4 | North | 88 | Playground | Old file/ Offline | Construction of Joybox or Playground at Ward No.86 (New Ward No.88) | 38.1 | 42 |  | MC Funds / General Quota | MC | Awarded | 27.23 | 15.65 | 2829 Dt.19-02-2026 | Y | Y | SE | No | Work Alloted |  | Y | Y | 67/EEA dt 25-02-2026 | M/s Subodh Batish | 22.96 | 2025-02-25 | 3 Months | 24-05-2026 | 2026-10-15 | JE Vikas Kumar | No | No | 0 |  | 0 | Delayed/Held Up |  | Held up due to Retaining Wall Work. |  | 2026-08-04
299 | MCL-0304 | B&R | A | A4 | North | 95 | RMC | - | Construction of Streets With RMC M-30 in Area Aman Vihar Colony Ward No.95. |  |  |  | MC Funds / General Quota | MC | Awarded | 43.51 | 36 | 2739 Dt.19-02-2026 | Y | Y | SE | No | Work Alloted |  | Y | Y | 68/EEA dt 25-02-2026 | M/s Navyug Company | 27.84 | 2026-02-25 | 3 Months | 24-05-2026 | 2026-09-15 | JE Vikas Kumar | No | No | 0 |  | 0 | Delayed/Held Up |  | Inauguration Pending. | WhatsApp Image 2026-08-04 at 6.53.28 PM.jpeg
300 | MCL-0305 | B&R | A | A4 | North | 1 | Bituminous | - | Construction of Adjoining Streets of Guru Har Rai Nagar with RMC M-30 in Ward No.1 |  |  |  | MC Funds / General Quota | MC | Awarded | 65.06 | 46. 99% | 2740 Dt.19-02-2026 | Y | Y | SE | No | Work Alloted |  | Y | Y | 71/EEA dt 25-02-2026 | M/s Asis Builders | 34.48 | 03-04-2026 | 3 Months | 24-05-2026 | 2026-10-15 | JE Vikas Kumar | No | No | 25 |  | 0 | In Progress |  | Work in Progress. | WhatsApp Image 2026-08-05 at Guru Har Rai Nagar.jpeg
301 | MCL-0306 | B&R | A | A4 | North | 89 | RMC | - | P/Laying RMC M-30 in Various Streets of Naali Mohalla in Ward No.89, Ludhiana | 1490.85 | 15.25 |  | MC Funds / General Quota | MC | Awarded | 81.82 | 46.99 | 2849 Dt.19-02-2026 | Y | Y | SE | No | Work alloted | 2025-12-05 | Y | Y | 72/EEA dt 25-02-2026 | M/s Asis Builders | 43.37 | 17-03-2026 | 3 Months | 24-05-2026 |  | JE Vikas Kumar | No | No | 40 |  | 0 | In Progress |  | Work in Progress. | WhatsApp Image 2026-08-05 at Naali Mohalla.jpeg
302 | MCL-0307 | B&R | A | A4 | North | 89 | Playground | Old file/ Offline | Construction of Joybox or Playground at Ward No.89 | 38.1 | 42 |  | MC Funds / General Quota | MC | Awarded | 27.23 | 15.66 | 2828 Dt.19-02-2026 | Y | Y | SE | No | Work Alloted |  | Y | Y | 73/EEA dt 25-02-2026 | M/s Subodh Batish | 22.96 | 2026-02-25 | 3 Months | 24-05-2026 | 2026-10-15 | JE Vikas Kumar | No | No | 0 |  | 0 | Delayed/Held Up |  | Inauguration pending. |  | 2026-08-04
303 | MCL-0308 | B&R | A | A4 | North | 94 | Playground | Old file/ Offline | Construction of Joybox or Playground at Ward No.94 | 238.1 | 42 |  | MC Funds / General Quota | MC | Awarded | 27.23 | -15.65 | 2830 Dt.19-02-2026 | Y | Y | SE | No | Work Alloted |  | Y | Y | 75/EEA dt 25-02-2026 | M/s Subodh Batish | 22.96 | 2026-02-25 | 3 Months | 24-05-2026 | 2026-10-15 | JE Vikas Kumar | No | No | 0 |  | 0 | Delayed/Held Up |  | Inauguration Pending. | WhatsApp Image 2026-08-04 at Ward no 95.jpeg | 2026-08-04
304 | MCL-0309 | B&R | A | A4 | North | 86 | RMC | Old file/ Offline | P/L of RMC M-30 in Streets B/S Ram Rai School & Sarvanand Colony in Ward No.86 | 469.51 | 20.5 |  | MC Funds / General Quota | MC | Awarded | 55.34 | -44.99 | 2470 Dt.05-01-2026 | Y | Y | SE | No | Work Alloted |  | Y | Y | 77/EEA dt 25-02-2026 | M/s Navdeep Gupta & Company | 30.44 | 06-01-2026 | 6 Months | 24-08-2026 | 2026-09-15 | JE Vikas Kumar | No | No | 10 |  | 0 | Delayed/Held Up |  | Work in Progress delayed due to laying of Water Supply & Sewer Lines. | WhatsApp Image 2026-08-07 at Sarvanand colony.jpeg | 2026-08-04
305 | MCL-0310 | B&R | A | A4 | North | 90 | RMC | 382574 | Construction of Main Kesar Ganj Mandi with RMC in Ward No.90, Ludhiana | 339.32 | 41.8 |  | MC Funds / General Quota | MC | Awarded | 82.51 | 40.5 | 3515 Dt.21-04-2026 | Y | Y | SE | No | Work Allotment |  | Y | Y | 94/EEA dt.05-05-2026 | M/S LRY Labour Contrator | 49.09 | 15-05-2026 | 4 Months | 09-04-2026 |  | JE Karan Pathak | No | No | 90 |  | 0 | In Progress |  | Work in Progress. |  | 2026-08-04
306 | MCL-0311 | B&R | A | A4 | North | 87 | RMC | 380978 | P/L of RMC M-30 on streets of Vaishnu Colony in Ward No.87 | 579.26 | 19 |  | MC Funds / General Quota | MC | Awarded | 41.79 | 45.65 | 3518 Dt.21-04-2026 | Y | Y | SE | No | Work Alloted | 2025-09-24 | Y | Y | 92/EEA dt.05-05-2026 | M/S GODWYN INFRA | 22.71 | 20-05-2026 | 3 Months | 08-04-2026 | 2026-09-15 | JE Vikas Kumar | No | No | 25 |  | 0 | Delayed/Held Up |  | Work in Progress delayed due to laying of Water Supply line. | WhatsApp Image 2026-08-05 at Vasihnu colony.jpeg | 2026-08-04
307 | MCL-0312 | B&R | A | A4 | North | 90 | RMC | 382811 | P/Laying RMC in adjoining streets of Bagh Wali Gali & Streets of Kutcha no 2-3-4 in Ward No.90, Ludhiana | 740.54 | 9.4 |  | MC Funds / General Quota | MC | Awarded | 34.21 | 44.99 | 3523 Dt.21-04-2026 | Y | Y | SE | No | Work Alloted |  | Y | Y | 88/EEA dt.05-05-2026 | M/S Capital Construction Co. | 18.82 | 18-05-2026 | 3 Months | 08-04-2026 |  | JE Karan Pathak | No | No | 30 |  | 0 | In Progress |  | Work in Progress. |  | 2026-08-04
308 | MCL-0313 | B&R | A | A4 | North | 1 | RMC | 382731 | Laying RMC M-30 in streets of Gurbaksh Nagar & adjoining area in Ward No. 1 | 440.54 | 18 |  | MC Funds / General Quota | MC | Awarded | 90.99 | 45.99% | 1650 Dt.13-10-2025 | Y | Y | SE | No | Work Alloted |  | Y | Y | 90/EEA dt.05-05-2026 | M/S Capital Construction Co. | 49.14 | 24-05-2026 | 6 Months | 11-04-2026 | 2026-08-31 | JE Vikas Kumar | No | No | 60 |  | 23.26 | In Progress |  | Work in Progress. | WhatsApp Image 2026-08-05 at Gurbaksh Nagar.jpeg
309 | MCL-0314 | B&R | A | A4 | North | 1 | RMC | 376079 | P/L of RMC M-30 in different streets of Geeta Colony & adjoining area in ward no 1 | 1400.91 | 46.66 |  | MC Funds / General Quota | MC | Awarded | 98.22 | 45.65% | 159 Dt.26-03-2025 | Y | Y | SE | No | Work Alloted | 2025-09-24 | Y | Y | 87/EEA dt.05-05-2026 | M/S Capital Construction Co. | 53.38 | 20-05-2026 | 6 Months | 11-04-2026 | 2026-09-15 | JE Vikas Kumar | No | No | 50 |  | 22.65 | In Progress |  | Work in Progress. | WhatsApp Image 2026-08-05 at Geeta colony.jpeg | 2026-08-04
310 | MCL-0315 | B&R | A | A4 | North | A4 | RMC | Old file/ Offline | Upgradation of Road with RMC in Area Guru Har Rai Nagar Nagesh Hosiery Road Adjoining Jalandhar Byepass, Ludhiana | 3680 | 30 |  | SASCI | SASCI | Awarded | 620.3 | 19.19 | 3287 Dt.25-02-2026 | Y | Y | SE | No | Work Alloted |  | Y | Y | 79/EEA dt 09/03/2026 | M/s NKC Construction Pvt. Ltd. | 501.26 | 20-03-2026 | 3 Months | 06-08-2026 | 2026-10-30 | JE Vikas Kumar | No | No | 20 |  | 83.19 | Delayed/Held Up |  | Delayed due to Payment Pending. | WhatsApp Image 2026-08-06 at Nagesh Hosiery2.jpeg | 2026-08-04
311 | MCL-0316 | B&R | A | A4 | North | A4 | RMC | 388359 | Upgradation of Various Main Roads With RMC in North Constituency Zone-A,Ludhiana. | 7011 | 27 |  | MDF | MDF | Awarded | 953.59 | -9.99 | 2898 Dt.19-02-2026 | Y | Y | SE | No | Work alloted |  | Y | Y | 81/EEA dt 25-03-2026 | M/s Gaanesh Kartikey | 858.33 | 04-04-2026 | 3 Months | 24-06-2026 | 2026-10-15 | JE Vikas Kumar | No | No | 50 |  | 182.88 | In Progress |  | Work in progress | WhatsApp Image 2026-08-06 at north Constituency.jpeg | 2026-08-04
312 | MCL-0317 | B&R | A | A4 | North | A4 | Bituminous | Old file/ Offline | Upgradation of Elevated Road from Jagroan Bridge to Chand Cinema by Laying Mastic Asphalt | 2x2256 | 2x26 |  | MDF | MDF | Awarded | 593.39 | 4.24 | 2678 Dt.11-02-2026 | Y | Y | SE | No | Work alloted |  | Y | Y | 82/EEA dt 25-03-2026 | M/s Dass Builders | 568.23 | 26-03-2026 | 3 Months | 24-06-2026 | 2026-10-15 | JE Vikas Kumar | No | No | 60 |  | 119.17 | In Progress |  | Work in progress | WhatsApp Image 2026-08-05 at Jagroan bridge.jpeg | 2026-08-04
313 | MCL-0318 | B&R | A | A4 | North | A4 | RMC | Old file/ Offline | Upgradation of Roads with RMC in Area Bharti Colony, Akash Nagar adjoining Jalandhar Byepass, Ludhiana | 7555 | 18 |  | MDF | MDF | Awarded | 631.49 | 9.5 | 2677 Dt.11-02-2026 | Y | Y | SE | No | Work Alloted |  | Y | Y | 80/EEA Dt.25-03-2026 | M/s Hitesh Aggarwal Cont | 571.5 | 04-04-2026 | 3 Months | 2026-03-25 | 2026-10-15 | JE Vikas Kumar | No | No | 35 |  | 195.5 | Delayed/Held Up |  | Held up due to Laying of Sewer Line. | WhatsApp Image 2026-08-06 at Bharti colony & Akash nagar.jpeg
314 | MCL-0319 | B&R | A | A4 | North | A4 | RMC | Old file/ Offline | Upgradation of various Roads with RMC in Ward No.95, Ludhiana | 7445 | 22 |  | MDF | MDF | Awarded | 672.67 | 5.55 | 2679 Dt.11-02-2026 | Y | Y | SE | No | Work Alloted |  | Y | Y | 84/EEA Dt.25-03-2026 | M/s Ashok Kumar Sobti | 635.34 | 26-03-2026 | 3 Months | 24-06-2026 | 2026-09-15 | JE Vikas Kumar | No | No | 75 |  | 338.54 | In Progress |  | Work in progress | WhatsApp Image 2026-08-04 at 6.28.06 PM.jpeg | 2026-08-04
315 | MCL-0320 | B&R | A | A4 | North | A4 | RMC | Old file/ Offline | Upgradation of various Roads with RMC in Ward No.1, Ludhiana | 7251.82 | 24.73 |  | MDF | MDF | Awarded | 725.42 | 4 | 2899 Dt.19-02-2026 | Y | Y | SE | No | Work Alloted |  | Y | Y | 85/EEA Dt.25-03-2026 | M/s Kabir Infra | 696.4 | 26-03-2026 | 3 Months | 2026-03-25 | 2026-10-30 | JE Vikas Kumar | No | No | 70 |  | 269.52 | Delayed/Held Up |  | Delayed due to Laying of Sewer Line. | WhatsApp Image 2026-08-05 at Ward no 1.jpeg
316 | MCL-0507 | B&R | D |  | West | 53 |  |  | Providing Zebra Crossong & Road Marking work at Various Streets of Ward no. 53 |  |  |  | MC Funds / General Quota | MC Funds |  | 9.95 | 25 | 2090 13-10-2025 | [8 empty] | 83/EED 04-11-2025 | M/s Dhindsa Enterprises | 7.46 |  | 2 | [5 empty] | 10 |  |  | In Progress |  | Work in Progress
317 | MCL-0508 | B&R | D |  | West | 54 |  |  | Laying BM & OGPC in various streets of Punjab Mata Nagar |  |  |  | MC Funds / General Quota | MC Funds |  | 38.39 | 2 | 1171 15-11-2023 | [8 empty] | 123/EED 16-01-2024 | M/s VKBS Const (P) Ltd | 37.6222 |  | 3 | [5 empty] | 85 |  |  | Delayed/Held Up |  | Premix Work Completed, Only road furniture Pending
318 | MCL-0509 | B&R | D |  | West | 54 |  |  | Laying BM & OGPC in Various Streets of Karnail Singh Nagar Ph-2 |  |  |  | MC Funds / General Quota | MC Funds |  | 153.1 | 35.88 | 2332 23-08-2024 | [8 empty] | 01/EED 01-04-2025 | M/s SK Const. Co. | 98.1677 |  | 3 | [5 empty] | 95 |  |  | Delayed/Held Up |  | Premix Work Completed, Only road furniture Pending
319 | MCL-0510 | B&R | D |  | West | 54 |  |  | Providing and Laying OGPC in various streets of Punjab Mata Nagar Opposite Dhami Property Dealer |  |  |  | MC Funds / General Quota | MC Funds |  | 36.84 | 24.99 | 3496 21-04-2026 | [8 empty] | 05/EED 07-05-2026 | M/s Somaya Infrastructures | 27.6337 |  | 3 | [5 empty] | 95 |  |  | Delayed/Held Up |  | Premix Work Completed, Only road furniture Pending
320 | MCL-0511 | B&R | D |  | West | 55 |  |  | P/L BM & OGPC in J Block Sarabha Nagar |  |  |  | MC Funds / General Quota | MC Funds |  | 83.03 | 27.9 | 2999 Dt. 8-11-2024 | [8 empty] | 18/EED 09-04-2025 | M/s IHR Associates | 59.8646 |  | 3 | [5 empty] | 85 |  |  | In Progress |  | Work in Progress
321 | MCL-0512 | B&R | D |  | West | 55 |  |  | Laying SDBC on Main Road from Zone-D Office to FZR Road Ward No.55 |  |  |  | N-CAP | N-CAP |  | 73.08 | 26.09 | 1861 13-10-2025 | [8 empty] | 141/EED 25-03-2026 | Maruti Construction Co. | 54.01 |  | 5 | [5 empty] | 95 |  |  | In Progress |  | Work in progress
322 | MCL-0513 | B&R | D |  | West | 55 |  |  | Laying SDBC on Roads of BRS Nagar Block-B W.No.55 |  |  |  | MC Funds / General Quota | MC Funds |  | 77.54 | 28.65 | 1772 13-10-2025 | [8 empty] | 136/EED 25-03-2026 | M/s Somaya Infrastructure | 55.3248 |  | 5 | [5 empty] | 95 |  |  | In Progress |  | Work in progress
323 | MCL-0514 | B&R | D |  | West | 55 |  |  | Laying SDBC on Roads of BRS Nagar Block-C W.No.55 |  |  |  | MC Funds / General Quota | MC Funds |  | 90.57 | 25.2 | 1770 13-10-2025 | [8 empty] | 142/EED 25-03-2026 | Maruti Construction Co. | 67.7464 |  | 5 | [5 empty] | 90 |  |  | In Progress |  | Work in progress
324 | MCL-0515 | B&R | D |  | West | 56 |  |  | Laying OGPC in Various Streets of Gobind Nagar W. No. - 56 |  |  |  | MC Funds / General Quota | MC Funds |  | 41.21 | 7.7 | 2602 11-02-2026 | [8 empty] | 128/EED 18-03-2026 & 129/EED 18-03-2026 | Soham Construction Company & CH Builders Pvt. Ltd | 38.0368 |  | 3 | [5 empty] | 0 |  |  | Not Started |  | Not Started
325 | MCL-0516 | B&R | D |  | West | 56 |  |  | Laying OGPC in Streets of New BRS Nagar, Sham Nagar and New Sham Nagar W. No. - 56 |  |  |  | MC Funds / General Quota | MC Funds |  | 71 | 17.36 | 2597 11-02-2026 | [8 empty] | 121/EED 18-03-2026 | Ganpati Infra | 58.6744 |  | 4 | [5 empty] | 20 |  |  | In Progress |  | Work in progress
326 | MCL-0517 | B&R | D |  | West | 57 |  |  | Laying BM & OGPC in Various Streets of Sunet W.No.72 |  |  |  | MC Funds / General Quota | MC Funds |  | 66.04 | 33.63 | 2329 23-08-2024 | [8 empty] | 101/EED 12-02-2025 | SK Const. Co. | 43.8307 |  | 3 | [5 empty] | 20 |  |  | In Progress |  | Work in Progress
327 | MCL-0518 | B&R | D |  | West | 57 |  |  | Laying OGPC in Streets of Sunet Village W. No. 57 |  |  |  | MC Funds / General Quota | MC Funds |  | 47.84 | 7.7 | 2590 11-02-2026 | [8 empty] | 130/EED 18-03-2026 & 131/EED 18-03-2026 | Soham Construction Company & CH Builders Pvt. Ltd | 44.1563 |  | 3 | [5 empty] | 0 |  |  | Not Started |  | work not started
328 | MCL-0519 | B&R | D |  | West | 57 & 55 |  |  | Laying SDBC on Main Road From Durga Mata Mandir to CFC School W. No. 57 & 55 |  |  |  | MC Funds / General Quota | MC Funds |  | 25.34 | 7.7 | 2529 11-02-2026 | [8 empty] | 132/EED 18-03-2026 | Soham Construction Company | 23.3888 |  | 2 | [5 empty] | 0 |  |  | Not Started |  | work not started
329 | MCL-0520 | B&R | D |  | West | 57 |  |  | Laying OGPC in Streets of E - Block Near Lodhi Club W. No. 57 |  |  |  | MC Funds / General Quota | MC Funds |  | 55.77 | 24.54 | 2598 11-02-2026 | [8 empty] | 117/EED 18-03-2026 | Somaya Infrastructure | 42.084 |  | 3 | [5 empty] | 95 |  |  | In Progress |  | Work in Progress
330 | MCL-0521 | B&R | D |  | West | 57 |  |  | Laying OGPC in Streets of BRS Nagar I - Block Near Cremation Ground W. No. 57 |  |  |  | MC Funds / General Quota | MC Funds |  | 80.56 | 18.36 | 2600 11-02-2026 | [8 empty] | 120/EED 18-03-2026 | Ganpati Infra | 65.7692 |  | 3 | [5 empty] | 0 |  |  | Not Started |  | Work Order Issued
331 | MCL-0522 | B&R | D |  | West | 57 |  |  | Laying OGPC in Streets of BRS Nagar I - Block Near Lodhi Club W. No. 57 |  |  |  | MC Funds / General Quota | MC Funds |  | 85.26 | 15.1 | 2599 11-02-2026 | [8 empty] | 119/EED 18-03-2026 | Soham Construction Company | 72.3857 |  | 3 | [5 empty] | 0 |  |  | Not Started |  | Not started
332 | MCL-0523 | B&R | D |  | West | 57 |  |  | Laying SDBC Main Sunet Road from Orient Market to Post Office Sunet. W. No. 57 |  |  |  | MC Funds / General Quota | MC Funds |  | 48.42 | 18.08 | 3221 25-02-2026 | [8 empty] | 139/EED 25/03/2026 | Maruti Construction Co. | 39.6657 |  | 3 | [5 empty] | 10 |  |  | In Progress |  | Work in Progress
333 | MCL-0524 | B&R | D |  | West | 58 |  |  | Laying OGPC in Various Streets of Rajouri garden and Gill Avenue W.No.58 |  |  |  | MC Funds / General Quota | MC Funds |  | 86.85 | 24.55 | 2048 13-10-2025 | [8 empty] | 148/EED 25/03/2026 | M/s Somaya Infrastructure | 65.5283 |  | 5 | [5 empty] | 95 |  |  | In Progress |  | Work in Progress
334 | MCL-0525 | B&R | D |  | West | 58 |  |  | Milling Laying BM & SDBC on Main Roads of J-Block, HJ Block, Lodhi Club to Namdev Chownk and under bridge side Slipway W.No.58 |  |  |  | MC Funds / General Quota | MC Funds |  | 96.89 | 25.2 | 2049 13-10-2025 | [8 empty] | 149/EED 25/03/2026 | M/s Durga Construction Company | 72.4737 |  | 5 | [5 empty] | 95 |  |  | In Progress |  | Work in Progress
335 | MCL-0526 | B&R | D |  | West | 58 |  |  | Laying OGPC in Various Streets of Flower Dale, Good Friend Colony and Bhai Daya Singh Nagar on Barewal Main Road W.No.58 |  |  |  | MC Funds / General Quota | MC Funds |  | 45.79 | 25.2 | 2047 13-10-2025 | [8 empty] | 147/EED 25/03/2026 | M/s Durga Construction Company | 34.2509 |  | 3 | [5 empty] | 5 |  |  | In Progress |  | Work in Progress
336 | MCL-0527 | B&R | D |  | West | 58 |  |  | Laying OGPC in Streets of Malkeet Avenue on Barewal Road Ward No. 58 |  |  |  | MC Funds / General Quota | MC Funds |  | 49.87 | 12.7 | 3567 21-04-2026 | [8 empty] | 06/EED 07-05-2026 | M/s Soham Construction | 43.5365 |  | 3 | [8 empty] | Not Started |  | Work Order Issued
337 | MCL-0528 | B&R | D |  | West | 58 |  |  | Laying OGPC in Various Streets of Pink Park and Raja Garden W.No.58 |  |  |  | MC Funds / General Quota | MC Funds |  | 45.43 | 26.41 | 3568 21-04-2026 | [8 empty] | 04/EED 07-05-2026 | M/s Somaya Infrastructure | 33.4319 |  | 3 | [5 empty] | 95 |  |  | In Progress |  | Work in Progress
338 | MCL-0529 | B&R | D |  | West | 59 |  |  | Providing & laying BM & OGPC in various streets of Mahaveer Enclave Barewal |  |  |  | MC Funds / General Quota | MC Funds |  | 174.71 | 34.26 | 3162 22-11-2024 | [8 empty] | 03/EED 01-04-2025 | SK Const. Co. | 114.8544 |  | 3 | [5 empty] | 85 |  |  | In Progress |  | Work in Progress
339 | MCL-0530 | B&R | D |  | West | 59 |  |  | P/L OGPC in Various Streets of Ajit Villa South City |  |  |  | MC Funds / General Quota | MC Funds |  | 118.16 | 2.51 | 871 06-05-2025 | [8 empty] | 53/EED 16-05-2024 | M/s Apex Builder | 115.1942 |  | 4 | [5 empty] | 60 |  |  | In Progress |  | Work in Progress
340 | MCL-0531 | B&R | D |  | West | 59 |  |  | Laying OGPC in various Streets of Parkash Colony W.No.-59 |  |  |  | MC Funds / General Quota | MC Funds |  | 25.07 | 7.7 | 2592 11-02-2026 | [8 empty] | 133/EED 18-03-2026 | Soham Construction Company | 23.1396 |  | 4 | [5 empty] | 0 |  |  | Not Started |  | Not Started
341 | MCL-0532 | B&R | D |  | West | 59 |  |  | Laying SDBC on Main Road From Environmental Friendly Park to Mahaveer Enclave. W. No. 59 |  |  |  | N-CAP | N-CAP |  | 30.55 | 18.08 | 1771 13-10-2025 | [8 empty] | 138/EED 25/03/2026 | Maruti Construction Co. | 25.0266 |  | 3 | [5 empty] | 95 |  |  | In Progress |  | Work in progress
342 | MCL-0533 | B&R | D |  | West | 60 |  |  | Laying BM & OGPC in Various Streets of Gurdev Nagar Adjoining Pakhowal Road and Ferozepur Road |  |  |  | MC Funds / General Quota | MC Funds |  | 154.77 | -1.09 | 2654 Dt. 11-02-2026 | [8 empty] | 94/EED 05-12-2025 | Vansh Engineers | 153.08 |  | 4 | [5 empty] | 30 |  |  | In Progress |  | Ongoing Work
343 | MCL-0534 | B&R | D |  | West | 60 |  |  | Laying BM & OGPC in Various Streets of New Lajpat Nagar |  |  |  | MC Funds / General Quota | MC Funds |  | 66.87 | 0.24 | 3505 Dt. 21-04-2026 | [8 empty] | 07/EED 07-05-2026 | S.K Construction | 66.7 |  | 5 | [5 empty] | 0 |  |  | Not Started |  | Work Order Issued
344 | MCL-0535 | B&R | D |  | West | 65 |  |  | Laying BM & OGPC in various streets of Pavittar nagar ward no 65. |  |  |  | MC Funds / General Quota | MC Funds |  | 70.58 | 1.5 | 1215 11-08-25 | [8 empty] | 100/EED 09-02-2026 | M/s Rajeev enterprises | 69.52 |  | 3 | [5 empty] | 0 |  |  | Delayed/Held Up |  | inauguration pending
345 | MCL-0536 | B&R | D |  | West | 65 |  |  | Laying BM & OGPC in various streets of Prem Nagar,Haqiqat Nagar and New patel Nagar. |  |  |  | MC Funds / General Quota | MC Funds |  | 96.18 | 7 | 692 Dt. 09-04-2025 | [8 empty] | 152/EED 25/03/2026 | M/s Somaya Infrastructure | 89.44 |  | 3 | [5 empty] | 90 |  |  | In Progress |  | Work in Progress
346 | MCL-0537 | B&R | D |  | West | 65 |  |  | Const of metaled roads in Joshi Nagar Part-1 W.No.81 |  |  |  | MC Funds / General Quota | MC Funds |  | 95.63 | [10 empty] | 37/EED 28-04-2025 | M/s Somaya Infrastructure | 64.88 |  | 4 | [5 empty] | 90 |  |  | In Progress |  | Work in progress
347 | MCL-0538 | B&R | D |  | West | 65 |  |  | Const of metaled roads in Joshi Nagar Part-2 W.No.81 |  |  |  | MC Funds / General Quota | MC Funds |  | 99.31 | [10 empty] | 37/EED 28-04-2025 | M/s Somaya Infrastructure | 67.38 |  | 4 | [5 empty] | 90 |  |  | In Progress |  | Work in progress
348 | MCL-0539 | B&R | D |  | West | 81 |  |  | Const. of metalled roads in ranjodh park, Haibowal Nagar and New Patel Nagar |  |  |  | MC Funds / General Quota | MC Funds |  | 94.66 | [10 empty] | 146/EED 25-03-2026 | M/s Durga Construction Company | 88.03 |  | 3 | [5 empty] | 0 |  |  | Not Started
349 | MCL-0540 | B&R | D |  | West | 69 |  |  | Providing and Laying OGPC in Green Park Society adjoining Prince Hostel. Ward no. 82 |  |  |  | MC Funds / General Quota | MC Funds |  | 89.49 | 7 | 3497 Dt. 21-04-2026 | [8 empty] | 10/EED 07/05/2026 | Anil Kumar and Sons | 83.22 |  | 4 | [8 empty] | Not Started |  | Work Order Issued
350 | MCL-0541 | B&R | D |  | West | 69 |  |  | Laying BM & SDBC on Saggu Chowk to Humbran Road |  |  |  | MC Funds / General Quota | MC Funds |  | 152.59 | 21.6 | 629 Dt. 09-04-2025 | [8 empty] | 162/EED 25/03/2026 | M/s NKC Construction Pvt. Ltd | 119.63 |  | 3 | [5 empty] | 90 |  |  | Delayed/Held Up |  | Premix Work Completed, Only road furniture Pending
351 | MCL-0542 | B&R | D |  | West | 71 |  |  | Laying OGPC in streets of Officer colony and adjoining Rakh Bagh |  |  |  | MC Funds / General Quota | MC Funds |  | 113.35 | 26.5 | 3009 Dt. 08-11-2024 | [8 empty] | 43/EED 08-05-2025 | Durga Construction | 83.31 |  | 3 | [5 empty] | 20 |  |  | In Progress |  | Ongoing Work
352 | MCL-0543 | B&R | D |  | West | 71 |  |  | P/l BM and OGPC In various streets of Ghumar Mandi. |  |  |  | MC Funds / General Quota | MC Funds |  | 66.92 | 7 | 3494 Dt. 21-04-2026 | [8 empty] | 09/EED 07-05-2026 | S.K Construction Co | 62.23 |  | 3 | [8 empty] | Not Started |  | Work Order Issued
353 | MCL-0544 | B&R | D |  | West | 72 |  |  | Laying BM & OGPC in Various Streets of Friends Colony, Partap Colony and Kartar Nagar in Ward no. 72 |  |  |  | MC Funds / General Quota | MC Funds |  | 68.43 | 7 | 3491 Dt. 21-04-2026 | [8 empty] | 08/EED 07-05-2026 | Global Construction | 63.64 |  | 3 | [8 empty] | Not Started |  | Work order Issued
354 | MCL-0545 | B&R | D |  | West | 72 |  |  | Laying BM & OGPC in Various Streets of Model Gram Ward no. 72 |  |  |  | MC Funds / General Quota | MC Funds |  | 234.39 | 7 | 3492 Dt. 21-04-2026 | [8 empty] | 11/EED 07-05-2026 | Ganpati Infra | 217.98 |  | 3 | [8 empty] | Not Started |  | Work order Issued
355 | MCL-0546 | B&R | D |  | West | 53 |  |  | Repair and Renovation of park Nehru Nagar & Shastri Nagar Ward no. 53 |  |  |  | MC Funds / General Quota | MC Funds |  | 20.22 | 25.02 | 2108 13-10-2025 | [8 empty] | 86/EED 04-11-2025 | M/s Dynamic Tiles | 15.16 |  | 3 | [5 empty] | 60 |  |  | In Progress |  | Work in Progress
356 | MCL-0547 | B&R | D |  | West | 55 |  |  | Repair and Renovation of Parks (7 No.s) in Block-C BRS Nagar in Ward no 55. |  |  |  | MC Funds / General Quota | MC Funds |  | 68.48 | 22.92 | 1206 11-08-2025 | [8 empty] | 79/EED 08-10-2025 | T & G Construction Co. | 52.7844 |  | 5 | [5 empty] | 95 |  |  | In Progress |  | Work in Progress
357 | MCL-0548 | B&R | D |  | West | 55 |  |  | Repair and Renovation of Parks (5 No.s) in Block -A and Block-B BRS Nagar in Ward no 55. |  |  |  | MC Funds / General Quota | MC Funds |  | 39.9 | 21 | 1205 11-08-2025 | [8 empty] | 82/EED 04-11-2025 | GLISTEN | 31.521 |  | 5 | [5 empty] | 70 |  |  | In Progress |  | Work in Progress
358 | MCL-0549 | B&R | D |  | West | 55 |  |  | Development of Green Belt outside Canal view apartments HIG Flats W.No.75 |  |  |  | MC Funds / General Quota | MC Funds |  | 47.49 | 35.36 | 864 06-05-2025 | [8 empty] | 57/EED 16-05-2025 | T&G Const.Co | 30.6975 |  | 3 | [5 empty] | 0 |  |  | Not Started |  | Not Started
359 | MCL-0550 | B&R | D |  | West | 55 |  |  | Repair and Renovation of Various Parks in Sarabha Nagar & BRS Nagar. W. No. 55. |  |  |  | MC Funds / General Quota | MC Funds |  | 39.98 | 6.66 | 1203 11-08-2025 | [8 empty] | 143&144/EED 25-03-2026 | M/s Apex Developers & K. S. Constructions | 37.3173 |  | 3 | [5 empty] | 10 |  |  | In Progress |  | Work in progress
360 | MCL-0551 | B&R | D |  | West | 55 |  |  | Providing and Fixing of Children Playing Equipments and Garden Gyms in Various Parks W. No. 55. |  |  |  | MC Funds / General Quota | MC Funds |  | 26.93 | 34.2 | 753 09-04-2025 | [8 empty] | 137/EED 25-03-2026 | M/s Ram Parkash kakkar | 17.7199 |  | 3 | [5 empty] | 0 |  |  | Not Started |  | Not Started
361 | MCL-0552 | B&R | D |  | West | 55 |  |  | Civil work in Rose Valley on sidhwan Canal Near Jawaddi Bridge |  |  |  | MC Funds / General Quota | MC Funds |  | 27.67 | 33.99 | 1512 18-01-2024 | [8 empty] | 88/EED 29-11-2024 | The Boha Co op L&C society ltd | 18.265 |  | 3 | [5 empty] | 90 |  |  | In Progress |  | Work in Progress
362 | MCL-0553 | B&R | D |  | West | 56 |  |  | P/F Cemented Benches in Various Parks of Ward No 56. |  |  |  | MC Funds / General Quota | MC Funds |  | 2.79 | 36.13 | 1204 11-08-2025 | [8 empty] | 76/EED 08-10-2025 | Rakesh Kumar Contractor | 1.782 |  | 2 | [5 empty] | 25 |  |  | In Progress |  | Work in Progress
363 | MCL-0554 | B&R | D |  | West | 57 |  |  | Repair & Renovation of Park near railway line D Block BRS Nagar |  |  |  | MC Funds / General Quota | MC Funds |  | 18.2 | 25.52 | 2547 24-09-2024 | [8 empty] | 33/EED 24-10-2024 | The Civil Engineers & Builders Co op L&C society ltd | 13.5554 |  | 3 | [5 empty] | 50 |  |  | In Progress |  | Work in Progress
364 | MCL-0555 | B&R | D |  | West | 57 |  |  | Construction of New Park in F Block BRS Nagar Near Ravidas Shamshan Ghat Ward No 72 |  |  |  | MC Funds / General Quota | MC Funds |  | 24.32 | 24.99 | 2541 05-02-2026 | [8 empty] | 154/EED 25/03/2026 | Varinder Singh Govt. Cont. | 18.2424 |  | 4 | [5 empty] | 0 |  |  | Not Started |  | Not started
365 | MCL-0556 | B&R | D |  | West | 57 |  |  | P/F Cemented Benches in Various Parks of Ward No 57. |  |  |  | MC Funds / General Quota | MC Funds |  | 9.77 | 36.13 | 1369 11-08-2025 | [8 empty] | 74/EED 08-10-2025 | Rakesh Kumar Contractor | 6.2401 |  | 2 | [5 empty] | 30 |  |  | In Progress |  | Work in Progress
366 | MCL-0557 | B&R | D |  | West | 58 |  |  | P/F Cemented Benches in Various Parks of Ward No 58. |  |  |  | MC Funds / General Quota | MC Funds |  | 8.37 | 36.13 | 1207 11-08-2025 | [8 empty] | 77/EED 08-10-2025 | Rakesh Kumar Contractor | 5.3459 |  | 2 | [5 empty] | 25 |  |  | In Progress |  | Work in Progress
367 | MCL-0558 | B&R | D |  | West | 58 |  |  | Construction & Various Works of Sports Court in Parks of BRS J-Block, Near RUB. W. No. 58 |  |  |  | MC Funds / General Quota | MC Funds |  | 8.84 | 17.77 | 634 09-04-2025 | [8 empty] | 85/EED 04-11-2025 | Subodh Batish | 7.2691 |  | 3 | [5 empty] | 95 |  |  | In Progress |  | Work in Progress
368 | MCL-0559 | B&R | D |  | West | 58 |  |  | Repair & Renovation of Various Parks in River Dale Colony in Barewal W.No. 58 |  |  |  | MC Funds / General Quota | MC Funds |  | 9.79 | 21.88 | 638 09-04-2025 | [8 empty] | 84/EED 04-11-2025 | Subodh Batish | 7.6479 |  | 5 | [5 empty] | 25 |  |  | In Progress |  | Work in Progress
369 | MCL-0560 | B&R | D |  | West | 58 |  |  | P/F Garden Gym in Various Parks of W. No. 58 |  |  |  | MC Funds / General Quota | MC Funds |  | 9.96 | 21.99 | 642 09-04-2025 | [8 empty] | 145/EED 25/03/2026 | M/s Khalsa Export Private Limited | 7.7698 |  | 2 | [5 empty] | 0 |  |  | Not Started |  | Not Started
370 | MCL-0561 | B&R | D |  | West | 58 |  |  | Repair & Renovation of Various Parks in J Block 64 Yards W.No.58 |  |  |  | MC Funds / General Quota | MC Funds |  | 46.7 | 32.26 | 2051 13-10-2025 | [8 empty] | 150/EED 25/03/2026 | M/s Varinder Singh Govt. Contractor | 31.6346 |  | 5 | [5 empty] | 25 |  |  | In Progress |  | Work in Progress
371 | MCL-0562 | B&R | D |  | West | 59 |  |  | Const. of Canopies, Gym Garden, Swings in various parks W.No.74 |  |  |  | MC Funds / General Quota | MC Funds |  | 48.93 | 31.99 | 2439 23-08-2024 | [8 empty] | 32/EED 24-10-2024 | The Akal Co op L&C Society Ltd | 33.2773 |  | 3 | [5 empty] | 60 |  |  | Delayed/Held Up |  | Work in Progress, 859 Dt. 6-5-25 PENDING
372 | MCL-0563 | B&R | D |  | West | 59 |  |  | Repair and Renvoation of various parks of sunil park, Flower Date Park, Citizen Enclave. Professor colony in Ward no 74. |  |  |  | MC Funds / General Quota | MC Funds |  | 35.07 | 25.71 | 2657 24-09-2024 | [8 empty] | 49/EED 29-10-2024 | M/s The Saharan Majra Co-op LC Society Ltd | 26.0535 |  | 5 | [5 empty] | 90 |  |  | In Progress |  | Work in Progress
373 | MCL-0564 | B&R | D |  | West | 59 |  |  | Repair & Renovation of Eco Friendly Park in Barewal Awana W. No. 59 |  |  |  | MC Funds / General Quota | MC Funds |  | 6.19 | 17.66 | 2601 11-02-2026 | [8 empty] | 122/EED 18-03-2026 | Varinder Singh Govt. Contractor | 5.0968 |  | 3 | [5 empty] | 0 |  |  | Not Started |  | Not Started
374 | MCL-0565 | B&R | D |  | West | 59 |  |  | Repair & Renovation of Various Parks in Parkash Colony & Madhuvan Enclave on Barewal Road W. No. 59 |  |  |  | MC Funds / General Quota | MC Funds |  | 11.28 | 30.1 | 1381 11-08-2025 | [8 empty] | 151/EED 25/03/2026 | M/s Dynamic tiles | 7.8847 |  | 2 | [5 empty] | 10 |  |  | In Progress |  | Work in progress
375 | MCL-0566 | B&R | D |  | West | 60 |  |  | Repari and Renovation of different parks of new Lajpat Nagar in Ward no 67 (2 nos. parks) |  |  |  | MC Funds / General Quota | MC Funds |  | 35.92 | 23.19 | 1169 15-11-2023 | [8 empty] | 113/EED 21-12-2023 | M/s The Civil Engineer & Builders Co-op L/C Society Ltd | 27.59 |  | 3 | [5 empty] | 80 |  |  | In Progress |  | Ongoing Work
376 | MCL-0567 | B&R | D |  | West | 60 |  |  | Repair & Renovation of parks (4 nos.) in Gurdev nagar (4 nos. parks) |  |  |  | MC Funds / General Quota | MC Funds |  | 49.28 | 37.5 | 3004 Dt. 08-11-2024 | [8 empty] | 34/EED 25-4-2025 | Ram Parkash Kakar | 30.8 |  | 3 | [5 empty] | 95 |  |  | In Progress | Sprinkler needs to be fixed in Kartar Park, New Lajpat Nagar, Gurdev Nagar | Ongoing Work
377 | MCL-0568 | B&R | D |  | West | 60 |  |  | Repair and Renovation of Park in Ghumar Mandi (1 No. park) |  |  |  | MC Funds / General Quota | MC Funds |  | 21.76 | 32 | 618 Dt. 09-04-2025 | [8 empty] | 47/EED 28-10-2024 | Dynamic Tiles | 14.79 |  | 2 | [5 empty] | 20 |  |  | In Progress |  | Ongoing Work
378 | MCL-0569 | B&R | D |  | West | 60 |  |  | Reapir and renovation of Murgi Farm Park and other parks of Gurdev Nagar w-60 |  |  |  | MC Funds / General Quota | MC Funds |  | 36.94 | -33.6 | 1860 Dt.13-10-2025 | [8 empty] | 125/EED 18-03-2026 | Ram Parkash Kakkar | 24.52 |  | 3 | [5 empty] | 20 |  |  | In Progress |  | Work in progress
379 | MCL-0570 | B&R | D |  | West | 61 |  |  | Repair and Renovation of various Parks in Ward no 61. (3 Nos. parks) |  |  |  | MC Funds / General Quota | MC Funds |  | 48.87 | 33.5 | 616 Dt. 09-04-2025 | [8 empty] | 63/EED 19-05-2025 | Dynamic Tiles | 32.49 |  | 3 | [5 empty] | 50 |  |  | In Progress |  | work in progress
380 | MCL-0571 | B&R | D |  | West | 62 |  |  | Construction of 2 new parks & Repair of other Parks in Ward No 78 |  |  |  | MC Funds / General Quota | MC Funds |  | 48.19 | 41.01 | 1662 Dt. 14-02-2024 | [8 empty] | 46/EED 15-05-2025 | M/s Dynamic tiles | 64.88 |  | 3 | [5 empty] | 60 |  |  | In Progress |  | Work in progress
381 | MCL-0572 | B&R | D |  | West | 63 |  |  | Repair and Renovation of various parks in ward no 63. |  |  |  | MC Funds / General Quota | MC Funds |  | 85.5 | 32.5 | 685 Dt. 09-04-2025 | [8 empty] | 105/EED 16-02-2026 | M/s Dynamic tiles | 57.71 |  | 3 | [5 empty] | 45 |  |  | In Progress |  | Work in progress
382 | MCL-0573 | B&R | D |  | West | 64 |  |  | Repair and renovation of corporation colony parks (2 nos.) in ward no. 78 |  |  |  | Other / Unspecified |  |  | 57.55 | 32.59 | 323 dt 26.03.25 | [8 empty] | 36/EED 28-04-2025 | M/S JP Builders | 38.79 |  | 3 | [5 empty] | 95 |  |  | In Progress |  | Work in progress
383 | MCL-0574 | B&R | D |  | West | 65 |  |  | Repair and Renovation of various parks in ward no 65. |  |  |  | MC Funds / General Quota | MC Funds |  | 83.28 | 35.88 | 1202 Dt. 11-08-2025 | [8 empty] | 153/EED 25/03/2026 | M/s Naresh kumar contractor | 53.4 |  | 3 | [5 empty] | 25 |  |  | In Progress |  | Work in progress
384 | MCL-0575 | B&R | D |  | West | 69 |  |  | Repair & renovation of various parks adjoining Cementry road W-82 (3 Nos. parks) |  |  |  | MC Funds / General Quota | MC Funds |  | 28.05 | 23.46 | 3010 Dt. 08-11-2024 | [8 empty] | 17/EED 09.04.2025 | M/s Smridhi Constructions | 21.46 |  | 3 | [5 empty] | 90 |  |  | In Progress |  | Ongoing Work
385 | MCL-0576 | B&R | D |  | West | 71 |  |  | Repair and renovation of Rajaram park in Mall Enclave. (1 No. park) |  |  |  | MC Funds / General Quota | MC Funds |  | 22.82 | 24.99 | 2671 Dt. 24-09-2024 | [8 empty] | 41/EED 28-10-2024 | The Sunet Co op L&C society ltd | 17.11 |  | 3 | [5 empty] | 95 |  |  | In Progress |  | Ongoing Work
386 | MCL-0577 | B&R | D |  | West | 71 |  |  | P/L Perforated interlocking tiles on side berms of various streets in Mall Enclave |  |  |  | MC Funds / General Quota | MC Funds |  | 32.81 | 41 | 652 Dt. 09-04-2025 | [8 empty] | 61/EED 19-05-2025 | Dynamic Tiles | 19.35 |  | 3 | [5 empty] | 60 |  |  | In Progress |  | Ongoing Work
387 | MCL-0578 | B&R | D |  | West | 72 |  |  | Repair & Renovation of Park in Kochar Market and Jawahar Camp (2 Nos. parks) |  |  |  | MC Funds / General Quota | MC Funds |  | 49.76 | 24.99 | 2672 Dt. 24-09-2024 | [8 empty] | 45/EED 28-10-2024 | The Sunet Co op L&C society ltd | 37.32 |  | 3 | [5 empty] | 95 |  |  | In Progress |  | Work in progress
388 | MCL-0579 | B&R | D |  | West | 72 |  |  | Repair and Renovation of park near potohari Gurudwara and Batra Park. (2 Nos. parks) |  |  |  | MC Funds / General Quota | MC Funds |  | 40.33 | 24.99 | 2670 24-09-2024 | [8 empty] | 51/EED 06-11-2024 | M/s The Sunet L/C Society Ltd | 30.25 |  | 3 | [5 empty] | 95 |  |  | In Progress |  | Work in progress
389 | MCL-0580 | B&R | D |  | West | 72 |  |  | Repair and renovation of parks (6 Nos.) In Model Gram Partap Colony & Friends Colony in Ward no. 72 (6 Nos. parks) |  |  |  | MC Funds / General Quota | MC Funds |  | 47.41 | 33 | Dt. 09-04-2025 | [8 empty] | 59/EED 19-05-2025 | Dynamic Tiles | 31.76 |  | 3 | [5 empty] | 30 |  |  | In Progress |  | Work in progress
390 | MCL-0581 | B&R | D |  | West | 72 |  |  | Construction of an entrance gate in jawahar nagar camp |  |  |  | MC Funds / General Quota | MC Funds |  | 18.37 | 5.2 | 2672 Dt. 11-02-2026 | [8 empty] | 106/EED 03-03-2026 | Asis Builders | 17.41 |  | 3 | [5 empty] | 30 |  |  | In Progress |  | Work in progress
391 | MCL-0582 | B&R | D |  | West | 73 |  |  | Repair and Renovation of Various Parks in Ward No 65 (3 Nos. parks) |  |  |  | MC Funds / General Quota | MC Funds |  | 48.97 | 35.88 | 321 26-03-2025 | [8 empty] | 13/EED 09-04-2024 | M/s Naresh Kumar Contarctor | 31.39 |  | 3 | [5 empty] | 30 | 0 |  | In Progress | Pavement done (concrete), canopies, benches done in 1 park. Gym area, jhule pending. | Ongoing Work
392 | MCL-0583 | B&R | D |  | West | 53 |  |  | Providing and Laying of 60mm thick interlocking tiles on side berms of Model Town Extension (Ishmeet Singh road) |  |  |  | MC Funds / General Quota | MC Funds |  | 43.03 | 35.66 | 2660 24-09-2024 | [8 empty] | 55/EED 06-11-2024 | M/s The Boha Co-op | 27.68 |  | 5 | [5 empty] | 75 |  |  | In Progress |  | Work in Progress
393 | MCL-0584 | B&R | D |  | West | 54 |  |  | P/L interlocking tiles on side berms of road in New Punjab Mata Nagar W.No.70 |  |  |  | MC Funds / General Quota | MC Funds |  | 56.96 | 41.01 | 2331 23-08-2024 | [8 empty] | 27/EED 11-04-2025 | M/s Dynamic Tiles | 33.6007 |  | 5 | [5 empty] | 5 |  |  | Delayed/Held Up |  | Work Held up due to NGT Guidelines
394 | MCL-0585 | B&R | D |  | West | 54 |  |  | P/Laying interlocking tiles on side berms of roads in Karnail Singh Nagar Ph-II |  |  |  | MC Funds / General Quota | MC Funds |  | 95.93 | 32.25 | 1288 20-11-2023 | [8 empty] | 118/EED 05-01-2024 | M/s J.P Builders | 64.9926 |  | 5 | [5 empty] | 30 |  |  | Delayed/Held Up |  | Work Held up due to NGT Guidelines, Moreover Case Sent to F&CC for Change of Site - PENDING 858 Dt. 6-5-25
395 | MCL-0586 | B&R | D |  | West | 56 |  |  | P/Laying Inter-locking tiles on side berms of roads in Vikas Nagar & Gobind Nagar Ward No 71 |  |  |  | MC Funds / General Quota | MC Funds |  | 223.68 | 13.85 | 6869 07-09-2022 | [8 empty] | 10/EED 26-12-2022 | M/s Aglow Builders | 192.7003 |  | 5 | [5 empty] | 95 |  |  | In Progress |  | Work in Progress, Revised vide F&CC Res. no. 880 dt. 06.05.2025
396 | MCL-0587 | B&R | D |  | West | 56 |  |  | P/L 80mm Thick Interlocking Tiles in Victoria Colony on 200' Road W. No. 56 |  |  |  | MC Funds / General Quota | MC Funds |  | 52.38 | 30.44 | 2850 19-02-2026 | [8 empty] | 134/EED 18-03-2026 | T&G Construction | 36.4355 |  | 4 | [5 empty] | 70 |  |  | In Progress |  | Work in progress
397 | MCL-0588 | B&R | D |  | West | 57 |  |  | P & Laying Interlocking Tiles on side Berms In D Block BRS Nagar Ward No 72 |  |  |  | MC Funds / General Quota | MC Funds |  | 98.63 | 42.88 | 1660 14-02-2024 | [8 empty] | 25/EED 11-04-2025 | Varinder Singh Govt. Cont. | 56.3375 |  | 4 | [5 empty] | 80 |  |  | In Progress |  | Work in Progress
398 | MCL-0589 | B&R | D |  | West | 57 |  |  | P/L 80mm thick interlocking tiles in village Sunet |  |  |  | MC Funds / General Quota | MC Funds |  | 17.33 | 40.88 | 419 26-03-2025 | [8 empty] | 11/EED 09-04-2025 | Varinder Singh Govt. Cont. | 10.2455 |  | 4 | [5 empty] | 70 |  |  | In Progress |  | Work in Progress
399 | MCL-0590 | B&R | D |  | West | 57 |  |  | P & Laying Interlocking Tiles on side Berms In L Block BRS Nagar Ward No 72 |  |  |  | MC Funds / General Quota | MC Funds |  | 62.66 | 42.88 | 1624 14-02-2024 | [8 empty] | 24/EED 11-04-2025 | Varinder Singh Govt. Cont. | 35.7914 |  | 3 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Work Held up due to Upgradation of Sewer Line
400 | MCL-0591 | B&R | D |  | West | 57 |  |  | P/L 80mm Thick Interlocking Tiles in Various Streets of Sunet. W. No. 57 |  |  |  | MC Funds / General Quota | MC Funds |  | 35.18 | 39.13 | 1202 11-08-2025 | [8 empty] | 75/EED 08-10-2025 | Rakesh Kumar Contractor | 21.4141 |  | 5 | [5 empty] | 0 |  |  | Delayed/Held Up |  | Work Held up due to Upgradation of Sewer Line
401 | MCL-0592 | B&R | D |  | West | 57 |  |  | P/L 60mm thick relaying tiles in streets of village Sunet near Shitla Mata Mandir W.No. 57 |  |  |  | MC Funds / General Quota | MC Funds |  | 23.06 | 42.66 | 2587 11-02-2026 | [8 empty] | 135/EED 18-03-2026 | Navdeep Gupta and Company | 13.2226 |  | 3 | [5 empty] | 0 |  |  | Not Started |  | work not started
402 | MCL-0593 | B&R | D |  | West | 58 |  |  | P/L 60mm Thick Perforated Interlocking Tiles on Side Berms of Barewal Sua Road W. No. 58 |  |  |  | MC Funds / General Quota | MC Funds |  | 62.29 | 33.99 | 1200 11-08-2025 | [8 empty] | 78/EED 08-10-2025 | Dynamic Tiles | 41.1176 |  | 5 | [5 empty] | 5 |  |  | In Progress |  | Work in Progress
403 | MCL-0594 | B&R | D |  | West | 58 |  |  | P/L 60mm Thick Perforated Interlocking Tiles on Side Berms of Magnet Resort Road W. No. 58 |  |  |  | MC Funds / General Quota | MC Funds |  | 82.56 | 36.96 | 1773 13-10-2025 | [8 empty] | 93/EED 02-12-2025 | R. K. Construction Co. | 52.0458 |  | 5 | [5 empty] | 5 |  |  | In Progress |  | Work in Progress
404 | MCL-0595 | B&R | D |  | West | 59 |  |  | Providing and Laying interlocking tiles on side berms of road in Mahaveer nagar Ward no 74. |  |  |  | MC Funds / General Quota | MC Funds |  | 65.29 | 37.99 | 860 06-05-2025 | [8 empty] | 48/EED 29-10-2024 | M/s Apex Developers | 40.4863 |  | 3 | [5 empty] | 80 |  |  | In Progress |  | Work in Progress & Case Approved by F&CC Res. no.860 Dt. 6-5-25 for Change of Site for Motar Wali Gali
405 | MCL-0596 | B&R | D |  | West | 61 |  |  | Prov. and laying perforated interlocking tiles in various streets of w. no. 76 |  |  |  | MC Funds / General Quota | MC Funds |  | 69.54 | 32 | 3006 Dt. 08-11-2024 | [8 empty] | 42//EED 08-05-2025 | Glisten | 47.22 |  | 3 | [5 empty] | 30 |  |  | In Progress |  | work in progress
406 | MCL-0597 | B&R | D |  | West | 63 |  |  | Prov. and fixing of 60mm thick interlocking tiles on side berms of different area Kitchlu Nagar Block E, F and G W. No. 77 |  |  |  | MC Funds / General Quota | MC Funds |  | 80.08 | 37 | 2386 Dt. 23-08-2024 | [8 empty] | 35/EED 28-04-2025 | M/s Dynamic tiles | 50.45 |  | 4 | [5 empty] | 40 |  |  | In Progress |  | Work in progress
407 | MCL-0598 | B&R | D |  | West | 65 |  |  | P/F of 60mm Interlocking Tiles in various streets of Prem Nagar ward no 65. |  |  |  | MC Funds / General Quota | MC Funds |  | 66.54 | 36.99 | 1216 Dt. 11-08-2025 | [8 empty] | 99/EED 09-02-2026 | M/s Apex developers | 41.93 |  | 3 | [5 empty] | 0 |  |  | Not Started |  | Work in Progress
408 | MCL-0599 | B&R | D |  | West | 71 |  |  | P/L Perforated interlocking tiles on side berms of Collage Road and Hira Singh Road |  |  |  | MC Funds / General Quota | MC Funds |  | 49.62 | 35 | 651 Dt. 09-04-2025 | [8 empty] | 62/EED 19-05-2025 | Dynamic Tiles | 32.25 |  | 3 | [5 empty] | 90 |  |  | In Progress |  | Ongoing Work
409 | MCL-0600 | B&R | D |  | West | 71 |  |  | P/L Perforated interlocking tiles on side berms of various streets in Mall Enclave |  |  |  | MC Funds / General Quota | MC Funds |  | 32.81 | 41 | 652 Dt. 09-04-2025 | [8 empty] | 61/EED 19-05-2025 | Dynamic Tiles | 19.35 |  | 3 | [5 empty] | 60 |  |  | In Progress |  | Ongoing Work
410 | MCL-0601 | B&R | D |  | West | 57 |  |  | P/L RMC (M-30) in Various Streets of Sunet. W. No. 57 |  |  |  | MC Funds / General Quota | MC Funds |  | 49.89 | 42.66 | 2591 11-02-2026 | [8 empty] | 118/EED 18-03-2026 | M/s Navdeep gupta & company | 28.6069 |  | 3 | [5 empty] | 60 |  |  | In Progress |  | Work in Progress
411 | MCL-0602 | B&R | D |  | West | 62 |  |  | P/Laying of RMC M-30 in streets of Mandeep Nagar ward no 62 |  |  |  | MC Funds / General Quota | MC Funds |  | 99.3 | 41.68 | 840 06.05.2025 | [8 empty] | 98/EED 05.02.2026 | M/s Navdeep gupta & company | 57.91 |  | 4 | [5 empty] | 80 |  |  | In Progress |  | Work in progress
412 | MCL-0603 | B&R | D |  | West | 62 |  |  | P/L of RMC M-30 in balance streets of Punj Peer road ward no 62 |  |  |  | MC Funds / General Quota | MC Funds |  | 30.31 | 41.82 | 839 06.05.2025 | [8 empty] | 97/EED 05.02.2026 | M/s Navdeep gupta & company | 17.63 |  | 3 | [5 empty] | 5 |  |  | In Progress |  | Work in progress
413 | MCL-0604 | B&R | D |  | West | 63 |  |  | P/L of RMC M-30 in Haqiqat nagar ward no 63. |  |  |  | MC Funds / General Quota | MC Funds |  | 33.67 | 34.51 | 690 Dt. 09-04-2025 | [8 empty] | 58/EED 19-05-2025 | M/s K.S Constructions | 22.05 |  | 3 | [5 empty] | 80 |  |  | In Progress |  | Work in progress
414 | MCL-0605 | B&R | D |  | West | 55 |  |  | Repair and renovation of various parks and sprinkler system in parks w. no. 55 |  |  |  | Rangla Punjab | Rangla Punjab |  | 20 | 7.77 | In Anticipation | [8 empty] | 28/EED 13-05-2026 | M/s Subodh Batish | 18.45 |  | 3 | [5 empty] | 10 |  |  | In Progress |  | Work Order Issued
415 | MCL-0606 | B&R | D |  | West | 59 |  |  | Repair and renovation by laying 60mm Thick Interlocking Tiles in streets of sanjha sahib gurudwara to village barewal T point of W. no. 59 |  |  |  | Rangla Punjab | Rangla Punjab |  | 10 | 12.12 | In Anticipation | [8 empty] | 29/EED 13-05-2026 | M/s Kohinoor Builders | 8.79 |  | 1 | [5 empty] | 50 |  |  | In Progress |  | Work in Progress
416 | MCL-0607 | B&R | D |  | West | 60 |  |  | Construction of Public Library in Gurdev Nagar in W. no. 60 |  |  |  | Rangla Punjab | Rangla Punjab |  | 12 | -2.05 | In Anticipation | [8 empty] | 27/EED 13-05-2025 | M/s Kohinoor Builders | 11.75 |  | 2 | [8 empty] | Not Started | Site not clear, Councillor ro provide clear land. SE/Xen to follow up and finalise. Proposed to be made in ward. | Work Order Issued
417 | MCL-0608 | B&R | D |  | West | 60 |  |  | Construction of Cricket Play ground Gurdev Nagar in W. no. 60 |  |  |  | Rangla Punjab | Rangla Punjab |  | 5 | -3.99 | In Anticipation | [8 empty] | 24/EED 13-05-2025 | MAA Chintpurani Construction | 4.8 |  | 2 | [8 empty] | Not Started | Land Issue, Councillor to provide land by 10/07/26 | Work Order Issued
418 | MCL-0609 | B&R | D |  | West | 63 |  |  | Construction of Joybox or Playground at Green Belt opp. Polytechnic College ward no 63. |  |  |  | Rangla Punjab | Rangla Punjab Scheme |  | 27.23 | 16.89 | In Anticipation | [8 empty] | 26/EED 13-05-2026 | M/s Teg Builders | 22.63 |  | 3 | [5 empty] | 5 |  |  | In Progress |  | Work in progress
419 | MCL-0610 | B&R | D |  | West | 72 |  |  | Construction of additional rooms at Ayurvedic Dispensary jawahar nagar camp near bus stand in W. no. 72 |  |  |  | Rangla Punjab | Rangla Punjab-1 |  | 15 | 8.77 | In Anticipation | [8 empty] | 25/EED 13-05-2026 | M/s Smridhi Construction | 13.68 |  | 2 | [5 empty] | 10 |  |  | In Progress |  | Work in progress
420 | MCL-0611 | B&R | D |  | West | New Ward No |  |  | Name of Work |  |  |  | Viveki Funds | Head |  | Est. Amount (In Lacs) | OAS (%) | TAC/F&CC resolution no. | [8 empty] | Work Order No. & Date | Name of Agency | Tender Amount (In Lacs) |  | Time Limit (in Months) | [8 empty] | Not Started |  | Remarks/Status
421 | MCL-0612 | B&R | D |  | West | 54 |  |  | Repair & Renovation of Jawaddi Dharmshalla |  |  |  | Viveki Funds | Viveki Funds |  | 16.66 | 20.1 | 2548 24-09-2024 | [8 empty] | 22/EED 11-04-2025 | M/s Smridhi Const. | 13.3113 |  | 6 | [5 empty] | 90 |  |  | In Progress |  | Work in Progress
422 | MCL-0613 | B&R | D |  | West | 57 |  |  | Repair & Renovation of Ravidass Dharmshalla Village Sunet |  |  |  | Viveki Funds | Viveki Funds |  | 16.67 | 20.1 | 2548 24-09-2024 | [8 empty] | 20/EED 11-04-2025 | M/s Smridhi Const. | 13.3193 |  | 2 | [5 empty] | 90 |  |  | In Progress |  | Work in Progress
423 | MCL-0614 | B&R | D |  | West | 57 |  |  | Repair & Renovation of Dharmshalla Near Masjid |  |  |  | Viveki Funds | Viveki Funds |  | 16.67 | 18.78 | 274 26-03-2025 | [8 empty] | 21/EED 11-04-2025 | M/s Smridhi Const. | 13.5394 |  | 2 | [5 empty] | 60 |  |  | In Progress |  | Work in Progress
424 | MCL-0615 | B&R | D |  | West | 55 |  |  | Laying SDBC on Main Road from Zone-D Office to FZR Road Ward No.55 |  |  |  | N-CAP | N-CAP |  | 73.08 | 26.09 | 1861 13-10-2025 | [8 empty] | 141/EED 25-03-2026 | Maruti Construction Co. | 54.01 |  | 5 | [5 empty] | 95 |  |  | In Progress |  | Work in progress
425 | MCL-0616 | B&R | D |  | West | 59 |  |  | Laying SDBC on Main Road From Environmental Friendly Park to Mahaveer Enclave. W. No. 59 |  |  |  | N-CAP | N-CAP |  | 30.55 | 18.08 | 1771 13-10-2025 | [8 empty] | 138/EED 25/03/2026 | Maruti Construction Co. | 25.0266 |  | 3 | [5 empty] | 95 |  |  | In Progress |  | Work in progress
426 | MCL-0617 | B&R | D | D2 | West | 53 |  |  | Construction Old Rooms In Guru Teg Bahadur Hospital,Shastri Nagar,Model Town,Ludhiana |  |  |  | MPLAD Funds | MPLAD Funds |  | 10 | 4.44 | [9 empty] | 15/EED 07/05/2026 | M/s Kohinoor Builders | 9.56 | [10 empty] | Not Started |  | Work Order Issue
427 | MCL-0618 | B&R | D | D3 | West | 55 |  |  | Installation of Swings & Development of Parks in GEE Green Welfare Society Park, 97-G BRS Nagar W. No. 55 |  |  |  | MPLAD Funds | MPLAD Funds |  | 5 | 5.12 | [9 empty] | 107/EED 05/03/2026 | M/s Kohinoor Builders | 4.744 | [7 empty] | 15 |  |  | In Progress |  | Work Order Issue
428 | MCL-0619 | B&R | D | D3 | West | 55 |  |  | Construction of Canopy and Benches in Flowerdale Park, B-Block BRS Nagar W. No. 55 |  |  |  | MPLAD Funds | MPLAD Funds |  | 5 | 1.13 | [9 empty] | 108/EED 05/03/2026 | M/s Varinder Singh Govt. Contractor | 4.9435 | [7 empty] | 70 |  |  | In Progress |  | Work Order Issue
429 | MCL-0620 | B&R | D | D3 | West | 55 |  |  | Development of Public Parks with Swings, Foothpath, Benches & Grills W. No. 55 (E, F, H, I, J Blocks of Sarabha Nagar and C Block of BRS Nagar) |  |  |  | MPLAD Funds | MPLAD Funds |  | 10 | 11 | [9 empty] | 109/EED 05/03/2026 | M/s Ram Parkash kakkar | 8.9 | [10 empty] | Not Started |  | Work Order Issue
430 | MCL-0621 | B&R | D | D3 | West | 55 |  |  | Development of Public Parks with Installation of Swings & Benches etc. in Park No. 245 BRS Nagar W. No. 55 |  |  |  | MPLAD Funds | MPLAD Funds |  | 3 | 4.55 | [9 empty] | 110/EED 05/03/2026 | M/s Kohinoor Builders | 2.8635 | [7 empty] | 100 |  |  | Completed |  | Work Order Issue
431 | MCL-0622 | B&R | D | D3 | West | 56 |  |  | Development of Public Parks with Installation of Steel Benches & Swings W. No. 56 (Vikas & SBS Nagar, G & D Block SBS Nagar, Housefed Flats) |  |  |  | MPLAD Funds | MPLAD Funds |  | 10 | 11 | [9 empty] | 111/EED 05/03/2026 | M/s Ram Parkash kakkar | 8.9 | [7 empty] | 60 |  |  | In Progress |  | Work Order Issue
432 | MCL-0623 | B&R | D | D3 | West | 56 |  |  | Installation of Swings and Steel (Cast Iron) Benches in F-Block SBS Nagar W. No. 56 |  |  |  | MPLAD Funds | MPLAD Funds |  | 3 | 15.99 | [9 empty] | 112/EED 05/03/2026 | M/s Maa Chintpurni Construction | 2.5203 | [7 empty] | 30 |  |  | In Progress |  | Work Order Issue
433 | MCL-0624 | B&R | D | D3 | West | 58 |  |  | Development of Public Parks with Installation of Swings W. No. 58 (A to D Blocks of Rajguru Nagar and J Block of BRS Nagar, Housing Board, B Block Aggar Nagar) |  |  |  | MPLAD Funds | MPLAD Funds |  | 10 | 11 | [9 empty] | 113/EED 05/03/2026 | M/s Ram Parkash kakkar | 8.9 | [7 empty] | 10 |  |  | In Progress |  | Work Order Issue
434 | MCL-0625 | B&R | D | D3 | West | 58 |  |  | Development of Public Parks with Swings, Foothpath, Canopy, Benches, Boundary Wall W. No. 58 (J Block Park Opp. Lodhi Club) |  |  |  | MPLAD Funds | MPLAD Funds |  | 10 | 7.12 | [9 empty] | 114/EED 05/03/2026 | M/s Kohinoor Builders | 9.288 | [7 empty] | 30 |  |  | In Progress |  | Work Order Issue
435 | MCL-0626 | B&R | D | D3 | West | 58 |  |  | Installation of Cement Benches and Construction of Shed (10' x 8') in Public Places, Gate No. 1 Verka Plant W. No. 58 |  |  |  | MPLAD Funds | MPLAD Funds |  | 1 | 6.66 | [9 empty] | 14/EED 07/05/2026 | M/s Kohinoor Builders | 0.93 | [10 empty] | Not Started |  | Work Order Issue
436 | MCL-0627 | B&R | D | D3 | West | 58 |  |  | Installation of Swings & Benches in B-Block Aggar Nagar W. No. 58 |  |  |  | MPLAD Funds | MPLAD Funds |  | 1.5 | 3.1 | [9 empty] | 115/EED 05/03/2026 | M/s Kohinoor Builders | 1.4535 | [7 empty] | 100 |  |  | Completed |  | Work Order Issue
437 | MCL-0628 | B&R | D | D3 | West | 58 |  |  | Construction of Badminton Court in B-Block Aggar Nagar, 524 - B W. No. 58 |  |  |  | MPLAD Funds | MPLAD Funds |  | 4 | 7.17 | [9 empty] | 17/EED 07/05/2026 | M/s Kohinoor Builders | 3.71 | [7 empty] | 40 |  |  | In Progress |  | Work Order Issue
438 | MCL-0629 | B&R | D | D3 | West | 58 |  |  | Installation of Cement Benches W. No. 58 |  |  |  | MPLAD Funds | MPLAD Funds |  | 0.29 | 7.77 | [9 empty] | 13/EED 07/05/2026 | M/s Kohinoor Builders | 0.27 | [10 empty] | Not Started |  | Work Order Issue
439 | MCL-0630 | B&R | D | D3 | West | 59 |  |  | Installation of Swings & Benches in Parks A-Block Aggar Nagar W. No. 59 |  |  |  | MPLAD Funds | MPLAD Funds |  | 1.5 | 3.12 | [9 empty] | 116/EED 05/03/2026 | M/s Kohinoor Builders | 1.4532 | [7 empty] | 100 |  |  | Completed |  | Work Order Issue
440 | MCL-0631 | B&R | D | D4 | West | 60 |  |  | Repair & Renovation of Kumra Park in Gurdev Nagar w no 60 |  |  |  | MPLAD Funds | MPLAD Funds |  | 3 | 7.77 | [9 empty] | 16/EED 07/05/2026 | M/s Kohinoor Builders | 2.77 | 2026-06-29 | [6 empty] | 20 |  |  | In Progress |  | Work Order Issue
441 | MCL-0632 | B&R | D | D1 | West | 62 |  |  | (Installation of swings, open gym and jogging tracks, construction of boundary wall, installation of 25 benches.) Develpoment of different public parks in W. no. 62 |  |  |  | MPLAD Funds | MPLAD Funds |  | 10 | 22.41 | [9 empty] | 158/EED 25/03/2026 | Bharat Nirman Infracon | 7.76 | [7 empty] | 10 |  |  | In Progress |  | Work Order Issue
442 | MCL-0633 | B&R | D | D1 | West | 63 |  |  | Development of public park w.no.63. |  |  |  | MPLAD Funds | MPLAD Funds |  | 10 | 24.93 | [9 empty] | 159/EED 25/03/2026 | Bharat Nirman Infracon | 7.5 | [7 empty] | 10 |  |  | In Progress |  | Work Order Issue
443 | MCL-0634 | B&R | D | D1 | West | 64 |  |  | Development of different public park W. no. 64.(Providing open Gym and benches.) |  |  |  | MPLAD Funds | MPLAD Funds |  | 4 | 24.99 | [9 empty] | 160/EED 25/03/2026 | Bharat Nirman Infracon | 3 | [7 empty] | 100 |  |  | Completed |  | Work Order Issue
444 | MCL-0635 | B&R | D | D1 | West | 64 |  |  | Construction of rooms at Adarsh Public school Kapil Park W no 64 |  |  |  | MPLAD Funds | MPLAD Funds |  | 15 | 5.15 | [9 empty] | 21/EED 07/05/2026 | M/s Kohinoor Builders | 14.23 | [10 empty] | Not Started |  | Work Order Issue
445 | MCL-0636 | B&R | D | D1 | West | 65 |  |  | Development of different public parks in w.no.65.(P/F mini mast lights and swings, footpath, benches, boundry walls, open gym, w.no. 65) |  |  |  | MPLAD Funds | MPLAD Funds |  | 10 | 23.49 | [9 empty] | 161/EED 25/03/2026 | Bharat Nirman Infracon | 7.65 | [7 empty] | 10 |  |  | In Progress |  | Work Order Issue
446 | MCL-0637 | B&R | D | D4 | West | 69 |  |  | P& Fixing Benches and Open Gym equipment in parks of Officer colony, Tagore Nagar, Kitchlu Nagar, Malerkotla House, Green Park, Police Line and Rajpura Pind W.No.69 |  |  |  | MPLAD Funds | MPLAD Funds |  | 10 | 24.8 | [9 empty] | 157/EED 25/03/2026 | M/s Ram Parkash kakkar | 7.52 | [7 empty] | 10 |  |  | In Progress |  | Work Order Issue
447 | MCL-0638 | B&R | D | D4 | West | 71 |  |  | Construction of Rooms at Goverment Collage for Girls Fzr Road Ldh |  |  |  | MPLAD Funds | MPLAD Funds |  | 25 | 7.26 | [9 empty] | 18/EED 07/05/2026 | M/s Kohinoor Builders | 23.18 | [10 empty] | Not Started |  | Work Order Issue
448 | MCL-0639 | B&R | D | D4 | West | 71 |  |  | Repair & Renovation of Park in Park Streets Collage Road W no 71 |  |  |  | MPLAD Funds | MPLAD Funds |  | 1 | 5.55 | [9 empty] | 19/EED 07/05/2026 | M/s Kohinoor Builders | 0.944 | [7 empty] | 40 |  |  | In Progress |  | Work Order Issue
449 | MCL-0640 | B&R | D | D4 | West | 71 |  |  | Repair & Renovation of park on Sangat road Backside Church Yard |  |  |  | MPLAD Funds | MPLAD Funds |  | 1 | 5.66 | [9 empty] | 20/EED 07/05/2026 | M/s Kohinoor Builders | 0.943 | [7 empty] | 40 |  |  | In Progress |  | Work Order Issue
450 | MCL-0641 | B&R | D | D4 | West | 73 |  |  | Providing Water Tanker in w no 73 of west Constituency Ludhiana |  |  |  | MPLAD Funds | MPLAD Funds |  | 2 | 8.88 | [9 empty] | 12/EED 07/05/2026 | M/s Kohinoor Builders | 1.82 | [10 empty] | Not Started |  | Work Order Issue
451 | MCL-0642 | B&R | D | D4 | West | 73 |  |  | P & Fixing Benches and open Gym Equipment in parks of Ashok Nagar,Sham Nagar W.No.73 |  |  |  | MPLAD Funds | MPLAD Funds |  | 8 | 2.89 | [9 empty] | 156/EED 25/03/2026 | M/s Varinder Singh Govt. Contractor | 7.77 | [10 empty] | Not Started |  | Work Order Issue
87 | MCL-0087 | B&R | A | A1 | Central | 83 |  |  | Construction Of Retaining Wall And Road Along Budha Nallah From Madhopuri Pulli To Sunder Nagar Pulli, Ludhiana. |  |  |  | MC Funds / General Quota | MC Funds |  | 366.48 |  | 931 dt. 06-05-2025 | [8 empty] | 88/EEA dt. 15-05-2025 | Gaaneshkartikey Construction Pvt. Ltd. | 301.02 | 2025-05-15 | 18 months | 2026-11-14 |  |  |  |  | 60% |  | 90 | Delayed/Held Up |  | Work delayed due to shortage of bitumen. Notice issue to Contractor
88 | MCL-0088 | B&R | A | A1 | Central | 9 & 10 | Roads - Bituminous |  | Construction of Main 70' Road Sunder Nagar in w.no.8 & 58. | 1250 | 20 |  | MC Funds / General Quota | MC Funds | Awarded | 57.19 | -24.99 | 102 dt. 26-03-2025 | [8 empty] | 83/EEA dt. 21-04-2025 | M/s C.H Builders Pvt. Ltd. | 42.89 | 2025-04-21 | 6 months | 2025-10-22 |  | Vikas Sethi (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) |  |  | 0% |  | NIL | Delayed/Held Up |  | Work delayed due to shortage of bitumen. Final Notice issued to Contractor
89 | MCL-0089 | B&R | B | B1 | Central | 81 | Building Work |  | Repair and Maintenance of Zone-B Main Building of Municipal Corporation Ludhiana. |  |  |  | MC Funds / General Quota | MC Funds |  | 123.69 | -21.13 | 124 dt. 26-03-2025 | [8 empty] | 91/EEA dt. 15-05-2025 | Teg Builders (Govt. Contractor) | 97.55 | 2025-05-15 | 6 months | 2025-10-16 |  | Karan Pathak (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) |  |  | 90% |  | 86.12 | In Progress |  | Work in progress
90 | MCL-0090 | B&R | A | A1 | Central | 83 & 85 | Roads - RMC / Cement Concrete |  | Laying RMC M-30 in various streets in vakilla Mohalla & Krishana Gali in ward no.59 & 61.(New w.no. 83 & 85) | 410 | 18 |  | MC Funds / General Quota | MC Funds |  | 25.19 | -44.55 | Tender F&CC Reso.no. 97 dt. 26-03-2025 | [8 empty] | 94/EEA dt. 01-08-2025 | Capital Construction Co. | 13.96 | 2025-08-01 | 6 months | 2026-01-02 |  | Vikas Sethi (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) |  |  | 75% |  | 8.36 | In Progress |  | Work in progress
91 | MCL-0091 | B&R | B | B1 | Central | 76 | Roads - Bituminous |  | Laying 30mm thick SDBC Kucha no.16 adjoining Janj Ghar w.no.63. (New w.no.76) | 240 | 20 |  | MC Funds / General Quota | MC Funds |  | 20.32 | -35.1 | Tender F&CC Reso.no. 100 dt. 26-03-2025 | [8 empty] | 95/EEA dt. 01-08-2025 | Capital Construction Co. | 13.18 | 2025-08-01 | 6 months | 2026-01-02 |  | Karan Pathak (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) |  |  | 10% |  | NIL | Delayed/Held Up |  | Work delayed due to shortage of bitumen.
92 | MCL-0092 | B&R | C |  | Central | 74 | Roads - Bituminous |  | Laying BM&PC on various streets of Industrial Area B adjoining overlock road in w.no.51. | 2000 |  |  | MC Funds / General Quota | MC Funds |  | 175.23 | -37 | Tender F&CC Reso.no. 761 dt. 09-04-2025 | [8 empty] | 101/EEA dt. 01-08-2025 | Hitesh Aggarwal Cont. | 110.39 | 2025-08-01 | 6 months | 2026-01-02 |  | Tejinder Singh (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) |  |  | 20% |  | NIL | Delayed/Held Up |  | Work delayed due to shortage of bitumen.
93 | MCL-0093 | B&R | A | A2 | Central | 78 | Parks & Green Belts |  | Renovation of various parks in ward no. 78, Ludhiana. |  |  |  | MC Funds / General Quota | MC Funds |  | 37.41 | -21 | Tender F&CC reso.no. 1821 dt. 13-10-2025 | [8 empty] | 103/EEA dt. 19-11-2025 | M/s Dynamic tiles | 29.55 | 2025-11-19 | 6 months | 2026-06-20 |  | Tejinder Singh (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) |  |  | 40% |  | NIL | In Progress |  | Work in progress
94 | MCL-0094 | B&R | B | B1 | Central | 80 | Roads - Bituminous |  | Laying SDBC in streets of Janakpuri Part-I in w.no.80. | 1130 |  |  | MC Funds / General Quota | MC Funds | Awarded | 39.89 | -7.7 | Tender F&CC reso.no. 2147 dt. 13-10-2025 | [8 empty] | 105/EEA dt. 19-11-2025 | M/s Soham Construction Company | 36.81 | 2025-11-19 | 6 months | 2026-06-20 |  | Karan Pathak (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) |  |  | 0% |  | NIL | Delayed/Held Up |  | Work delayed due to shortage of bitumen.
95 | MCL-0095 | B&R | A | A1 | Central | 9 | Building |  | Construction of New Toilets and Repair & Renovation of Sunder Nagar Fire Station. |  |  |  | MC Funds / General Quota | MC Funds |  | 24.33 | -20.58 | Tender F&CC reso.no. 1811 dt. 13-10-2025 | [8 empty] | 106/EEA dt. 19-11-2025 | M/s Prince Sharma | 19.32 | 2025-11-19 | 6 months | 2026-06-20 |  | Vikas Sethi (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) |  |  | 60% |  | 12.61 | In Progress |  | Work in progress
96 | MCL-0096 | B&R | A | A2 | Central | 78 | Roads - RMC / Cement Concrete |  | Laying RMC M30 In Streets No.1,2,3,4 & Links of Mohar Singh Nagar, W.No.78, Ludhiana. | 1230 |  |  | MC Funds / General Quota | MC Funds |  | 93.11 | -42.7 | Tender F&CC reso.no. 1823 dt. 13-10-2025 | [8 empty] | 108/EEA dt. 19-11-2025 | K.S Constructions | 53.35 | 2025-11-19 | 6 months | 2026-06-20 |  | Tejinder Singh (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) |  |  | 70% |  | 50.7 | In Progress |  | Work in progress
97 | MCL-0097 | B&R | A | A1 | Central | 10 | Roads - RMC / Cement Concrete |  | Laying RMC in street of Mohalla New Madho Puri in w.no.58 (New w.no.10) Part-II. | 370 |  |  | MC Funds / General Quota | MC Funds |  | 83.72 | -42.7 | Tender F&CC reso.no. 1819 dt. 13-10-2025 | [8 empty] | 110/EEA dt. 19-11-2025 | K.S Constructions | 47.97 | 2025-11-19 | 7 months | 2026-05-20 |  | Vikas Sethi (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) |  |  | 60% |  | 18.75 | In Progress |  | Work in progress
98 | MCL-0098 | B&R | A | A1 | Central | 83 | Roads - RMC / Cement Concrete |  | Laying RMC M-30 in street of Mohalla Mehmoodpura in w.no.61. (New w.no.83) | 890 |  |  | MC Funds / General Quota | GQ |  | 71.84 | -42.7 | Tender F&CC reso.no. 1814 dt. 13-10-2025 | [8 empty] | 111/EEA dt. 19-11-2025 | K.S. Constructions | 41.16 | 2025-11-19 | 6 months | 2026-05-20 |  | Vikas Sethi (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) |  |  | 40% |  | 7.89 | In Progress |  | Work in progress
99 | MCL-0099 | B&R | B | B1 | Central | 81 | Roads - RMC / Cement Concrete |  | Laying RMC M-30 in streets of Harcharan Nagar in w.no.57. | 810 |  |  | MC Funds / General Quota | MC Funds |  | 56.74 | -45.56 | Tender F&CC reso.no.758 dt. 09-04-2025 | [8 empty] | 114/EEA dt.19-11-2025 | Varinder Singh Govt. Contractor | 30.88 | 2025-11-19 | 4 months | 2026-02-20 |  | Karan Pathak (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) |  |  | 0% |  | NIL | Delayed/Held Up |  | Contractor is not ready to do this work because work order was not issued within tender validity period as NIT tender validity period is 150 days from dated of open of tender however the work order was not issued within the said validity period.
100 | MCL-0100 | B&R | A | A2 | Central | 82 | Roads - Interlocking Tiles |  | P/F 60/80mm I/Tiles on RMC in Streets of Dhoka Mohalla, Ludhiana. (Rs. 33,89,445.15 Only (1/2 of total Tender Cost: 67,78,890.30) ) | 1270 |  |  | MC Funds / General Quota | MC Funds |  | 121.03 | -43.99 | Tender F&CC reso.no. 1795 dt. 13-10-2025 | [8 empty] | 115/EEA dt.19-11-2025 & 116/EEA dt.19-11-2025 | M/s Apex Devlopers & M/s K.S. Constructions | 67.78 | 2025-11-19 | 7 months | 2026-05-20 |  | Tejinder Singh (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) |  |  | 50% |  | 13.72 | In Progress |  | Work in progress
101 | MCL-0101 | B&R | A | A1 | Central | 83 | Roads - RMC / Cement Concrete |  | Laying RMC M-30 in street of Bharam Puri in w.no.83. | 530 |  |  | MC Funds / General Quota | MC Funds | Awarded | 24.93 | -43.05 | Tender F&CC reso.no. 2153 dt. 13-10-2025 | [8 empty] | 124/EEA dt.18-02-2026 | Godwyn Infra | 14.19 | 2026-02-18 | 6 months | 2026-07-17 |  | Vikas Sethi (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) |  |  | 0% |  | NIL | Not Started |  | Work not started Notice issued
102 | MCL-0102 | B&R | A | A2 | Central | 78 | Roads - RMC / Cement Concrete |  | Laying RMC M30 In Streets No. 5,6 & Links of Mohar Singh Nagar, W.No.78, Ludhiana. | 850 |  |  | MC Funds / General Quota | GQ |  | 73.03 | -42.3 | Tender F&CC reso.no. 1809 dt. 13-10-2025 | [8 empty] | 127/EEA dt.18-02-2026 | LRY Labour Contractor | 42.13 | 2026-02-18 | 6 months | 2026-07-17 |  | Tejinder Singh (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) |  |  | 65% |  | NIL | In Progress |  | Work in progress
103 | MCL-0103 | B&R | A | A2 | Central | 78 | Roads - RMC / Cement Concrete |  | Laying RMC M30 In Streets No.7, 8 & Links of Mohar Singh Nagar, W.No.78, Ludhiana. | 1410 |  |  | Councillor Quota (CQ) | CQ |  | 99.68 | -42.3 | Tender F&CC reso.no. 1890 dt. 13-10-2025 | [8 empty] | 128/EEA dt.18-02-2026 | LRY Labour Contractor | 57.51 | 2026-02-18 | 6 months | 2026-07-17 |  | Tejinder Singh (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) |  |  | 50% |  | NIL | In Progress |  | Work in progress
104 | MCL-0104 | B&R | A | A1 | Central | 85 | Building |  | Repair & Renovation of Sub Zone-A1 Office at Daresi. W. No. 85. |  |  |  | MC Funds / General Quota | GQ |  | 35.53 | -19.99 | Tender F&CC reso.no. 3266 dt. 25-02-2026 | [8 empty] | 131/EEA dt.18-03-2026 & 132/EEA dt.18-03-2026 | The Sobha Gram Co Operative Labour and Construction Society Ltd. & Apex Devlopers | 28.42 | 2026-03-18 | 7 months | 2026-09-17 |  | Vikas Sethi (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) |  |  | 15% |  | NIL | In Progress |  | Work in progress
105 | MCL-0105 | B&R | B | B1 | Central | 75 | Roads - Bituminous |  | Laying 30mm thick SDBC on Kidwai Nagar Main Road & Road from Suffian Chowk to Janakpuri in w.no.75. | 710 |  |  | MC Funds / General Quota | GQ |  | 38.33 | -10.99 | Tender F&CC reso.no. 3263 dt. 25-02-2026 | [8 empty] | 133/EEA dt. 18-03-2026 | Capital Construction Co. | 34.11 | 2026-03-18 | 6 months | 2026-08-17 |  | Karan Pathak (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) |  |  | 10% |  | NIL | Delayed/Held Up |  | Work delayed due to shortage of bitumen.
106 | MCL-0106 | B&R | A | A1 | Central | 83 | Roads - RMC / Cement Concrete |  | Laying RMC M-30 in St.no.1 Madhopuri & Links in w.no.83. | 670 |  |  | MC Funds / General Quota | GQ | Awarded | 46.89 | -44.99 | Tender F&CC reso.no. 3267 dt. 25-02-2026 | [8 empty] | 135/EEA dt. 18-03-2026 | N.S. Infra | 25.79 | 2026-03-18 | 6 months | 2026-08-17 |  | Vikas Sethi (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) |  |  | 0% |  | NIL | Delayed/Held Up |  | Inaguration pending
107 | MCL-0107 | B&R | A | A1 | Central | 83 | Roads - RMC / Cement Concrete |  | Laying RMC M-30 in street of Ghati Mohalla in ward no. 83. | 270 |  |  | Councillor Quota (CQ) | CQ |  | 11.4 | -40.99 | Tender F&CC reso.no. 3265 dt. 25-02-2026 | [8 empty] | 137/EEA dt. 18-03-2026 | K.S. Constructions | 6.72 | 2026-03-18 | 6 months | 2026-08-17 |  | Vikas Sethi (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) |  |  | 10% |  | NIL | In Progress |  | Work in progress
108 | MCL-0108 | B&R | A | A2 | Central | 82 | Roads - RMC / Cement Concrete |  | Laying RMC M-30 in street of Mohalla Taj Ganj in ward no.82. |  |  |  | Councillor Quota (CQ) | CQ |  | 24.65 | -43.31 | Tender F&CC reso.no. 3264 dt. 25-02-2026 | [8 empty] | 139/EEA dt. 18-03-2026 | K.S. Constructions | 13.97 | 2026-03-18 | 3 months | 2026-05-17 |  | Tejinder Singh (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) |  |  | 90% |  | NIL | In Progress |  | Work in progress
109 | MCL-0109 | B&R | A | A2 | Central | 75 | Roads - RMC / Cement Concrete |  | Laying RMC (M-30) in various streets of ward no.75. | 1010 |  |  | Councillor Quota (CQ) | CQ |  | 63.32 | -45.13 | Tender F&CC reso.no. 3268 dt. 25-02-2026 | [8 empty] | 141/EEA dt. 18-03-2026 | K.S. Constructions | 34.74 | 2026-03-18 | 6 months | 2026-08-17 |  | Karan Pathak (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) |  |  | 70% |  | 14.62 | In Progress |  | Work in progress
110 | MCL-0110 | B&R | A | A2 | Central | 78 | Parks & Green Belts |  | Re-Development of Children Friendly Park on Old Jail Road, Ludhiana. |  |  |  | MC Funds / General Quota | GQ |  | 66.68 | -35.99 | Tender F&CC reso.no. 2788 dt. 19-02-2026 | [8 empty] | 142/EEA dt. 18-03-2026 | Navdeep Gupta and Company | 42.68 | 2026-03-18 | 6 months | 2026-08-17 |  | Tejinder Singh (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) |  |  | 60% |  | NIL | In Progress |  | Work in progress
111 | MCL-0111 | B&R | B | B1 | Central | 80 | Roads - RMC / Cement Concrete |  | Laying RMC M-30 in St.no.1,2,3 & 4 of Janakpuri w.no.80. | 1580 |  |  | MC Funds / General Quota | GQ |  | 69.55 | -45.51 | Tender F&CC reso.no. 2794 dt. 19-02-2026 | [8 empty] | 143/EEA dt. 18-03-2026 | Vansh Engineers | 37.89 | 2026-03-18 | 7 months | 2026-09-17 |  | Karan Pathak (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) |  |  | 10% |  | NIL | In Progress |  | Work in progress
112 | MCL-0112 | B&R | A | A2 | Central | 77 | Roads - RMC / Cement Concrete |  | Laying RMC streets in internal streets of Mochpura Bazar. | 220 |  |  | SASCI | Under Special Central Assistance Scheme |  | 26.98 | -44.99 | Tender F&CC reso.no. 2574 dt. 11-02-2026 | [8 empty] | 144/EEA dt. 20-03-2026 | Maa Chintpurni Construction | 14.84 | 2026-03-20 | 3 months | 2026-05-21 |  | Tejinder Singh (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) |  |  | 100% |  | 14.51 | Completed |  | Completed.
113 | MCL-0113 | B&R | B | B1 | Central | 80 | Roads - Bituminous |  | Laying SDBC in streets of Janakpuri Part-II in w.no.80. | 660 |  |  | MC Funds / General Quota | GQ/MLA |  | 24.15 | -21.59 | Tender F&CC reso.no. 3578 dt. 21-04-2026 | [8 empty] | 151/EEA dt. 06-05-2026 | Capital Construction Co. | 18.93 | 2026-05-06 | 6 months | 2026-10-07 |  | Karan Pathak (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) |  |  | 10% |  | NIL | Delayed/Held Up |  | Work delayed due to shortage of bitumen. Notice issue
114 | MCL-0114 | B&R | A | A1 | Central | 85 | Roads - RMC / Cement Concrete | E 388259 | Laying RMC M-30 in street of Mohalla Shankar Puri, Veer Nagar & SDP College Quilla Mohalla in w.no.85. | 1390 |  |  | Rangla Punjab | Under Rangla Punjab Vikas Scheme Ph-I |  | 85.9 | -45.99 | 3196 dt. 25-02-2026 | [8 empty] | 150/EEA dt. 05-05-2026 | Maa Chintpurni Construction | 46.39 | 2026-05-05 | 7 months | 2026-11-06 |  | Vikas Sethi (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) |  |  | 45% |  | NIL | In Progress |  | Work in progress. Work will be completed upto 15-07-2026
115 | MCL-0115 | B&R | A | A2 | Central | 82 | Roads - RMC / Cement Concrete | E 388261 | Laying RMC M-30 in Shanti Niketen School St & Links Streets of Mohalla Fateh Ganj in Ward No-82. | 290 |  |  | Rangla Punjab | Under Rangla Punjab Vikas Scheme Ph-I |  | 43.22 | -38.7 | 3271 dt. 25-02-2026 | [8 empty] | 148/EEA dt. 05-05-2026 | LRY Labour Contractor | 26.49 | 2026-05-05 | 3 months | 2026-07-06 |  | Tejinder Singh (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) |  |  | 25% |  | NIL | In Progress |  | Work in progress. Work will be completed upto 15-07-2026
116 | MCL-0116 | B&R | A | A2 | Central | 82 | Roads - RMC / Cement Concrete | E 388263 | Laying RMC M-30 in streets near Gajja Jain Mandir in Tilak Nagar w.no.82. | 310 |  |  | Rangla Punjab | Under Rangla Punjab Vikas Scheme Ph-I |  | 27.91 | -38.7 | 3274 dt. 25-02-2026 | [8 empty] | 147/EEA dt. 05-05-2026 | LRY Labour Contractor | 17.1 | 2026-05-05 | 4 months | 2026-08-06 |  | Tejinder Singh (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) |  |  | 15% |  | NIL | In Progress |  | Work in progress. Work will be completed upto 15-07-2026
117 | MCL-0117 | B&R | B | B1 | Central | 79 | Roads - RMC / Cement Concrete | E 388264 | Laying RMC M-30 in Hargobind Nagar & its adjoining streets of w.no.79. | 700 |  |  | Rangla Punjab | Under Rangla Punjab Vikas Scheme Ph-I |  | 53.15 | -43.17 | 3273 dt. 25-02-2026 | [8 empty] | 149/EEA dt. 05-05-2026 | Capital Construction Co. | 30.2 | 2026-05-05 | 4 months | 2026-08-06 |  | Karan Pathak (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) |  |  | 10% |  | NIL | In Progress |  | Work in progress. Work will be completed upto 15-07-2026
118 | MCL-0118 | B&R | B | B1 | Central | 80 | Roads - RMC / Cement Concrete | E 388266 | Laying RMC M-30 in streets of New Kidwai Nagar in w.no. 80. | 470 |  |  | Rangla Punjab | Under Rangla Punjab Vikas Scheme Ph-I |  | 39.8 | -43.17 | 3272 dt. 25-02-2026 | [8 empty] | 146/EEA dt. 05-05-2026 | Godwyn Infra | 22.61 | 2026-05-05 | 7 months | 2026-11-06 |  | Karan Pathak (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) |  |  | 10% |  | NIL | In Progress |  | Work in progress. Work will be completed upto 15-07-2026
119 | MCL-0119 | B&R |  |  | Central | Gen. |  |  | Remodeling of Nallah & Constructions of roads from Shingar Cinema Bridge to Shamshan Ghat Bridge. |  |  |  | MC Funds / General Quota | PUEIP Ph-III |  |  |  | 2021-11-26 | [8 empty] | 153/EEA/LOA dt. 13-12-2021 | M/s Kabir Infra | 939.21 | 2021-12-13 | 12 months | 2021-12-14 |  |  |  |  | 60% |  | 300.62 | Delayed/Held Up |  | Work delayed because of pending IPS construction work causing obstruction at the site. Work in progress (Amt. approved from under PUEIP PH-III 600 lacs) but Orginal Est. Cost is 948.70 & vetted Est. amt. 942.05 lacs
120 | MCL-0121 | B&R | A |  | Central | Gen. | Roads - Bituminous |  | Laying SDBC Links between Vijay Nagar Road & Suffian Chowk Road, Links Nearby Night Shelter Moti Nagar, Main Road from Basti Jodhewal to Sunder Nagar Pulley Both Sides, Gaushalla Main Road, Ghora Colony & Links and Links between RK Road & Kabir Road in central Constituency. | 10530 | 25 |  | MDF | MDF Funds |  | 877.87 | [14 empty] | 6 months |  |  | Vikas Sethi (JE) Tejinder Singh (JE) Karan Pathak (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) | [5 empty] | Not Started |  | Under technical evaluation
121 | MCL-0122 | B&R | A |  | Central | Gen. | Roads - RMC / Cement Concrete |  | Laying RMC M-30 in streets of Old Madho Puri Part-I & II, Janakpuri, Hargobind Nagar Road, Ambedkar Nagar & Ram Nagar, Industrial area, Basti Sheikh Mohamadh, Mohalla Vijay Nagar & New Shiva Ji Nagar of Central Constituency. | 7180 | 20 |  | MDF | MDF Funds |  | 601.4 | [14 empty] | 6 months |  |  | Vikas Sethi (JE) Karan Pathak (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) | [5 empty] | Not Started |  | Under technical evaluation
122 | MCL-0123 | B&R | A |  | Central | Gen. | Roads - RMC / Cement Concrete |  | Laying RMC M-40 in Various Streets of Transport Nagar Part-II Ward No.30. | 2240 | 30 |  | MDF | MDF Funds |  | 701.92 | [14 empty] | 6 months |  |  | Karan Pathak (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) | [5 empty] | Not Started |  | Under technical evaluation
123 | MCL-0124 | B&R | A |  | Central | Gen. | Roads - Bituminous |  | Laying BM & SDBC on Guru Nanak Dev Market, Main Hargobind Marg, Main Textile Colony Road and Brown Road & Islamia School Road and Main Road from 3 No. Division to CMC Chowk. | 5200 | 30 |  | MDF | MDF Funds |  | 553.56 | [14 empty] | 6 months |  |  | Tejinder Singh (JE) Karan Pathak (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) | [5 empty] | Not Started |  | Under technical evaluation
124 | MCL-0125 | B&R | A |  | Central | Gen. | Roads - RMC / Cement Concrete |  | Laying RMC M-30 in streets of Mohalla Islam Ganj, Mustak Ganj and Ucha Tibba in w.no.75, Various Kuchas in w.no.76, Various Streets of Shivaji Nagar in w.no.79, Streets of Kashmir Nagar & Narinder Nagar in w.no.81 and Main Road of Dal Bazar, Hindi Bazar & Chawal Bazar and Main Hosiery Road. | 10840 | 25 |  | MDF | MDF Funds |  | 652.17 | [14 empty] | 6 months |  |  | Vikas Sethi (JE) Tejinder Singh (JE) Karan Pathak (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) | [5 empty] | Not Started |  | Under technical evaluation
125 | MCL-0126 | B&R | B | B1 | Central | 30 | Roads - RMC / Cement Concrete |  | Laying RMC M-30 in Various Streets of Bihari Colony in ward no.30. | 770 | 20 |  | Rangla Punjab | Rangla Punjab-II |  | 73.82 | [14 empty] | 6 months |  |  | Karan Pathak (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) | [5 empty] | Not Started |  | F&CC approved in anticipation Tender to be called
126 | MCL-0127 | B&R | B | B1 | Central | 79 | Roads - RMC / Cement Concrete |  | Laying RMC M-30 in Street No.1,2,3 & Links Hari Kartar Colony in ward no.79. | 560 | 20 |  | Rangla Punjab | Rangla Punjab-II |  | 53.46 | [14 empty] | 6 months |  |  | Karan Pathak (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) | [5 empty] | Not Started |  | F&CC approved in anticipation Tender to be called
127 | MCL-0128 | B&R | B | B1 | Central | 76 | Roads - RMC / Cement Concrete |  | Laying RMC M-30 in link Streets of Kusht Ashram Road in ward no.76. | 1430 | 15 |  | Rangla Punjab | Rangla Punjab-II |  | 72.81 | [14 empty] | 6 months |  |  | Karan Pathak (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) | [5 empty] | Not Started |  | F&CC approved in anticipation Tender to be called
128 | MCL-0129 | B&R | B | B1 | Central | 76 | Roads - RMC / Cement Concrete |  | Laying RMC M-30 in Different Streets of Prem Nagar Part-II in ward no.76. | 970 | 15 |  | Rangla Punjab | Rangla Punjab-II |  | 49.81 | [14 empty] | 6 months |  |  | Karan Pathak (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) | [5 empty] | Not Started |  | F&CC approved in anticipation Tender to be called
129 | MCL-0130 | B&R |  |  | Central | Gen. | Roads - RMC / Cement Concrete |  | Upgradation of RMC Roads in various wards of Central Constituency. | 10680 | 20 |  | SASCI | Special Central Assistance Scheme |  | 835.61 | -11.21% | 2676 dt. 11-02-2026 | [8 empty] | 123/EEA dt. 18-02-2026 | M/s J.K.Infocon Pvt. Ltd | 741.93 | 2026-02-18 | 3 months |  |  | Tejinder Singh (JE) Karan Pathak (JE) Simranjit Singh (SDO) Sanjeev Sharma (XEN) |  |  | 90% |  |  | In Progress |  | Work will be completed upto 30-06-2026
|  | B&R | D | D1 | North | 66 | Roads - RMC / Cement Concrete | 389674 | P/laying RMC M-30 in streets of Durgapuri st no. 12 to 14 Links in ward no. 66. | 1180 |  |  | MC Funds / General Quota | GQ | Not started | 70.66 | -29.99 | 3768 dt 15-06-2026 | Y | Y | SE | N |  |  | Y | Y | 14/EED dt 12.07.2026 | M/s K.S Construction | 49.47 | 12.07.2026 | 4 | 15.11.2026 |  | Er. Ranjit Singh | N | N | __ |  |  | Not Started |  | Inauguration pending
|  | B&R | D | D1 | North | 66 | Roads - RMC / Cement Concrete | 389680 | P/laying RMC M-30 in streets of Durgapuri st no. 9 to 11 in ward no. 66. | 1340 | 20 |  | MC Funds / General Quota | GQ | Not started | 97.64 | -32.99 | 3764 dt 15-06-2026 | Y | Y | SE | N |  |  | Y | Y | 16/EED dt 12.07.2026 | M/s Apex Developers | 65.43 | 12.07.2026 | 5 | 15.12.2026 |  | Er. Ranjit Singh | N | N | __ |  |  | Not Started |  | Inauguration pending
|  | B&R | D | D1 | North | 67 | Roads - RMC / Cement Concrete | 389581 | P/Laying RMC M-30 in Anand Nagar st no. 2 to 5 & links Part-1 w.no. 67. | 1060 | 20 |  | Councillor Quota (CQ) | CQ | In Progress | 65.82 | -34.1 | 3765 dt 15-06-2026 | Y | Y | SE | N |  |  | Y | Y | 12/EED dt 02.07.2026 | M/s Regis contractors | 43.38 | 02.07.2026 | 4 | 10.11.2026 |  | Er. Ranjit Singh | N | N | 50% |  |  | In Progress |  | Work in progress | https://drive.google.com/file/d/1MAeoHIcC_OWpjpPUO62llu8RebxiRN6y/view?usp=sharing
|  | B&R | D | D1 | North | 67 | Roads - RMC / Cement Concrete | 389585 | P/Laying RMC M-30 in Anand Nagar st no. 6 to 10 & links Part-2 w.no. 67. | 1030 | 20 |  | Councillor Quota (CQ) | CQ | In Progress | 64.15 | -30.66 | 3767 dt 15-06-2026 | Y | Y | SE | N |  |  | Y | Y | 23/EED dt 02.07.2026 | M/s Apex Developers | 44.48 | 02.07.2026 | 4 | 10.11.2026 |  | Er. Ranjit Singh | N | N | 20% |  |  | In Progress |  | Work in progress | https://drive.google.com/file/d/1gTFYV5Bg0iwmeDfOfo8A33gb2lQTLCwP/view?usp=sharing
|  | B&R | D | D1 | North | 67 | Roads - RMC / Cement Concrete | 389587 | P/Laying RMC M-30 in street no. 5 & Links in Raghubir park ward no. 67. | 1160 | 20 |  | MC Funds / General Quota | GQ | In Progress | 66.73 | -31.55 | 3775 dt 15-06-2026 | Y | Y | SE | N |  |  | Y | Y | 13/EED dt 02.07.2026 | M/s K.S Construction | 45.68 | 02.07.2026 | 4 | 10.11.2026 |  | Er. Ranjit Singh | N | N | 50% |  |  | In Progress |  | Work in progress | https://drive.google.com/file/d/1Dk9TrUvp0oulwMFNwPQCecHYe2YVLMJ-/view?usp=sharing
|  | B&R | D | D1 | North | 67 | Roads - RMC / Cement Concrete | 389623 | P/Laying RMC M-30 in streets of New Tagore nagar st no. 5,6 & Shakti Vihar ward no. 67. | 440 | 22' |  | Councillor Quota (CQ) | CQ | Not started | 29.37 | -35.8 | 3780 dt 15-06-2026 | Y | Y | XEN | N |  |  | Y | Y | 20/EED dt 12.07.2026 | M/s Regis contractors | 18.86 | 12.07.2026 | 3 | 15.10.2026 |  | Er. Ranjit Singh | N | N | __ |  |  | Not Started |  | Inauguration pending
|  | B&R | D | D1 | North | 91 | Roads - RMC / Cement Concrete | 389673 | P/Laying RMC M-30 in streets of New Kundanpuri ward no. 91. | 820 | 18' |  | Councillor Quota (CQ) | CQ | Not started | 51.75 | -30.99 | 3766 dt 15-06-2026 | Y | Y | SE | N |  |  | Y | Y | 19/EED dt 12.07.2026 | M/s K.S Construction | 41.4 | 12.07.2026 | 4 | 15.11.2026 |  | Er. Ranjit Singh | N | N | __ |  |  | Not Started |  | Inauguration pending
|  | B&R | D | D1 | North | 91 | Roads - RMC / Cement Concrete | 389666 | P/Laying RMC M-30 in streets of Vivek Nagar ward no. 91. | 650 | 20 |  | MC Funds / General Quota | GQ | Not started | 54.15 | -34.51 | 3778 dt 15-06-2026 | Y | Y | SE | N |  |  | Y | Y | 22/EED dt 12.07.2026 | M/s Regis contractors | 35.46 | 12.07.2026 | 4 | 15.11.2026 |  | Er. Ranjit Singh | N | N | __ |  |  | Not Started |  | Inauguration pending
|  | B&R | D | D1 | North | 92 | Roads - RMC / Cement Concrete | 389657 | P/Laying RMC M-30 in remaining streets of Mohalla Shamsher Nagar ward no. 92. | 430 | 20 |  | Councillor Quota (CQ) | CQ | Not started | 29.18 | -27.51 | 3770 dt 15-06-2026 | Y | Y | XEN | N |  |  | Y | Y | 18/EED dt 12.07.2026 | M/s K.S Construction | 21.15 | 12.07.2026 | 3 | 15.10.2026 |  | Er. Ranjit Singh | N | N | __ |  |  | Not Started |  | Inauguration pending
|  | B&R | D | D1 | North | 93 | Others | 389685 | P/Laying brick paving road from Jassian road to Razori Garden near railway line w.no. 93. | 274.39 | 25 |  | MC Funds / General Quota | GQ | Not started | 17.76 | -6.66 | 3769 dt 15-06-2026 | Y | Y | SDO | N |  |  | Y | Y | 24/25 EED dt 12.07.2026 | M/s Goyal Builders M/s N.S Infra | 16.58 | 12.07.2026 | 3 | 15.10.2026 |  | Er. Ranjit Singh | N | N | __ |  |  | Not Started |  | Inauguration pending
|  | B&R | D | D1 | North | 92 | Bituminous | 391964 | P/Laying BM & PC at Civil city Sandhu nagar road w.no. 92. | 457.31 | 25 |  | Councillor Quota (CQ) | CQ | Not started | 25.08 | -19.56 | 3837 dt 15-06-2026 | Y | Y | XEN | N |  |  | Y | Y | 15/EED dt 12.07.2026 | M/s Somaya Infrastructure | 20.17 | 12.07.2026 | 3 | 15.10.2026 |  | Er. Ranjit Singh | N | N | __ |  |  | Not Started |  | Inauguration pending
|  | B&R | D | D1 | North | 92 | Bituminous | 391962 | P/Laying BM & SDBC in streets of Bishan Enclave ward no. 92. | 985.58 | 25 |  | Councillor Quota (CQ) | CQ | Not started | 46.63 | -21.35 | 3898 dt 15-06-2026 | Y | Y | XEN | N |  |  | Y | Y | 17/EED dt 12.07.2026 | M/s Somaya Infrastructure | 36.67 | 12.07.2026 | 4 | 15.11.2026 |  | Er. Ranjit Singh | N | N | __ |  |  | Not Started |  | Inauguration pending
|  | B&R | D | D1 | North | 92 | Roads - RMC / Cement Concrete | 391959 | P/Laying RMC M-30 in Jaiswal streest, Gangadham bridh aashram & SCO Parking civil city ward no. 92. | 450 | 20 |  | MC Funds / General Quota | GQ | Not started | 32.27 | -37.16 | 3885 dt 15-06-2026 | Y | Y | XEN | N |  |  | Y | Y | 21/EED dt 12.07.2026 | M/s Apurva Inc. | 20.28 | 12.07.2026 | 3 | 15.10.2026 |  | Er. Ranjit Singh | N | N | __ |  |  | Not Started |  | Inauguration pending
|  | B&R | D | D1 | North | Gen | Others | 391946 | Construction of Planter for plants along with Budha Dariya from Haibowal puli to Kundanpuri puli. |  |  |  | MC Funds / General Quota | GQ | in Progress | ` | -4.31 | 3828 dt 15-06-2026 | Y | Y | SDO | N |  |  | Y | Y | 26/EED dt 21.07.2026 | Apurva Inc. | 22.39 | 21.07.2026 | 3 | 25.10.2026 |  | Er. Ranjit Singh | N | N | 30% |  |  | In Progress |  | Work in progress | https://drive.google.com/file/d/1GEZRot1qtKuHMlI2SID3ca6CA-r6ZQcu/view?usp=sharing
|  | B&R | D |  | West |  |  |  | Upgradation of RMC Roads in various wards of West Constituency.
|  | B&R |  |  | North |  |  |  | Upgradation of Various Bitumen Main Roads in North Constituency Zone-A Ludhiana
|  | B&R | [6 empty] | Laying BM and SDBC on road in Sub Zone D2 Atam Nagar Halka
|  | B&R | [6 empty] | Upgradation of Bituminious Roads in various wards of Central Constituency.
|  | B&R | [6 empty] | Upgradation of Main Bhamian Road from Chandigarh road to upto MC Limit, Main Phirni of Village Mundian Kalan from Chd road to Sunder Nagar 33' Road and from Chd Road to Rasila Nagar Back side Blind School.
B&R
B&R
B&R
B&R
|  | B&R | B | B3 | East | 12 | I/tiles | _ | P/F 80mm thick Interlocking tiles paver block M-40 grade in the remaining streets of Sutantar Nagar W No.7 | 778.66 | 18 |  | MC | Councillor | Ongoing | 48.59 | 24.99% | _ | Y | Y | XEN | N | 05, dt 13.12.2019 |  | Y | Y | 10 dt 31.08.2020 | M/s RK Const Co. | 36.45 | 31.08.2020 | 3 | 30.11.2020 |  | Sh Parveen Singla | N | N | 60% |  |  | Ongoing | Work was held up due to laying of Sewerline in the balance area. | _ | _ | _
|  | B&R | B | B3 | East | 14 | I/Tiles | _ | P/F 60/80mm thick Interlocking tiles in streets of Gita Nagar & Jagdishpura W No.14 | 339.94 | 21 |  | MC | Councillor | Ongoing | 30.85 | 22.88% | 6845 Dt 07.09.2022 | Y | Y | XEN | N | 81/SE(TIC) Dt 07.11.2022 | 24.11.2022 | Y | Y | 07 Dt 20.03.2023 | M/s The Khairay Co-Op L&C Society Ltd. | 23.79 | 20.03.2023 | 3 | 19.06.2023 | 20.08.2026 | Sh Parveen Singla | N | N | 60% |  |  | Ongoing | _ | Work was held up due to non-laying of W/s & Sewerlines. Now same has been laid. Work is in progress | _ | _
|  | B&R | B | B2 | East | 29 | Park | _ | Repair & Renovation of various parks in LIG W No.19 | _ | _ |  | MC | General | Ongoing | 62.03 | 39.99 | 1786 dt. 27.02.2024 | Y | Y | XEN | N | 62/SE(TIC) 12.08.2024 | 28.08.2024 | Y | Y | 82 dt 04.12.2024 | M/s Prince Sharma | 37.22 | 04.12.2024 | 6 | 03.06.2024 |  | Sh Parveen Singla | Y | N | 80% |  |  | Ongoing | No progress on ground, billing issue, quality issue of the work | Work is in Progress | _ | 2026-08-07
|  | B&R | B | B3 | East | 12 | I/tiles | _ | P/F I/tiles in various streets of W No.12 | 1215.85 | 19 |  | MC | General | Ongoing | 93.51 | 42.99 | 1788 dt. 27.02.2024 | Y | Y | XEN | N | 62/SE(TIC) 12.08.2024 | 28.08.2024 | Y | Y | 83 dt 04.12.2024 | M/s Apex Developers | 53.31 | 04.12.2024 | 5 | 03.05.2024 | 25.08.2026 | Sh Parveen Singla | Y | N | 70% |  |  | Ongoing | _ | Work was held up due to non-laying of W/s line in Guru Nanak Estate . Now same has been laid. Work is in progress | _ | _
|  | B&R | B | B2 | East | 17 & 19 | I/tiles | _ | P/F I/tiles in streets of Guru Arjun Dev Nagar, Jaswant Nagar and Indrapuri St No.4 W No.17 & 19 | 364.33 | 13 |  | MC | General | Ongoing | 20.81 | 41.65 | 2696 dt. 24.09.2024 | Y | Y | SDO | N | 153/SE(TIC) 24.10.2024 | 04.11.2024 | Y | Y | 86 dt 04.12.2024 | Capital Const Co. | 12.14 | 04.12.2024 | 3 | 03.03.2024 | 31.12.2026 | Sh Parveen Singla | Y | N | 25% |  |  | Ongoing | Dispute at site for the balance work | Work is in Progress Dispute at site for the balance work | _ | _
|  | B&R | B | B2 | East | 20 | Park | _ | Const of Park on Bhamian Road Near Football Ground W No.16 (New W No.20) | _ | _ |  | MC | General | Ongoing | 50 | 31.89 | 2706 dt. 24.09.2024 | Y | Y | XEN | N | 255/SE(TIC) 31.01.2025 |  | Y | Y | 01 16.04.2025 | M/s Teg Builders | 34.06 | 16.04.2025 | 6 | 15.10.2025 |  | Sh Parveen Singla | Y | N | 10% |  |  | Ongoing | Heldup due to construction of water tank by O&M Cell | _ | _ | _
|  | B&R | B | B3 | East | 11,12 | I/tiles | _ | P/F I/tiles in St No.4 Mayapuri upto RK Property Dealor at KS Grewal Road W No.11 & 12 | 856.71 | 21 |  | MC | General | Ongoing | 64.24 | 42.72% | 2698 24.09.2024 | Y | Y | SE | N | 185/SE(TIC) 21.11.2024 | 05.12.2024 | Y | Y | 7 16.04.2025 | Asis Builders | 36.8 | 16.04.2025 | 4 | 15.08.2025 |  | Sh Parveen Singla | Y | N | 90% |  |  | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B3 | East | 12 | I/tiles | _ | P/F I/tiles in streets of Juneja Colony and Karamsar Colony W No.12 | 562.5 | 20 |  | MC | General | Ongoing | 50 | 41.99% | 2700 24.09.2024 | Y | Y | XEN | N | 185/SE(TIC) 21.11.2024 | 05.12.2024 | Y | Y | 9 16.04.2025 | Apex Developers | 29 | 16.04.2025 | 4 | 15.08.2025 | 25.09.2026 | Sh Parveen Singla | Y | N | 15% | 0 | 0 | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B3 | East | 10 | I/tiles | _ | P/F 80mm thick Interlocking tiles in streets of Mohalla New Subhash Nagar on Towerline No. 2 & 5 and St No.10 & St No.2/10 & 2/11 of Subhash Nagar W No.10 | 393.29 | 19 |  | MC | General | Ongoing | 29.69 | 41.55% | 2701 24.09.2024 | Y | Y | XEN | N | 185/SE(TIC) 21.11.2024 | 05.12.2024 | Y | Y | 10 16.04.2025 | Capital Const Co. | 17.35 | 16.04.2025 | 3 | 15.07.2025 | 15.09.2026 | Sh Parveen Singla | Y | N | 30% | 0 | 0 | Ongoing | _ | Work heldup due to upgradation of W/s lines, Now same has been completed. Work is in progress now. | _ | _
|  | B&R | B | B3 | East | 9 | I/tiles | _ | P/F I/tiles in remaining streets of Shastri Nagar and link of New Shakti Nagar W No.09 | 425 | 17 |  | MC | General | Ongoing | 34.61 | 42.61% | 2702 24.09.2024 | Y | Y | XEN | N | 185/SE(TIC) 21.11.2024 | 05.12.2024 | Y | Y | 11 16.04.2025 | T&G Const Co. | 19.86 | 16.04.2025 | 3 | 15.07.2025 | 25.09.2026 | Sh Parveen Singla | Y | N | 70% |  |  | Ongoing | Work heldup due to upgradation of W/s lines & S/w Line in the balance area | _ | _ | _
|  | B&R | B | B4 | East | 28 | I/tiles | _ | P/F I/tiles in streets No.2 of Hargobindpura & Links W No.28 | 504.27 | 16 |  | MC | General | Ongoing | 34.21 | 41.55% | 2704 24.09.2024 | Y | Y | XEN | N | 185/SE(TIC) 21.11.2024 | 05.12.2024 | Y | Y | 13 16.04.2025 | Capital Const Co. | 19.99 | 16.04.2025 | 3 | 15.07.2025 | 31.08.2026 | Sh Parveen Singla | Y | N | 90% |  |  | Ongoing | _ | Balance work was heldup due to upgradation of W/S line in the balance area, now same has been laid. Work is in Progress now. | _ | _
|  | B&R | B | B3 | East | 11 | I/tiles | _ | P/F I/tiles in streets of Sandhu Colony | 1596.95 | 24 |  | MC | General | Ongoing | 145.87 | 44.09% | 1783 dt. 27.02.2024 | Y | Y | CE | N | 178/SE(TIC) 20.11.2024 |  | Y | Y | 20 11.07.2025 | T&G Const Co. | 81.55 | 11.07.2025 | 6 | 10.01.2026 |  | Sh Parveen Singla | Y | N | 90% |  |  | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B2 | East | _ | Others | _ | Providing & Fixing of Sign Boards in different areas of Sub Zone B2 | _ | _ |  | MC | General | Ongoing | 34.03 | 32 | 457 dt 09.04.2025 | Y | Y | XEN | N | 75/SE(TIC) 09.05.2025 | 28.05.2025 | Y | Y | 22 14.08.2025 | Glisten | 23.14 | 14.08.2025 | 3 | 13.11.2025 |  | Sh Parveen Singla | N | N | 50% |  |  | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B3 | East | _ | Others | _ | Providing & Fixing of Sign Boards in different areas of Sub Zone B3 | _ | _ |  | MC | General | Ongoing | 43.13 | 32 | 461 dt 09.04.2025 | Y | Y | XEN | N | 75/SE(TIC) 09.05.2025 | 28.05.2025 | Y | Y | 23 14.08.2025 | Glisten | 29.33 | 14.08.2025 | 4 | 13.12.2025 |  | Sh Parveen Singla | N | N | 60% |  |  | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B3 | East | 12 | Parks | _ | Development of Green Belt on Towerline No.2 and 5 | _ | _ |  | MC | General | Ongoing | 309.16 | 29.99 | 3365 dt. 05.12.2024 | Y | Y | CE | N | 113/SE(TIC) 27.06.2025 | 15.07.2025 | Y | Y | 24 27.08.2025 | RK Const Co. | 216.44 | 27.08.2025 | 6 | 26.02.2026 |  | Sh Parveen Singla | N | N | 65% | 0 | 0 | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B3 | East | 16,18,20 &29 | Others | _ | Construction of Central Verge on Tajpur raod . | _ | _ |  | MC | General | Ongoing | 217.47 | 14.15 | 3366 dt. 05.12.2024 | Y | Y | CE | N | 113/SE(TIC) 27.06.2025 | 15.07.2025 | Y | Y | 25 27.08.2025 | Navyug Comapany | 186.7 | 27.08.2025 | 6 | 26.02.2026 |  | Sh Parveen Singla | N | N | 65% |  |  | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B4 | East | 19 | Parks | _ | P/F different type of Open garden gym machines in ward no 19. | _ | _ |  | MC | General | Ongoing | 16.03 | 36.99 | 464 dt 09.04.2025 | Y | Y | SDO | N | 76/SE(TIC) 09.05.2025 | 28.05.2025 | Y | Y | 27 15.01.2026 | Khalsa Exports Pvt Ltd. | 10.1 | 15.01.2026 | 2 | 14.03.2026 |  | Sh Parveen Singla | N | N | _ |  |  | Ongoing | _ | Inauguration is to be done | _ | _
|  | B&R | B | B4 | East | 19 | Parks | _ | Repair & Renovation of various Park in Sec 39 Block-I | _ | _ |  | MC | General | Ongoing | 36.2 | 28.59 | 1801 dt. 27.02.2024 | Y | Y | XEN | N | 75/SE(TIC) 09.05.2025 | 28.05.2025 | Y | Y | 32 15.01.2026 | RK Const Co. | 25.85 | 15.01.2026 | 3 | 14.04.2026 |  | Sh Parveen Singla | N | N | 75% |  |  | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B4 | East | 19 | Parks | _ | Repair & Renovation of various Park in Sec 39 Block-II | _ | _ |  | MC | General | Ongoing | 38.85 | 28.59 | 1802 dt. 27.02.2024 | Y | Y | XEN | N | 75/SE(TIC) 09.05.2025 | 28.05.2025 | Y | Y | 33 15.01.2026 | RK Const Co. | 27.74 | 15.01.2026 | 3 | 14.04.2026 |  | Sh Parveen Singla | N | N | 75% |  |  | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B4 | East | 19 | Others | _ | Renovation of Disposal site and Fixing of Information Board at enterance of Sec-39 near Vardhman Chowk W No.19 | _ | _ |  | MC | Councillor | Ongoing | 20.7 | 5.89% | 1972 dt 13.10.2025 | Y | Y | SDO | N | 263/SE(TIC) 17.10.2025 |  | Y | Y | 43 15.01.2026 | Teg Builders | 19.48 | 15.01.2026 | 2 | 14.03.2026 |  | Sh Parveen Singla | N | N | 80% |  |  | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B3 | East | 16 | RMC | _ | Const of Road by laying RMC from Gita Nagar Pully to Vijay Nagar Pully W No.16 | 426.22 | 28 |  | MC | General | Ongoing | 66.47 | 36.69% | 1123 dt 11.08.2025 | Y | Y | SE | N | 262/SE(TIC) 14.10.2025 | 30.10.2025 | Y | Y | 44 15.01.2026 | RK Const Co. | 42.08 | 15.01.2026 | 4 | 14.05.2026 | 01.10.2026 | Sh Parveen Singla | N | N | 5% | 0 | 0 | Ongoing | Work heldup due to upgradation of Sewer line | _ | _ | _
|  | B&R | B | B4 | Sahnewal | _ | Others | _ | Providing & Fixing of Sign Boards in different areas of Sub Zone B4 | _ | _ |  | MC | General | Ongoing | 36.92 | 32 | 462 dt 09.04.2025 | Y | Y | XEN | N | 75/SE(TIC) 09.05.2025 | 28.05.2025 | Y | Y | 46 29.01.2026 | Glisten | 25.11 | 29.01.2026 | 3 | 28.04.2026 |  | Sh Parveen Singla | N | N | 50% |  |  | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B4 | East | 19 | Parks | _ | P/F of Garden Benches in various park of W No.19 | _ | _ |  | MC | General | Ongoing | 7.91 | 18.5 | 466 dt 09.04.2025 | Y | Y | SDO | N | 76/SE(TIC) 09.05.2025 | 28.05.2025 | Y | Y | 48 29.01.2026 | Glisten | 6.45 | 29.01.2026 | 1 | 28.02.2026 |  | Sh Parveen Singla | N | N | _ |  |  | Ongoing | _ | Inauguration is to be done | _ | _
|  | B&R | B | B4 | East | 28 | Parks | _ | P/F Garden Benches, Open Gym Machines & Children Playing Equipments in W No.28 | _ | _ |  | MC | General | Ongoing | 12.92 | 20.5 | 467 dt 09.04.2025 | Y | Y | SDO | N | 76/SE(TIC) 09.05.2025 | 28.05.2025 | Y | Y | 49 16.02.2026 | Glisten | 10.27 | 16.02.2026 | 1 | 15.03.2026 |  | Sh Parveen Singla | N | N | _ |  |  | Ongoing | _ | Inauguration is to be done | _ | _
|  | B&R | B | B3 | East | 13 | Others | _ | Development of Badminton Court in Banda Bhadur Colony near Shamshanghat W No.13 | _ | _ |  | MC | General | Ongoing | 7.92 | 2.22% | 2429 dt 05.01.2026 | Y | Y | SDO | N | 444/SE(TIC) 07.01.2026 | 19.01.2026 | Y | Y | 50 16.02.2026 | Sachdeva Art Gallery | 7.74 | 16.02.2026 | 1 | 15.03.2026 |  | Sh Parveen Singla | N | N | 70% | 0 | 0 | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B4 | East | 21 | Bituminous | _ | Const.of bituminous road in GRD colony | 1164.63 | 22 |  | MC | General | Ongoing | 49.88 | 19.05% | 3278 dt. 29.11.2024 | Y | Y | XEN | N | 295/SE(TIC) 10.11.2025 | 20.11.2025 | Y | Y | 52 16.02.2026 | Somaya Infrastructure | 40.38 | 16.02.2026 | 5 | 15.07.2026 | 31.10.2026 | Sh Parveen Singla | N | N | 0% |  |  | Ongoing | Work heldup due to upgradation of W/S line | _ | _ | _
|  | B&R | B | B3 | East | 11 | Park | _ | Re-devlopment of New Shastri Nagar Park W No.11 | _ | _ |  | MC | General | Ongoing | 4.7 | 7.89% | 1572 dt 13.10.2025 | Y | Y | SDO | N | 313/SE(TIC) 18.11.2025 | 08.12.2025 | Y | Y | 54 16.02.2026 | Teg Builders | 4.33 | 16.02.2026 | 3 | 15.05.2026 |  | Sh Parveen Singla | N | N | 90% | 0 | 0 | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B4 | East | 19 | I/tiles | _ | P/F Perforated I/tiles on side berms of GRD Colony W NO.19 | 286.59 | 22 |  | MC | Councillor | Ongoing | 24.53 | 30.35% | 1941 dt 13.10.2025 | Y | Y | SDO | N | 313/SE(TIC) 18.11.2025 | 08.12.2025 | Y | Y | 55 16.02.2026 | Navyug Company | 17.08 | 16.02.2026 | 3 | 15.05.2026 |  | Sh Parveen Singla | N | N | 5% |  |  | Ongoing | Work heldup due to upgradation of sewerline. | _ | _ | _
|  | B&R | B |  | East | _ | Bituminous | _ | Upgradation of Gurudwara road urban estate phase 1&2 from Metro road to Jeewan Nagar chowk, Road along budha nallah from NHAI to MC limit , Main Bhadur Ke Road from Sabji Mandi upto MC Limit, Main New Azad Nagar 30' Road from Kainth Property Dealer upto Gaur Property Dealer and Roads of Onkar Vihar. | 7466.16 | 18 |  | Special Assistance Scheme | Special Assistance Scheme | Ongoing | 535.05 | 3.25% | Approved inanticipation by W/Mayor vide dt 20.11.2025 & Regular approval by F&CC 2689 dt 19.02.2026 | Y | Y | CE | N | 316/SE(TIC) 19.11.2025 |  | Y | Y | 60 18.02.2026 | CH Builders Pvt. Ltd. | 517.66 | 18.02.2026 | 3 | 17.05.2026 | 30.09.2026 | Sh Parveen Singla | N | N | 15% |  |  | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B |  |  | _ | Bituminous | _ | Upgradation of Main Metro Road from Jamalpur Chowk to Kangaroo Industry, Jaswant Singh Dental College to Delhi road via Sethi Sweets, Internal Roads of Sec-39, Road from Primary Govt School to NRI Police Station in Sec-39, Main Jain Colony road from Rahon Road to Swastik Enclave and Main Road of Guru Arjun Dev Nagar from GT Road upto Greenland School, Sabji Mandi Road from Chd road to Puda road, EWS colony main road from Jacha Bacha Hospital upto Tajpur road. | 12724.09 | 23 |  | Special Assistance Scheme | Special Assistance Scheme | Ongoing | 718.12 | 4.25% | Approved inanticipation by W/Mayor vide dt 20.11.2025 & Regular approval by F&CC 2690 dt 19.02.2026 | Y | Y | CE | N | 316/SE(TIC) 19.11.2025 |  | Y | Y | 61 20.02.2026 | Kabir Infra Pvt. Ltd. | 687.6 | 20.02.2026 | 3 | 19.05.2026 | 30.09.2026 | Sh Parveen Singla | N | N | 25% | 161.79 |  | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B2 | East | 20 | Bituminous | _ | Const.of bituminous road in Sukhdev Nagar | 884.15 | 25 |  | MC | General | Ongoing | 49.95 | 19.05% | 3280 dt. 29.11.2024 | Y | Y | XEN | N | 295/SE(TIC) 10.11.2025 | 20.11.2025 | Y | Y | 66 09.03.2026 | Somaya Infrastructure | 40.43 | 09.03.2026 | 5 | 08.08.2026 | 31.10.2026 | Sh Parveen Singla | N | N | 5% |  |  | Ongoing | Heldup due to Rainy Season & shortage of Bitumen | _ | _ | _
|  | B&R | B | B3 | East | 7 | I/tiles | _ | P/F I/tiles in street No.5/1 to 5/6 & Links of New Subhash Nagar on Towerline No.5 W No.7 | 1007.93 | 22 |  | MC | General | Ongoing | 78.55 | 35.39% | 1665 dt 13.10.2025 | Y | Y | SE | N | 313/SE(TIC) 18.11.2025 | 08.12.2025 | Y | Y | 67 09.03.2026 | Navyug Company | 50.75 | 09.03.2026 | 5 | 08.08.2026 | 28.08.2026 | Sh Parveen Singla | N | N | 60% | 0 | 0 | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B4 | East | 19 | Park | _ | Renovation of remaining Parks in Sec-39 Block- II W No.19 | _ | _ |  | MC | Councillor | Ongoing | 97.59 | 30.66% | 1974 dt 13.10.2025 | Y | Y | SE | N | 313/SE(TIC) 18.11.2025 | 08.12.2025 | Y | Y | 71 09.03.2026 | Apex Developers | 67.67 | 09.03.2026 | 5 | 08.08.2026 |  | Sh Parveen Singla | N | N | 10% |  |  | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B3 | East | 12 | Parks | _ | Repair & Renovation of Sawtantar Nagar Park in W No.12 | _ | _ |  | MC | General | Ongoing | 18.99 | 13.89% | 1319 dt 11.08.2025 | Y | Y | SDO | N | 438/SE(TIC) 02.01.2026 |  | Y | Y | 72 09.03.2026 | Teg Builders & Varinder Singh Govt Contractor | 16.35 | 09.03.2026 | 3 | 08.06.2026 |  | Sh Parveen Singla | N | N | 70% | 0 | 0 | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B3 | East | 13 | Others | _ | Development of Box Cricket in Banda Bhadur Colony near Shamshanghat W No.13 | _ | _ |  | MC | General | Ongoing | 30.16 | 5.89% | 2430 dt 05.01.2026 | Y | Y | XEN | N | 444/SE(TIC) 07.01.2026 | 19.01.2026 | Y | Y | 75 09.03.2026 | Teg Builders & Varinder Singh Govt Contractor | 28.38 | 09.03.2026 | 4 | 08.07.2026 |  | Sh Parveen Singla | N | N | 50% | 0 | 0 | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B3 | East | 13 | Others | _ | Construction of Entrance Gates for Karamsar Colony & Sutantar Nagar in w no.13. | _ | _ |  | MC | General | Ongoing | 26.34 | 2.89% | 2266, dt 21.11.2025 | Y | Y | XEN | N | 444/SE(TIC) 07.01.2026 | 19.01.2026 | Y | Y | 76 09.03.2026 | Teg Builders & Varinder Singh Govt Contractor | 25.58 | 09.03.2026 | 4 | 08.07.2026 |  | Sh Parveen Singla | N | N | _ | 0 | 0 | Ongoing | _ | Inauguration is to be done | _ | _
|  | B&R | B | B3 | East | 13 | I/tiles | _ | P/Fixing I/tiles in Karamsar Colony & Nalwa Coloiny W No.13 | 1283.23 | 18 |  | MC | Councillor | Ongoing | 83.89 | 36.99% | 2043 dt 13.10.2025 | Y | Y | SE | N | 313/SE(TIC) 18.11.2025 |  | Y | Y | 77 12.03.2026 | Apex Developers | 52.86 | 12.03.2026 | 4 | 11.07.2026 | 04.10.2026 | Sh Parveen Singla | N | N | 20% | 0 | 0 | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B3 | East | 13 | I/tiles | 383067 | P/Fixing I/tiles in streets of Grewal Colony & Raju Colony W No.13 | 770.12 | 19 |  | MC | Councillor | Ongoing | 49.53 | 11.89% | 2261, dt 21.11.2025 | Y | Y | XEN | N | 526/SE(TIC) 12.02.2026 | 23.02.2026 | Y | Y | 09 13.05.2026 | Teg Builders | 43.64 | 13.05.2026 | 4 | 12.09.2026 | 25.10.2026 | Sh Parveen Singla | N | N | _ | 0 | 0 | Ongoing | _ | Inauguration is to be done | _ | _
|  | B&R | B | B3 | East | 13 | I/tiles | 383068 | P/Fixing I/tiles in streets of Heera Vihar & Sutantar Nagar W No.13 | 713.41 | 17 |  | MC | Councillor | Ongoing | 49.8 | 11.89% | 2262, dt 21.11.2025 | Y | Y | XEN | N | 526/SE(TIC) 12.02.2026 | 23.02.2026 | Y | Y | 10 13.05.2026 | Varinder Singh Govt Contractor | 43.88 | 13.05.2026 | 4 | 12.09.2026 | 25.08.2026 | Sh Parveen Singla | N | N | 30% | 0 | 0 | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B4 | East | 19 | RMC | 383072 | Laying RMC in streets of New Kirti Nagar W No.19 | 122.56 | 20 |  | MC | General | Ongoing | 18.07 | 15.89 | 2525 dt 05.02.2026 | Y | Y | SDO | N | 560/SE(TIC) dt 24.02.20226 |  | Y | Y | 11 13.05.2026 | Teg Builders | 15.2 | 13.05.2026 | 3 | 12.08.2026 | 31.08.2026 | Sh Parveen Singla | N | N | 25% |  |  | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B4 | East | 28 | I/tiles | 403395/ 383073 | P/F I/tiles in street of Saini Colony W No.28 | 1061.28 | 17 |  | MC | Councillor | Ongoing | 88.68 | 28.89 | 2528 dt 05.02.2026 | Y | Y | SE | N | 560/SE(TIC) dt 24.02.2026 |  | Y | Y | 12 13.05.2026 | Teg Builders | 63.06 | 13.05.2026 | 5 | 12.10.2026 | 31.12.2026 | Sh Parveen Singla | N | N | _ |  |  | Ongoing | Work heldup due to upgradation of W/S line | _ | _ | _
|  | B&R | B | B4 | East | 19 | Others | 383076 | Const of RCC Boundary wall adj GRD Colony Sec-39 W No.19 | _ | _ |  | MC | General | Ongoing | 24.65 | 5.89 | 2531 dt 05.02.2026 | Y | Y | SDO | N | 560/SE(TIC) dt 24.02.2026 |  | Y | Y | 13 13.05.2026 | Varinder Singh Govt Contractor | 23.5 | 13.05.2026 | 3 | 12.08.2026 |  | Sh Parveen Singla | N | N | 10% |  |  | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B4 | East | 28 | Bituminous | 383078 | Const.of bituminous road of Moti Nagar Block-C W No.28 | 610.67 | 32 |  | MC | Councillor | Ongoing | 65.52 | 5 | 2533 dt 05.02.2026 | Y | Y | SE | N | 560/SE(TIC) dt 24.02.2026 |  | Y | Y | 14 13.05.2026 | Shiva Construction | 62.24 | 13.05.2026 | 5 | 12.10.2026 | 31.10.2026 | Sh Parveen Singla | N | N | _ |  |  | Ongoing | _ | Inauguration is to be done | _ | _
|  | B&R | B | B3 | East | 13 | I/tiles | 383085 | P/Fixing I/tiles in left side streets of Banda Singh Bhadur Colony W No.13 | 1172.87 | 17 |  | MC | General | Ongoing | 88.4 | 39.99 | 2453 dt 05.01.2026 | Y | Y | SE | N | 525/SE(TIC) dt 12.02.2026 |  | Y | Y | 16 13.05.2026 | Varinder Singh Govt Contractor | 53.05 | 13.05.2026 | 6 | 12.11.2026 | 25.10.2026 | Sh Parveen Singla | N | N | 10% | 0 | 0 | Ongoing | Heldup due to upgradation of Sewer line | _ | _ | _
|  | B&R | B | B3 | East | 13 | I/tiles | 383087 | P/Fixing I/tiles in right side streets of Banda Singh Bhadur Colony W No.13 | 832.62 | 20 |  | MC | General | Ongoing | 68.69 | 39.99 | 2454 dt 05.01.2026 | Y | Y | SE | N | 525/SE(TIC) dt 12.02.2026 |  | Y | Y | 17 13.05.2026 | Varinder Singh Govt Contractor | 41.22 | 13.05.2026 | 5 | 12.10.2026 | 15.11.2026 | Sh Parveen Singla | N | N | _ | 0 | 0 | Ongoing | Heldup due to upgradation of Sewer line | _ | _ | _
|  | B&R | B | B3 | East | 13 | I/tiles | 383089 | P/Fixing I/tiles in various Streets of juneja colony W No.13 | 1312.5 | 20 |  | MC | General | Ongoing | 76.4 | 28.64 | 2480 dt 05.01.2026 | Y | Y | SE | N | 525/SE(TIC) dt 12.02.2026 |  | Y | Y | 18 13.05.2026 | Varinder Singh Govt Contractor | 54.52 | 13.05.2026 | 5 | 12.10.2026 | 10.10.2026 | Sh Parveen Singla | N | N | _ | 0 | 0 | Ongoing | _ | Inauguration is to be done | _ | _
|  | B&R | B | B2 | East | 20 | Bituminous | 390829 | Const.of bituminous road Guru Nanak Nagar Bhamian 27' Road | 548.78 | 14 |  | MC | General | Ongoing | 35.74 | 8.35 | 3279 dt. 29.11.2024 | Y | Y | XEN | N | 652/SE(TIC) 27.03.2026 |  | Y | Y | 23 27.05.2026 | Shiva Construction | 32.76 | 27.05.2026 | 5 | 26.10.2026 | 31.08.2026 | Sh Parveen Singla | N | N | 70% |  |  | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B3 | East | 17 | RMC | 383684 | Laying RMC on road connecting Mahavir Jain Colony & from STP pully towards garbage Dump W No.17 | 155.49 | 39.5 |  | MC | General | Ongoing | 54.93 | 10.06 | 2267, dt 21.11.2025 | Y | Y | SE | N | 556/SE(TIC) dt 23.02.2026 | 05.03.2026 | Y | Y | 26 03.08.2026 | Ashok Kumar Sobti | 49.4 | 03.08.2026 | 5 | 02.01.2027 |  | Sh Parveen Singla | N | N | _ | 0 | 0 | Ongoing | _ | Report received from DCFA dt 24.07.2026 Work order to be issued | _ | _
|  | B&R | B | B3 | East | 11& 12 | I/tiles | 390831 | P/Fixing I/tiles in streets of Subhash Nagar adjoining Towerline No.2 & 5 in W No.11 & 12 | 438.41 | 20 |  | MC | General | Ongoing | 29.74 | 23.6 | 2958 dt 25.02.2026 | Y | Y | XEN | N | 624/SE(TIC) 18.03.2026 |  | Y | Y | 27 03.08.2026 | Navyug Company | 22.72 | 03.08.2026 | 4 | 02.12.2026 |  | Sh Parveen Singla | N | N | _ | 0 | 0 | Ongoing | _ | Report received from DCFA dt 24.07.2026 Work order to be issued | _ | _
|  | B&R | B | B2 | Sahnewal | 24 | Parks | _ | Repair & Renovation of park in Village Mundian Kalan W No.24 | _ | _ |  | MC | General | Ongoing | 22.58 | 37.77 | 1805 dt 27.02.2024 | Y | Y | SDO | N | 62/SE(TIC) 12.08.2024 | 28.08.2024 | Y | Y | 65 dt 29.11.2024 | M/s Prince Sharma | 14.05 | 29.11.2024 | 5 | 28.04.2025 |  | Sh Parveen Singla | Y | N | 90% |  |  | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B2 | Sahnewal | 24 | Parks | _ | Repair & Renovation of GK Estate Parks, Mundian Kalan W No.24 | _ | _ |  | MC | General | Ongoing | 35.03 | 39.99 | 1806 dt 27.02.2024 | Y | Y | XEN | N | 62/SE(TIC) 12.08.2024 | 28.08.2024 | Y | Y | 66 dt 29.11.2024 | M/s Prince Sharma | 21.02 | 29.11.2024 | 3 | 28.02.2025 |  | Sh Parveen Singla | Y | N | 90% |  |  | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B2 | Sahnewal | 24 | I/tiles | _ | P/F of I/tiles in Village Mundian Kalan W No.24 | 1146.34 | 15 |  | MC | General | Ongoing | 62.52 | 42.07 | 1792 dt 27.02.2024 | Y | Y | SE | N | 62/SE(TIC) 12.08.2024 | 28.08.2024 | Y | Y | 73 dt 04.12.2024 | Capital Const Co. | 36.22 | 04.12.2024 | 3 | 03.03.2025 | 31.08.2026 | Sh Parveen Singla | Y | N | 70% |  |  | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B4 | Sahnewal | 21 | Parks | _ | Repair & Renovation of LIG, MIG & Sec-38 Parks W No.21 | _ | _ |  | MC | General | Ongoing | 59.36 | 27.27 | 1793 dt 27.02.2024 | Y | Y | SE | N | 62/SE(TIC) 12.08.2024 | 28.08.2024 | Y | Y | 74 dt 04.12.2024 | The Gill Co-Op Diiploma Holder Society Ltd. | 43.17 | 04.12.2024 | 5 | 03.05.2025 |  | Sh Parveen Singla | Y | N | 90% |  |  | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B4 | Sahnewal | 28 | RMC | _ | Const of road by laying RMC (M-30) in Ishwar colony W No.28 | 751.52 | 19 |  | MC | General | Ongoing | 52 | 41.65 | 1807 dt 27.02.2024 | Y | Y | SE | N | 153/SE(TIC) 24.10.2024 | 04.11.2024 | Y | Y | 75 dt 04.12.2024 | Capital Const Co. | 30.34 | 04.12.2024 | 4 | 03.04.2025 | 31.12.2026 | Sh Parveen Singla | Y | N | 0% |  |  | Ongoing | Heldup due to non laying of Sewerline | _ | _ | _
|  | B&R | B | B4 | Sahnewal | 28 | I/tiles | _ | P/F 80mm thick I/Tiles in Balance streets of Prem Nagar & New Durga Colony W No.28 | 827.13 | 21 |  | MC | General | Ongoing | 71.89 | 42.89% | 1795 dt 27.02.2024 | Y | Y | SE | N | 185/SE(TIC) 21.11.2024 | 05.12.2024 | Y | Y | 15 16.04.2025 | T&G Const Co. | 41.06 | 16.04.2025 | 5 | 15.09.2025 | 31.08.2026 | Sh Parveen Singla | Y | N | 50% |  |  | Ongoing | _ | Work was heldup due to upgradation of W/S Line, now same has been laid. Work is in Progress | _ | _
|  | B&R | B | B4 | Sahnewal | 24 | Park | _ | Re-Development of Main Jeevan Nagar Park W No.24 | _ | _ |  | MC | General | Ongoing | 26.72 | 30.4% | 1953 dt 06.03.2024 | Y | Y | XEN | N | 185/SE(TIC) 21.11.2024 | 05.12.2024 | Y | Y | 16 16.04.2025 | Asis Builders | 18.6 | 16.04.2025 | 3 | 15.07.2025 |  | Sh Parveen Singla | Y | N | 80% |  |  | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B4 | Sahnewal | 28 | Park | _ | Re-Development of Park Backside Gov.Sen.Sec School Dhandari Khurd Ludhiana W No.28 | _ | _ |  | MC | General | Ongoing | 25.74 | 33.99% | 1808 dt 27.02.2024 | Y | Y | XEN | N | 185/SE(TIC) 21.11.2024 | 05.12.2024 | Y | Y | 17 16.04.2025 | Apex Developers | 16.99 | 16.04.2025 | 3 | 15.07.2025 |  | Sh Parveen Singla | Y | N | 70% |  |  | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B2 | Sahnewal | 22 | I/tiles | _ | P/F I/tiles in streets of Jyoti Colony | 349.09 | 19 |  | MC | General | Ongoing | 23.07 | 34.99 | 459 dt 09.04.2025 | Y | Y | SDO | N | 75/SE(TIC) 09.05.2025 | 28.05.2025 | Y | Y | 26 15.01.2026 | Capital Const Co. | 15 | 15.01.2026 | 2 | 14.03.2026 | 31.10.2026 | Sh Parveen Singla | N | N | 5% |  |  | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B2 | Sahnewal | 22 | Park | _ | Renovation of Tikoni park | _ | _ |  | MC | General | Ongoing | 15.02 | 24.99% | 3275 dt. 29.11.2024 | Y | Y | SDO | N | 295/SE(TIC) 10.11.2025 | 20.11.2025 | Y | Y | 57 16.02.2026 | Varinder Singh Govt Contractor and Maa Chintpurni Const | 11.27 | 16.02.2026 | 3 | 15.05.2026 |  | Sh Parveen Singla | N | N | _ |  |  | Ongoing | _ | Inauguration is to be done | _ | _
|  | B&R | B | B4 | Sahnewal | 21 | Park | _ | Renovation of park in Urban Estate Phase-II on Chd Road | _ | _ |  | MC | General | Ongoing | 105.91 | 34.1% | 3367 dt. 05.12.2024 | Y | Y | CE | N | 216/SE(TIC) 12.09.2025 | 30.09.2025 | Y | Y | 59 16.02.2026 | Ram Parkash Kakkar | 69.79 | 16.02.2026 | 6 | 15.08.2026 |  | Sh Parveen Singla | N | N | 30% |  |  | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B2 | Sahnewal | 22 | RMC | _ | Laying RMC in streets of Village Kuliewal W No.22 | 911.28 | 10 |  | MC | Councillor | Ongoing | 86.8 | 38.7% | 1956 dt 13.10.2025 | Y | Y | SE | N | 313/SE(TIC) 18.11.2025 | 08.12.2025 | Y | Y | 74 09.03.2026 | KS Constructions | 53.21 | 09.03.2026 | 5 | 08.08.2026 | 31.10.2026 | Sh Parveen Singla | N | N | 30% |  |  | Ongoing | Heldup due to non laying of W/s line | _ | _ | _
|  | B&R | B | B2 | Sahnewal | 22 | RMC | _ | Laying RMC in streets of Jamalpur Awana W No.22 | 621.95 | 11 |  | MC | Councillor | Ongoing | 69.91 | 39.99% | 1957 dt 13.10.2025 | Y | Y | SE | N | 313/SE(TIC) 18.11.2025 | 08.12.2025 | Y | Y | 78 12.03.2026 | Apex Developers | 41.95 | 12.03.2026 | 5 | 11.08.2026 | 31.10.2026 | Sh Parveen Singla | N | N | 45% |  |  | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B2 | Sahnewal | 24 | Bituminous | _ | Const of Bituminous roads in GK Estate main Road | 3115.85 | 19 |  | MC | General | Ongoing | 117.76 | 5 | 3368 dt. 05.12.2024 | Y | Y | CE | N | 113/SE(TIC) 27.06.2025 | 15.07.2025 | Y | Y | 80 20.03.2026 | CH Builders Pvt. Ltd. | 111.87 | 20.03.2026 | 6 | 19.09.2026 | 31.10.2026 | Sh Parveen Singla | N | N | 15% |  |  | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B4 | Sahnewal | 25 | I/tiles | _ | P/F 80mm thick I/Tiles in Shiv colony | 1680.18 | 17 |  | MC | General | Ongoing | 112.48 | 41.72 | 1784 dt 27.02.2024 | Y | Y | CE | N | 195/SE(TIC) 22.11.2024 | 16.12.2024 | Y | Y | 85 24.03.2026 | T&G Const Co. | 65.55 | 24.03.2026 | 6 | 23.09.2026 | 15.10.2026 | Sh Parveen Singla | N | N | 40% |  |  | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B4 | Sahnewal | 21 | Bituminous | 383060 | Const of Bituminous Road of Jeewan Nagar & Guru Bag Colony Main Road of W No.21 | 945.73 | 20 |  | MC | General | Ongoing | 48.52 | 5.3 | 2529 dt 05.02.2026 | Y | Y | XEN | N | 560/SE(TIC) dt 24.02.2026 |  | Y | Y | 20 13.05.2026 | Maruti Const Co. | 45.95 | 13.05.2026 | 4 | 12.09.2026 | 31.10.2026 | Sh Parveen Singla | N | N | _ |  |  | Ongoing | _ | Inauguration is to be done | _ | _
|  | B&R | B | B4 | Sahnewal | 21 | Parks | 405451 | Renovation and Development of various parks Urban Estate Phase-II, Jamalpur of W No.21 | _ | _ |  | MC | Councillor | Ongoing | 78.46 | 24.9 | 2497 dt 05.01.2026 | Y | Y | SE | N | 525/SE(TIC) dt 12.02.2026 |  | Y | Y | 21 13.05.2026 | Ram Parkash Kakkar | 58.92 | 13.05.2026 | 5 | 12.10.2026 |  | Sh Parveen Singla | N | N | _ |  |  | Ongoing | _ | Inauguration to be done | _ | _
|  | B&R | B | B2 | Sahnewal | 24 | Bituminous | 390830 | Const of Bituminous Road from Chandigarh Road to GTB Nagar Near Jassal Factory | 341.46 | 24 |  | MC | General | Ongoing | 15.02 | 8.35 | 3276 dt. 29.11.2024 | Y | Y | SDO | N | 652/SE(TIC) 27.03.2026 |  | Y | Y | 24 27.05.2026 | Shiva Construction | 13.77 | 27.05.2026 | 3 | 26.08.2026 | 31.08.2026 | Sh Parveen Singla | N | N | 90% |  |  | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B4 | Sahnewal | 21 | Bituminous | 390836 | Const of Bituminous Road of Guru Bag Colony W No.21 | 3136.59 | 18 |  | MC | General | Ongoing | 99.8 | 17.27 | 3052 dt 25.02.2026 | Y | Y | SE | N | 624/SE(TIC) 18.03.2026 |  | Y | Y | 26 01.06.2026 | Rajesh Kumar Sood | 82.56 | 01.06.2026 | 5 | 30.11.2026 | 31.10.2026 | Sh Parveen Singla | N | N | 5% |  |  | Ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | B2 | Sahnewal | 24 | I/tiles | 389249 | P/F I/tiles in streets of Hari Nagar | 384.15 | 23 |  | MC | MC | Ongoing | 35.09 | 38.55 | 3277 dt. 29.11.2024 | Y | Y | XEN | N | 224/SE(TIC) 17.09.2025 |  | Y | Y | 28 03.08.2026 | Godwyn Infra | 21.56 | 03.08.2026 | 3 | 02.11.2026 |  | Sh Parveen Singla | N | N | _ |  |  | Ongoing | _ | Inauguration to be done | _ | _
|  | B&R | B | B4 | Sahnewal | 21 | Others | 390834 | P/F of RCC Garden Benches in various park of W No.21 | _ | _ |  | MC | Councillor | Ongoing | 2.79 | 5.99 | 2530 dt 05.02.2026 | Y | Y | SDO | N | 653/SE(TIC) 27.03.2026 |  | Y | Y | 29 03.08.2026 | Maa Chintpurni Construction | 2.62 | 03.08.2026 | 1 | 02.09.2026 |  | Sh Parveen Singla | N | N | _ |  |  | Ongoing | _ | Inauguration to be done | _ | _
|  | B&R | B | B4 | Sahnewal | 28 | RMC | _ | Const of Road by laying RMC in Prem Nagar W No.28 | 2600.3 | 21 |  | MDF | MDF | ongoing | 191.52 | 32.87 | 417 dt 31.08.2023 | Y | Y | CE | N | 119/SE/TIC 01.09.2023 |  | Y | Y | 23 dt 20.10.2023 | M/s Capital Const Co. | 128.57 | 20.10.2023 | 6 | 19.04.2024 | 31.10.2026 | Sh Parveen Singla | Y | N | 55% |  |  | ongoing | Work heldup due to upgradation of W/s & Sewer lines in the balance streets | _ | _ | _
|  | B&R | B | B4 | Sahnewal | 28 | RMC | _ | Laying RMC in street of New Durga Colony W No.28 | 2359.15 | 20 |  | MDF | MDF | ongoing | 196.63 | 8.05% | 419 dt 31.08.2023 | Y | Y | CE | N | 178/SE/TIC 03.10.2023 |  | Y | Y | 44A & 44B dt 20.11.2023 | M/s Glisten and Ashok Kumar Sobti (50%-50% allotted) | 180.8 | 20.11.2023 | 6 | 19.05.2024 | 31.10.2026 | Sh Parveen Singla | Y | N | 55% |  |  | ongoing | Work heldup due to upgradation of W/s lines in the balance streets | _ | _ | _
|  | B&R | B | B3 | East | 15 | Bitumionus | _ | Const of Bituminous Road on Mata Karam Kaur Road W No.15 | 698.17 | 19 |  | MDF | MDF | ongoing | 25 | 1.5 | 408 dt 31.08.2023 | Y | Y | SDO | N | 216/SE/TIC 30.10.2023 |  | Y | Y | 47 dt 20.11.2023 | Shiva Construction | 24.62 | 20.11.2023 | 3 | 19.02.2024 | 31.10.2026 | Sh Parveen Singla | Y | N | 20% | 0 | 0 | ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | Focal Point | Sahnewal |  | Bitumen | _ | Const of Various Bituminous Roads in Phase - V & VII Focal Point Ludhiana (Roter Kanda towards Jiwan Nagar Chown, Disposal Rd.and E-654) & (E-773 to E-778 and Roter Kanda Rd to Fortis Hospital Chd Rd) | 2425.61 | 32 |  | SIDBI/MC | SIDBI/MC | ongoing | 158.55 | 7.19 | 1095 dt 27.10.2023 | Y | Y | CE | N | 363/SE(TIC) 10.12.2025 |  | Y | Y | 08 13.05.2026 | Maruti Const Co. | 147.15 | 13.05.2026 | 6 | 12.11.2026 | 31.10.2026 | Sh Parveen Singla | N | N | 15% |  |  | ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | Focal Point | Sahnewal |  | RMC | _ | Const of Various Roads by laying RMC(M-40) in Phase-V,VI,VII & VIII Focal Point Ludhiana (Satya Industry Phase 5, D-51 to D-58 )(A13E & A13A) (Opp. RCJ Auto Forge E-756 and C-202 A to C-203 C(E-701 to E-706 | 737.2 | 28 |  | SIDBI/MC | SIDBI/MC | ongoing | 136.09 | 41.99 | 1096 dt 27.10.2023 | Y | Y | CE | N | 195/SE(TIC) 22.11.2024 | 16.12.2024 | Y | Y | 30 15.01.2026 | Apex Developers | 78.95 | 15.01.2026 | 6 | 14.07.2026 | 31.10.2026 | Sh Parveen Singla | N | N | 45% |  |  | ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | Focal Point | East |  | Parks | _ | Development of various Parks in Phase-I Focal Point (OPP Kay Jay Forjing and Opp E-2) | _ | _ |  | SIDBI/MC | SIDBI/MC | ongoing | 53.25 | 28.89 | 362 dt 26.03.2025 | Y | Y | SE | N | 220/SE(TIC) 12.09.2025 | 24.09.2025 | Y | Y | 34 15.01.2026 | Teg Builders | 37.87 | 15.01.2026 | 5 | 14.06.2026 |  | Sh Parveen Singla | N | N | 60% |  |  | ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | Focal Point | East |  | Parks | _ | Development of various Parks in Phase-IV Focal Point (OPP E-90 and Opp E-132) | _ | _ |  | SIDBI/MC | SIDBI/MC | ongoing | 78.08 | 28.89 | 363 dt 26.03.2025 | Y | Y | SE | N | 220/SE(TIC) 12.09.2025 | 24.09.2025 | Y | Y | 35 15.01.2026 | Teg Builders | 55.52 | 15.01.2026 | 5 | 14.06.2026 |  | Sh Parveen Singla | N | N | 90% |  |  | ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | Focal Point | East |  | Parks | _ | Development of various Parks in Phase-IVA Focal Point (Opp D-145, Opp D-148 and Opp D-152) | _ | _ |  | SIDBI/MC | SIDBI/MC | ongoing | 8.05 | 21.26 | 364 dt 26.03.2025 | Y | Y | SDO | N | 220/SE(TIC) 12.09.2025 | 24.09.2025 | Y | Y | 29 15.01.2026 | Varinder Singh Contractor | 6.34 | 15.01.2026 | 3 | 14.04.2026 |  | Sh Parveen Singla | N | N | 80% |  |  | ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | Focal Point | Sahnewal |  | Parks | _ | Construction of Various Parks of Focal Point Phase-V , Ludhiana (D-114, C-86,B-37, C-115, D-130) | _ | _ |  | SIDBI/MC | SIDBI/MC | ongoing | 217.72 | 28.1 | 365 dt 26.03.2025 | Y | Y | CE | N | 222/SE(TIC) 17.09.2025 | 08.10.2025 | Y | Y | 36 15.01.2026 | RK Const Co. | 156.54 | 15.01.2026 | 6 | 14.07.2026 |  | Sh Parveen Singla | N | N | 30% |  |  | ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | Focal Point | Sahnewal |  | Parks | _ | Construction of Various Parks of Focal Point Phase-VI , Ludhiana (Park No.1,2,4,6,7 & 8) | _ | _ |  | SIDBI/MC | SIDBI/MC | ongoing | 348.82 | 18.2 | 366 dt 26.03.2025 | Y | Y | CE | N | 222/SE(TIC) 17.09.2025 | 08.10.2025 | Y | Y | 37 15.01.2026 | Navyug Company | 285.33 | 15.01.2026 | 6 | 14.07.2026 |  | Sh Parveen Singla | N | N | 5% |  |  | ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | Focal Point | Sahnewal |  | Parks | _ | Construction of Various Parks of Focal Point Phase-VII Ludhiana (Park No.2,3,4,5 & 6) | _ | _ |  | SIDBI/MC | SIDBI/MC | ongoing | 123.11 | 28.99 | 367 dt 26.03.2025 | Y | Y | CE | N | 222/SE(TIC) 17.09.2025 | 08.10.2025 | Y | Y | 38 15.01.2026 | RK Const Co. | 87.42 | 15.01.2026 | 6 | 14.07.2026 |  | Sh Parveen Singla | N | N | 25% |  |  | ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | Focal Point | Sahnewal |  | Parks | _ | Development of various Parks in Phase-VIII Focal Point (Adj F-170 & F171,Adj F-155 & F156 , Adj F-179 & F176, Adj F-194 & F195 and Opp F-251) | _ | _ |  | SIDBI/MC | SIDBI/MC | ongoing | 168.7 | 23.51 | 368 dt 26.03.2025 | Y | Y | CE | N | 222/SE(TIC) 17.09.2025 | 08.10.2025 | Y | Y | 39 15.01.2026 | KS Constructions | 129.04 | 15.01.2026 | 6 | 14.07.2026 |  | Sh Parveen Singla | N | N | 30% |  |  | ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | Focal Point | Sahnewal |  | Parks | _ | Repair & Renovation of various Parks in 34 Acre Scheme Focal Point (Park Opp F-309, Opp K-312) | _ | _ |  | SIDBI/MC | SIDBI/MC | ongoing | 25.32 | 31.26 | 369 dt 26.03.2025 | Y | Y | XEN | N | 193/SE(TIC) 02.09.2025 |  | Y | Y | 31 15.01.2026 | Varinder Singh Contractor | 17.4 | 15.01.2026 | 4 | 14.05.2026 |  | Sh Parveen Singla | N | N | 90% |  |  | ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | Focal Point | East | _ | Parks | _ | Development of Green Belt along Surpal cycle Road Phase-I Focal Point | _ | _ |  | 50%MDF & 50%MC | 50%MDF & 50%MC | ongoing | 146.06 | 18.2 | 2166 dt 13.10.2025 | Y | Y | CE | N | 379/SE(TIC) dt 15.12.2025 |  | Y | Y | 01 10.04.2026 | Navyug Company | 119.48 | 10.04.2026 | 6 | 09.10.2026 |  | Sh Parveen Singla | N | N | 10% |  |  | ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | Focal Point | East | _ | Parks | _ | Const of Green Belt on Sanatan Dharam Mandir Road Phase-III Focal Point Ludhiana | _ | _ |  | 50%MDF & 50%MC | 50%MDF & 50%MC | ongoing | 79.02 | 32.2 | 2164 dt 13.10.2025 | Y | Y | SE | N | 241/SE(TIC) dt 03.10.2025 | 06.11.2025 | Y | Y | 40 15.01.2026 | Ram Parkash Kakkar | 53.58 | 15.01.2026 | 4 | 14.05.2026 |  | Sh Parveen Singla | N | N | 20% |  |  | ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | Focal Point | East | _ | Parks | _ | Re-Development of Green Belts & Parks near E-76 to E-92, E-93 to E-106, E-107 to E-145 & E-21, E-173 & E-190 in Phase-IV Focal Point Ludhiana | _ | _ |  | 50%MDF & 50%MC | 50%MDF & 50%MC | ongoing | 99.85 | 27.99 | inanticipation by W Mayor dt 03.10.2025 & regular approval by F&CC vide reso No.2167 dt 13.10.2025 | Y | Y | SE | N | 241/SE(TIC) dt 03.10.2025 | 06.11.2025 | Y | Y | 41 15.01.2026 | Apex Developers | 71.9 | 15.01.2026 | 5 | 14.06.2026 |  | Sh Parveen Singla | N | N | 5% |  |  | ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | Focal Point | East | _ | RMC | _ | Laying RMC along Kangaroo Industry & Upgradation of Junction Near BJ Computer Kanda on Metro Road Phase-IV Focal Point Ludhiana | 609.15 | 27 |  | 50%MDF & 50%MC | 50%MDF & 50%MC | ongoing | 117.69 | 37.8 | inanticipation approval of F&CC by W/Mayor vide dt 03.10.2025 & Regular approval by F&CC vide No.2159 dt 13.10.2025 | Y | Y | CE | N | 241/SE(TIC) dt 03.10.2025 | 13.11.2025 | Y | Y | 02 10.04.2026 | LRY Labour Contractor | 73.2 | 10.04.2026 | 5 | 09.10.2026 | 31.10.2026 | Sh Parveen Singla | N | N | 80% |  |  | ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | Focal Point | Sahnewal | _ | RMC | _ | Widening of Main Focal point Road by laying RMC(M-40) from Railwayline to Metro Tyre, Phase V Focal Point Ludhiana | 1128.05 | 30 |  | 50%MDF & 50%MC | 50%MDF & 50%MC | ongoing | 427.18 | 24.99 | inanticipation approval of F&CC by W/Mayor vide dt 15.12.2025 & Regular approval by F&CC vide No.2491 dt 05.01.2026 | Y | Y | CE | N | 7/SE(TIC) dt 01.04.2026 | 23.04.2026 | Y | Y | _ | LRY Labour Contractor | 320.43 | _ | 6 | _ |  | Sh Parveen Singla | N | N | _ |  |  | ongoing | _ | _ | _ | _
|  | B&R | B | Focal Point | Sahnewal | _ | RMC | _ | Const of road by laying RMC from Rishi Raj D-40 to Udehra Mechanical Works and other various locations in Focal Point Phase V, Ludhiana . | 1038.11 | 24 |  | 50%MDF & 50%MC | 50%MDF & 50%MC | ongoing | 151.9 | 37.8 | inanticipation approval of F&CC by W/Mayor vide dt 03.10.2025 & Regular approval by F&CC vide No. 2161 dt 13.10.2025 | Y | Y | CE | N | 241/SE(TIC) dt 03.10.2025 | 13.11.2025 | Y | Y | 03 10.04.2026 | LRY Labour Contractor | 94.48 | 10.04.2026 | 6 | 09.10.2026 | 31.10.2026 | Sh Parveen Singla | N | N | 10% |  |  | ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | Focal Point | Sahnewal | _ | Bituminous | _ | Widening of Road from Jeewan Nagar Chowk upto Junction of Akal Spring Road, Phase-V and laying RMC in links between C-215 & C-216 near Dainik Jagran Road and Rectification of level at various Junctions in Focal Point, Ludhiana. | 771.34 | 22 |  | 50%MDF & 50%MC | 50%MDF & 50%MC | ongoing | 169.46 | 37.8 | inanticipation approval of F&CC by W/Mayor vide dt 03.10.2025 & Regular approval by F&CC vide No.2158 dt 13.10.2025 | Y | Y | CE | N | 241/SE(TIC) dt 03.10.2025 | 13.11.2025 | Y | Y | 04 10.04.2026 | LRY Labour Contractor | 105.4 | 10.04.2026 | 6 | 09.10.2026 | 31.10.2026 | Sh Parveen Singla | N | N | 20% |  |  | ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | Focal Point | Sahnewal | _ | Parks | _ | Development of Green Belt From Jeewan Nagar Road to Rotar Kanda Phase-V Focal Point Ludhiana (Park No.1,2,3, 4,5 & 6) | _ | _ |  | 50%MDF & 50%MC | 50%MDF & 50%MC | ongoing | 173.65 | 21.89 | 2165 dt 13.10.2025 | Y | Y | CE | N | 241/SE(TIC) dt 03.10.2025 | 13.11.2025 | Y | Y | 62 09.03.2026 | Navyug Co. | 135.64 | 09.03.2026 | 7 | 08.10.2026 |  | Sh Parveen Singla | N | N | 5% |  |  | ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | Focal Point | Sahnewal | _ | Parks | _ | Re-Development of Green Belts & Parks near D-119, C-207 C-82, B-37, D-42 D-51 & D-70 in Phase-V Focal Point Ludhiana (Park No.12,13,15,18,21 & 22) | _ | _ |  | 50%MDF & 50%MC | 50%MDF & 50%MC | ongoing | 215.85 | 18.83 | 2168 dt 13.10.2025 | Y | Y | CE | N | 379/SE(TIC) dt 15.12.2025 |  | Y | Y | 05 10.04.2026 | Navyug Company | 175.21 | 10.04.2026 | 6 | 09.10.2026 |  | Sh Parveen Singla | N | N | 5% |  |  | ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | Focal Point | Sahnewal | _ | Parks | _ | Re-Development of Green Belts & Parks near D-190d, E-362 & E-393 in Phase-VI Focal Point Ludhiana (Park No.9,10,11 & 12) | _ | _ |  | 50%MDF & 50%MC | 50%MDF & 50%MC | ongoing | 99.41 | 31.6 | 2169 dt 13.10.2025 | Y | Y | SE | N | 241/SE(TIC) dt 03.10.2025 | 06.11.2025 | Y | Y | 42 15.01.2026 | Ram Parkash Kakkar | 68 | 15.01.2026 | 4 | 14.05.2026 |  | Sh Parveen Singla | N | N | 5% |  |  | ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | Focal Point | Sahnewal | _ | Parks | _ | Re-Development of Green Belts & Parks near E-581, E-626 & C-202A in Phase-VII Focal Point Ludhiana (Park No.2 & 3) | _ | _ |  | 50%MDF & 50%MC | 50%MDF & 50%MC | ongoing | 198.84 | 19.59 | 2170 dt 13.10.2025 | Y | Y | CE | N | 241/SE(TIC) dt 03.10.2025 | 13.11.2025 | Y | Y | 79 12.03.2026 | RK Const Co. | 159.89 | 12.03.2026 | 8 | 11.11.2026 |  | Sh Parveen Singla | N | N | 65% |  |  | ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | Focal Point | Sahnewal | _ | Bituminous | _ | Const of mettaled Road Opp ESI Dispensery Phase - V and Residential pocket Phase VIII Focal Point, Ludhiana. | 1737.8 | 20 |  | 50%MDF & 50%MC | 50%MDF & 50%MC | ongoing | 147.05 | 29.5 | inanticipation approval of F&CC by W/Mayor vide dt 03.10.2025 & Regular approval by F&CC vide No.2160 dt 13.10.2025 | Y | Y | CE | N | 241/SE(TIC) dt 03.10.2025 | 13.11.2025 | Y | Y | 06 10.04.2026 | Somaya Infrastructures | 103.67 | 10.04.2026 | 6 | 09.10.2026 | 31.10.2026 | Sh Parveen Singla | N | N | 80% |  |  | ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | Focal Point | Sahnewal | _ | Parks | _ | Re-Development of Parks near C-246, C-256, 164 & 241 & Residential Pocket in Phase-VIII (Park No.2,3,6 & 9) & Parks in 34 Acre Scheme Focal Point Ludhiana (Park No.2) | _ | _ |  | 50%MDF & 50%MC | 50%MDF & 50%MC | ongoing | 113.02 | 9 | 2171 dt 13.10.2025 | Y | Y | CE | N | 379/SE(TIC) dt 15.12.2025 |  | Y | Y | 07 10.04.2026 | Ashok Kumar Sobti | 102.85 | 10.04.2026 | 8 | 09.12.2026 |  | Sh Parveen Singla | N | N | 5% |  |  | ongoing | _ | Work is in Progress | _ | _
|  | B&R | B | Focal Point | East & Sahnewal | _ | Others | _ | Providing & Fixing of Sign Boards in different areas of Focal Point Ludhiana | _ | _ |  | 50%MDF & 50%MC | 50%MDF & 50%MC | Tenders Reinvited | 176.17 | _ | 2162 dt 13.10.2025 | Y | Y | CE | N | _ |  | N | N | _ | _ | _ | _ | _ |  |  | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Reinvited | _ | Tenders Reinvited | _ | _
|  | B&R | B | Focal Point | East & Sahnewal | _ | Others | _ | P/L Road Marking with Thermoplastic in different areas of Focal Point Ludhiana | _ | _ |  | 50%MDF & 50%MC | 50%MDF & 50%MC | Tenders Reinvited | 155.13 | _ | 2163 dt 13.10.2025 | Y | Y | CE | N | _ |  | N | N | _ | _ | _ | _ | _ |  |  | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Reinvited | _ | Tenders Reinvited | _ | _
|  | B&R | B | B3 | East | 17 | RMC | 401521 | Laying RMC from Main Tibba road upto Mahavir Jain Colony W No.17 | 466.46 | 27 |  | MC | General | Workorder to be issued | 114.51 | 33 | 3316, dt 25.02.2026 | Y | Y | SE | Y | 7/SE(TIC) 01.04.2026 | 23.04.2026 | Y | Y | _ | Capital const Co. | 76.72 | _ | 6 |  | 25.11.2026 | Sh Parveen Singla | N | N | _ | _ | _ | Workorder to be issued | _ | Heldup due to non laying of Sewerline (Sent to DCFA for report) | _ | _
|  | B&R | B | B4 | East | 26 | Parks | 390837 | Upgradation of Park Backside lovely sweets in HL Colony W No.26 | _ | _ |  | MC | General | Workorder to be issued | 23.03 | 16.54 | 3137 dt 25.02.2026 | Y | Y | SDO | Y | 624/SE(TIC) 18.03.2026 |  | Y | Y | _ | Asis Builders | 19.22 | _ | 3 |  |  | Sh Parveen Singla | N | N | _ | _ | _ | Workorder to be issued | _ | Report obtained from DCFA dt 29.07.2026 As per decision of F&CC vide Reso No. 3876 dt 15.06.2026 workorder to be issued after taking NOC from GALADA & has been approved | _ | _
|  | B&R | B | B2 | Sahnewal | 22 | RMC | 390212 | P/L RMC(M-30) in Streets of Bank Colony W. No. 22 | 821.65 | 20 |  | MC | General | Workorder to be issued | 65.95 | 38.7 | 3080 dt 25.02.2026 | Y | Y | SE | Y | 624/SE(TIC) 18.03.2026 |  | Y | Y | _ | LRY Labour Contractor | 40.43 | _ | 6 |  | 31.12.2026 | Sh Parveen Singla | N | N | _ | _ | _ | Workorder to be issued | _ | W/ Mayor has approved the case dt 14.05.2026 inanticipation of approval by F&CC. For regular approval, case was sent to F&CC, as per decision of F&CC vide Reso No.3926 dt 15.06.2026. To be putup in next meeting of F&CC. Report obtained from DCFA dt 29.07.2026 & Sent to JC(V) Sir dt 29.07.2026 for Regular Approval Workorder to be issued only after connections(W/s & Sewerage) of House holds | _ | _
|  | B&R | B | B2 | Sahnewal | 22 | I/tiles | 390233 | P/F 80mm Thick I/Tiles in Streets of Ganpati Vihar & Ahloowalia Colony W. No. 22 | 794.21 | 28 |  | MC | General | Workorder to be issued | 94.5 | 28.77 | 3082 dt 25.02.2026 | Y | Y | SE | Y | 624/SE(TIC) 18.03.2026 |  | Y | Y | _ | JP Builders | 67.31 | _ | 6 |  |  | Sh Parveen Singla | N | N | _ | _ | _ | Workorder to be issued | _ | W/ Mayor has approved the case dt 14.05.2026 inanticipation of approval by F&CC. For regular approval, case was sent to F&CC, as per decision of F&CC vide Reso No.3960 dt 15.06.2026. To be putup in next meeting of F&CC. Report obtained from DCFA dt 16.07.2026 & sent to JC(V) sir dt 29.07.2026 for regular approval Workorder to be issued only after laying of S/w line on Main Road (Sarpanch Colony | _ | _
|  | B&R | B | B3 | East | 16& 29 | Others | _ | Renovation of Bus Workshop of Municipal Corporation on Tajpur road Ludhiana | _ | _ |  | MC | MC | Tenders Received | 123.35 | 27.5% | 1359 dt 30.11.2023 | Y | Y | CE | Y | 35/SE(TIC) 10.07.2024 |  | Y | Y | _ | Glisten | 89.43 | _ |  |  |  | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Received | _ | 1122, dt 11.08.2025 Workorder to be issued | _ | _
|  | B&R | B | B4 | East | 19 | I/tiles | _ | P/F Perforated I/tiles on side berms of Sec-39 Phase-I | 1829.27 | 15 |  | Sponj City | Sponj City | Tenders Received | 99.79 | 35% | Approved inanticipation by W/Mayor vide dt 28.11.2025 & Regular approval by F&CC2692 dt 19.02.2026 | Y | Y | SE | Y | 339/SE(TIC) 01.12.2025 | 15.12.2025 | Y | Y | _ | Dynamic Tiles | 64.86 | _ | 4 |  |  | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Received | _ | 2767 dt 19.02.2026 Workorder to be issued after availability of funds | _ | _
|  | B&R | B | B4 | East | 19 | I/tiles | _ | P/F Perforated I/tiles on side berms of Sec-39 Phase-II | 1224.39 | 15 |  | Sponj City | Sponj City | Tenders Received | 89.81 | 33.08% | Approved inanticipation by W/Mayor vide dt 28.11.2025 & Regular approval by F&CC 2693 dt 19.02.2026 | Y | Y | SE | Y | 339/SE(TIC) 01.12.2025 | 15.12.2025 | Y | Y | _ | Glisten | 60.1 | _ | 4 |  |  | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Received | _ | 2768 dt 19.02.2026 Workorder to be issued after availability of funds | _ | _
|  | B&R | B | B3 | East | 7 | Others | 380030 | Providing & Fixing of Sign Boards in different areas of W No.07 | _ | _ |  | MC | General | Tenders Received | 7.19 | 25 | 1662 dt 13.10.2025 | Y | Y | SDO | Y | 556/SE(TIC) dt 23.02.2026 | 05.03.2026 | Y | Y | _ | Glisten | 5.39 | _ | 1 |  |  | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Received | _ | Report obtained from DCFA dt 24.07.2026 and Agenda sent to Supdt Agenda dt 28.07.2026 | _ | _
|  | B&R | B | B4 | East | 26 | Parks | 405451 | Renovation and Development of various parks Urban Estate Phase-I,Jamalpur of W No.26 | _ | _ |  | MC | Councillor | Tenders Received | 145.95 | 24.95 | 3060 dt 25.02.2026 | Y | Y | SE | Y | 7/SE(TIC) 01.04.2026 | 23.04.2026 | Y | Y | _ | Ram Parkash Kakkar | 109.54 | _ | 6 |  |  | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Received | _ | Report received from DCFA dt 29.07.2026 & Sent to JC(V) Sir dt 30.07.2026 for approval of tenders | _ | _
|  | B&R | B | B3 | East | 15 | RMC | 405432 | Laying RMC from Dump site upto MC Limit on Kakka Village W No.15 | 801.83 | 22 |  | MC | General | Tenders Received | 159.5 | 27.33 | 3077, dt 25.02.2026 | Y | Y | CE | Y | 7/SE(TIC) 01.04.2026 | 23.04.2026 | Y | Y | _ | Rajesh Kumar Sood | 115.91 | _ | 6 |  |  | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Received | _ | Report received from DCFA dt 29.07.2026 & Sent to JC(V) Sir dt 30.07.2026 for approval of tenders | _ | _
|  | B&R | B | B3 | East | 7 | I/tiles | 405433 | P/Fixing I/tiles in various Streets of New Sarwan Park W No.07 | 2106.4 | 20 |  | MC | General | Tenders Received | 144.39 | 25 | 3084, dt 25.02.2026 | Y | Y | CE | Y | 7/SE(TIC) 01.04.2026 | 23.04.2026 | Y | Y | _ | Varinder Singh Govt Contractor | 108.29 | _ | 6 |  |  | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Received | _ | Report received from DCFA dt 29.07.2026 & Sent to JC(V) Sir dt 30.07.2026 for approval of tenders 149.07=144.39+4,67,582/- royality | _ | _
|  | B&R | B | B2 | East | 20 | I/tiles | 405435 | P/L Interlocking Tiles in Streets of Preet Nagar near Central Jail W. No. 20 | 1364.02 | 16 |  | MC | General | Tenders Received | 101.09 | 27.99 | 3172, dt 25.02.2026 | Y | Y | CE | Y | 7/SE(TIC) 01.04.2026 | 23.04.2026 | Y | Y | _ | Apex Developers | 72.79 | _ | 6 |  |  | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Received | _ | Report received from DCFA dt 24.07.2026 & sent to JC(V) Sir dt 28.07.2026 for approval of tenders | _ | _
|  | B&R | B | B3 | East | 15 | I/tiles | 413292 | P/Fixing I/tiles in different streets of W No.15 | 1096.34 | 20 |  | MC | Councillor | Tenders Received | 82.23 | 21.99 | 2956, dt 25.02.2026 | Y | Y | SE | Y | 100/SE(TIC) 07.05.2026 |  | Y | Y | _ | Apex Developers | 64.15 | _ |  |  |  | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Received | _ | Report received from DCFA dt 29.07.2026 & Sent to JC(V) Sir dt 30.07.2026 for approval of tenders 82.82=82.23+Royality Rs. 59,086/- | _ | _
|  | B&R | B | B3 | East | 7 | I/tiles | 413301 | P/Fixing I/tiles in various Streets of Chanderlok Colony & Indra Colony in W No.07 | 1260.37 | 20 |  | MC | Councillor | Tenders Received | 80.81 | 25.55 | 3061, dt 25.02.2026 | Y | Y | SE | Y | 100/SE(TIC) 07.05.2026 |  | Y | Y | _ | Capital Const Co. | 60.16 | _ |  |  |  | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Received | _ | Report received from DCFA dt 29.07.2026 & Sent to JC(V) Sir dt 30.07.2026 for approval of tenders 81.47=80.81+ Royality Rs. 65,662/- | _ | _
|  | B&R | B | B2 | East | 20 | I/tiles | 411205 | P/L 80mm Thick Interlocking Tiles in Streets of Sanjay Gandhi Colony. W. No. 20 | 1101.52 | 18 |  | MC | Councillor | Tenders Received | 89.02 | 24.99 | 3114, dt 25.02.2026 | Y | Y | SE | Y | 100/SE(TIC) 07.05.2026 |  | Y | Y | _ | Infinity Business Services | 66.77 | _ |  |  |  | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Received | _ | Report received from DCFA dt 24.07.2026 & sent to JC(V) Sir dt 29.07.2026 for approval of tenders | _ | _
|  | B&R | B | B3 | East | 7 | I/tiles | 413298 | P/Fixing I/tiles in various streets of New Attal Nagar W No.07 | 499.09 | 20 |  | MC | General | Tenders Received | 31.6 | 22.72 | 3076, dt 25.02.2026 | Y | Y | XEN | Y | 100/SE(TIC) 07.05.2026 |  | Y | Y | _ | T&G Const Co. | 24.42 | _ |  |  |  | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Received | _ | Report received from DCFA dt 29.07.2026 & Sent to JC(V) Sir dt 30.07.2026 for approval of tenders | _ | _
|  | B&R | B | B3 | East | 7 | I/tiles | 413308 | P/Fixing I/tiles in various streets of Chanderlok Colony W No.07 | 1485.67 | 20 |  | MC | General | Tenders Received | 99.41 | 24.99 | 3086, dt 25.02.2026 | Y | Y | SE | Y | 100/SE(TIC) 07.05.2026 |  | Y | Y | _ | Varinder Singh Govt Contractor & Infinity Business Services | 74.57 | _ |  |  |  | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Received | _ | Report received from DCFA dt 29.07.2026 & Sent to JC(V) Sir dt 30.07.2026 for approval of tenders 99.76=99.41+ Royality Rs. 34,594/- | _ | _
|  | B&R | B | B2 | East | 20 | Parks | 411208 | Repair & Renovation of Park Opp. GRD Nagar W. No. 20 | _ | _ |  | MC | General | Tenders Received | 9.49 | 16.66 | 3170, dt 25.02.2026 | Y | Y | SDO | Y | 100/SE(TIC) 07.05.2026 |  | Y | Y | _ | Sachdeva Art Gallery | 7.91 | _ |  |  |  | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Received | _ | Report received from DCFA dt 24.07.2026 & sent to JC(V) Sir dt 27.07.2026 for approval of tenders 9.49+ Royality Rs. 10,761/- | _ | _
|  | B&R | B | B2 | East | 20 | Parks | 411211 | P/F Cemented Benches in Various areas of W. No. 20 | _ | _ |  | MC | Councillor | Tenders Received | 2.79 | 19.99 | 3117, dt 25.02.2026 | Y | Y | SDO | Y | 100/SE(TIC) 07.05.2026 |  | Y | Y | _ | Sachdeva Art Gallery | 2.23 | _ |  |  |  | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Received | _ | Report received from DCFA dt 24.07.2026 & sent to JC(V) Sir dt 29.07.2026 for approval of tenders | _ | _
|  | B&R | B | B4 | Sahnewal | 25 | I/tiles | 390835 | P/F I/tiles on Sharu Steel Main Road Phase-VII W No.25 | 132.62 | 22 |  | MC | Councillor | Tenders Received | 11.82 | 5.98 | 2942 dt 25.02.2026 | Y | Y | SDO | Y | 624/SE(TIC) 18.03.2026 |  | Y | Y | _ | Varinder Singh Govt Contractor | 11.11 | _ | 3 |  |  | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Received | _ | Report received from DCFA dt 29.07.2026. As per decision of F&CC vide Reso No. 3922 dt 15.06.2026. To be putup in next meeting of F&CC. | _ | _
|  | B&R | B | B2 | East | 20 | Others | 414632 | Providing & Fixing of Sign Boards in Different Areas of W. No. 20 | _ | _ |  | MC | Councillor | Tenders Received | 4.33 | 24.99 | 3116, dt 25.02.2026 | Y | Y | SDO | Y | 100/SE(TIC) 07.05.2026 |  | Y | Y | _ | Sachdeva Art Gallery | 3.25 | _ |  |  |  | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Received | _ | Report received from DCFA & Sent to JC(V) Sir dt 03.08.2026 for approval of tenders | _ | _
|  | B&R | B | B2 | East | 20 | Others | 382648 | Upgradation of Play Ground on Main Bhamian Road W. No. 20 | _ | _ |  | Rangla Punjab | Rangla Punjab | Tenders Received | 371.42 | 0.6 | 3425 dt 21.04.2026 | Y | Y | CE | Y | 330/SE(TIC) 23.06.2026 |  | Y | Y | _ | Chadha Sports (Regd.) | 369.19 | _ |  |  |  | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Received | _ | Financial Bid Received & got vetted from CE and sent to DCFA for report (371.42+Royality Rs. 1.81 Lacs) | _ | _
|  | B&R | B | B4 | Sahnewal | 25 | I/tiles | _ | P/F 80/60mm thick Interlocking Tiles in streets of Jasveer Colony, Fauji Colony and Choudhary Colony | 1979.88 | 16 |  | MC | MC | Tenders Received | 136.9 | 38.69 | 1785 dt 27.02.2024 | Y | Y | CE | Y | 195/SE(TIC) 22.11.2024 | 16.12.2024 | Y | Y | _ | T&G Const Co. | 83.93 | _ |  |  |  | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Received | _ | Held up due to upgradation of Sewer Line | _ | _
|  | B&R | B | B4 | Sahnewal | 21 | I/tiles | _ | P/F I/tiles in streets of Jeewan Nagar W No.21 | 3013.41 | 23 |  | MC | General | Tenders Received | 253.84 | 33 | 2526 dt 05.02.2026 | Y | Y | CE | Y | 7/SE(TIC) 01.04.2026 | 23.04.2026 | Y | Y | _ | Capital Const Co. | 170.07 | _ | 6 |  |  | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Received | _ | Sent to CE for vetting of Comparative Statement | _ | _
|  | B&R | B | B4 | Sahnewal | 21 | Bituminous | _ | Widening of road from Veer Palace to Jeewan Nagar Chowk. | 2443.29 | 25 |  | MC | General | Tenders Received | 200.91 | 28.26 | 2527 dt 05.02.2026 | Y | Y | CE | Y | 7/SE(TIC) 01.04.2026 | 23.04.2026 | Y | Y | _ | Varinder Singh Govt Contractor | 144.13 | _ | 6 |  |  | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Received | _ | Sent to CE for vetting of Comparative Statement Royality Rs. 24,579/- | _ | _
|  | B&R | B | B4 | Sahnewal | 21 | Bituminous | 405447 | Upgradation of various Roads in Urban Estate Phase- 2 W No.21 | 4060.06 | 12 |  | MC | General | Tenders Received | 132.4 | 29.99 | 3081 dt 25.02.2026 | Y | Y | SE | Y | 7/SE(TIC) 01.04.2026 | 23.04.2026 | Y | Y | _ | Shiva Construction | 92.69 | _ | 6 |  |  | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Received | _ | Report received from DCFA dt 29.07.2026 & Sent to JC(V) Sir dt 30.07.2026 for approval of tenders | _ | _
|  | B&R | B | B4 | Sahnewal | 21 | Parks | 415209 | Renovation of Shri Radha Krishan Park & Gaushalla Park in W No.21 | _ | _ |  | MC | General | Tenders Received | 32.9 | 6.96 | 3300, dt 25.02.2026 | Y | Y | XEN | Y | 100/SE(TIC) 07.05.2026 |  | Y | Y | _ | Varinder Singh Govt Contractor | 30.61 | _ |  |  |  | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Received | _ | Report received from DCFA dt 29.07.2026 (32.90+ Royality Rs. 20,129/-) | _ | _
|  | B&R | B | B2 | Sahnewal | 23 | Others | 411213 | P/F Cemented Benches in W. No. 23 | _ | _ |  | MC | Councillor | Tenders Received | 5.19 | 21.2 | 3303, dt 25.02.2026 | Y | Y | SDO | Y | 100/SE(TIC) 07.05.2026 |  | Y | Y | _ | Ram Parkash Kakkar | 4.09 | _ |  |  |  | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Received | _ | Financial Bid Received & Report received from DCFA dt 24.07.2026. Sent to JC(V) Sir dt 29.07.2026 for approval of Tenders | _ | _
|  | B&R | B | B2 | Sahnewal | 22 | Others | 411215 | P/F Cemented Benches in various areas of W. No. 22 | _ | _ |  | MC | Councillor | Tenders Received | 4.91 | 21.2 | 3304, dt 25.02.2026 | Y | Y | SDO | Y | 100/SE(TIC) 07.05.2026 |  | Y | Y | _ | Ram Parkash Kakkar | 3.87 | _ |  |  |  | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Received | _ | Financial Bid Received & Report received from DCFA dt 24.07.2026 and Sent to JC(V) Sir dt 29.07.2026 for approval of Tenders | _ | _
|  | B&R | B | B2 | Sahnewal | 24 | Others | _ | Renovation of Playground opp Mundian School W No.24 | _ | _ |  | MC | General | Tenders Received | 278.3 | 12% above | 3317, dt 25.02.2026 | Y | Y | CE | Y | 340/SE(TIC) 01.07.2026 |  | Y | Y | _ | Baljit Singh Gill | 311.7 | _ |  |  |  | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Received | _ | Financial Bid Received & sent to CE for vetting of Comparative Statement (vetted Est 284.27= 278.30+ Royality Rs. 5,97,000/-) | _ | _
|  | B&R | B | B2 | Sahnewal | 23 | Others | 414605 | Providing & Fixing of Sign Boards in Different Areas of W. No. 23 | _ | _ |  | MC | Councillor | Tenders Received | 4.29 | 24.99 | 3302, dt 25.02.2026 | Y | Y | SDO | Y | 100/SE(TIC) 07.05.2026 |  | Y | Y | _ | Sachdeva Art Gallery | 3.22 | _ |  |  |  | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Received | _ | Report received from DCFA dt 29.07.2026 & Sent to JC(V) Sir dt 30.07.2026 for approval of tenders | _ | _
|  | B&R | B | B4 | East | 19 | Others | _ | Renovation of Tubewell Rooms in parks of Sec-39 W No.19 | _ | _ |  | MC | General | Tenders Invited | 12.53 | _ | 2535 dt 05.02.2026 | Y | Y | SDO | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Tenders re Invited ivth time dt 29.07.2026 (Uploaded) | _ | _
|  | B&R | B | B3 | East | 11& 12 | I/tiles | _ | P/Fixing I/tiles in streets near New Bhagwan Nagar adjoining Towerline No.2 & 5 in W No.11 & 12 | 1299.7 | 20 |  | MC | General | Tenders Invited | 85.49 | _ | 2957, dt 25.02.2026 | Y | Y | SE | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Tenders Reinvited dt 24.07.2026 (Uploaded) ( 85.49+Royality Rs. 60,819/-) | _ | _
|  | B&R | B | B3 | East | 7 | I/tiles | _ | P/Fixing I/tiles in various Streets of Chanderlok Colony & Shiv Vihar in W No.07 | 446.65 | 19 |  | MC | Councillor | Tenders Invited | 35.39 | _ | 3062, dt 25.02.2026 | Y | Y | XEN | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Tenders invited dt 24.07.2026 (Uploaded) | _ | _
|  | B&R | B | B3 | East | 7 | I/tiles | _ | P/Fixing I/tiles in various Streets of Golden Evenue W No.07 | 1635.98 | 22 |  | MC | General | Tenders Invited | 107.49 | _ | 3075, dt 25.02.2026 | Y | Y | SE | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Tenders re- Invited dt 30.06.2026 | _ | _
|  | B&R | B | B3 | East | 16 | Parks | _ | Renovation & Development of various parks in Dairy Complex & GK Estate Block-C W No.16 | _ | _ |  | MC | General | Tenders Invited | 38.73 | _ | 3078, dt 25.02.2026 | Y | Y | XEN | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Tenders invited dt 24.07.2026 (Uploaded) (38.47+ Royality Rs. 24,901/-) | _ | _
|  | B&R | B | B3 | East | 15 | I/tiles | _ | P/Fixing I/tiles on road from Tibba police station upto MC Limit W No.15 | 426.83 | 24 |  | MC | General | Tenders Invited | 41.1 | _ | 3079, dt 25.02.2026 | Y | Y | XEN | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Tenders invited dt 24.07.2026 Uploaded | _ | _
|  | B&R | B | B3 | East | 16 | I/tiles | _ | P/Fixing I/tiles in various streets of Iqbal Nagar & New Preet Nagar W No.16 | 105.49 | 27 |  | MC | Councillor | Tenders Invited | 12.53 | _ | 3087, dt 25.02.2026 | Y | Y | SDO | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Tenders invited dt 24.07.2026 Uploaded (12.36+ Royality Rs. 16,396/-) | _ | _
|  | B&R | B | B2 | East | 18 | Parks | _ | Repair & Renovation of Various Parks in EWS Colony W. No. 18 | _ | _ |  | MC | General | Tenders Invited | 41.91 | _ | 3171, dt 25.02.2026 | Y | Y | XEN | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Tenders invited dt 24.07.2026 Uploaded (40.85+Royality Rs. 1,06,350/-) | _ | _
|  | B&R | B | B2 | East | 18 | I/tiles | _ | P/F 60mm Thick Perforated Interlocking Tiles in Different Parking Area of EWS Colony. W. No. 18 | 118.14 | 48 |  | MC | General | Tenders Invited | 45.53 | _ | 3173, dt 25.02.2026 | Y | Y | XEN | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Under Technical Evaluation (44.99+ Royality Rs. 54,160/-) | _ | _
|  | B&R | B | B2 | East | 20 | Others | _ | Construction of Box Cricket in Guru Nanak Nagar W. No. 20 | _ | _ |  | MC | General | Tenders Invited | 25.65 | _ | 3174 dt 25.02.2026 | Y | Y | XEN | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Tenders invited dt 24.07.2026 Uploaded (25.48+ Royality Rs. 17,567/-) | _ | _
|  | B&R | B | B3 | East | 14 | I/tiles | _ | P/Fixing I/tiles in various Streets of Rishi Nagar & Punjabi Bagh W No.14 | 1202.44 | 19 |  | MC | General | Tenders Invited | 71.55 | _ | 3299, dt 25.02.2026 | Y | Y | SE | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Tenders invited dt 24.07.2026 Uploaded (71.43+Royality Rs. 12,425/-) | _ | _
|  | B&R | B | B3 | East | 14 | I/tiles | _ | P/Fixing I/tiles in various Streets of Kishan Vihar, New Rishi & Gopal Nagar Gurudwara Sahib Wali Gali W No.14 | 1103.05 | 18 |  | MC | General | Tenders Invited | 62.26 | _ | 3297, dt 25.02.2026 | Y | Y | SE | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Tenders invited dt 24.07.2026 Uploaded (62.02+ Royality Rs. 23,495/-) | _ | _
|  | B&R | B | B3 | East | 12 | I/tiles | 382514 | P/Fixing I/tiles in links of street 10/3 Subhash Nagar W No.12 | 409.15 | 20 |  | MC | GQ | Tenders Invited | 28.95 | _ | 3544 dt 21.04.2026 | Y | Y | XEN | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Tenders to be invited (28.60+Royality Rs. 35,622/-) | _ | _
|  | B&R | B | B3 | East | 13 | Others | 382569 | Development of leisure valley near shamshan ghat ward no. 13 | _ | _ |  | MC | GQ | Tenders Invited | 98.27 | _ | 3545 dt 21.04.2026 | Y | Y | SE | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Tenders to be invited (98.08+Royality Rs. 19,031/-) | _ | _
|  | B&R | B | B2 | East | 18 | I/tiles | 379942 | P/L Interlocking Tiles in EWS Colony W. No. 18 | 420.43 | 37 |  | MC | CQ | Tenders Invited | 25.05 | _ | 3553 dt 21.04.2026 | Y | Y | XEN | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Tenders to be invited for amounting to Rs.24.76 Lacs | _ | _
|  | B&R | B | B3 | East | 13 | Others | 381585 | Renovation and floor raising Urban Community health centre W No.13 | _ | _ |  | MPLAD | MPLAD | Tenders Invited | 13.99 | _ | 3551 dt 21.04.2026 | Y | Y | SDO | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Tenders to be invited (13.37+ Royality Rs. 61,309/-) | _ | _
|  | B&R | B | B2 | East | 20 | I/tiles | 379953 | P/L Interlocking Tiles in Sanjay Gandhi Colony Near Mandir W. No. 20 | 17.68 | 24 |  | MC | Councillor | Tenders Invited | 2.92 | _ | 3550 dt 21.04.2026 | Y | Y | SDO | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Tenders to be invited for amounting to Rs.2.77 Lacs | _ | _
|  | B&R | B | B2 | East | 18 | Others | 379970 | P/F Cemented Benches in W. No. 18 | _ | _ |  | MC | CQ | Tenders Invited | 2.79 | _ | 3549 dt 21.04.2026 | Y | Y | SDO | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Tenders to be invited | _ | _
|  | B&R | B | B2 | East | 29 | RMC & I/tiles | 379977 | Const. of Various Streets of GAD Nagar W. No. 29 (i.e GAD Nagar & Kishore Nagar) | 400.91 | 18 |  | MDF | MDF | Tenders Invited | 25.95 | _ | Approved by W/Mayor inanticipation of approval by F&CC dt 08.05.2026 & sent to F&CC for regular approval dt 18.05.2026 | Y | Y | XEN | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Zero bid received Tenders To be reinvited | _ | _
|  | B&R | B | B3 | East | 11 | I/tiles | _ | Providing and fixing interlocking tiles in various streets of Mayapuri and various streets of Manjit Nagar & Preet Nagar w-11 | 5128.35 | 18 |  | MDF | MDF | Tenders Invited | 278.72 | _ | Do | Y | Y | CE | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | 03Tenders Received (Under Technical Evaluation) 278.59+ Royality Rs. 13,153/- | _ | _
|  | B&R | B | B3 | East | 11 | I/tiles | _ | Providing and fixing interlocking tiles in various streets of new shakti nagar near dada motors and various streets of shakti nagar left side w-11 | 5334.45 | 19 |  | MDF | MDF | Tenders Invited | 290.23 | _ | Do | Y | Y | CE | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | 03 Tenders Received (Under Technical Evaluation) 289.92+ Royality Rs. 30,404/- | _ | _
|  | B&R | B | B3 | East | 11 | RMC | _ | Laying RMC in various streets of shastri nagar w- 11 | 219.51 | 20 |  | MDF | MDF | Tenders Invited | 16.76 | _ | Do | Y | Y | SDO | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Zero bid received Tenders To be reinvited | _ | _
|  | B&R | B | B3 | East | 12 | I/tiles | _ | P/F I/tiles on Towerline No.02 Subhash Nagar W No.12 | 1667.38 | 13 |  | MDF | MDF | Tenders Invited | 135.14 | _ | Do | Y | Y | SE | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Tenders to be Reinvited 134.59+ Royality Rs. 55,000/- | _ | _
|  | B&R | B | B3 | East | 12 | I/tiles | _ | P/F I/tiles on streets of New Subhash Nagar around tanky wala park W No.12 | 597.56 | 24 |  | MDF | MDF | Tenders Invited | 61.82 | _ | Do | Y | Y | SE | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Tenders To be reinvited | _ | _
|  | B&R | B | B3 | East | 13 | I/tiles | _ | Providing and fixing interlocking tiles in various streets of new raju colony w-13 | 774.39 | 18 |  | MDF | MDF | Tenders Invited | 43.33 | _ | Do | Y | Y | XEN | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | 03 Tenders Received (Under Technical Evaluation) | _ | _
|  | B&R | B | B3 | East | 13 | I/tiles | _ | Providing and fixing interlocking tiles in various streets of new karamsar colony w-13 | 423.17 | 18 |  | MDF | MDF | Tenders Invited | 22.1 | _ | Do | Y | Y | SDO | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | 03 Tenders Received (Under Technical Evaluation) | _ | _
|  | B&R | B | B3 | East | 14 | I/tiles | _ | Providing and fixing interlocking tiles in various streets of new karamsar colony opp nalwa colony w-14 | 1102.13 | 20 |  | MDF | MDF | Tenders Invited | 65.42 | _ | Do | Y | Y | SE | N | _ | 08.12.2025 | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Zero bid received Tenders To be reinvited | _ | _
|  | B&R | B | B4 | East | 19 | Bituminous | _ | Const of Bituminous Main Road between Sec-38 & Sec-39 from Police colony Chowk to Malhotra Chowk W No.19 | 457.32 | 35 |  | MDF | MDF | Tenders Invited | 70.22 | _ | Do | Y | Y | SE | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Technical Evaluation Done | _ | _
|  | B&R | B | B3 | East | 15 | Others | 388590 | Development and construction of sports area & Library in ward no. 15 | _ | _ |  | Rangla Punjab | Rangla Punjab | Tenders Invited | 99.26 | _ | inanticipation approval by W Mayor dt 12.05.2026 & Regular approval by F&CC vide Reso No.3871, dt 15.06.2026 | Y | Y | SE | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Tenders invited dt 24.07.2026 Uploaded 98.54+ Royality Rs. 72,210/- To be Sent to DCFA for Report after opening of financial bid. | _ | _
|  | B&R | B | B2 | East | 20 | Others | 388742 | Construction of Library in ward no. 20 | _ | _ |  | Rangla Punjab | Rangla Punjab | Tenders Invited | 27.51 | _ | inanticipation approval by W Mayor dt 11.05.2026 & Regular approval by F&CC No.3813 dt 15.06.2026 | Y | Y | XEN | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Tenders invited dt 24.07.2026 Uploaded (27.40+ Royality Rs.10948/-) | _ | _
|  | B&R | B | B3 | East |  | Others | 394314 | Const of Retaining wall along Budha Nallah from GT road to Satsang Ghar Pulli Ludhiana | _ | _ |  | MC | General | Tenders Invited | 1283.15 | _ | Approved by W/ Mayor dt 28.05.2026 inanticipation approval by F&CC and Regular approval by F&CC vide Reso No.3882, dt 15.06.2026 | Y | Y | CE | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Tenders invited dt 03.08.2026 | _ | _
|  | B&R | B | B2 | East | 29 | Others | 379961 | Const. of Badminton Court in LIG Colony W. No. 29 | _ | _ |  | MC | Councillor | Tenders Invited | 17.12 | _ | 3623 dt 15.06.2026 | Y | Y | SDO | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Tenders to be invited (17.07+ Royality Rs. 5270/-) Report has been received from DCFA on dt 16.07.2026 and afterward sent to JC(V) for n.a. | _ | _
|  | B&R | B | B2 | East | 18 | Others | 379929 | Const of EWS Colony Dharamshalla W No.18 | _ | _ |  | MC | General | Tenders Invited | 49.95 | _ | 3614 dt 15.06.2026 | Y | Y | XEN | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | (Tenders to be invited) Report obtained from DCFA dt 24.07.2026 (49.78+ Royality Rs. 17,000/-) | _ | _
|  | B&R | B | B3 | East | 12& 13 | I/tiles | 382577 | P/Fixing I/tiles in streets of Karamsar Colony and Laying RMC in main street near Bhawani Model School W No.12 & 13 | 2229.88 | 19 |  | MC | General | Tenders Invited | 147.65 | _ | 3617 dt 15.06.2026 | Y | Y | SE | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | (Tenders to be invited) (146.78+Royality Rs. 86,396/-) | _ | _
|  | B&R | B | B2 | East | 18 | Bituminous | 379949 | Rejuvenation of Streets in MIG Colony, Ludhiana. W. No. 18 | 1833.54 | 15 |  | MC | Councillor | Tenders Invited | 96.66 | _ | 3616 dt 15.06.2026 | Y | Y | SE | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | (Tenders to be invited) | _ | _
|  | B&R | B | B3 | East | 7 | Park | 382538 | Renovation and Development of Golden Avenue W No.7 | _ | _ |  | MC | Councillor | Tenders Invited | 20.49 | _ | 3608 dt 15.06.2026, | Y | Y | SDO | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Committee is to be constitued by W/ Mayor for checking of Estimate Sent to DCFA for availability of funds | _ | _
|  | B&R | B | _ | Sahnewal | _ | Bituminous | _ | Upgradation of Main Bhamian Road from Chandigarh road to upto MC Limit, Main Phirni of Village Mundian Kalan from Chd road to Sunder Nagar 33' Road and from Chd Road to Rasila Nagar Back side Blind School. | 5929.88 | 23 |  | Special Assistance Scheme | Special Assistance Scheme | Tenders Invited | 520 | _ | Approved inanticipation by W/Mayor vide dt 20.11.2025 & Regular approval by F&CC 2691 dt 19.02.2026 | Y | Y | CE | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Case Pending in Honble High Court | _ | _
|  | B&R | B | B2 | Sahnewal | 22 | I/tiles | _ | P/F 80mm Thick I/Tiles in Streets of Baba Balak Nath Mandir Road W. No. 22 | 280.49 | 18 |  | MC | General | Tenders Invited | 30.27 | _ | 3085 dt 25.02.2026 | Y | Y | XEN | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Technical Bid Opened. (29.14+Royality Rs. 1,12,162/-) | _ | _
|  | B&R | B | B2 | Sahnewal | 24 | Parks | _ | Repair & Renovation of various parks in GK Estate on Chd Road W No.24 | _ | _ |  | MC | General | Tenders Invited | 30.92 | _ | 3175 dt 25.02.2026 | Y | Y | XEN | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Technical Bid Opened. (30.34+ Royality Rs. 57,461/-) | _ | _
|  | B&R | B | B2 | Sahnewal | 23 | I/tiles | _ | P/F I/Tiles in Various Streets of W. No. 23 (i.e. Sunder Nagar, Ram Nagar, Ramandeep Colony etc.) | 369.82 | 19 |  | MDF | MDF | Tenders Invited | 29.55 | _ | Approved by W/Mayor inanticipation of approval by F&CC dt 08.05.2026 & sent to F&CC for regular approval dt 18.05.2026 | Y | Y | XEN | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | 02 Tenders received (Under Technical Evaluation) 29.41+ Royality Rs. 14,422/- | _ | _
|  | B&R | B | B2 | Sahnewal | 23 | I/tiles | _ | P/F I/Tiles in Govt. Flats W. No. 23 | 482.32 | 22 |  | MDF | MDF | Tenders Invited | 55.07 | _ | Do | Y | Y | SE | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | 02 Tenders received (Under Technical Evaluation) | _ | _
|  | B&R | B | B2 | Sahnewal | 24 | I/tiles | _ | P/L 80mm Thick Interlocking Tiles in Streets of GTB Nagar Near Veer Palace W. No. 24 | 91.46 | 25 |  | MDF | MDF | Tenders Invited | 8.31 | _ | Do | Y | Y | SDO | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | 04 Tenders received (Under Technical Evaluation) | _ | _
|  | B&R | B | B4 | Sahnewal | 21 | Bituminous | _ | Const of Bituminous roads in Sec-38 and Bituminous streets of LIG,MIG & Labour Colony W No.21 | 4008.23 | 20 |  | MDF | MDF | Tenders Invited | 353.02 | _ | Do | Y | Y | CE | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Financial Bid Opened | _ | _
|  | B&R | B | B4 | Sahnewal | 21 & 25 | I/tiles | _ | P/fixing I/tiles in streets of LIG,MIG & Labour Colony W No.21 and streets of Dhandari W No.25 | 3000.91 | 13 |  | MDF | MDF | Tenders Invited | 347.07 | _ | Do | Y | Y | CE | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | 04 Tenders received (Under Technical Evaluation) | _ | _
|  | B&R | B | B4 | Sahnewal | 25 | Bituminous | _ | Upgradation of Main Dhandari Bridge in W No.25 | 5106.71 | 16 |  | MDF | MDF | Tenders Invited | 200.76 | _ | Do | Y | Y | CE | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Financial Bid Opened | _ | _
|  | B&R | B | B4 | Sahnewal | 25 | RMC | _ | Laying RMC from Durga Colony Disposal to Devgan Kanda W No.25 | 2820.12 | 30 |  | MDF | MDF | Tenders Invited | 532.92 | _ | Do | Y | Y | CE | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Technical Evaluation Done | _ | _
|  | B&R | B | B2 | Sahnewal | 24 | I/tiles | 379461 | P/L Interlocking Tiles on Mundian Road W. No. 24 | 64.02 | 28 |  | MC | General | Tenders Invited | 7.06 | _ | 3661 dt 15.06.2026 | Y | Y | SDO | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Tenders to be invited | _ | _
|  | B&R | B | B2 | Sahnewal | _ | Others | 415195 | Selection of Architecture services for Beautification & Designing of Dream Park, Ludhiana | _ | _ |  | MC | General | Tenders Invited | 9 | _ | Approved by W/CC vide dt 19.01.2026 | Y | Y | SDO | N | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Tenders Invited | _ | Report received from DCFA & Sent to JC(V) Sir dt 03.08.2026 for approval of tenders | _ | _
|  | B&R | B | B4 | East | 19 | Others | _ | Const of Boundary wall between Sector-39 and New Moti Nagar W No.19 | _ | _ |  | MC | General | Sent to F&CC | 3.42 | _ | _ | Y | Y | SDO | Y | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Sent to F&CC | _ | Est Pending (Lambit) vide Reso No.465 dt 09.04.2025 | _ | _
|  | B&R | B | B2 | East | 20 | I/tiles | 394629 | P/L Interlocking Tiles in Streets of Bhola Colony Near Masjid W. No. 20 | 150.3 | 14.5 |  | MC | General | Sent to F&CC | 8.49 | _ | _ | Y | Y | SDO | Y | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Sent to F&CC | _ | Report has been obtained from DCFA dt 17.07.2026 & sent to JC(V) Sir dt 29.07.2026 for approval of Estimate | _ | _
|  | B&R | B | B2 | East | 20 | Park | 394633 | Construction of Various Parks in Sanjay Gandhi Colony W. No. 20 | _ | _ |  | MC | General | Sent to F&CC | 22.5 | _ | _ | Y | Y | SDO | Y | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Sent to F&CC | _ | Report has been obtained from DCFA dt 17.07.2026 & sent to JC(V) Sir dt 29.07.2026 for approval of Estimate (22.33+ Royality Rs. 16,756/-) | _ | _
|  | B&R | B | B2 | East | 20 | I/tiles | 394631 | P/F Tiles in Different Parking Area of Sanjay Gandhi Colony. W. No. 20 | 89.33 | 34 |  | MC | General | Sent to F&CC | 12.13 | _ | _ | Y | Y | SDO | Y | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Sent to F&CC | _ | Report has been obtained from DCFA dt 17.07.2026 & sent to JC(V) Sir dt 29.07.2026 for approval of Estimate | _ | _
|  | B&R | B | B2 | East | 20 | I/tiles | 394614 | P/L Interlocking Tiles in Various Streets of W. No. 20 | 473.78 | 20 |  | MC | General | Sent to F&CC | 42.31 | _ | _ | Y | Y | XEN | Y | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Sent to F&CC | _ | Report has been obtained from DCFA dt 17.07.2026 & sent to JC(V) Sir dt 29.07.2026 for approval of Estimate | _ | _
|  | B&R | B | B2 | East | 20 | I/tiles | 395771 | P/L Interlocking Tiles in Streets of Baba Jeevan Singh Nagar W. No. 20 | 445.43 | 18 |  | MC | Councillor | Sent to F&CC | 31.08 | _ | _ | Y | Y | XEN | Y | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Sent to F&CC | _ | Report has been obtained from DCFA dt 17.07.2026 & sent to JC(V) Sir dt 29.07.2026 for approval of Estimate | _ | _
|  | B&R | B | B2 | East | 20 | I/tiles | 395768 | P/F Tiles in Different Vacant Area of Sanjay Gandhi Colony. W. No. 20 | 60.98 | 39 |  | MC | Councillor | Sent to F&CC | 8.61 | _ | _ | Y | Y | SDO | Y | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Sent to F&CC | _ | Report received from DCFA dt 24.07.2026 & sent to JC(V) Sir dt 29.07.2026 for approval of Estimate | _ | _
|  | B&R | B | B3 | East | 7 | I/tiles | 402863 | P/Fixing I/tiles in various Streets of Jain Colony W No.07 | 1821.34 | 25 |  | MC | General | Sent to F&CC | 138.54 | _ | _ | Y | Y | SE | Y | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Sent to F&CC | _ | Report received from DCFA dt 29.07.2026 & Sent to JC(V) Sir dt 30.07.2026 for approval of Estimate (138.37+ Royality Rs. 17,815/-) | _ | _
|  | B&R | B | B3 | East | 16 | I/tiles | 402858 | P/Fixing I/tiles in various Streets of gurmail park W No.16 | 617.99 | 19 |  | MC | Councillor | Sent to F&CC | 42.48 | _ | _ | Y | Y | XEN | Y | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Sent to F&CC | _ | Report received from DCFA dt 29.07.2026 & Sent to JC(V) Sir dt 30.07.2026 for approval of Estimate (42.26 + Royality Rs. 22,699/-) | _ | _
|  | B&R | B | B3 | East | 16 | I/tiles | 402865 | P/fixing interlocking tiles in various streets of ward no. 16 | 2670.12 | 19 |  | MC | General | Sent to F&CC | 149.93 | _ | _ | Y | Y | SE | Y | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Sent to F&CC | _ | Report received from DCFA dt 29.07.2026 & Sent to JC(V) Sir dt 30.07.2026 for approval of Estimate | _ | _
|  | B&R | B | B3 | East | 16 | I/tiles | 402860 | P/Fixing I/tiles in various Streets of GK Estate Block-C & Company Bagh W No.16 | 770.73 | 27 |  | MC | Councillor | Sent to F&CC | 58.84 | _ | _ | Y | Y | SE | Y | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Sent to F&CC | _ | Report received from DCFA dt 29.07.2026 & Sent to JC(V) Sir dt 30.07.2026 for approval of Estimate 58.74 + Royality Rs. 10,826/- | _ | _
|  | B&R | B | B2 | East | 18 | Others | 405428 | Const. of Badminton Court in MIG Colony W. No. 18 | _ | _ |  | MC | General | Sent to F&CC | 8.96 | _ | _ | Y | Y | SDO | Y | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Sent to F&CC | _ | Report received from DCFA dt 24.07.2026 & sent to JC(V) Sir dt 29..07.2026 for approval of Estimate Rs.8.92 Lacs + Rs.3953/-Royalty | _ | _
|  | B&R | B | B2 | East | 18 | Others | 405429 | Football Ground in MIG Colony W. No. 18 | _ | _ |  | MC | General | Sent to F&CC | 14.35 | _ | _ | Y | Y | SDO | Y | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Sent to F&CC | _ | Sent to DCFA For report Rs.12.72 Lacs + Rs.1,63,672/-Royalty | _ | _
|  | B&R | B | B2 | East | 18 | Others | 405430 | Const. of Volley Ball Court in MIG Colony W. No. 18 | _ | _ |  | MC | General | Sent to F&CC | 20.87 | _ | _ | Y | Y | SDO | Y | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Sent to F&CC | _ | Report received from DCFA dt 24.07.2026 & sent to JC(V) Sir dt 29.07.2026 for approval of Estimate Rs.20.77 Lacs + Rs.10,309/-Royalty | _ | _
|  | B&R | B | B2 | East | 18 & 20 | Bituminous | 398614 | Rejuvenation of Main Puda Road, Ludhiana. W. No. 18 & 20. | 2821.95 | 22 |  | MC | General | Sent to F&CC | 340.02 | _ | _ | Y | Y | CE | Y | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Sent to F&CC | _ | Report has been obtained from DCFA dt 24.07.2026 & Agenda sent dt28.07.2026 to vivek verma | _ | _
|  | B&R | B | B2 | East |  | Bituminous | 398605 | Rejuvenation of Main Tajpur Road from Main GT Road upto MC Limit. | 5701.22 | 26 |  | NCAP | NCAP | Sent to F&CC | 723.94 | _ | _ | Y | Y | CE | Y | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Sent to F&CC | _ | Report has been obtained from DCFA dt 24.07.2026 & Agenda sent dt28.07.2026 to vivek verma for regular approval | _ | _
|  | B&R | B | B4 | East | 26 | I/tiles | 395177 | P/fixing I/tiles in streets of HIG B/S Lovely sweets W No.26 . | 261.28 | 22 |  | MC | General | Sent to F&CC | 21.57 | _ | _ | Y | Y | SDO | Y | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Sent to F&CC | _ | Report received from DCFA dt 29.07.2026 & Sent to JC(V) Sir dt 30.07.2026 for approval of Estimate | _ | _
|  | B&R | B | B3 | East | 16 | Others | 412428 | Construction of Retaining wall along Budha Nallah from Radha Swami Satsang Ghar Pully to Geeta Nagar Pully Ludhiana | _ | _ |  | MC | General | Sent to F&CC | 770.25 | _ | _ | Y | Y | CE | Y | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Sent to F&CC | _ | Report obtained from DCFA dt 24.07.2026 & sent to JC(V) Sir dt 29.07.2026 for approval of Estimate | _ | _
|  | B&R | B | B4 | East | 26 | Others | 390009 | Construction of Box Cricket & Basket Ball Court in W. No. 26 | _ | _ |  | MC | Councillor | Sent to F&CC | 51.32 | _ | _ | Y | Y | SE | Y | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Sent to F&CC | _ | Proposed Estimate | _ | _
|  | B&R | B | B2 | Sahnewal | 22 | Others | _ | P/F of Convex Mirror 32" Complete in Different areas of W No.22 | _ | _ |  | MC | General | Sent to F&CC | 3 | _ | _ | Y | Y | SDO | Y | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Sent to F&CC | _ | Est Pending (Lambit) vide Reso No.458 dt 09.04.2025 | _ | _
|  | B&R | B | B4 | Sahnewal | 21 | Bituminous | _ | Const.of bituminous road in Sec-38 W No.21 | _ | _ |  | MC | General | Sent to F&CC | 59.23 | _ | _ | Y | Y | SE | Y | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Sent to F&CC | _ | Pending (Lambit) by F&CC vide Reso No. 3083 dt 25.02.2026 to be putup in next meeting | _ | _
|  | B&R | B | B2 | Sahnewal | 23& 24 | Bituminous | 398613 | Rejuvenation of Main 33' Road, Ludhiana. W. No. 23 & 24. | 2865.85 | 28 |  | NCAP | NCAP | Sent to F&CC | 244.39 | _ | _ | Y | Y | CE | Y | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Sent to F&CC | _ | As report has been obtained from DCFA dt 16.07.2026 & sent to JC(V) Sir dt 29.07.2026 for approval inanticipation of F&CC | _ | _
|  | B&R | B | B2 | Sahnewal | 24 | Others | 405426 | For Gas Furnance of Cremation Ground at W No.24 | _ | _ |  | MPLAD | MPLAD | Sent to F&CC | 3 | _ | _ | Y | Y | SDO | Y | _ |  | N | N | _ | _ | _ | _ | _ | _ | _ | Sh Parveen Singla | N | N | _ | _ | _ | Sent to F&CC | _ | Report obtained from DCFA dt 24.07.2026 & to be sent to JC(V) Sir for approval of Estimate | _ | _

## O&M
Sr. No. | Project ID | Branch | Zone | Sub-Zone | Assembly Constituency | Ward | Nature of Work | E office number | Name of Work / Description | Length (Rmt) | Road Width (Ft) | No. of Units | Fund / Quota Type | Quota (as recorded) | Current Status | Est./Vetted Cost (Lacs) | OAS % | Resolution No. & Date | Administrative Approval (Y/N) | Technical Sanction (Y/N) | TS Accorded By | Accounts / SE Certificate (Y/N) | Tender Float Date | Tender End Date | Technical Evaluation (Y/N) | Financial Evaluation (Y/N) | Work Order No. & Date | Executing Agency | Tender Cost (Lacs) | Start Date | Time Limit (Months) | Scheduled End Date | Actual Completion Date | Supervising Officer (JE/SDO/XEN) | Third Party Inspection (Y/N) | Completion Certificate (Y/N) | Physical Progress % | Financial Progress % | Expenditure / Payment (Lacs) | Status | Issues / Bottlenecks | Remarks / Status Notes | Geo-tagged Photograph (Link) | Last Updated On
1 | MCL-0321 | O&M | A | A2 | Central | 78 | Sewerage | NA | Rough Cost Estimate Pro. Laying of Water Supply Line and Sewer Line in Mohar singh nagar st no 2-4 & 7 Ward No78. |  | NA | 1 | Councillor Quota (CQ) | CQ | Awarded | 24.1 | -13.13% | 1442 Dt. 11/08/2025 | Yes | Yes | SDO | N/A | 11.04.2025 | 28.04.2025 | Yes | Yes | 45/G-33 Dt. 25/09/2025 | M/s Kohinoor Builders | 22.7 | 2025-10-01 | 3 | 2026-07-10 |  | Sachin JE Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN |  |  | 80% |  | 19.3 | In Progress |  | Work in Progress
2 | MCL-0322 | O&M | A | A2 | Central | 84 | Sewerage | NA | Rough Cost Estimate Prov. Laying/Up-gradation and mtc. of Water Supply & Sewer Line At Different Localities of Ward No. 84. | S/W 83.84 W/s 22.62 | NA | 1 | Councillor Quota (CQ) | CQ | Awarded | 9.85 | -16% | 2201 Dt.21/11/2025 | Yes | Yes | SDO | N/A | 2025-08-04 | 2025-12-08 | Yes | Yes | 71/G-33 Dt. 22/12/2025 | M/s Brar Brothers | 8.36 | 2025-11-23 | 3 | 2026-07-10 | 21/.2/2026 | Sachin JE Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | 85% | 0 | 7.11 | In Progress |  | Work in Progress
3 | MCL-0323 | O&M | A | A1 | Central | 10 | Sewerage | NA | Rough Cost Estimate Prov. Laying/Up-gradation and mtc. of Water Supply & Sewer Line At Different Localities of Ward No. 10 | S/W 65.55 W/s 22.62 | NA | 1 | Councillor Quota (CQ) | CQ | Awarded | 9.9 | -20 | 2622 Dt. 24/02/2026 | Yes | Yes | SDO | N/A | 2025-07-11 | 2-3/12/2025 | Yes | Yes | 83/G-33 Dt. 24/02/2026 | As Contractor | 7.92 | 2026-02-24 | 3 | 2026-07-10 | 2026-05-23 | Sachin JE Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | 80% | 95% | 6.34 | In Progress |  | Work in Progress
4 | MCL-0324 | O&M | A | A1 | Central | 9 | Sewerage | NA | Rough Cost Estimate Prov. Laying of Sewer Line and Water Supply Line in Basti Sheikh Mohammad Ward No. 9 | S/W 204.27W/s 219.51 | NA | 1 | Councillor Quota (CQ) | CQ | Awarded | 21.1 | -12.65% | 2607 Dt.11/02/2026 | Yes | Yes | SDO | N/A | 2025-07-11 | 2-3/12/2025 | Yes | Yes | 100/G-33 Dt. 24/02/2026 | Surya Construction | 18.4 | 2026-02-24 | 3 | 2026-10-30 | 2026-05-23 | Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | nil | nil | nil | Not Started |  | Narrow Streets work will start after monsoon
5 | MCL-0325 | O&M | A | A1 | Central | 83 | Sewerage | NA | Rough Cost Estimate Prov. Laying of Sewer and Water Supply Line Mohalla Balmiki Ghatti Ward No. 83 | S/W 381.10 W/s 396.34 | NA | 1 | MC Funds / General Quota | GQ | Awarded | 29.38 | -11.65% | 2608 Dt.11/02/2026 | Yes | Yes | XEN | N/A | 2025-07-11 | 2-3/12/2025 | Yes | Yes | 97/G-33 Dt. 24/02/2026 | Kohinoor Builders | 26 | 2026-02-24 | 3 | 2026-08-30 | 2026-05-23 | Rajneesh Kumar JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | 50% | nil | 13 | In Progress |  | Work in proress
6 | MCL-0326 | O&M | A | A2 | Central | 62 | Water Supply | NA | Providing & Installation of 25 HP Straight Bore T/Well against failed T/Well in Bangru Mohalla, Ward no. 62. | NA | NA | 1 | MC Funds / General Quota | GQ | Awarded | 12.6 | -3.03% | 2367 Dt.23/08/2024 | Yes | Yes | SDO | N/A | 2024-01-07 | 2024-07-16 | Yes | Yes | 09/G-33 Dt. 18/09/2024 | The Ananda coop L&C Society Ltd. | 12.6 | 2024-09-18 | 3 | 2026-08-30 | 2024-12-17 | Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | 10% | 0 | - | In Progress |  | Work Delay due to Narrow street site
7 | MCL-0327 | O&M | A | A1 | Central | 60 | Water Supply | NA | Providing and Installation of 12.5 HP Submersible T/well in Mohalla Nau Ghara Ward No. 60 | NA | NA | 1 | MC Funds / General Quota | GQ | Awarded | 6.53 | -16.01% | 2361 Dt.23/08/2024 | Yes | Yes | SDO | N/A | 2024-12-06 | 2024-06-27 | Yes | Yes | 17/G-33 Dt. 07/10/2024 | The Ananda coop L&C Society Ltd. | 5.48 | 2024-10-07 | 3 | 2026-08-30 | 2025-06-01 | Rajneesh Kumar JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | 0 | 0 | - | Not Started |  | The streets at the site are narrow, so the machine couldn't be set up. Now, Mr. Thapar has said that they will open a new route, and the work can start after that
8 | MCL-0328 | O&M | A | A2 | Central | 84 | Water Supply | NA | Providing & Installation of 12.5 HP Straight Bore T/Well Against Failed T/well Ktaira Norian Near Dal Bazar Ward No. 84 | NA | NA | 1 | Councillor Quota (CQ) | CQ | Awarded | 6.75 | -5.55% | 1724 Dt.13/10/2025 | Yes | Yes | SDO | N/A | 2025-08-05 | 2025-05-23 | Yes | Yes | 66G-33 Dt. 06/11/2025 | M/s Bedi Pump Store | 6.38 | 2025-11-06 | 2 | 2026-07-30 | 2026-05-01 | Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | 100% |  | -
9 | MCL-0329 | O&M | A | A2 | Central | 82 | Water Supply | NA | Providing and Installation of 25 HP Straight Bore T/Well in Mohalla Harbanspura, Ward No. 82, Ludhiana. (MP Lad) | NA | NA | 1 | MPLAD Funds | MP LAD | Awarded | 13.5 | -18.89% | 2665 Dt.11/02/2026 | Yes | Yes | SDO | N/A | 2025-07-11 | 2-3/12/2025 | Yes | Yes | 80/G-33 Dt. 24/02/2026 | JCS Electric Works | 11 | 2026-02-24 | 3 | 2026-07-15 |  | Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | 100% |  | 11 | Delayed/Held Up |  | Bore Work completed, only electrict meter pending
10 | MCL-0330 | O&M | A | A2 | Central | 78 | Water Supply | NA | Providing & Installation of 25 HP Straight Bore T/Well Mohar Singh Nagar,Ward No. 78(new) | NA | NA | 1 | MC Funds / General Quota | GQ | Awarded | 12.7 | -18.75% | 2614 Dt.11/02/2026 | Yes | Yes | SDO | N/A | 2025-07-11 | 2-3/12/2025 | Yes | Yes | 79/G-33 Dt. 24/02/2026 | JCS Electric Works | 10.4 | 2026-02-24 | 3 | 2026-06-30 |  | Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | 0% |  |  | Not Started |  | site dispute
11 | MCL-0331 | O&M | A | A2 | Central | 78 | Water Supply | NA | Providing and Installation of 25 HP Straight Bore T/Well Against Failed T/well Sadhu Sundar Singh Colony St No. 4 Issa Nagri Ward No. 78 | NA | NA | 1 | MC Funds / General Quota | GQ | Awarded | 12.7 | -14.55% | 2786 Dt.19/02/2026 | Yes | Yes | SDO | N/A | 2025-07-11 | 2-3/12/2025 | Yes | Yes | 103/G-33 Dt. 05/03/2026 | Rajdeep Enterprises | 10.9 | 2026-03-05 | 3 | 2026-07-10 | 2026-05-23 | Rajneesh Kumar JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | 95% |  | 0 | Delayed/Held Up |  | Bore work completed starter pending
12 | MCL-0332 | O&M | A | A1 | Central | 83 | Water Supply | NA | Providing & Installation of 25 HP Straight Bore T/Well Mohalla Balmik Ghatti Ward No. 83(new) | NA | NA | 1 | MC Funds / General Quota | GQ | Awarded | 12.7 | -7.04% | 2785 Dt.19/02/2026 | Yes | Yes | SDO | N/A | 2025-07-11 | 2-3/12/2025 | Yes | Yes | 104/G-33 Dt. 05/03/2026 | ESS Elechmech Enterprises | 11.8 | 2026-03-05 | 3 | 2026-07-10 | 2026-04-06 | Rajneesh Kumar JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | 100% |  | 0
13 | MCL-0333 | O&M | A | A4 | Central | 59 | Water Supply | NA | Rough Cost Estimate Prov. Laying / Up-Gradation of Water Supply Line, Sewer line in Kohlu Wali Gali Qilla Mohalla Near Dispansary Petrol Pump Wali Gali & Mandir Wali Gali in Ward No. 59 | NA | NA | 1 | MC Funds / General Quota | GQ | Awarded | 45.81 | -8.75% | 1648 14-02-2024 | Yes | Yes | XEN | N/A |  |  | Yes | Yes | 61/g/33 07-03-2024 | The Dynamic Coop. L&C Society Ltd. | 41.81 | 2024-07-03 | 3 | 2026-09-30 |  | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN |  |  | 20% |  | 8.36 | In Progress |  | Machinary not entered at proposed site due to narrow streets/ Now contractor will arrange small machine and start the work
14 | MCL-0334 | O&M | A | A2 | Central | 56 | Sewerage | NA | Rough Cost Estimate Prov. Laying / Up-Gradation of Water Supply Line, Sewer line in Dhoka Mohalla Street No. 1 and 2, Near Kalra Hospital, Ward No. 56 |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 38.4 | -13.04% | 351 Dt.26/03/2025 | Yes | Yes | XEN | N/A | 2024-12-03 | 2024-12-31 | Yes | Yes | 05/G-33 Dt. 14/04/2025 | M/s Surya Const. | 33.2 | 2025-04-14 | 3 | 2026-09-30 |  | Rajneesh Kumar JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | 60% |  | 19.9 | Delayed/Held Up |  | Low laying area pending work start to be done after monsoon
15 | MCL-0335 | O&M | A | A2 | Central | 54 | Sewerage | NA | Rough Cost Estimate Prov. Laying of Water Supply Line and Sewer Line At Fatehganj Shanti Nikaten Wali Gali and Near Gurudwara Sahib Wali Gali, Ward No. 54 |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 24 | -3.5% | 558 Dt.09/04/2025 | Yes | Yes | SDO | N/A | 2024-12-03 | 2024-12-31 | Yes | Yes | 15/G-33 Dt. 28/04/2025 | Dynamic Tiles | 23.1 | 2025-04-28 | 3 | 2026-09-30 |  | Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | 50% |  | 11.6 | Delayed/Held Up |  | Pending Sewer work to be done after monsoon
16 | MCL-0336 | O&M | A | A2 | Central | 56 | Water Supply | NA | Rough Cost Estimate Prov. Laying of Water Supply Line Gulchaman Gali and Its Branch line in Ward No. 56 |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 44 | -8.6% | 560 Dt.09/04/2025 | Yes | Yes | XEN | N/A | 2024-12-03 | 2024-12-31 | Yes | Yes | 16/G-33 Dt. 28/04/2025 | ESS Elechmech Enterprises | 40.2 | 2025-04-28 | 3 | 2026-07-30 |  | Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | 90% |  | 36.2 | In Progress |  | Duplicate file sent to FC&cc for approval
17 | MCL-0337 | O&M | A | A1 | Central | 9 | Sewerage | NA | Rough Cost Estimate Prov. Laying of Water Supply Line and Sewer Line From Sunder Nagar Pully to Bajwa Nagar Pully along Budha Dariya Ward No. 83 (old 61) | S/W 486.28 W/s 335.60 |  | 1 | MC Funds / General Quota | GQ | Awarded | 31.2 | -16.16% | 110 Dt.11/08/2025 | Yes | Yes | XEN | N/A | 11.04.2025 | 28.04.2025 | Yes | Yes | 49/G-33 Dt. 25/09/2025 | Ess Elecmech Enterprises | 26.2 | 2025-09-25 | 3 | 2026-09-30 | 2025-12-24 | Rajneesh Kumar JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | - |  | - | Not Started |  | Work hold due to road level issue
18 | MCL-0338 | O&M | A | A1 | Central | 84 | Sewerage | NA | Rough Cost Estmate Prov. Laying of Water Supply Line and Sewer Line in Maddi Bhature Wali Gali & Dr. Kheda wali Gali Ward No. 84 | S/W 205.79 W/s 181.4 |  | 1 | Councillor Quota (CQ) | CQ | Awarded | 21 | -14.76% | 2623 Dt.11/02/2026 | Yes | Yes | SDO | N/A | 2025-07-11 | 2-3/12/2025 | Yes | Yes | 84/G-33 Dt. 24/02/2026 | ESS Elechmech Enterprises | 17.9 | 2026-02-24 | 3 | 2026-07-30 | 2026-05-23 | Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | 100% |  | 7.15
19 | MCL-0339 | O&M | A | A1 | Central | 9 | Sewerage | NA | Rough Cost Estimate Prov. Laying of Water Supply and Sewer Line at Basti Mani Singh Ward No. 9 |  |  | 1 | Councillor Quota (CQ) | CQ | Awarded | 42.9 | -14.65% | 2606 Dt.11/02/2026 | Yes | Yes | XEN | N/A | 2025-07-11 | 2-3/12/2025 | Yes | Yes | 99/G-33 Dt. 24/02/2026 | Surya Construction | 36.6 | 2026-02-24 | 3 | 2026-09-30 |  | Rajneesh Kumar JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | 45% |  | 11 | In Progress |  | Work in Progress till 30-06-2026 & balance work will start after monsoon
20 | MCL-0340 | O&M | A | A2 | North | 90 | Sewerage | NA | Rough Cost Estimate Pro. Laying / Up-Gradation of Water Supply line, sewer line IN Thaper PCO wali gali and Hanuman mandir wali gali Ward No.90 | S/W 274.39 W/s 314 |  | 1 | Councillor Quota (CQ) | CQ | Awarded | 27.7 | -8.18% | 2478 Dt.05/01/2026 | Yes | Yes | SDO | N/A | 2025-11-21 | 15-16/12/2025 | Yes | Yes | 74/G-33 Dt. 30/01/2026 | Kohinoor Builders | 25.4 | 2026-01-30 | 3 | 2026-09-30 |  | Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | 60% |  |  | In Progress |  | Work delayed due to narrow sreets
21 | MCL-0341 | O&M | A | A2 | North | 90 | Sewerage | NA | Rough Cost Estimate Prov. Laying/Up-gradation and mtc. of Water Supply & Sewer Line At Different Localities of Ward No. 90 |  |  | 1 | Councillor Quota (CQ) | CQ | Awarded | 9.96 | -20.99% | 3285 Dt.25/02/2026 | Yes | Yes | SDO | N/A | 2025-07-11 | 2-3/12/2025 | Yes | Yes | 107/G-33 Dt. 27/03/2026 | N.S Infra | 7.9 | 2026-03-27 | 3 | 2026-08-31 |  | Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | 20% |  | 1.19 | In Progress |  | This work as per maintenance work
22 | MCL-0342 | O&M | A | A2 | North | 90 | Sewerage | NA | Rough Cost Estimate Prov. Laying / Up-Gradation of Water Supply Line, Sewer line (Missing Link) in Kucha No. 5,6,7 Field Ganj, Fish Market, Tyre Market Ward No. 64 |  |  | 1 | Councillor Quota (CQ) | CQ | Awarded | 48.7 | -8% | 1644 Dt14/02/2024 | Yes | Yes | XEN | N/A |  |  | Yes | Yes | 49/G-33 Dt. 29/02/2024 | The Rajowal Coop. L&C Society Ltd. | 45.7 | 2024-02-29 | 3 | 2026-10-30 |  | Sachin JE Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | 65% |  | 29.7 | In Progress |  | Work in Progress till 30-06-2026 & balance work will start after monsoon
23 | MCL-0343 | O&M | A | A2 | North | 90 | Water Supply | NA | Rough Cost Estimate Pro. Laying of Water Supply Line and Sewer Line in Backside Local Adda Streets Ward no. 90 | S/W 428.35 W/s 346.54 |  | 1 | Councillor Quota (CQ) | CQ | Awarded | 37.19 | -14.65% | 1675 Dt.13/10/2025 | Yes | Yes | XEN | N/A | 2025-07-11 | 2-3/12/2025 | Yes | Yes | 75/G-33 Dt. 30/01/2026 | Kohinoor Builders | 37.2 | 2026-01-02 | 3 | 2026-10-30 |  | Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | 80% |  | 18.6 | In Progress |  | Work in Progress till 30-06-2026 & balance work will start after monsoon
24 | MCL-0344 | O&M | A | A3 | East | 2 | Sewerage | 389807 | Providing, Laying / Up-Gradation of 16" & 24" dia. NP-3 HDPE pipe Sewer Line from Jivan Jyoti School to Phambran Disposal Ward No. 2 | S/W : 933.54 W/S: 45.73 | 15-30 Road width changes | 1 | MC Funds / General Quota | GQ | Awarded | 121.83 | -24.99% | 2239 dt.21/11/2025 | Yes | Yes | SE | N/A | 26.12.2025 | 21.01.2026 | Yes | Yes | 05/G-33/XEN/Z-A dt. 01/06/2026 | M/s Deepak Madaan | 91.39 | 01.06.2026 | 3 | 30.09.2026 | 30.09.2026 | Er. Parwinder Singh (JE) Er. Sukhdeep Singh(SDO) Er. Kamal Ram (XEN) | N/A | N/A | - | - | - | Not Started |  | Work will be done after monsoon
25 | MCL-0345 | O&M | A | A3 | East | 2,3 | Sewerage | 380141 | Providing, Laying /Up-gradation of 20" dia. NP=3 HDPE pipe Sewer Line from Phambran Disposal to Shivpuri Chownk. Ward No. 2 | S/W : 1778.66 W/S: 76.22 | 15-35 Road width changes | 1 | MC Funds / General Quota | GQ | Awarded | 126 | -13.13% | 2240 dt. 21/11/2025 | Yes | Yes | SE | N/A | 26.12.2025 | 21.01.2026 | Yes | Yes | 03/G-33/XEN/Z-A dt. 09/05/2026 | Kohinoor Builders | 109.42 | 09.05.2026 | 3 | 08.08.2026 | 31.08.2026 | Er. Parwinder Singh (JE) Er. Sukhdeep Singh(SDO) Er. Kamal Ram (XEN) | N/A | N/A | 80% | - | - | In Progress |  | Work in Progress. Earlier stopped but again started as per directions of MLA East
26 | MCL-0346 | O&M | A | A3 | East | 3 | Sewerage/Water supply | N/A | Providing, Laying Upgradation of 12'' dia UPVC Sewer Line and 4" dia. DI K7 water supply Line at Near Shani Dev Mandir, Extension Basant Vihar ward 3 | S/W : 356.71 W/S: 675.30 | 15 | 1 | Councillor Quota (CQ) | CQ | Awarded | 44.99 | -20.21 | 955 dt. 06/05/2025 | Yes | Yes | XEN | N/A | 2025-04-11 | 2025-04-28 | Yes | Yes | 19/G-33 Dt. 15/05/2025 | ESS Elechmech Enterprises | 35.89 | 2025-05-15 | 3 | 14.08.2025 | 15.08.2026 | Er. Parwinder Singh (JE) Er. Sukhdeep Singh(SDO) Er. Kamal Ram (XEN) | N/A | N/A | 100% | - | - | Completed
27 | MCL-0347 | O&M | A | A3 | East | 4 | Sewerage/Water supply | N/A | Providing, Laying 10'' dia UPVC Sewer Line at Vivek Dham and 4" dia. DI K7 water supply Line at Vivek Dham & Sant Cheema Singh Nagar ward 4 | S/W : 278.96 W/S: 670.73 | 22 | 1 | Councillor Quota (CQ) | CQ | Awarded | 38.53 | -20.19% | 1301 dt. 11/08/2025 | Yes | Yes | XEN | N/A | 11.04.2025 | 28.04.2025 | Yes | Yes | 42/G-33 Dt. 25/09/2025 | Kohinoor Builders | 30.75 | 2025-09-25 | 3 | 24.12.2025 | 31.08.2026 | Er. Parwinder Singh (JE) Er. Sukhdeep Singh(SDO) Er. Kamal Ram (XEN) | N/A | N/A | 70% | - | - | In Progress |  | Work in Progress. Earlier stopped but again started as per directions of MLA East
28 | MCL-0348 | O&M | A | A3 | East | 5 | Sewerage/Water supply | N/A | Providing Laying 10” UPVC SN-8 Sewer Line and 4” dia. DI K7 water supply Line at Beas Hosiery Complex at East Constituency. Ward 5 | S/W : 240.79 W/S: 926.83 | 25 | 1 | Councillor Quota (CQ) | CQ | Awarded | 44.47 | -23.31% | 2624 dt. 11/02/2026 | Yes | Yes | XEN | N/A | 2025-07-11 | 2-3/12/2025 | Yes | Yes | 87/G-33/XEN/Z-A dt. 24/02/2026 | Friends & Company | 34.1 | 2026-02-24 | 3 | 23.05.2026 | 15.08.2026 | Er. Parwinder Singh (JE) Er. Sukhdeep Singh(SDO) Er. Kamal Ram (XEN) | N/A | N/A | 100% | - | - | Completed |  | Completed
29 | MCL-0349 | O&M | A | A3 | East | 5 | Sewerage/Water supply | N/A | Providing , Laying 10”dia. UPVC pipe Sewer Line at Flower Vally and 4” dia. DI K7 water supply Line at Flower Vally & Gagandeep colony at East Constituency. Ward No. 5 | S/W : 251.46 W/S: 509.02 | 20 | 1 | Councillor Quota (CQ) | CQ | Awarded | 41.39 | -20.22% | 2666 dt. 11/02/2026 | Yes | Yes | XEN | N/A | 2025-11-07 | 2025-12-16 | Yes | Yes | 94/G-33/XEN/Z-A dt. 24/02/2026 | Friends & Company | 33.02 | 2026-02-24 | 3 | 23.05.2026 | 15.08.2026 | Er. Parwinder Singh (JE) Er. Sukhdeep Singh(SDO) Er. Kamal Ram (XEN) | N/A | N/A | 100% | - | - | Completed
30 | MCL-0350 | O&M | A | A3 | East | 6 | Sewerage | N/A | Providing, Laying Upgradation of 12" dia. UPVC SN-8 pipe Sewer Line from Kuldeep Nagar St No. 4 to near Mohalla Clinic ward 6 | S/W : 506.1 | 17 | 1 | Councillor Quota (CQ) | CQ | Awarded | 45.13 | -30.29% | 949 dt. 06/05/2025 | Yes | Yes | XEN | N/A | 2024-12-03 | 2024-12-31 | Yes | Yes | 20/G-33 Dt. 15/05/2025 | ESS Elechmech Enterprises | 31.46 | 2025-05-15 | 3 | 14.08.2025 | 31.08.2026 | Er. Parwinder Singh (JE) Er. Sukhdeep Singh(SDO) Er. Kamal Ram (XEN) | N/A | N/A | 100% | - | - | Completed
31 | MCL-0351 | O&M | A | A3 | East | 6 | Sewerage/Water supply | N/A | Providing, Laying ,Upgradation of sewer line NP-3 16'' Shere punjab School to Kailash Nagar Road, 4" dia. DI K7 W/s Line at Janta Colony, 6" dia. DI K7 w/s Line at Lucky Enclave to Basti Jodhewal Chownk ward 6 | S/W : 388.72 W/S: 487.81 | 16 | 1 | Councillor Quota (CQ) | CQ | Awarded | 47.3 | -17.22% | 2027 dt. 13/10/2025 | Yes | Yes | XEN | N/A | 11.04.2025 | 28.04.2025 | Yes | Yes | 55/XEN/Z-A Dt. 13/10/2025 | Kohinoor Builders | 39.15 | 2025-10-13 | 3 | 12.01.2026 | 15.08.2026 | Er. Parwinder Singh (JE) Er. Sukhdeep Singh(SDO) Er. Kamal Ram (XEN) | N/A | N/A | 90% | 26% | 1219845 | In Progress
32 | MCL-0352 | O&M | A | A3 | East | 6 | Water Supply | N/A | Providing laying Water Supply Line & Sewer Line at Kailash Nagar to Gehlewal and its Branch lines in East Constituency Zone-A | W/S: 1252.13 |  | 1 | MC Funds / General Quota | GQ | Awarded | 49.48 | -6.36% | 3386 dt. 05/12/2024 | Yes | Yes | XEN | N/A | 14.11.2024 | 02.12.2024 | Yes | Yes | 66/G-33 Dt. 05/12/2024 | M/s Rajdeep Enterprises | 46.33 | 05.12.2024 | 3 | 04.03.2025 | 31.08.2026 | Er. Parwinder Singh (JE) Er. Sukhdeep Singh(SDO) Er. Kamal Ram (XEN) | N/A | N/A | 60% | 2500% | 1220118 | In Progress |  | Balance work Case sent for site change. E.comp. No. 404820
348 | MCL-0353 | O&M | A | A4 | North | 86 | Storm Water Drainage | 381150 | Construction of Storm Water Disposal Well in Near Shani Mandir, Shivpuri Pully Ward No. 86 | 200 | - |  | Councillor Quota (CQ) | CQ | Awarded | 30.48 | -5.55% | 1444 11/08/2025 | Yes | Yes | XEN | N/A | 2025-05-19 | 2025-06-27 | Yes | Yes | 43/G-33 Dt. 25/09/2025 | M/s Kohinoor Builders | 29.13 | 2025-09-30 | 3 | 2026-07-30 |  | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN |  |  | 95% |  | 27.67 | In Progress |  | Work in Progress
349 | MCL-0354 | O&M | A | A4 | North | 86 | Storm Water Drainage | 379821 | Construction of Storm Water Disposal Well in Near Gandhi Nagar Pully Ward No. 86 | 330 | - |  | Councillor Quota (CQ) | CQ | Awarded | 24.7 | -7.86% | 1445 11/08/2025 | Yes | Yes | SDO | N/A | 2025-05-19 | 2025-06-27 | Yes | Yes | 46/G-33 Dt. 25/09/2025 | M/s Kohinoor Builders | 22.76 | 2025-09-30 | 3 | 2026-06-30 |  | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN |  |  | 95% |  | 21.62 | In Progress |  | Work in Progress
350 | MCL-0355 | O&M | A | A4 | North | 88 | Storm Water Drainage | NA | Making of Dispossal well at Shivpuri Pulli at ward no 88. |  | - |  | Councillor Quota (CQ) | CQ | Awarded | 25.78 | 6.66% | 2076 13/10/2025 | Yes | Yes | XEN | N/A | 2025-05-19 | 2025-06-27 | Yes | Yes | 61/G-33 Dt. 03/11/2025 | M/s Kohinoor Builders | 24.03 | 2025-08-11 | 1 | 2026-06-30 |  | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN |  |  | 95% |  | 22.83 | In Progress |  | Work in Progress
351 | MCL-0356 | O&M | A | A4 | North | 70,88,89 | Others | NA | Construction of Toilet Set in Ward No. 70,88,89 (under SBM 2.0) | - | - | 3 | SBM (Swachh Bharat Mission) | SBM | Awarded | 30.38 | 5.54% | 1643 13/10/2025 | Yes | Yes | XEN | N/A | 2025-05-19 | 2025-06-27 | Yes | Yes | 63/G-33 Dt. 03/11/2025 | M/s Ess Elecmech Enterprises | 28.7 | 2025-10-11 | 2 | 2026-07-30 |  |  |  |  | 45% |  | 12.92 | In Progress |  | site issue
352 | MCL-0357 | O&M | A | A4 | North | 89 | Sewerage | NA | Rehabilitation/Diversion of Existing Sewer line with Dia 18" RCC HDPE Pipe at Janjh Ghar Road and Manna Singh Nagar to close the Dhakka colony outlet point fall in Buddah Daria in Ward no. 89 |  | - |  | Councillor Quota (CQ) | CQ | Awarded | 68.16 | 7.62% | 2655 11/02/2026 | Yes | Yes | SDO | N/A | 2025-11-07 | 2025-12-16 | Yes | Yes | 77/G-33 Dt. 30/01/2026 | M/s Joytee Builders | 55.86 | 2026-05-02 | 3 | 1900-01-10 |  |  |  |  | 60% |  | 33.52 | In Progress |  | balance work will be done after monsoon
353 | MCL-0358 | O&M | A | A4 | North | 89 | Sewerage | NA | Prov. & Laying of Sewer Line at Nalli Mohalla Chowani Mohalla Shani Mandir Piru Banda Mohalla Ward No. 89 |  | - |  | MC Funds / General Quota | GQ | Awarded | 33.29 | 8% | 2621 11/02/2026 | Yes | Yes | SDO | N/A | 2025-11-07 | 2025-12-16 | Yes | Yes | 90/G-33 Dt. 24/02/2026 | Surya Construction | 30.63 | 2026-02-28 | 4 | 2026-10-15 |  |  |  |  | 20% |  | 6.13 | In Progress |  | narrow streets manual work in progress
354 | MCL-0359 | O&M | A | A4 | North | 88 | Sewerage | NA | Rehablitation of sewer line at Surinder Nagar Chand Cinena Adjoining Petrol Pump & Noor Maszid Ward No. 88 | 1106 | - |  | Councillor Quota (CQ) | CQ | Awarded | 48.44 | -18.19% | 2611 11/02/2026 | Yes | Yes | SDO | N/A | 2025-11-07 | 2025-12-16 | Yes | Yes | 93/G-33 Dt. 24/02/2026 | ESS Elechmech Enterprises | 39.63 | 2026-02-28 | 4 | 2026-10-30 |  | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN |  |  | 15% |  | 5.94 | In Progress |  | narrow streets manual work in progress
355 | MCL-0360 | O&M | A | A4 | North | 8,86 | Sewerage | NA | Making of additional manhole scaver points others miscellaneous works in ward no. 8 & 86 | - | - |  | Councillor Quota (CQ) | CQ | Awarded | 41.46 | 29.99% | 2604 11/02/2026 | Yes | Yes | XEN | N/A | 2025-11-07 | 2025-12-16 | Yes | Yes | 82/G-33 Dt. 24/02/2026 | Prince Sharma | 29.03 | 30-02-2026 | 3 | 2026-07-15 |  | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN |  |  | 35% |  | 10.16 | In Progress |  | maintenance type work
356 | MCL-0361 | O&M | A | A4 | North | 86 | Sewerage | NA | Rough Cost Estimate Prov. Laying/Up-gradation and mtc. of Water Supply & Sewer Line At Different Localities of Ward No. 8 and 86. | 415 | - |  | MC Funds / General Quota | GQ | Awarded | 32.7 | 27.86% | 2605 11/02/2026 | Yes | Yes | XEN | N/A | 2025-11-07 | 2025-12-16 | Yes | Yes | 98/G-33 Dt. 24/02/2026 | RS Builders | 23.59 | 2026-03-03 | 3 | 2026-07-15 |  | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN |  |  | 10% |  | 2.36 | In Progress |  | Material is reached at site
357 | MCL-0362 | O&M | A | A4 | North | 8 | Water Supply | NA | Rough Cost Estimate Prov. Laying of Sewer Line and Water Supply Line in Sarvanand Colony Ward No. 8 | 503 | - |  | MC Funds / General Quota | GQ | Awarded | 49.87 | 25% | 2610 11/02/2026 | Yes | Yes | SDO | N/A | 2025-11-07 | 2025-12-16 | Yes | Yes | 89/G-33 Dt. 24/02/2026 | Prince Sharma | 18.7 | 2026-02-28 | 3 | 2026-05-07 |  | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN |  |  | 80% |  | 14.96 | In Progress |  | Work in Progress
358 | MCL-0363 | O&M | A | A4 | North | 88 | Water Supply | NA | Up- Gradartion of Water Supply Line in Fatehgarh Mohalla Near Noori Maszid Ward No. 88 | 427 | - |  | MC Funds / General Quota | GQ | Awarded | 48.44 | 2.5% | 2620 11/02/2026 | Yes | Yes | JE | N/A | 2025-11-07 | 2025-12-16 | Yes | Yes | 102/G-33 Dt. 02/03/2026 | Kohinoor Builders | 10.32 | 2026-05-03 | 3 | 2026-11-15 |  | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN |  |  | 5% |  | 0.52 | In Progress |  | Work will be started after rain
359 | MCL-0364 | O&M | A | A4 | North | 95 | Water Supply | NA | Providing & Installation of 25 HP Straight Bore T/Well Guru Har Rai Nagar Ward No. 95 | - | - |  | MC Funds / General Quota | GQ | Awarded | 15.05 | -19.68% | 2609 11/02/2026 | Yes | Yes | SDO | N/A | 2025-11-07 | 2025-12-16 | Yes | Yes | 92/G-33 Dt. 24/02/2026 | Rajdeep Enterprises | 12.09 |  | 3 | [7 empty] | - | Not Started |  | File sent for change of site
360 | MCL-0365 | O&M | A | A4 | North | 86 | Water Supply | NA | Providing & Installation of 25 HP Straight Bore Tubewell against failed Tubewell In Dr. Ashwani Clinic Ward No. 86 | - | - |  | MC Funds / General Quota | GQ | Awarded | 12.72 | -15.54% | 2618 11/02/2026 | Yes | Yes | SDO | N/A | 2025-11-07 | 2025-12-16 | Yes | Yes | 91/G-33 Dt. 24/02/2026 | Rajdeep Enterprises | 10.74 |  | 3 |  |  | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN |  |  |  |  | - | Not Started |  | site issue
361 | MCL-0366 | O&M | A | A4 | North | 87 | Water Supply | NA | Rehabilitation Missing Link of Water Supply line and Sewer line in Ward No. 87 | - | - |  | MC Funds / General Quota | GQ | Awarded | 31.2 | 15.15% |  | Yes | Yes | SDO | N/A |  |  | Yes | Yes | 58/G-33 Dt. 02/12/2024 | Rajdeep Enterprises | 26.46 | 2024-12-15 | 2 |  |  | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN |  |  | 95% |  | 25.14 | In Progress |  | File sent for 25% Enhancement
362 | MCL-0367 | O&M | A | A4 | North | 86 | Sewerage | 391646 | Prov. Laying of Water Supply Line and Sewer Line in Bal Singh Nagar Gli No. 8 and Pritampuri, Ward No. 86. | 307 | - |  | Councillor Quota (CQ) | CQ | Awarded | 28.52 | 8% | 3381 05/12/2024 | Yes | Yes | SDO | N/A |  |  | Yes | Yes | 62/G-33 Dt. 05/12/2024 | surya contractor | 26.24 | 2024-08-12 | 3 |  |  | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN |  |  | 95% |  | 24.93 | In Progress |  | File sent for 25% Enhancement
363 | MCL-0368 | O&M | A | A4 | North | 85 | Water Supply | NA | Providing & Laying 4" Water Supply Line at Gandhi Nagar, ward no.85. | 1993 | - |  | Councillor Quota (CQ) | CQ | Awarded | 49.97 |  |  | Yes | Yes | XEN | N/A |  |  | Yes | Yes | 11/G-33 Dt. 28/04/2025 | Bedi Pump Store | 47.42 | 2025-05-05 | 3 | 2026-07-15 |  |  |  |  | 85% |  | 40.31 | In Progress |  | narrow streets manual work in progress
364 | MCL-0369 | O&M | A | A4 | North | 85 | Water Supply | NA | Rehablitation of Water Supply line Due to Water Conteminations at Basant Nagar/ Gandhi Nagar, Ward no.85 | 1937 | - |  | Councillor Quota (CQ) | CQ | Awarded | 49.38 | 4.59% | 1128 11/08/2025 | Yes | Yes | XEN | N/A | 11.04.2025 | 28.04.2025 | Yes | Yes | 48/G-33 Dt. 25/09/2025 | Bedi Pump Store | 47.11 | 2025-09-30 | 3 | 2026-07-15 |  |  |  |  | 80% |  | 37.69 | In Progress |  | narrow streets manual work in progress
365 | MCL-0370 | O&M | A | A4 | North | 1,95 | Water Supply | NA | Rehabilitation/Missing link of Water Supply line and Sewer Line in Different Localities Ward No.1 & 95. | - | - |  | Councillor Quota (CQ) | CQ | Awarded | 31.72 |  |  | Yes | Yes | XEN | N/A | 11.04.2025 | 28.04.2025 | Yes | Yes | 62/G-33 Dt. 03/11/2025 | Dynamic Tiles | 26.96 | 2025-08-11 | 2 | 2026-07-15 |  | Balwinder Singh JE Himanshu Sharma JE Anshul Garcha SDO KamalRam XEN |  |  | 80% |  | 21.57 | In Progress |  | Work in Progress
366 | MCL-0371 | O&M | A | A4 | North | 84 | Water Supply | NA | Rehablitation of Water Supply line Due to Water Conteminations at Various Areas in North Consitituency Like Dakka Colony, Peeru Mohalla, Karabara Chownk & Badour House | 923 | - |  | Councillor Quota (CQ) | CQ | Awarded | 36.89 | 26.55% | 2026-11-02 | Yes | Yes | XEN | N/A | 2025-12-26 | 2026-01-23 | Yes | Yes | 81/G-33 Dt. 24/02/2026 | Prince Sharma | 34.08 | 2026-02-28 | 3 | 2026-07-15 |  |  |  |  | 40% |  | 13.63 | In Progress |  | Work in Progress
367 | MCL-0372 | O&M | A | A4 | North | 88 | Sewerage | NA | Rough Cost Estimate Prov. Laying Up-gradation of water supply line and sewer line at Sekhewal 60' Road, Ward No. 88. | 563 | - |  | Councillor Quota (CQ) | CQ | Awarded | 39.05 | 23.1% | 2613 11/02/2026 | Yes | Yes | SDO | N/A | 2025-12-26 | 2026-01-23 | Yes | Yes | 96/G-33 Dt. 24/02/2026 | Sushil Kumar Contractor | 30.03 | 2026-07-03 | 4 | 2026-07-30 |  | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN |  |  | 10% |  | 3 | In Progress |  | Work in Progress
53 |  | O&M |  |  | East | 7 | Water Supply | NA | Providing & Installation of 25 HP Straight Bore T/Well at Gujjar Colony, Jagirpur Road in Ward No. 7 (against failed tubewell) (Now Jain Colony) . |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 12.62 |  |  | Yes | Yes |  | N/A |  |  | Yes | Yes | [13 empty] | Not Started
54 | MCL-0373 | O&M | B | B3 | East | 7 | Water Supply |  | Providing & Installing of 25 HP Deep straight Bore Tubewell at Atal Nagar in Ward No. 7 (MP LAD Scheme). | NA | NA | 1 | MPLAD Funds | MP LAD | Awarded | 13.5 | 19.68% | 2750 19-02-2026 | Yes | Yes | XEN | N/A | 2025-11-07 | 2025-12-15 | Yes | Yes | 114/G33 06-03-2026 | Rajdeep Enterprises | 10.84 | 2025-10-11 | 3 | 2026-10-07 |  | Ramandeep Singh-J.E Sukhdeep Singh-SDO Baljinder Singh-XEN | N/A | N/A | 100% |  | 9.76 | Completed
55 | MCL-0374 | O&M | B | B3 | East | 7 | Water Supply |  | Rough Cost Estimate for P/L of 4” dia DIK7 water supply line at Atal Nagar, St. No. 2,3,4 & 5 in W. No. 7. |  | __ | 1 | MC Funds / General Quota | GQ | Awarded | 61.99 | 1.89% | 1377 11-08-2025 | Yes | Yes | SE | N/A | 2024-11-14 | 2024-12-31 | Yes | Yes | 66/G33 07-11-2025 | CNC Precision Engineering | 60.82 | 10-Nov-1015 | 3 | 2026-08-31 |  | Ramandeep Singh-J.E Sukhdeep Singh-SDO Baljinder Singh-XEN | N/A | N/A | 50% |  | 15.21 | In Progress |  | Work in progress
56 | MCL-0375 | O&M | B | B3 | East | 11 | Water Supply |  | Rough Cost Estimate for Upgradation of 4” dia DIK7 water supply line in various areas of W. No. 9. |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 38.61 | 1.71% | Approved in anticipation of F&CC vide order dated 14-02-2025 | Yes | Yes | XEN | N/A | 2024-12-03 | 2024-12-12 | Yes | Yes | 257/G33 17-03-2025 | CNC Precision Engineering | 37.95 | 2025-03-20 | 3 | 2026-10-07 |  | Ramandeep Singh-J.E Sukhdeep Singh-SDO Baljinder Singh-XEN | N/A | N/A | 100% |  | 30.36 | Completed
57 | MCL-0376 | O&M | B | B3 | East | 13 | Water Supply |  | Rough cost estimate for Up gradation of 4” dia DIK-7 water supply line and missing link of 8” UPVC sewer line in various areas of W. No. 13 |  |  | 2 | MC Funds / General Quota | GQ | Awarded | 95.16 | 20.21% | 935 06-05-2025 | Yes | Yes | SE | N/A | 2025-04-11 | 2025-04-28 | Yes | Yes | 45/G33 14-05-2025 | A.B. Construction Co. | 75.93 | 2025-05-15 | 4 | 2026-07-15 |  | Ramandeep Singh-J.E Sukhdeep Singh-SDO Baljinder Singh-XEN | N/A | N/A | 90% |  | 68.34 | In Progress |  | Work in progress
58 | MCL-0377 | O&M | B | B3 | East | 13 | Water Supply |  | Rough cost estimate for Up gradation of 4” & 6” dia DIK-7 water supply line in various areas of W. No. 13 |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 20.17 | 15.39% | 938 06-05-2025 | Yes | Yes | XEN | N/A | 2025-04-11 | 2025-04-28 | Yes | Yes | 39/G33 14-05-2025 | CNC Precision Enginering | 17.07 | 2025-05-15 | 2 | 2026-07-15 |  | Ramandeep Singh-J.E Sukhdeep Singh-SDO Baljinder Singh-XEN | N/A | N/A | 100% |  | 15.36 | Completed
59 | MCL-0378 | O&M | B | B3 | East | 14 | Water Supply |  | Upgradation of 4” dia DIK7 water supply line and 8” & 12” UPVC Sewer line at New Karamsar Colony in W. No. 14. |  |  | 1 | Councillor Quota (CQ) | CQ | Awarded | 81.01 | 25% | 3343 21-04-2026 | Yes | Yes | SE | N/A | 2025-11-07 | 2025-12-02 | Yes | Yes | 146/G33 07-05-2026 | Manmohan Singh Contractor | 60.76 | 2026-10-05 | 4 | 2026-11-15 |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | N/A | N/A | 50% |  | 30.38 | In Progress |  | Balance work will be done after rainy season
60 | MCL-0379 | O&M | B | B4 | East | 19 | Sewerage |  | Prov/Laying of 12” UPVC pipe at Kirti Nagar, St. No. 3&4, at W. No. 19 in East Constituency (Upgradation). | S/W 207.31 | N/A | 1 | Councillor Quota (CQ) | CQ | Awarded | 13.94 | -30.6% | 2882 Dt.19/02/2026 | Yes | Yes | XEN | N/A | 2025-12-26 | 2025-01-13 | Yes | Yes | 119/G33 06-03-2026 | Ess Elechmech Enterprises | 9.67 | 2026-03-06 | 2 | 2026-11-15 |  | Harinder Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | - | - | - | Not Started |  | Material reached at site, Work Start after monsoon
61 | MCL-0380 | O&M | B | B3 | East | 14,15,18&29 | Water Supply |  | Rough Cost Estimate for P/L of 4” dia DIK7 water supply line in various wards of East Constituency (Missing Link). |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 18.72 | 1.71% | Approved in anticipation of F&CC vide order dated 14-02-2025 | Yes | Yes | XEN | N/A | 2024-12-03 | 2024-12-12 | Yes | Yes | 269/G33 17-03-2025 | CNC Precision Engineering | 18.4 | 2026-03-20 | 3 | 2026-07-31 |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | N/A | N/A | 80% |  | 14.72 | In Progress |  | Work in progress
62 | MCL-0381 | O&M | B | B3 | East | 17 | Water Supply |  | Providing & Installing of 25 HP Deep straight Bore Tubewell at Shiv Shankar Colony in Ward No. 17. | N/A | N/A | 1 | MC Funds / General Quota | GQ | Awarded | 12.62 | 20.09% | 3278 25-02-2026 | Yes | Yes | XEN | N/A | 2025-12-26 | 2026-01-13 | Yes | Yes | 125/G33 25-03-2026 | Bedi Pump Store | 10.08 | 2026-03-26 | 3 | 2026-07-15 |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | N/A | N/A | 60% |  | 6.05 | In Progress |  | Work in progress
63 | MCL-0382 | O&M | B | B4 | East | 19 | Sewerage |  | Pro/Laying of 12” UPVC Pipe at 177 Welfare Society, Sector-39, Ward No-19 in East Constituency. (Upgradation). | S/W 146.34 | N/A | 1 | Councillor Quota (CQ) | CQ | Awarded | 9.21 | -29.13% | 3351 Dt 21/04/2026 | Yes | Yes | XEN | N/A | 2026-02-05 | 2026-02-16 | Yes | Yes | 136/G33 07-05-2026 | Bedi Pump Store | 6.53 | 2026-05-07 | 3 | 2026-09-30 |  | Harinder Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | 50% | - | 5.88 | In Progress |  | Work in progress
64 | MCL-0383 | O&M | B | B3 | East | 20 | Water Supply |  | Providing & Installing of 12.5 HP Deep straight Bore Tubewell at Bhola Colony, Nr. Gurdwara Sahib in Ward No. 20. | N/A | N/A | 1 | MC Funds / General Quota | GQ | Awarded | 5.82 | 17.24% | 2709 19-02-2026 | Yes | Yes | XEN | N/A | 2025-11-07 | 2025-12-02 | Yes | Yes | 99/G33 06-03-2026 | Sai Enterprises | 4.82 | 2026-10-03 | 2 | 2026-07-31 |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | N/A | N/A | - |  | - | Not Started |  | Work will start next week
65 | MCL-0384 | O&M | B | B3 | East | 20 | Water Supply |  | Rough cost Estimate for providing & Installing of 25 HP Deep straight Bore Tubewell at Mahajan Vihar in Ward No. 20. | N/A | N/A | 1 | MC Funds / General Quota | GQ | Awarded | 12.62 | 16.33% | 2747 19-02-2026 | Yes | Yes | XEN | N/A | 2025-08-13 | 2025-08-28 | Yes | Yes | 101/G33 06-03-2026 | CNC Precision Engineering | 10.56 | 2026-06-03 | 3 | 2026-10-07 |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | N/A | N/A | 95% |  | 10.03 | In Progress |  | Work in progress
66 | MCL-0385 | O&M | B | B4 | East | 26 | Water Supply |  | Pro/Laying DIK-7 water supply line 6”, 4” at Focal Point, Phase-4A (Replace of old water supply line) W. No. 26, in East Constituency. | W/S 4"=2300 W/S 6"=1200 | N/A | 1 | MC Funds / General Quota | GQ | Awarded | 86.33 | -11.58% | 2427 Dt 05/01/2026 | Yes | Yes | XEN | N/A | 2025-05-08 | 2025-05-23 | Yes | Yes | 92/G33 19-01-2026 | Baljit Singh Gill | 76.33 |  | 3 |  |  | Harinder Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | - | - | - | Not Started |  | Site Changed
67 | MCL-0386 | O&M | B | B4 | East | 26 | Water Supply |  | Providing & Installing of 25 HP Deep straight Bore Tubewell at Rajiv Gandhi Colony in Ward No. 26. | NA | N/A | 1 | MC Funds / General Quota | GQ | Awarded | 12.64 | -17.25% | 2854 Dt 19/02/2026 | Yes | Yes | XEN | N/A | 2025-11-07 | 2025-12-02 | Yes | Yes | 105/G33 06-03-2026 | ESS Elechmech Enterprises | 10.46 | 2026-03-06 | 3 |  |  | Harinder Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | 100% |  | 9.41 | Delayed/Held Up |  | Electric Connection Pending
68 | MCL-0387 | O&M | B | B4 | East | 26 | Water Supply |  | Rough Cost Estimate for Prov/Installation of New 25HP Deep Straight Bore Tubewell at Rajiv Gandhi Colony, HE Colony, Ward No. 26 (M.P Quota) in East Constituency. | NA | N/A | 1 | MPLAD Funds | MP Quota | Awarded | 12.59 | -21.39% | 3352 Dt 21/04/2026 | Yes | Yes | XEN | N/A | 2026-02-05 | 2026-02-16 | Yes | Yes | 135/G33 07-05-2026 | Rajdeep Enterprises | 9.89 | 2026-05-07 | 3 | 2026-09-30 |  | Harinder Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | - |  | - | Not Started |  | Notice Issued to Contractor,
69 | MCL-0388 | O&M | B | B3 | East | 29 | Water Supply |  | Providing & Installing of 25 HP Deep straight Bore Tubewell at L.I.G Flat in Ward No. 29 (MP LAD Scheme). | NA | N/A | 1 | MPLAD Funds | MP LAD | Awarded | 13.5 | 19.68% | 2851 19-02-2026 | Yes | Yes | XEN | N/A | 2025-11-07 | 2025-12-02 | Yes | Yes | 102/G33 06-03-2026 | Rajdeep Enterprises | 10.84 | 2026-07-03 | 3 |  |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | N/A | N/A | - |  | - | Delayed/Held Up |  | Delyed due to site dispute
70 | MCL-0389 | O&M | B | B3 | East | 29 | Water Supply |  | Providing & Installing of 25 HP Deep straight Bore Tubewell at Vishkarma Nagar, Nr. Baba Deep Singh Gurdwara in Ward No. 29 (against 25 HP failed tubewell) | NA | N/A | 1 | MC Funds / General Quota | GQ | Awarded | 12.62 | 21.09% | 3342 21-04-2026 | Yes | Yes | XEN | N/A | 2026-02-05 | 2026-02-16 | Yes | Yes | 142/G33 07-05-2026 | Bedi Pump Store | 9.96 | 2026-10-05 | 4 | 2026-08-30 |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | N/A | N/A | - |  | - | Not Started |  | Work will start by 1/7/2026
71 | MCL-0390 | O&M | B | B3 | East | 7 | Sewerage |  | Rough Cost Estimate for Upgradation of 10" & 12” UPVC SN-8 sewer line at Indra Colony & Chanderlok Colony in W. No. 7. |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 87.88 | 24.99% | Approved in anticipation of F&CC vide order dated 14-02-2025. | Yes | Yes | SE | N/A | 2024-11-14 | 2024-12-02 | Yes | Yes | 267/G33 17-03-2025 | CNC Precision Engg. | 65.92 | 2025-03-20 | 3 | 2026-07-20 |  | Ramandeep Singh-J.E Sukhdeep Singh-SDO Baljinder Singh-XEN | N/A | N/A | 70% |  | 46.14 | Balance work will be done after monsoon |  | Balance work will be done after monsoon
72 | MCL-0391 | O&M | B | B3 | East | 7 | Sewerage |  | Rough Cost Estimate for Upgradation of 8” UPVC SN-8 sewer line at Golden Colony in W. No. 7. |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 70.1 | 24.99% | Approved in anticipation of F&CC vide order dated 14-02-2025. | Yes | Yes | SE | N/A | 2024-11-14 | 2024-12-02 | Yes | Yes | 265/G33 17-03-2025 | CNC Precision Engg. | 52.58 | 2025-03-20 | 3 | 2026-09-30 |  | Ramandeep Singh-J.E Sukhdeep Singh-SDO Baljinder Singh-XEN | N/A | N/A | 40% |  | 13.15 | Balance work will be done after monsoon |  | Balance work will be done after monsoon
73 |  | O&M | B | B3 | East | 11 | Sewerage |  | Upgradation of 8" UPVC SN-8 sewer line at Gulabi Bagh, Prem Vihar, Charan Nagar & Juneja Colony in W. No. 11, 12 & 13. |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 34.7 | 24.99% | Approved in anticipation of F&CC vide order dated 14-02-2025. | Yes | Yes | SE | N/A | 2024-11-14 | 2024-12-02 | Yes | Yes | 264/G33 17-03-2025 | CNC Precision Engg. | 26.03 |  | 3 |  |  | Ramandeep Singh-J.E Sukhdeep Singh-SDO Baljinder Singh-XEN | N/A | N/A |  |  |  | Not Started
74 | MCL-0392 | O&M | B | B3 | East | 17 | Water Supply |  | Prov/Laying of 6" DIK7 water suplly line at Main Tibba Road Dump Site in W. No. 17 (GQ) |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 43.87 | 16.8% | 3345 21-04-2026 | Yes | Yes | SE | N/A | 2026-02-05 | 2026-02-16 | Yes | Yes | 143/G33 07-05-2026 | Friends and Company | 36.49 | 2026-08-05 | 3 | 2026-11-15 |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | N/A | N/A | - |  | - | Not Started |  | Work will start after monsoon
75 | MCL-0393 | O&M | B | B3 | East | 17 | Sewerage |  | Prov/Laying of 30" RCC NP3 sewer line at Mahavir jain (Puneet Nagar) in W. No. 17 (GQ) |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 52.54 | 27% | 3340 21-04-2026 | Yes | Yes | SE | N/A | 2026-02-05 | 2026-02-16 | Yes | Yes | 144/G33 07-05-2026 | Surya Construction | 38.35 | 2026-08-05 | 3 | 2026-10-15 |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | N/A | N/A | - |  | - | Not Started |  | Work will start after monsoon
76 | MCL-0394 | O&M | B | B3 | East | 17 | Sewerage |  | Prov/Laying of 18" RCC NP3 sewer line at Main Tibba Road Dump Site in W. No. 17 (GQ) |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 59.84 | 27% | 3337 21-04-2026 | Yes | Yes | SE | N/A | 2026-02-05 | 2026-02-16 | Yes | Yes | 140/G33 07-05-2026 | Surya Construction | 43.68 | 2026-08-05 | 4 | 2026-11-15 |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | N/A | N/A | - |  | - | Not Started |  | Work will start after monsoon
77 | MCL-0395 | O&M | B | B3 | East | 19 | Sewerage |  | Pro/Laying of 12” UPVC pipe at GRD Colony, Sector-39, W. No. 19, in East Constituency. (Upgaddation). |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 60.13 | 33.1% | 2426 05-01-2026 | Yes | Yes | SE | N/A | 2026-02-05 | 2026-02-16 | Yes | Yes | 91/G33 19-01-2026 | Glisten | 40.23 | 2026-01-20 | 3 | 2026-07-20 |  | Harinder Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | 90% |  | 36.21 | In Progress |  | Work in progress
78 | MCL-0396 | O&M | B | B4 | East | 19 | Sewerage |  | Prov/Laying of 12” UPVC pipe at Sec-39, Back side Pal Petrol Pump in W. No. 19 in East Constituency (Upgradation). | S/W 289.63 | N/A | 1 | Councillor Quota (CQ) | CQ | Awarded | 14.1 | -27.86% | 2855 Dt19/02/2026 | Yes | Yes | SDO | N/A | 2025-11-07 | 2025-12-02 | Yes | Yes | 106/G33 06-03-2026 | R.S. Builders | 10.17 | 2026-03-06 | 3 |  |  | Harinder Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | 20% |  | 6.1 | In Progress |  | Work in progress
79 | MCL-0397 | O&M | B | B3 | East | 20 | Sewerage |  | Rough Cost Estimate for Prov/Laying of 8" UPVC Sewer line at New GRD Nagar in Ward No. 16 (Site Changed) |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 16.35 | -20.8 | 2420 23-08-2024 | Yes | Yes | SDO | N/A | 2024-03-07 | 2024-06-11 | Yes | Yes | 145/G33 9/18/2024 | The Sutlej Co-Op L&C Society Ltd. | 12.95 | 2024-09-20 | 3 | 2026-10-30 |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | N/A | N/A | 50% |  | 6.48 | In Progress |  | File Approved in F&CC dated:- 24/06/2026 for change of site now work started again
80 | MCL-0398 | O&M | B | B4 | East | 28 | Sewerage |  | Pro/Laying of 12” UPVC pipe at Street No. ¼, Heera Nagar, in W. No. 28 in East Constituency. | S/W 167.68 | N/A | 1 | MC Funds / General Quota | GQ | Awarded | 6.93 | -28.62% | 1750 Dt 13/10/2025 | Yes | Yes | SDO | N/A | 2025-05-08 | 2025-05-23 | Yes | Yes | 84/G33 07-11-2025 | Rajdeep Enterprises | 4.95 | 2025-11-07 | 2 | 2026-08-10 |  | Harinder Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | 20% |  | 0.99 | Not Started
81 | MCL-0399 | O&M | B | B4 | East | 26 | Sewerage |  | Construction of Additional Machine hole chamber at Vishkarma Colony in W. No. 26. | N/A | N/A | 1 | Councillor Quota (CQ) | CQ | Awarded | 1.92 | -28.77% | 3360 Dt21/04/2026 | Yes | Yes | SDO | N/A | 2026-02-05 | 2026-02-16 | Yes | Yes | 147/G33 07-05-2026 | K.B. Builders | 1.37 | 2026-05-07 | 2 | 2026-10-30 |  | Harinder Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | - |  | - | Not Started |  | Work Start After Mansoon
82 | MCL-0400 | O&M | B | B3 | East | 29 | Water Supply |  | Prov/Laying of 8” UPVC Sewer line and 4” dia DIK7 water supply line missing link at various streets of G.A.D Nagar in W. No. 29 (C.Q). |  |  | 2 | Councillor Quota (CQ) | CQ | Awarded | 7.02 | 24.99% | 2513 05-01-2026 | Yes | Yes | SDO | N/A | 2025-11-07 | 2025-12-02 | Yes | Yes | 95/G33 27/1/2026 | Sushil Contractor | 5.27 | 2026-01-30 | 2 | 2026-07-15 |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | N/A | N/A | 80% |  | 4.22 | In Progress |  | Work in progress
83 | MCL-0401 | O&M | B | B3 | East | B | Sewerage |  | Upgradation of M/Hole Chamber of main 48” Sewer line at Dump Site (Tibba Road). |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 24.83 | 26.2% | 3277 25-02-2026 | Yes | Yes | SDO | N/A | 2025-12-26 | 2026-01-13 | Yes | Yes | 124/G33 25-03-2026 | Kohinoor Builders | 18.33 | 2026-03-25 | 2 | 2026-10-15 |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | N/A | N/A | 40% |  | 7.33 | In Progress |  | Balance Work will start after monsoon
84 | MCL-0402 | O&M | B | B3 | East | B3 | Sewerage |  | Construction of Raising of manhole hole chambers and Prov and fixing of manhole cover sets i.e EHD, HD, MD sets in different localities of East Constituency (GQ) |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 36.65 | 32.78% | 3400 21-04-2026 | Yes | Yes | SDO | N/A | 2026-02-05 | 2026-02-16 | Yes | Yes | 131/G33 07-05-2026 | Prince Sharma | 24.64 | 2026-10-05 | 3 | 2026-11-15 |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | N/A | N/A | - |  | - | Not Started |  | Work will start after monsoon
85 | MCL-0403 | O&M | B | B3 | East | B | Sewerage |  | Prov.& Laying Of 1100MM RCC NP-3 class Sewer line at Tajpur MPS chowk to Tajpur road Police Chonky Nr. Central Jail (G.Q) |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 191.28 | 30.6% | 3338 21-04-2026 | Yes | Yes | SE | N/A | 2025-12-26 | 2026-01-21 | Yes | Yes | 130/G33 07-05-2026 | Ludhiana Construction Company | 132.75 | 2026-10-05 | 6 | 2026-10-07 |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | N/A | N/A | 30% |  | 39.83 | In Progress |  | Work in progress
86 | MCL-0404 | O&M | B | B3 | East | B3 | Sewerage |  | Providing & Laying of 250mm, 300mm, 400mm & 600mm RCC NP3 HDPE Line & UPVC SN-8 Sewer line at Mahavir Jain Textile Colony. |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 177.32 | 28.62% | 3341 21-04-2026 | Yes | Yes | SE | N/A | 2025-12-26 | 2026-01-21 | Yes | Yes | 145/G33 07-05-2026 | Ludhiana Construction Company | 126.57 | 2026-07-05 | 6 | 2027-02-28 |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | N/A | N/A | - |  | - | Not Started |  | Work will start after monsoon
87 | MCL-0405 | O&M | B | B3 | East | B | Sewerage |  | Prov.& Laying Of 1000MM RCC NP-3 class Sewer line at Vardhman Chowk to MPS (Tajpur Road) in Sub Zone-B3. |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 256.39 | 30.6% | Approved in anticipation of F&CC vide order dated 21-05-2026. | Yes | Yes | CE | N/A | 2025-12-26 | 2026-01-21 | Yes | Yes | 149/G33 21-05-2026 | Ludhiana Construction Company | 177.93 | 2026-05-22 | 6 | 2026-12-31 |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | N/A | N/A | - |  | - | Not Started |  | Work will start after work order no. 130
88 |  | O&M | B | B3 | East | B3 | Sewerage |  | Providing & Laying of 200mm, 400mm, 800mm & 900mm RCC NP3 Sewer line at Jaswal Complex. |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 305.62 | 9.5% | Approved in anticipation of F&CC vide order dated __________. | Yes | Yes | CE | N/A | 2026-02-24 | 2026-03-09 | Yes | Yes | 151/G33 26-07-2026 | M/s Glisten | 276.59 |  | 6 | 2027-01-25 |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | N/A | N/A |  |  |  | Not Started
89 |  | O&M | B | B3 | East | B3 | Sewerage |  | Providing & Laying of 200mm, 400mm & 450mm RCC NP3 HDPE Line & UPVC SN-8 Sewer line at Mahavir Jain Complex. |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 300.83 | 9.5% | Approved in anticipation of F&CC vide order dated __________. | Yes | Yes | CE | N/A | 2026-02-24 | 2026-03-09 | Yes | Yes | 150/G33 26-07-2026 | M/s Glisten | 272.25 |  | 6 | 2027-01-25 |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | N/A | N/A |  |  |  | Not Started
90 | MCL-0406 | O&M | B | B1 | Central | 75 | Water Supply | __ | Providing & Installation of (200 mm) 25 HP Deep Straight Bore Tubewell at Gurdware wali gali in W. No.75 (Against Failed T/W) (Central Constituency) | NA | NA | 1 | MC Funds / General Quota | GQ | Awarded | 12.45 | 12.39% | 1712 13-10-2025 | YES | YES | XEN | N/A | 2023-05-08 | 2025-05-23 | YES | YES | 77/G33 07-11-2025 | Baljit Singh Gill | 10.91 | 2025-11-15 | 3 |  |  | Rajinder Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | N/A | N/A | - |  | - | Not Started |  | Due to site issue (not adequate space)
91 |  | O&M | B | B1 | Central | 75 | Water Supply | __ | Prov & Inst. of 12.5 HP straight bore tubewell at Arjan meet wali gali, islam ganj in ward No. 75. | NA | NA | 1 | MC Funds / General Quota | GQ | Awarded | 6.41 | 12.38% | 2858 19-02-2026 | YES | YES | XEN | N/A | 2025-11-07 | 15-16/12/2026 | YES | YES | 109/G33 06-03-2026 | Bedi Pump Store | 5.62 | 2026-03-12 | 2 |  |  | Rajinder Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | N/A | N/A | 80% |  |  | Work in Progress
92 | MCL-0407 | O&M | B | B1 | Central | 80 | Water Supply | XEN | Prov/Inst. of 12.5 HP Straight bore Tubewell at st no 10, Hargobind Nagar in W. No. 53 (Against Failed T/w) (Central Constituency). | NA | NA | 1 | MC Funds / General Quota | GQ | Awarded | 6.53 | 14.8% | 2428 23-08-2024 | YES | YES | XEN | N/A | 2024-03-07 | 27-28/06/2024 | YES | YES | 125/G33 9/18/2024 | Rana Electrical Works | 5.56 | 2024-09-25 | 2 |  |  | Rajinder Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | N/A | N/A | - |  | - | Not Started |  | Due to site issue (not adequate space)
93 | MCL-0408 | O&M | B | B1 | Central | 80 | Water Supply | __ | Prov/Inst. of 25 HP Straight bore Tubewell at Gabe wali Gali, Kidwai Nagar in W. No. 53 (Against Failed T/w) (Central Constituency). | NA | NA | 1 | MC Funds / General Quota | GQ | Awarded | 12.34 | 17.6% | 291 26-03-2025 | YES | YES | XEN | N/A | 2024-12-03 | 2024-12-31 | YES | YES | 03/G33 11-04-2025 | Bedi Pump Store | 10.17 |  | 3 |  |  | Rajinder Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | N/A | N/A | - |  | - | Not Started |  | Due to site issue (not adequate space)
94 |  | O&M | B | B1 | Central | 63 | Sewerage | __ | Raising of Slab of M/H in St. No. 6-1/2, Janakpuri in W. No. 63 (Old). | NA | NA | 1 | MC Funds / General Quota | GQ | Awarded | 4.13 | 16.2% | 292 26-03-2025 | YES | YES | XEN | N/A | 2024-12-03 | 09-10/01/2025 | YES | YES | 06/G33 11-04-2025 | R.S. Builders | 3.46 |  | 1 |  |  | Rajinder Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | N/A | N/A | 80% |  |  | Work in Progress
95 |  | O&M | B | B1 | Central | 76 | Sewerage | __ | Prov & Laying of Additional Machine hole chamber in ward No. 76. | NA | NA | 1 | MC Funds / General Quota | GQ | Awarded | 5.08 | 25.99% | 2860 19-02-2026 | YES | YES | XEN | N/A | 2025-11-07 | 15-16/12/2025 | YES | YES | 111/G33 06-03-2026 | G.K. Contractor | 3.76 |  | 2 |  |  | Rajinder Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | N/A | N/A | - |  |  | Not Started
96 |  | O&M | B | B1 | Central | 79 | Sewerage | __ | Prov & Laying of Additional Machine hole chamber in ward No. 79. | NA | NA | 1 | MC Funds / General Quota | GQ | Awarded | 4.62 | 25.99% | 2861 19-02-2026 | YES | YES | XEN | N/A | 2025-11-07 | 15-16/12/2025 | YES | YES | 112/G33 06-03-2026 | G.K. Contractor | 3.42 |  | 2 |  |  | Rajinder Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | N/A | N/A | 50% |  |  | In Progress
97 | MCL-0409 | O&M | B | B1 | Central | B1 | Sewerage | __ | Repair & Upgaradation of Shingar Disposal. | NA | NA | 1 | MC Funds / General Quota | GQ | Awarded | 27.24 | 25.86% | 3350 21-04-2026 | YES | YES | XEN | N/A | 2026-02-05 | 2026-02-20 | YES | YES | 137/G33 07-05-2026 | G.K. Contractor | 20.2 |  | 3 |  |  | Rajinder Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | N/A | N/A | 40% |  | 8.08 | In Progress |  | Work in progress
98 | MCL-0410 | O&M | B | B2 | Sahnewal | 25 | Water Supply | __ | Providing & Installing of 40 HP Rig Bore Tubewell at Phase-VII Focal Point Water Tanki Wala Park Near Marshell Kanda Ward No.28 (Against Failed Tubewell). | NA |  | 1 | SIDBI | MDF/GQ (SIDBI) | Awarded | 23.99 | 12.33% | 282 26-03-2025 | YES | YES | XEN | N/A | 2024-11-14 | 2024-12-02 | YES | YES | 19/G33 11-04-2025 | CNC Precision Engineering | 21.03 | 2025-11-04 | 3 | 2026-10-07 |  | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | 90% |  | 18.93 | In Progress |  | Work in progress
99 | MCL-0411 | O&M | B | B2 | Sahnewal | 25 | Water Supply | __ | Missing Links For 4" dia DIK-7 water supply at Different Areas Of Sub Zone-B2. | 3150 |  | 1 | MC Funds / General Quota | GQ | Awarded | 74.12 | 3.34% | 279 26-03-2025 | YES | YES | XEN | N/A | 2024-11-14 | 2024-12-02 | YES | YES | 16/G33 11-04-2025 | Friends & Co. | 71.64 | 2025-12-04 | 4 | 2026-10-07 |  | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | 85% |  | 60.89 | In Progress |  | Work in progress
100 | MCL-0412 | O&M | B | B2 | Sahnewal | 25 | Water Supply | __ | Providing & Installing of 40 HP Rig Bore Tubewell at Phase-VIII Focal Point opp Perfect Dyeing. | NA |  | 1 | SIDBI | MDF/GQ (SIDBI) | Awarded | 24 | 16.92% | 2879 19-02-2026 | YES | YES | XEN | N/A | 2025-10-10 | 2025-10-28 | YES | YES | 116/G33 06-03-2026 | CNC Precision Engineering | 19.94 | 2026-07-03 | 3 | 2026-10-07 |  | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | 90% |  | 17.95 | In Progress |  | Work in progress
101 | MCL-0413 | O&M | B | B2 | Sahnewal | 25 | Water Supply | __ | Providing & Installing of 40 HP Rig Bore Tubewell at Tikona park Near Metro Tyre Phase-V. | NA |  | 1 | SIDBI | MDF/GQ (SIDBI) | Awarded | 24 | 16.92% | 3275 25-02-2026 | YES | YES | XEN | N/A | 2025-10-10 | 2025-10-28 | YES | YES | 123/G33 25-03-2026 | CNC Precision Engineering | 19.94 | 2026-03-25 | 3 | 2026-10-07 |  | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | 90% |  | 17.95 | In Progress |  | Work in progress
102 | MCL-0414 | O&M | B | B2 | Sahnewal | 21 | Sewerage | __ | Upgradation of sewer line in W. No. 24 and 25 (50% - 50% Work Alloted). | 1461.59 |  | 1 | MC Funds / General Quota | GQ | Awarded | 87.73 | 24.99% | 175 26-03-2025 | YES | YES | SE | N/A | 2024-11-14 | 2024-12-02 | YES | YES | 25/G33 17-04-2025 | Deepak Madaan | 32.9 | 2025-04-20 | 4 | 2026-10-07 |  | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | 90% |  | 29.61 | In Progress |  | Work in progress
103 | MCL-0415 | O&M | B | B2 | Sahnewal | 23 | Sewerage | __ | Upgradation of sewer line in W. No. 25, 26 and 27. | 1870.43 |  | 1 | MC Funds / General Quota | GQ | Awarded | 98.39 | 24.99% | 178 26-03-2025 | YES | YES | SE | N/A | 2025-11-14 | 2025-12-02 | YES | YES | 11/G33 11-04-2025 | Friends & Co. | 73.8 | 2025-11-04 | 4 | 2026-10-07 |  | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | 90% |  | 66.42 | In Progress |  | Work in progress
104 | MCL-0416 | O&M | B | B2 | Sahnewal | 25 | Sewerage | __ | Upgradation of 18” Sewer line from Shiv Colony to Devgan Kanda Sua Road in Sub Zone-B2 (Sahnewal Constituency). | 1134.16 |  | 1 | Councillor Quota (CQ) | CQ | Awarded | 64.93 | 25.5% | 2885 19-02-2026 | YES | YES | SE | N/A | 2025-11-07 | 2025-12-02 | YES | YES | 122/G33 06-03-2026 | Bharat Bhushan Contractor | 48.37 | 2026-10-03 | 4 | 2026-08-15 |  | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | - |  | - | Not Started |  | Material reached at site
105 | MCL-0417 | O&M | B | B2 | Sahnewal | B2 | Sewerage | __ | Prov/Laying of RCC NP3 HDPE Lining UPVC SN-8 & HDPE Pipes of dia 250 MM, 300 MM, 400 MM & 450 MM From M.C Limit G.T Road (Ludhiana To Delhi NH) Near Eastman Cast and Forge Ltd. to UCO Bank Juginan Road Ldh. | 2111.48 |  | 1 | MC Funds / General Quota | GQ | Awarded | 173.71 | 24.99% | 197 26-03-2025 | Yes | Yes | CE | N/A | 2024-08-01 | 2024-08-27 | Yes | Yes | 10/G33 11-04-2025 | Deepak Madaan | 130.3 | 2025-11-04 | 6 |  |  | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | - |  | - | Delayed/Held Up |  | NOC Pending from NHAI
106 | MCL-0418 | O&M | B | B2 | Sahnewal | B2 | Sewerage | __ | Providing & Laying Of 8",10",12" UPVC SN-8 & 16" RCC NP-3 HDPE Lining Sewer Line Missing Links at different places in sub zone B2. | 1364.03 |  | 1 | MC Funds / General Quota | GQ | Awarded | 71.17 | 24.99% | 280 26-03-2025 | Yes | Yes | CE | N/A | 2024-11-14 | 2024-12-02 | Yes | Yes | 14/G33 11-04-2025 | Deepak Madaan | 53.38 | 2025-11-04 | 4 | 2026-07-15 |  | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | 90% |  | 48.04 | In Progress |  | Work in progress
107 | MCL-0419 | O&M | B | B2 | Sahnewal | B2 | Sewerage | __ | Providing & Laying Of 8",10",12" UPVC SN-8 & 16" RCC NP-3 HDPE Lining Sewer Line Missing Links at different places in sub zone B2. | 1425.61 |  | 1 | MC Funds / General Quota | GQ | Awarded | 91.28 | 24.99% | 287 26-03-2025 | Yes | Yes | CE | N/A | 2024-11-14 | 2024-12-02 | Yes | Yes | 15/G33 11-04-2025 | Friends & Co. | 68.47 | 2025-11-04 | 4 | 2026-07-15 |  | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | 85% |  | 58.2 | In Progress |  | Work in progress
108 | MCL-0420 | O&M | B | B2 | Sahnewal | B2 | Sewerage | __ | Prov./Laying of 900 mm dia RCC NP3 Sewer line at main chandigarh road near Police Colony Chowk. | 330.49 |  | 1 | MC Funds / General Quota | GQ | Awarded | 84.23 | 23.73% | 3357 21-04-2026 | Yes | Yes | CE | N/A | 2025-11-24 | 2025-12-09 | Yes | Yes | 129/G33 07-05-2026 | Rajdeep Enterprises | 64.24 | 2026-05-20 | 4 |  |  | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | - |  | - | Delayed/Held Up |  | NOC Pending from NHAI
109 | MCL-0421 | O&M | B | B4 | South | 32 | Water Supply |  | Rough Cost Estimate For Prov/Installation of 40 HP Straight Bore Tube well at Sherpur Khurd, Backside Kabristaan , Ward No- 22 in South Constituency (Against Failed T/Well Tanki wala). | NA | NA | 1 | MC Funds / General Quota | GQ | Awarded | 24.99 | 15.77% | 960 06-05-2025 | Yes | Yes | SDO | N/A | 2024-07-01 | 2024-07-16 | Yes | Yes | 48/G33 20/05/2025 | Guru Kirpa & Co. | 21.05 |  | 3 |  |  | Harinder Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A |  |  | - | Not Started |  | Not Started, Notice issued to contractor.
110 | MCL-0422 | O&M | B | B4 | South | 32 | Water Supply |  | Prov/Laying of DIK7 4" & 6" Water Supply line in various areas in W. No. 22. | W/S 4"=2745.92 W/S 6"=1084.80 | NA | 1 | MDF / SASCI | MDF | Awarded | 92.16 | 0.07% | 669 09-04-2025 | Yes | Yes | SDO | N/A | 2024-12-04 | 2024-12-19 | Yes | Yes | 35/G33 05-05-2025 | Bedi Pump Store | 92.1 | 2025-07-05 | 3 | 2026-10-30 |  | Harinder Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | 75% |  | 69.08 | In Progress |  | Work in progress
111 | MCL-0423 | O&M | B | B4 | South | 32 | Water Supply |  | Upgradation of 3” GI Pipe Water Supply Line at old Sherpur Village, Sherpur Khurd, Ward No-22 in South Constituency. | S/W 1432.92 | NA | 1 | MC Funds / General Quota | GQ | Awarded | 23.63 | -2% | 774 Dt 09/04/2025 | Yes | Yes | SDO | N/A | 2024-02-24 | 2025-03-05 | Yes | Yes | 32/G33 05-05-2025 | Surya Construction | 23.16 | 2025-05-05 | 3 |  |  | Harinder Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A |  |  | - | Not Started |  | Work Shifted to Zone-A under CBD as funds not received work not started
112 | MCL-0424 | O&M | B | B4 | South | 32 | Water Supply |  | Prov/Inst. of 3000 ltr. water tanker in Sherpur ward no. 16 (old) 32 (new) under MP LAD Scheme. | NA | NA | 1 | MPLAD Funds | MP LAD | Awarded | 2.11 | -8% | 2883 Dt 19/02/2026 | Yes | Yes | SDO | N/A | 2025-12-26 | 2026-01-13 | Yes | Yes | 120/G33 06-03-2026 | Ram Parkash Kakar | 1.94 | 2026-03-06 | 2 |  |  | Harinder Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | - |  | - | Not Started |  | Notice issued to contractor.
113 | MCL-0425 | O&M | B | B4 | South | 27 | Sewerage |  | Prov & Laying of 12” UPVC Pipe at Kailash Nagar, St. No. 3-1/2 (Cancer Road Sherpur) in W. No. 27 in South Constituency. | S/W 256.09 | NA | 1 | Councillor Quota (CQ) | CQ | Awarded | 12.49 | 30.6% | 2880 19-02-2026 | Yes | Yes | SDO | N/A | 2025-12-26 | 2026-01-13 | Yes | Yes | 117/G33 06-03-2026 | Ess Elechmech Enterprises | 8.67 | 2026-07-03 | 3 | 2026-11-15 |  | Harinder Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | - |  | - | Not Started |  | Work will start after monsoon
114 | MCL-0426 | O&M | C | C-1 | Atam Nagar | 44 | WATER | N/A | Prov./Laying 4” id DIK-7 Water Supply lines at street no.7 Partap Nagar Ward no. 41 old. MC Funds |  |  |  | MC Funds / General Quota | MCL | Awarded | 9.47 | 5.9% | 518/09.04.2025 | Yes | Yes | SDO | N/A | 24.02.2025 | 14.03.2025 | Yes | Yes | 1173/G/33 Dated 30-04-2025 | Bedi Pump Store | 8.99 | 2025-04-30 | 2 | 2026-10-07 |  | Ibqal Singh JE / Manpreet Singh XEN | NO | NO | 90% |  | 5.39 | Delayed/Held Up |  | Work Has been delayed by Councillor
115 | MCL-0427 | O&M | C | C-4 | Atam Nagar | 48 | WATER | N/A | Prov./Laying 4” id Dik-7 water supply lines at Bhai Himmat Singh Nagar (ward no. 48) MC Funds |  |  |  | MC Funds / General Quota | MCL | Awarded | 49.59 | 4.6% | 520/09.04.2025 | YES | YES | XEN | N/A | 24.02.2025 | 14.03.2025 | YES | YES | 1174/G/33 Dated 30-04-2025 | Bedi Pump Store | 47.31 | 2025-04-30 | 3 |  |  | Sunpreet Singh JE- Amandeep Singh Grewal SDO Manpreet Singh XEN | NO | NO | 60% |  | 28.39 | Delayed/Held Up |  | Work has been stopped by MLA Sir due to approval of road work
116 | MCL-0428 | O&M | C | C-1 | Atam Nagar | C-1 | WATER | N/A | Prov./Installation of 3 nos. 25 hp Submersible T/wells and 2 nos. 12.5 hp Submersible T/wells in Sub Zone C-1 (AFT T/well) |  |  |  | MC Funds / General Quota | MCL | Awarded | 49.88 | 19% | 2812/19.02.2026 | YES | YES | XEN | N/A | 15.12.2025 | 30.12.2025 | YES | YES | 1243/G/33 Dated 29.04.2026 | Bedi pump Store | 40.38 | 2025-04-30 | 3 |  |  | Ibqal Singh JE / Manpreet Singh XEN | NO | NO | 70% |  | 8.08 | In Progress |  | T/well to be Installed Against failed as per requirment
117 | MCL-0429 | O&M | C | C-4 | Atam Nagar | 40 | WATER | 373405 | Prov./Laying 6" id Dik-7 water supply line at main Maya soap ward no. 40 |  |  |  | MC Funds / General Quota | MCL | Awarded | 31.63 | 15.1% | 3390/21.04.2026 | YES | YES | XEN | N/A | 26.12.2025 | 16.01.2026 | YES | YES | 1258/G/33 Dated 13.05.2026 | Shushil Kumar | 26.85 | 2026-05-15 | 3 | 2026-10-10 |  | Sunpreet Singh JE- Amandeep Singh Grewal SDO Manpreet Singh XEN | NO | NO | - |  | - | Not Started |  | work to be start after monsoon
118 | MCL-0430 | O&M | C | C-4 | Atam Nagar | 40 | WATER | N/A | Prov./Installation of 25 hp New Submersible T/well at street no. 12 1/2 chimeny road Shimlapuri ward no. 40 |  |  | 1 | MC Funds / General Quota | MCL | Awarded | 12.7 | 19.2% | 2806/19.02.2026 | YES | YES | SDO | N/A | 15.12.2025 | 30.12.2025 | YES | YES | 1269/G/33 Dated 20.05.2026 | JCS Electric works | 10.26 | 2026-05-22 | 3 | 2026-08-25 |  | Sunpreet Singh JE- Amandeep Singh Grewal SDO Manpreet Singh XEN | NO | NO | - |  | - | Not Started |  | Inaugration done
119 | MCL-0431 | O&M | C | C-4 | Atam Nagar | 41 | WATER | N/A | Prov./Installation of 25 hp Submersible T/well at street no. 13 Shimlapuri (AFT 25 hp T/well)ward no. 41 |  |  | 1 | MC Funds / General Quota | MCL | Awarded | 12.7 |  | 2814/19.02.2026 | YES | YES | SDO | N/A | 15.12.2025 | 30.12.2025 | YES | YES | 1270/G/33 Dated 20.05.2026 | Ess Elechmec | 10.36 | 2026-05-22 | 3 | 2026-08-20 |  | Sunpreet Singh JE- Amandeep Singh Grewal SDO Manpreet Singh XEN | NO | NO | 65% |  | - | In Progress |  | Material reached at site
120 | MCL-0432 | O&M | C | C-1 | Atam Nagar | 44 | Sewerage | N/A | Upgradation of 10" id UPVC sewer line in SAS Nagar ward no. 44 |  |  |  | MC Funds / General Quota | MCL | Awarded | 22.63 | 24.9% | 2808/19.02.2026 | YES | YES | SDO | N/A | 15.12.2025 | 30.12.2025 | YES | YES | 1233/G/33 Dated 18.03.2026 | Joytee Builedrs | 16.97 |  | 3 |  |  | Ibqal Singh JE / Manpreet Singh XEN | NO | NO | - |  | - | Delayed/Held Up |  | Notice issued to contractor for delay in start
121 | MCL-0433 | O&M | C | C-1 | Atam Nagar | 44 | Sewerage | N/A | Upgradation of 12" id UPVC sewer line in Miltary Camp ward no. 44 |  |  |  | MC Funds / General Quota | MCL | Awarded | 22.98 | 28.6% | 2809/19.02.2026 | YES | YES | SDO | N/A | 15.12.2025 | 30.12.2025 | YES | YES | 1234/G/33 Dated 18.03.2026 | ESS Elechmec | 16.42 | 2026-03-20 | 3 | 2026-07-31 |  | Ibqal Singh JE / Manpreet Singh XEN | NO | NO | 100% |  | 9.85 | Completed |  | Work in Progress
122 | MCL-0434 | O&M | C | C-4 | Atam Nagar | 41 | Sewerage | N/A | Upgradation of 16" id RCC NP3 HDPE sewer line from Waheguru road to Daba road Dhand Palace ward no.41 |  |  |  | MC Funds / General Quota | MCL | Awarded | 92.55 | 26.1% | 2781/19.02.2026 | YES | YES | SE | N/A | 25.08.2025 | 15.09.2025 | YES | YES | 1266/G/33 Dated 13.05.2026 | Bharat Bhushan | 68.39 | 2026-05-13 | 3 | 2026-11-15 |  | Sunpreet Singh JE- Amandeep Singh Grewal SDO Manpreet Singh XEN | NO | NO | 60% |  | 41.03 | Delayed/Held Up |  | Work stopped and will start after monsoon
123 | MCL-0435 | O&M | C | C-1 | South | 31 | WATER | N/A | Prov./Laying 4" id DIK-7 water supply lines at street no. 9,16,17 Bhagwan nagar ward no. 50 old |  |  |  | MC Funds / General Quota | MCL | Awarded | 9.9 |  | 999/06.05.2025 | YES | YES | SDO | N/A | 11.04.2025 | 25.04.2025 | YES | YES | 1189/G/33 Dated 14-05-2025 | APEX Developers | 9.9 | 2025-05-15 | 2 | 2026-07-31 |  | Avneet Singh JE JAgroop Singh SDO Manpreet Singh XEN | NO | NO | 70% |  | 5.94 | In Progress |  | work in progress
124 | MCL-0436 | O&M | C | C-3 | South | 32 | WATER | N/A | Prov./Installation of 25 hp new Submersible T/well at street no.22 Makkar colony Dhandari kalan ward no.32 MC fund |  |  | 1 | MC Funds / General Quota | MCL | Awarded | 12.7 | 16.5% | 2816/19.02.2026 | YES | YES | SDO | N/A | 15.12.2025 | 30.12.2025 | YES | YES | 1238/G/33 Dated 09.04.2026 | Ess Elechmec | 10.61 | 2026-10-04 | 3 | 2026-07-15 |  | Avneet Singh JE JAgroop Singh SDO Manpreet Singh XEN | NO | NO | 90% |  | 4.24 | In Progress |  | work in progress
125 | MCL-0437 | O&M | C | C-3 | South | C-3 | WATER | N/A | Prov./Installation of 4 nos. 25 hp submersible T/wells (AFT 25 hp t/wells) in South Constituency (MC funds.) |  |  | 1 | MC Funds / General Quota | MCL | Awarded | 49.56 |  | 2036/13.10.2025 | YES | YES | SDO | N/A | 14.07.2025 | 28.07.2025 | YES | YES | 1219/G/33 Dated 04-11-2025 | Bedi pump Store | 48.77 | 2025-06-11 | 3 |  |  | Avneet Singh JE JAgroop Singh SDO Manpreet Singh XEN | NO | NO | 75% |  | 36.58 | In Progress |  | T/well to be Installed Against failed as per requirment
126 | MCL-0438 | O&M | C | C-3 | South | 29 | WATER | N/A | Providing Laying 4" i/d DIK-7 water supply line at Makkar Colony Ward No.29 |  |  |  | MC Funds / General Quota | MCL | Awarded | 34.8 | 3%ABOVE | 220/11.03.2025 | YES | YES | XEN | N/A | 03.12.2024 | 20.12.2024 | YES | YES | 1161/G/33 Dated 11-04-2025 | APEX Developers | 35.84 | 2025-04-15 | 3 | 2026-07-31 |  | Avneet Singh JE JAgroop Singh SDO Manpreet Singh XEN | NO | NO | 90% |  | 28.67 | Delayed/Held Up |  | Work stopped by MLA, until road estimate to be approved
127 | MCL-0439 | O&M | C | C-3 | South | 36 | WATER | N/A | Prov./Installation of 25 hp new Submersible T/well at street no.1 Chahal road Sukhdev Nagar ward no.36 MC fund |  |  | 1 | MC Funds / General Quota | MCL | Awarded | 12.7 | 18.8% | 2538/05.02.2026 | YES | YES | SDO | N/A | 13.08.2025 | 25.08.2025 | YES | YES | 1240/G/33 Dated 20.04.2026 | Amarpal Singh Bawa | 10.57 | 2026-04-20 | 3 | 2026-07-20 |  | Avneet Singh JE JAgroop Singh SDO Manpreet Singh XEN | NO | NO | 100% |  | 8.98 | Work Completed |  | Work Completed
128 | MCL-0440 | O&M | C | C-2 | South | 37 | WATER | N/A | Prov./Installation of 25 hp new Submersible T/well at street no. 13 Guru Gobind singh nagar barota road ward no.37 MC fund |  |  | 1 | MC Funds / General Quota | MCL | Awarded | 12.7 | 19.2% | 2810/19.02.2026 | YES | YES | SDO | N/A | 15.12.2025 | 30.12.2025 | YES | YES | 1235/G/33 Dated 09.04.2026 | JCS Electric works | 10.26 |  | 3 |  |  | Dilpreet Singh JE Harbir Singh SDO Manpreet Singh XEN | NO | NO | 50% |  | - | Work in Progress |  | Work In Progress
129 | MCL-0441 | O&M | C | C-2 | South | 37 | WATER | N/A | Prov./Installation of 25 hp New Submersible T/well at Guru Gobind singh nagar street no. 10/3 ward no. 37 |  |  | 1 | MC Funds / General Quota | MCL | Awarded | 10.58 | 16.7% | 2540/05.02.2026 | YES | YES | SDO | N/A | 13.08.2025 | 25.08.2025 | YES | YES | 1236/G/33 Dated 09.04.2026 | Amarpal Singh Bawa | 10.58 | 2026-10-04 | 3 | 2026-10-07 |  | Dilpreet Singh JE Harbir Singh SDO Manpreet Singh XEN | NO | NO | 85% |  | 8.99 | In Progress |  | Work In Progress
130 | MCL-0442 | O&M | C | C-2 | South | 37 | WATER | N/A | Prov./Laying 4" id Dik-7 water supply lines at Barota road and Branch streets of Guru Gobind Singh Nagar ward no. 37 |  |  |  | MC Funds / General Quota | MCL | Awarded | 47.33 | 15.1% | 2819/19.02.2026 | YES | YES | XEN | N/A | 15.12.2025 | 30.12.2025 | YES | YES | 1242/G/33 Dated 27.04.2026 | Sushil Kumar contractor | 40.18 |  | 3 |  |  | Dilpreet Singh JE Harbir Singh SDO Manpreet Singh XEN | NO | NO | - |  | - | Delayed/Held Up |  | Work stopped by MLA, until road estimate to be approved
131 | MCL-0443 | O&M | C | C-2 | South | 43 | WATER | N/A | Prov./Installation of 25 hp new Submersible t/well at New Amar nagar stret no. 10-B ward no. 43 |  |  | 1 | MC Funds / General Quota | MCL | Awarded | 12.7 | 19.4% | 2818/19.02.2026 | YES | YES | SDO | N/A | 15.12.2025 | 30.12.2025 | YES | YES | 1237/G/33 Dated 09.04.2026 | Ess Elechmec | 10.24 | 2026-10-04 | 3 | 2026-07-15 |  | Dilpreet Singh JE Harbir Singh SDO Manpreet Singh XEN | NO | NO | 90% |  | 6.14 | In Progress |  | Work In Progress(PSPCL Meter Pending)
132 | MCL-0444 | O&M | C | C-1 | South | 44 | WATER | N/A | Prov./Laying 4” id DIK-7 Water Supply lines at street no.4 Kot Mangal Singh Ward no. 41 old. MC Funds |  |  |  | MC Funds / General Quota | MCL | Awarded | 10 | 2.7% | 517/09.04.2025 | YES | YES | SDO | N/A | 24.02.2025 | 15.03.2025 | YES | YES | 1168/G/33 Dated 30-04-2025 | The Boha Co.op L&C Society ltd. | 9.73 |  | 2 |  |  | Ibqal Singh JE / Manpreet Singh XEN | NO | NO | 5% |  | - | Delayed/Held Up |  | Due To road dispute of Public work not started
133 | MCL-0445 | O&M | C | C-1 | South | 45 | WATER | N/A | Prov./Laying 4" id Dik-7 water supply lines in street no. 11, 14 & 15 at Vishkarma colony ward no. 50 old |  |  |  | MC Funds / General Quota | MCL | Awarded | 9.87 | 5.1% | 516/09.04.2025 | YES | YES | SDO | N/A | 24.02.2025 | 15.03.2025 | YES | YES | 1169/G/33/30.04.2025 | Bedi pump store | 9.37 | 2025-04-30 | 2 |  |  | Ibqal Singh JE / Manpreet Singh XEN | NO | NO | 90% |  | 6.56 | Delayed/Held Up |  | Work Held up due to political dispute
134 | MCL-0446 | O&M | C | C-3 | South | 31 | WATER SESWER | N/A | Upgradation of 4" id DIK water supply lines & 12" UPVC sewer line at street no 3,4,5,6 Hargobind Nagar ward no. 31 |  |  |  | MC Funds / General Quota | MCL | Awarded | 97.61 | 26% | 2890/19.02.2026 | YES | YES | XEN | N/A | 15.12.2025 | 30.12.2025 | YES | YES | 1247/G/33 Dated 11.05.2026 | APEX Developers | 72.24 | 2026-05-15 | 3 | 2026-10-15 |  | Avneet Singh JE JAgroop Singh SDO Manpreet Singh XEN | NO | NO | - |  | - | Not Started |  | work to be start after monsoon
135 | MCL-0447 | O&M | C | C-3 | South | 34 | WATER SESWER | N/A | Prov./Laying missing links 4" id DIK-7 water supply lines & 10" id UPVC sewer lines at Lachman nagar & Ajit Colony ward no. 34 |  |  |  | MC Funds / General Quota | MCL | Awarded | 8.67 | 25% | 2811/19.02.2026 | YES | YES | SDO | N/A | 15.12.2025 | 30.12.2025 | YES | YES | 1250/G/33 Dated 11.05.2026 | GK Contractor | 6.5 | 2026-05-15 | 2 | 2026-10-08 |  | Avneet Singh JE JAgroop Singh SDO Manpreet Singh XEN | NO | NO | 35% |  | 1.63 | In Progress |  | Work in Progress
136 | MCL-0448 | O&M | C | C-3 | South | 33 | WATER SESWER | N/A | Prov./Laying missing links 4" id DIK-7 water supply lines for missing links & 10" id UPVC sewer lines at Mahadev nagar, Samrat Colony & Laxmi Nagar ward no. 33 |  |  |  | MC Funds / General Quota | MCL | Awarded | 18.19 | 21% | 2807/19.02.2026 | YES | YES | SDO | N/A | 15.12.2025 | 30.12.2025 | YES | YES | 1251/G/33 Dated 11.05.2026 | NS Infra | 14.37 | 2026-05-13 | 3 | 2026-08-15 |  | Avneet Singh JE JAgroop Singh SDO Manpreet Singh XEN | NO | NO | 40% |  | 3.59 | In Progress |  | Work in Progress
137 | MCL-0449 | O&M | C | C-3 | South | 36 | WATER SESWER | N/A | Upgradation of 4" id DIK water supply lines & 12" id UPVC sewer line at Gill colony Sappan wala mandir ward no. 36 |  |  |  | MC Funds / General Quota | MCL | Awarded | 90.46 | 25% | 2891/19.02.2026 | YES | YES | SE | N/A | 15.12.2025 | 30.12.2025 | YES | YES | 1249/G/33 Dated 11.05.2026 | Friennds & company | 67.85 | 2026-05-15 | 3 | 2026-08-31 |  | Avneet Singh JE JAgroop Singh SDO Manpreet Singh XEN | NO | NO | 60% |  | 13.57 | In Progress |  | Work in Progress
138 | MCL-0450 | O&M | C | C-3 | South | 32 | WATER | 374275 | Purchase of 3000 litters water tanker for ward no. 16 old new ward no. 32 MP Quota |  |  | 1 | MPLAD Funds | MP Lad | Awarded | 2.11 |  | 3386/21.04.2026 | YES | YES | JE | N/A | 26.12.2025 | 16.01.2026 | YES | YES | 1252/G/33 Dated 13.05.2026 | Ram Parkash Kakkar | 1.94 | 2026-05-15 | 2 | 2026-12-07 |  | Avneet Singh JE JAgroop Singh SDO Manpreet Singh XEN | NO | NO | - |  | - | Not Started |  | Manufacturing under process
139 | MCL-0451 | O&M | C | C-3 | South | 32 | WATER | 374298 | Purchase of 3000 litters water tanker for ward no. 30 old new ward no. 32 MP Quota |  |  | 1 | MPLAD Funds | MP Lad | Awarded | 2.11 |  | 3382/21.04.2026 | YES | YES | JE | N/A | 26.12.2025 | 16.01.2026 | YES | YES | 1253/G/33 Dated 13.05.2026 | Ram Parkash Kakkar | 1.94 | 2026-05-15 | 2 | 2026-12-07 |  | Avneet Singh JE JAgroop Singh SDO Manpreet Singh XEN | NO | NO | - |  | - | Not Started |  | Manufacturing under process
140 | MCL-0452 | O&M | C | C-3 | South | 34 | WATER | 379090 | Prov./Installation of 25 hp New Submersible T/well at street no. 8 Gagan Nagar ward no. 34 |  |  | 1 | MC Funds / General Quota | MCL | Awarded | 12.7 | 20.4% | 3524/21.04.2026 | YES | YES | SDO | N/A | 26.12.2025 | 16.01.2026 | YES | YES | 1254/G/33 Dated 13.05.2026 | Bedi pump Store | 10.11 | 2026-05-13 | 3 | 2026-08-15 |  | Avneet Singh JE JAgroop Singh SDO Manpreet Singh XEN | NO | NO | 40% |  | - | Not Started
141 | MCL-0453 | O&M | C | C-1 | South | 43 | WATER | 374769 | Prov./Installation of 25 hp New Submersible T/well at street no. 33 Kot Mangal Singh Nagar ward no. 43 |  |  | 1 | MC Funds / General Quota | MCL | Awarded | 12.7 | 20.4% | 3388/21.04.2026 | YES | YES | SDO | N/A | 26.12.2025 | 16.01.2026 | YES | YES | 1256/G/33 Dated 13.05.2026 | Bedi pump Store | 10.11 | 2026-05-13 | 3 | 2026-08-15 |  | Ibqal Singh JE / Manpreet Singh XEN | NO | NO | - |  | - | Not Started
142 | MCL-0454 | O&M | C | C-2 | South | 32 & 33 old | WATER | N/A | Prov./Suction tanker for desilting of sewer in various area of ward no. 32 & 33 old sub Zone C-2 |  |  | 1 | MC Funds / General Quota | MCL | Awarded | 9.86 |  | 3379/21.04.2026 | YES | YES | SDO | N/A | 15.12.2025 | 30.12.2025 | YES | YES | 1257/G/33 Dated 13.05.2026 | Sai Enterprises | 5.95 | 2026-05-13 | 3 | 2026-08-15 |  | Dilpreet Singh JE Harbir Singh SDO Manpreet Singh XEN | NO | NO | 50% |  | 2.98 | Not Started
143 | MCL-0455 | O&M | C | C-2 | South | 36 | WATER | N/A | Prov./Laying 4" id DIK-7 water supply lines & 10" id UPVC sewer lines at Dhillon nagar ward no. 36 |  |  |  | MC Funds / General Quota | MCL | Awarded | 76.74 | 27% | 2892/19.02.2026 | YES | YES | SE | N/A | 15.12.2025 | 30.12.2025 | YES | YES | 1267/G/33 Dated 13.05.2026 | Apex Developers | 56.03 | 2026-05-13 | 3 | 2026-11-30 |  | Dilpreet Singh JE Harbir Singh SDO Manpreet Singh XEN | NO | NO | - |  | - | Not Started |  | Work will start after monsoon
144 | MCL-0456 | O&M | C | C-1 | South | 31 | Sewerage | N/A | Upgradation of 10" id UPVC sewer line in Gandhi Nagar Ward no. 50 |  |  |  | MC Funds / General Quota | MCL | Awarded | 29.95 | 3% | 3408/05.12.2024 | YES | YES | XEN | N/A | 14.11.2025 | 26.11.2026 | YES | YES | 1143/G/33 Dated 05-12-2024 | M/S Kohinoor Builders | 29.05 | 2024-07-12 | 3 |  |  | Ibqal Singh JE / Manpreet Singh XEN | NO | NO | 85% |  | 24.69 | In Progress |  | As per original contract work is completed. File sent for change of site for balance fund.
145 | MCL-0457 | O&M | C | C-3 | South | 34 | WATER SESWER | N/A | Providing Laying 10" UPVC Sewer line & 4" i/d DIK-7 water supply line Near BSUP Flats Ward No.31 |  |  |  | MC Funds / General Quota | MCL | Awarded | 9.2 | 18.3% | 332/26.03.2025 | YES | YES | SDO | N/A | 05.09.2024 | 20.09.2025 | YES | YES | 1162/G/33 Dated 11-04-2025 | The Sarabha Co. Op. L&C Society Ltd. | 7.52 | 2025-04-13 | 2 | 2026-07-31 |  | Avneet Singh JE JAgroop Singh SDO Manpreet Singh XEN | NO | NO | 70% |  | 5.26 | Delayed/Held Up |  | Work in Progress, delay due to clearance from building branch
146 | MCL-0458 | O&M | C | C-3 | South | 34 | WATER SESWER | 374269 | Upgradation of 4" id DIK water supply lines & 10" UPVC sewer line at City Garden colony ward no. 34 |  |  |  | MC Funds / General Quota | MCL | Awarded | 95.02 | 27% | 3381/21.04.2026 | YES | YES | SE | N/A | 15.12.2025 | 30.12.2025 | YES | YES | 1245/G/33 Dated 11.05.2026 | APEX Developers | 69.37 | 2026-12-05 | 3 | 2026-09-15 |  | Avneet Singh JE JAgroop Singh SDO Manpreet Singh XEN | NO | NO | 45% |  | 13.87 | In Progress |  | Work in Progress
147 | MCL-0459 | O&M | C | C-3 | South | 32 | Sewerage | 374185 | Upgradation of 24" id RCC NP3 HDPE sewer line at Singla Cycle road ward no. 32 |  |  |  | MC Funds / General Quota | MCL | Awarded | 97.79 | 27.6% | 3383/21.04.2026 | YES | YES | SE | N/A | 15.12.2025 | 30.12.2025 | YES | YES | 1246/G/33 Dated 11.05.2026 | Rajdeep Enterprises | 70.06 | 2026-04-20 | 4 | 2026-09-30 |  | Avneet Singh JE JAgroop Singh SDO Manpreet Singh XEN | NO | NO | 50% |  | 14.01 | In Progress |  | Work in Progress
148 | MCL-0460 | O&M | C | C-3 | South | 32 | Sewerage | N/A | Prov./Laying 12" id UPVC sewer lines at Mittal kanda Dhandari Kalan near Skoda showroom ward no. 32 |  |  |  | MC Funds / General Quota | MCL | Awarded | 29.08 | 34.6% | 2813/19.02.2026 | YES | YES | XEN | N/A | 15.12.2025 | 30.12.2025 | YES | YES | 1248/G/33 Dated 11.05.2026 | Prince Sharma | 19.01 | 2026-05-14 | 3 |  |  | Avneet Singh JE JAgroop Singh SDO Manpreet Singh XEN | NO | NO | 40% |  | - | In Progress |  | Work in Progress
149 | MCL-0461 | O&M | C | C-2 | South | 39 | Sewerage | N/A | Upgradation of 12" id UPVC sewer line at street no. 8 Harkrishan nagar ward no. 39 |  |  |  | MC Funds / General Quota | MCL | Awarded | 34.04 | 35.3% | 2815/19.02.2026 | YES | YES | XEN | N/A | 15.12.2025 | 30.12.2025 | YES | YES | 1268/G/33 Dated 13.05.2026 | Prince Sharma | 22.04 | 2026-05-14 | 3 | 2026-09-15 |  | Dilpreet Singh JE Harbir Singh SDO Manpreet Singh XEN | NO | NO | - |  | - | Not Started
150 | MCL-0462 | O&M | C | C1 | Central | 74 | Sewerage | 376972 | Raising & Construction of M/H Slabs & Additional M/H Chambers , Prov./Laying 8" id sewer line for missing links in ward no. 74 |  | NA |  | MC Funds / General Quota | MCL | Awarded | 9.6 | 20% | 3380/21.04.2026 | Yes | Yes | SDO | N/A | 15.12.2025 | 16.12.2025 | Yes | Yes | 1260/G/33 Dated 13.05.2026 | Kohinoor Builders | 7.66 | 2026-05-14 | 3 | 2026-07-30 |  | Ibqal Singh JE / Manpreet Singh XEN | NO | N/A | 70% |  | 3.83 | In Progress |  | Work in progress
151 | MCL-0463 | O&M | C | C1 | Central | 74 | Sewerage | 381357 | Upgradation of 10" id UPVC storm sewer line from Gill road to Loha Mandi Indra market opp. Indra market ward no. 74 | 600 | NA |  | MC Funds / General Quota | MCL | Awarded | 28.17 | 29.51% | 3547/21.04.2026 | Yes | Yes | XEN | N/A | 5.2.2026 | 17.2.2026 | Yes | Yes | 1263/G/33 Dated 13.05.2026 | Friennds & company | 19.86 | 2026-05-14 | 3 | 2026-11-15 |  | Ibqal Singh JE / Manpreet Singh XEN | NO | N/A | - |  | - | Not Started |  | Work will be start after monsoon
152 | MCL-0464 | O&M | C | C1 | Central | 74 | Sewerage | 377042 | Raising & Constyruction of M/H slabs and construction of add. M/H chambers in Ward no. 74 |  | NA |  | MC Funds / General Quota | MCL | Awarded | 7.4 | 21.12% | 3387/21.04.2026 | Yes | Yes | SDO | N/A | 7.11.2025 | 16.12.2025 | Yes | Yes | 1264/G/33 Dated 13.05.2026 | Bharat Nirman Infracon | 5.84 | 2026-05-14 | 2 | 2026-07-30 |  | Ibqal Singh JE / Manpreet Singh XEN | NO | N/A | 40% |  | 1.17 | In Progress |  | Work in progress
153 | MCL-0465 | O&M | C | C1 | Central | 74 | Sewerage | 381366 | Upgradation of 10" id UPVC sewer lines in Industrial Estate ward no. 74 | 700 | NA |  | MC Funds / General Quota | MCL | Awarded | 35.34 | 29.52% | 3578/21.04.2026 | Yes | Yes | XEN | N/A | 5.2.2026 | 17.2.2026 | Yes | Yes | 1265/G/33 Dated 13.05.2026 | Friennds & company | 24.9 | 2026-05-14 | 3 | 2026-11-15 |  | Ibqal Singh JE / Manpreet Singh XEN | NO | N/A | - |  | - | Not Started |  | Work will start after monsoon
154 | MCL-0466 | O&M | D | D1 | North | North | WATER Supply &SEWERAGE | NA | Rehabitation/Missing links of 8" and 12"UPVC Sewer line and 2" G.I & 4" water supply line at Various wards of North Constituency | 1085 |  |  | MC Funds / General Quota | G.Q | Awarded |  |  | 242 26-03-2025 & 2233 21/11/2026 |  |  | XEN | N/A |  |  | Yes | Yes | 03/G-33 Dt. 15/04/2025 & 358/XEN/D 10/09/2025 | M/s Rajdeep Enterprises | 49.38 | 2025-04-20 | (upto 10/11/2025) | 2026-10-07 |  | Sh. Gurdeep Singh JE, Sh. Anshul Garcha SDO, Sh. RAndeep SIngh XEN |  |  | 95% |  | 46.91 | Delayed/Held Up |  | Work was delayed due to road work was not approved. now work under progress
155 | MCL-0467 | O&M | D | D1 | North | 91 | Sewerage | 385246 | P/Laying 12” id storm sewer line at on the road outside the park, near Silver Spoon, New Deep Nagar, Ward No. 91. (G.Q) (E Comp No. 385246) | 183 | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 11.83 | -24.99% | 256 26-03-2025 | Yes | Yes | SDO | N/A | 2026-04-01 | 2026-04-16 | Yes | Yes | 6/g/33 11-05-2026 | M/S Sushil Kumar Contractor, Ludhiana | 9.31 | 2026-05-15 | 2 months | 2026-07-14 | 2026-08-10 | Sh. Gurdeep Singh JE, Sh. Anshul Garcha SDO, Sh. RAndeep SIngh XEN | N/A | N/A | 80% |  | - | 80% |  | Work in Progress
156 | MCL-0468 | O&M | D | D1 | North | D1 | Water Supply | NA | Rehablitation/Missing link of 4" Water Supply line at various wards of Subzone-D1 | 3983 | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 74.45 | -7.07% | 2025-11-06 | Yes | Yes | SE | N/A | 2025-03-11 | 2025-04-05 | Yes | Yes | 104/G-33 Dt. 06/11/2025 | M/S ESS Elecmech Enterprises | 69.18 | 2025-11-10 | 3 Months | 2026-02-08 | 2026-07-15 | Sh. Gurdeep Singh JE, Sh. Anshul Garcha SDO, Sh. RAndeep SIngh XEN | N/A | N/A | 95 |  | 65.72 | Delayed/Held Up |  | Work is delayed Due to rehablitation work
157 | MCL-0469 | O&M | D | D1 | North | 66 | TUBEWELL | NA | Providing & Installation of 12.5 HP submersible T/well at Gaganpreet Vihar in Ward No-66. (G.Q) | NA |  |  | MC Funds / General Quota | G.Q | Awarded | 5.29 | -15.7% | 2627 11-02-2026 | Yes | Yes | JE | N/A | 2025-03-11 | 2025-04-05 | Yes | Yes | 107/G/33 20-02-2026 | M/s JCS Electric Works | 4.45 | 2026-05-20 | 2 months | 2026-07-15 | 2026-07-15 | Sh. Gurdeep Singh JE, Sh. Anshul Garcha SDO, Sh. RAndeep SIngh XEN | N/A | N/A | 60 |  | 0.45 | In Progress |  | Work in Progress
158 | MCL-0470 | O&M | D | D1 | North | 93 | DISPOSAL WELL | NA | Making of Disposal Well at new Kundanpuri (PeeruBanda) Railway bridge Sandhu Showroom in ward no-93 . (G.Q) | NA |  |  | MC Funds / General Quota | G.Q | Awarded | 28.73 | -11.86% | 2615 11-02-2026 | Yes | Yes | XEN | N/A | 2025-03-11 | 2025-04-05 | Yes | Yes | 108/G/33 20-02-2026 | M/s Bedi Pump Srore | 25.12 | 2026-02-21 | 3 months | 2026-06-30 | 2026-07-15 | Sh. Gurdeep Singh JE, Sh. Anshul Garcha SDO, Sh. RAndeep SIngh XEN | N/A | N/A | 95 |  | 21.6 | Delayed/Held Up |  | Only Gen set pending
159 | MCL-0471 | O&M | D | D1 | North | 66,68,92 | WATER Supply &SEWERAGE | NA | Rehablition of water supply & Sewer line at Gokul Vihar, Tersem Colony, Jaganath Purm, Preet Vihar, Civil City, New Sant Nagar in Ward no. 66, 68, 92(C.Q) | 815 |  |  | Councillor Quota (CQ) | C.Q | Awarded | 34.27 | -20.1% | 2625 11-02-2026 | Yes | Yes | XEN | N/A | 2025-03-11 | 2025-04-05 | Yes | Yes | 110/G/33 20-02-2026 | M/s Sushil Kumar Contractor | 27.38 | 2026-04-15 | 3 months | 2026-07-30 |  | Sh. Gurdeep Singh JE, Sh. Anshul Garcha SDO, Sh. RAndeep SIngh XEN | N/A | N/A | 25% |  | 6.85 | Not Started
160 | MCL-0472 | O&M | D | D1 | North | 93 | Water Supply | NA | Rehablition of water supply line at sunil nagar in ward no 93. | 1738 |  |  | Councillor Quota (CQ) | C.Q | Awarded | 49.86 | -19.1% | 2867 19-02-2026 | Yes | Yes | XEN | N/A | 2025-03-11 | 2025-04-05 | Yes | Yes | 123/g/33 26-02-2026 | M/s Sushil Kumar Contractor | 40.33 | 2026-02-27 | 3 months | 2026-05-07 |  | Sh. Gurdeep Singh JE, Sh. Anshul Garcha SDO, Sh. RAndeep SIngh XEN | N/A | N/A | 95% |  | 38.31 | Not Started
161 | MCL-0473 | O&M | D | D1 | North | - | TUBEWELL | NA | Providing & Installing of 2nos.12.5 HP, 1 nos. 25 HP & 1 nos. 40 HP Tubewells in place of against failed tubewells and water shortage in Emergency Situations in various areas under North Constituency. (G.Q) (E Comp No. 376246) | NA |  |  | MC Funds / General Quota | G.Q | Awarded | 48.19 | 10% | 3378 21-04-2026 | Yes | Yes | XEN | N/A | 7.11.2025 | 16.12.2025 | Yes | Yes | 1/g/33 08-05-2026 | M/S Rana Electrical Works, Ludhiana. | 43.37 | 2026-11-05 | 12 months | 2027-10-05 |  | Sh. Gurdeep Singh JE, Sh. Anshul Garcha SDO, Sh. RAndeep SIngh XEN | N/A | N/A | 90% |  | 39.03 | Not Started
162 | MCL-0474 | O&M | D | D1 | North | 70 | TUBEWELL | NA | Providing & Installation of 25 HP submersible T/well in Pahwa dharamshala against failed T/well in Ward no- 70.. (G.Q) (E Comp No. 374186) | NA |  |  | MC Funds / General Quota | G.Q | Awarded | 10.73 | -23.5% | 3346 21-04-2026 | Yes | Yes | SDO | N/A | 7.11.2025 | 16.12.2025 | Yes | Yes | 4/g/33 11-05-2026 | M/S Bharat Nirman Infracon, Ludhiana. | 8.2 | 2026-12-05 | 3 months | 2026-10-08 |  | Sh. Gurdeep Singh JE, Sh. Anshul Garcha SDO, Sh. RAndeep SIngh XEN | N/A | N/A | - |  | - | Not Started |  | Notice Issued
163 | MCL-0475 | O&M | D | D1 | North | 93 | Water Supply | NA | Rehablition of water supply line at Kehar Singh Nagar in ward no 93. (C.Q) (E Comp No. 377250) | 2700 |  |  | Councillor Quota (CQ) | C.Q | Awarded | 73.21 | -16.5% | 3573 21-04-2026 | Yes | Yes | SE | N/A | 7.11.2025 | 16.12.2025 | Yes | Yes | 7/g/33 11-05-2026 | M/S Friends and Company, Ludhiana.. | 61.12 | 2026-12-05 | 4 months | 2026-10-09 |  | Sh. Gurdeep Singh JE, Sh. Anshul Garcha SDO, Sh. RAndeep SIngh XEN | N/A | N/A | - |  | - | Not Started |  | Notice Issued
164 | MCL-0476 | O&M | D | D2 | Atam Nagar | 47 | Water supply | NA | Providing and Laying 4"dia DIK-7 water supply line at the area of Kartar Nagar in Ward No-49 | 1396.04 MTR | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 31.97 | -1.49% | 241 03-12-2024 | Yes | Yes | XEN | NA | 2024-12-03 | 2024-12-28 | YES | Yes | 4/G/33 11-04-2025 | M/S ESS Elecmech Enterprices, Ludhiana.. | 31.49 | 2026-04-20 | 3 months | 2026-07-19 | NA | Harjotpal Singh JE/Baljeet Singh SDO/Randeep Singh Xen | NA | NA | 55% |  | 17.32 | Delayed/Held Up |  | Work stopped by MLA saab and work to be done after road work allotment
165 | MCL-0477 | O&M | D | D2 | Atam Nagar | 47 | Water supply | NA | Providing and Laying 4"dia DIK-7 water supply line at the area of Ambedker Nagar, street no-9, in Ward No-48 | 1480 MTR | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 33.37 | -4.59% | 543 09-04-2025 | Yes | Yes | SE | NA | 2025-03-24 | 2025-04-18 | YES | Yes | 40/G/33 25-04-2025 | M/S Bedi Pump Store , Ludhiana | 31.83 | 2025-04-25 | 3 months | 2025-07-19 | NA | Harjotpal Singh JE/Baljeet Singh SDO/Randeep Singh Xen | NA | NA | - |  | - | Delayed/Held Up |  | Work stopped by MLA saab and work to be done after road work allotment
166 | MCL-0478 | O&M | D | D2 | Atam Nagar | 47 | Water supply | NA | Providing and Laying 4"dia DIK-7 water supply line at the area of Anbedker Nagar in Ward No-48 | 900 MTR | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 23.74 | -7.07% | 540 09-04-2025 | Yes | Yes | Xen | NA | 2025-03-24 | 2025-04-18 | YES | Yes | 42/G/33 25-04-2025 | M/S ESS Elecmech Enterprises, Ludhiana | 22.06 | 2025-04-25 | 2 months | 2025-07-19 | NA | Harjotpal Singh JE/Baljeet Singh SDO/Randeep Singh Xen | NA | NA | - |  | - | Delayed/Held Up |  | Work stopped by MLA saab and work to be done after road work allotment
167 | MCL-0479 | O&M | D | D2 | Atam Nagar | 52 | Water supply | NA | Providing and Laying 4"dia DIK-7 water supply line at the area of Abdulapur Basti in Ward No-47. | 958 MTR | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 24.7 | -7.07% | 541 09-04-2025 | Yes | Yes | Xen | NA | 24.03.2025 | 18.04.2025 | YES | Yes | 41/G/33 25-04-2025 | M/S ESS Elecmech Enterprises, Ludhiana | 22.95 | 2025-04-30 | 3 months | 2026-07-15 | NA | Kuldeep Singh JE/Baljeet Singh SDO/Randeep Singh Xen | NA | NA | 60% |  | 13.77 | In Progress |  | Area is conjusted and there was sewer issue due to which excavation was not possible work started after sewer is cleared
168 | MCL-0480 | O&M | D | D2 | Atam Nagar | 52 | Water supply | NA | Prov/Inst. of 25 HP Straight bore T/well at Abdulapur basti Vikas dharamshalla in W. No. 52 (against failed t/well 40 HP) |  | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 12.66 | -20.58% | 1458 13-10-2025 | Yes | Yes | SDO | NA | 2025-06-27 | 2026-07-14 | YES | Yes | 97/G/33 03-11-2025 | M/S Rajdeep Enterprises | 10.06 | 2025-10-11 | 3 months | 2026-07-15 | NA | Kuldeep Singh JE/Baljeet Singh SDO/Randeep Singh Xen | NA | NA | 95% |  | 9.56 | Not Started
169 | MCL-0481 | O&M | D | D2 | Atam Nagar | 51 | Water supply | NA | Prov/Inst. of 2 No. New 25 HP Straight bore Tube wells in Ward No. 51. |  | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 25.33 | -17.77% | 2379 05-01-2026 | Yes | Yes | SDO | NA | 2025-05-02 | 2025-05-29 | YES | Yes | 106/G/33 27-01-2026 | M/S Rajdeep Enterprises | 20.29 | 2026-04-02 | 3 months | 2026-07-15 | NA | Harjotpal Singh JE/Baljeet Singh SDO/Randeep Singh Xen | NA | NA | 90% |  | 18.26 | Not Started
170 | MCL-0482 | O&M | D | D2 | Atam Nagar | 50 | Water supply | NA | Providing and Installation of 25 HP Straight Bore Submersible Tubewell at 200 ft. road, Urban Estate, Ph-3 in Ward No 50.(C.Q) |  | NA | 1 | Councillor Quota (CQ) | C.Q | Awarded | 12.66 | 18.6% | 2631 11-02-2026 | Yes | Yes | SDO | NA | 2025-12-26 | 2026-01-23 | YES | Yes | 116/G/33 20-02-2026 | M/s ESS Elechmech Enterprises | 10.31 | 2026-02-25 | 3 months | 2026-07-15 | NA | Harjotpal Singh JE/Baljeet Singh SDO/Randeep Singh Xen | NA | NA | 65% |  | 6.7 | Not Started
171 | MCL-0483 | O&M | D | D2 | Atam Nagar | 49 | Water supply | NA | Providing and Installation of 25 HP Straight Bore Submersible Tubewell at Ph-1, Near Dr. Grewal Park in Ward No 49 (against 12.5HP failed tubewell )(G.Q). |  | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 12.66 | 18.6% | 2636 110-2-2026 | Yes | Yes | SDO | NA | 2025-12-26 | 2026-01-23 | YES | Yes | 117/G/33 20-02-2026 | M/s ESS Elechmech Enterprises | 10.31 | 2026-02-25 | 3 months | 2026-05-07 | NA | Gokaran Kumar JE/Baljeet Singh SDO/Randeep Singh Xen | NA | NA | 80% |  | 8.25 | Not Started
172 | MCL-0484 | O&M | D | D2 | Atam Nagar | 50 | Water supply | NA | Providing and Installation of 25 HP Straight Bore Submersible Tubewell at L.I.G Flat, Urban Estate, Ph-3, Near Army Flat in Ward No 50.(C.Q) |  | NA | 1 | Councillor Quota (CQ) | C.Q | Awarded | 12.66 |  | 2633 11-02-2026 | Yes | Yes | SDO | NA | 2025-12-26 | 2026-01-23 | YES | Yes | 120/G/33 20-02-2026 | M/s JCS Electric Works | 10.3 | 2026-02-21 | 3 months | 2026-07-15 | NA | Harjotpal Singh JE/Baljeet Singh SDO/Randeep Singh Xen | NA | NA | Not Started |  | - | Not Started |  | Notice Issued
173 | MCL-0485 | O&M | D | D2 | Atam Nagar | 47 | Water supply | NA | Providing and Installation of 25 HP Straight Bore Submersible Tubewell at Kartar Nagar (Apna Park), in Ward No 47 (against 40HP failed tubewell). (G.Q). |  | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 12.66 | -19.56% | 2637 11-02-2026 | Yes | Yes | SDO | NA | 2025-12-26 | 2026-01-23 | YES | Yes | 121/G/33 20-02-2026 | M/s JCS Electric Works | 10.18 | 2026-02-25 | 3 months | 2026-07-15 | NA | Harjotpal Singh JE/Baljeet Singh SDO/Randeep Singh Xen | NA | NA | 95% |  | 9.67 | Delayed/Held Up |  | only electric connection pending
174 | MCL-0486 | O&M | D | D2 | Atam Nagar | 50 | Water supply | NA | Providing and Installation of 25 HP Straight Bore Submersible Tubewell at Chhoti Jawaddi in Ward No 50. (C.Q) |  | NA | 1 | Councillor Quota (CQ) | C.Q | Awarded | 12.66 | -19.7% | 2638 11-02-2026 | Yes | Yes | SDO | NA | 2025-12-26 | 2026-01-23 | YES | Yes | 122/G/33 20-02-2026 | M/s JCS Electric Works | 10.17 | 2026-02-25 | 3 months | 2026-07-31 | NA | Harjotpal Singh JE/Baljeet Singh SDO/Randeep Singh Xen | NA | NA | Not Started |  | - | Not Started |  | Notice Issued
175 | MCL-0487 | O&M | D | D2 | Atam Nagar | D2 | Water supply | NA | Prepare of Foundation of 100 HP Motor Pump at Water Works Plant, Ph1, Dugri in Sub Zone D2. (C.Q) (E Comp No. 375948) |  | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 2.64 |  | 3347 21-4-02026 | Yes | Yes | SDO | NA | 2025-12-26 | 2026-01-23 | YES | Yes | 9/g/33 11-05-2026 | M/S G.K Contractor, Ludhiana | 1.96 | 2026-12-05 | 2 months | 2026-11-07 | NA | Gokaran Kumar JE/Baljeet Singh SDO/Randeep Singh Xen | NA | NA | Not Started |  | - | Not Started
176 | MCL-0488 | O&M | D | D2 | Atam Nagar | 47 | Sewerage | NA | Prov/Laying of Sewer line (missing links) in W. No. 47..(C.Q) |  | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 9.95 | -26.01% | 2632 11-02-2026 | Yes | Yes | XEN | NA | 2025-12-26 | 2026-01-23 | YES | Yes | 119/G/33 20-02-2026 | M/s G.K. Contractor | 7.36 | 2026-02-25 | 2 months | 2026-07-15 | 2026-08-30 | Harjotpal Singh JE/Baljeet Singh SDO/Randeep Singh Xen | NA | NA | 50% |  | 3.68 | 50% |  | Mannual work is being done
177 | MCL-0489 | O&M | D | D3 | West | 59 | Water Supply | NA | P/I or New Sub. 40 HP Tubewell at Big Park, Chhpar wali park, Ward No-74. |  | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 28.87 | 7.81% | 255 & 26-03-2025 | Yes | Yes | XEN | N/A | 2024-11-14 | 2024-12-03 | Yes | Yes | 15/G/33 11-04-2025 | CNC Precision Engineering | 26.62 |  | 3 months |  |  | Naresh kumar JE, Jatinder Sodhi SDO, Randeep SIngh Xen | N/A | N/A | - |  | - | Not Started | Stata of site is not suitable. New site requirement | Stata of site is not suitable. New site requirement
178 | MCL-0490 | O&M | D | D3 | West | 60 | Water Supply | NA | Rough Cost Estimate For Prov. & Laying of 4” DIK-7 Water Supply lines & 8” SN-8 UPVC sewer lines at Sargodha Colony &Gurdev Nagar, Backside Silver Arc Mall in Ward No.60 | 297 Mtr | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 29.14 | -20.1% | 973 06-05-2025 | Yes | Yes | XEN | N/A | 2025-04-11 | 2025-04-28 | Yes | Yes | 67/G/33 14-05-2025 | M/s Bharat Bhushan Contractor | 29.14 | 2025-05-20 | 3 months | 2025-08-15 | 2026-07-15 | Naresh kumar JE and Harkesh kumar JE, Jatinder Sodhi SDO, Randeep SIngh Xen | N/A | N/A | 80% |  | 17.48 | In Progress |  | Work In Progress
179 | MCL-0491 | O&M | D | D3 | West | Gen. | Water Supply | NA | Rough cost of Estimate For Providing & Installation of 40 HP. Rig Bore Tubewell at against failed T/well) Ward General T/well West |  | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 20.54 | -17.79% | 961 06-05-2025 | Yes | Yes | SDO | N/A | 2025-04-11 | 2025-04-28 | Yes | Yes | 72/G/33 14-05-2025 | M/s Guru Kirpa & Co | 20.54 | not Started | 3 months | 2025-08-30 | not Started | Naresh kumar JE and Harkesh kumar JE, Jatinder Sodhi SDO, Randeep SIngh Xen | N/A | N/A | - |  | - | Not Started | Notice Issued | Notice Issued
180 | MCL-0492 | O&M | D | D3 | West | 72 | Water Supply | NA | Prov. & Laying of 4” DIK-7 Water Supply Line at Jawahar Nagar Camp Ward No-72. | 1939 Mtr | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 43.41 | -12.3% | 1871 13-10-2025 | Yes | Yes | XEN | N/A | 2025-08-04 | 2025-08-12 | Yes | Yes | 89/G/33 03-11-2025 | M/S Bharat Bhushan Contractor | 43.41 | 2025-10-11 | 3 months | 2026-01-15 | 2026-07-15 | Naresh kumar JE and Harkesh kumar JE, Jatinder Sodhi SDO, Randeep SIngh Xen | N/A | N/A | 95% |  | 41.24 | Delayed/Held Up |  | Only one street pending mannual work in being done
181 | MCL-0493 | O&M | D | D3 | West | 72 | Water Supply | NA | Rough Cost Estimate For 4" DIK-7 Water Supply Line at Bus Stand to Bharat Nagar chowk Ward No-72. | 1120 Mtr | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 29.16 | -0.04% | 1870 13-10-2025 | Yes | Yes | XEN | N/A | 2025-08-04 | 2025-08-12 | Yes | Yes | 90/G/33 03-11-2025 | 1 Apex Devlopers, Ludhiana. 2. M/S Kohinoor Builders, Ludhiana. | 29.16 | 2025-08-11 | 3 months | 2025-11-11 | 2026-07-15 | Naresh kumar JE and Harkesh kumar JE, Jatinder Sodhi SDO, Randeep SIngh Xen | N/A | N/A | 70% |  | 14.58 | In Progress |  | Not further work required in this file
182 | MCL-0494 | O&M | D | D3 | West | 54 | Water Supply | NA | Providing & Installation of 25 HP. Submersible new Tubewell at J- Block, Sarabha Nagar (Against Failed Tubewell) Ward No-55. shifted to karnail singh nagar |  | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 13.13 | -1.25% | 1460 13-10-2025 | Yes | Yes | SDO | N/A | 2025-08-04 | 2025-08-12 | Yes | Yes | 95/G/33 03-11-2025 | M/S Amarpal Singh Bawa | 12.96 | 2025-11-10 | 2 months | 2026-07-15 | 2026-07-15 | Naresh kumar JE and Harkesh kumar JE, Jatinder Sodhi SDO, Randeep SIngh Xen | N/A | N/A | 100% |  | 11.02 | Work Done
183 | MCL-0495 | O&M | D | D3 | West | 59 | Water Supply | 373959 | Upgradaiton of 4" DIK7 Water Supply line at Indra Colony, Barewal Road, Ward No-59. (C.Q) (E Comp No. 373959) | 542 mtr | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 13.8 | -16.1% | 3371 21-04-2026 | Yes | Yes | SDO | N/A | 2025-12-26 | 2026-01-15 | Yes | Yes | 5/g/33 11-05-2026 | M/S Sushil Kumar Contractor, Ludhiana | 11.57 | not Started | 3 months | 2026-08-08 | not Started | Naresh kumar JE and Harkesh kumar JE, Jatinder Sodhi SDO, Randeep SIngh Xen | N/A | N/A | - |  | - | Not Started |  | Work not Started due to Rainy Season
184 | MCL-0496 | O&M | D | D3 | West | 55 | Sewerage | NA | Estimate For Prov. & Laying of 10” UPVC SN-8 Pipe Sewer Line at H. No.-22 Block-K, Sarabha Nagar in Ward No-55, Ludhiana | 109 Mtr | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 6.95 | -23..50% | 3250 29-11-2024 | Yes | Yes | SDO | N/A | 2024-08-26 | 20-82024 | Yes | Yes | 52/G/33 02-12-2024 | Bharat Bhusan Contractor | 5.31 | not started | 2 months | 2025-02-10 | not Started | Naresh kumar JE and Harkesh kumar JE, Jatinder Sodhi SDO, Randeep SIngh Xen | N/A | N/A | - |  | - | Not Started | New Road constucted so hold up | New Road constucted
185 | MCL-0497 | O&M | D | D3 | West | 59 | Sewerage | NA | Rough Cost Estimate For Upgradation of 315mm UPVC SN-8 Pipe Sewer Line at Barewal Shamshan Ghat Road in Ward No-74, Ludhiana. | 125 Mtr | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 9.95 | -26% | 3248 29-11-2024 | Yes | Yes | SDO | N/A | 2024-08-26 | 20-82024 | Yes | Yes | 50/G/33 02-12-2024 | Bedi Pump Store., Ludhiana. | 7.37 | not started | 2 months | 2025-02-10 | not Started | Naresh kumar JE and Harkesh kumar JE, Jatinder Sodhi SDO, Randeep SIngh Xen | N/A | N/A | - |  | - | Not Started | New Road constucted so hold up | New Road constucted
186 | MCL-0498 | O&M | D | D4 | West | 56 | Sewerage | NA | Up-gradation of 12” SN-8 UPVC Sewer line at House No.-3H to Opp. Key Hotel Wd. No.-71. |  | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 42.28 | -31.31% | 976 06-05-2026 | Yes | Yes | XEN | N/A | 2025-04-11 | 2025-04-28 | Yes | Yes | 66/G/33 14-05-2025 | M/s Anmol Katyal Contractor | 29.04 | not started | 3 months | 2025-08-15 | not Started | Naresh kumar JE and Harkesh kumar JE, Jatinder Sodhi SDO, Randeep SIngh Xen | N/A | N/A | - |  | - | Not Started | road level issue so hold up. | road level issue so hold up.
187 | MCL-0499 | O&M | D | D3 | West | 56 | Sewerage | NA | Providing & Laying of 8” SN-8 UPVC Sewer Line at keys Hotel back side, S.B.S Nagar in Ward No- 56, Ludhiana.(C.Q) |  | NA | 1 | Councillor Quota (CQ) | C.Q | Awarded | 22.64 | -19.7% | 2638 11-02-2026 | Yes | Yes | SDO | N/A | 2025-11-07 | 2025-12-16 | Yes | Yes | 112/G/33 20-02-2026 | M/s N.S. Infra | 17.21 | 2026-02-25 | 3 months | 2026-05-30 | 2026-07-30 | Naresh kumar JE and Harkesh kumar JE, Jatinder Sodhi SDO, Randeep SIngh Xen | N/A | N/A | 100% |  | 15.49 | In Progress | Work Done | Notice Issued
188 | MCL-0500 | O&M | D | D3 | West | 55 | Sewerage | 379488 | Providing & Laying 12" UPVC SN-8 Storm Sewer Line at Block-G, B.R.S Nagar in Ward No-55, Ludhiana. (G.Q) (E Comp No. 379488) | 963 Mtr | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 85.14 | -30.76% | 3408 21-04-2026 | Yes | Yes | SE | N/A | 2025-12-26 | 2026-01-15 | Yes | Yes | 8/g/33 11-05-2026 | M/S Friends and Company, Ludhiana.. | 58.95 | 2026-05-15 | 4 months | 2026-08-14 | 2026-08-14 | Naresh kumar JE and Harkesh kumar JE, Jatinder Sodhi SDO, Randeep SIngh Xen | N/A | N/A | 50% |  | 29.48 | In Progress | Colony residents informed that work is very slow and of poor quality | Concerned officials to visit. ZC to visit as well and report on status
189 | MCL-0501 | O&M | D | D4 | West | 61 | Water Supply | NA | Providing & installation of a new tubewell (against failure) of 40 HP in Rose Garden-2 (inside the park) under Ward No.-61. |  | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 26.74 | -15.69% | 962 06-05-2025 | Yes | Yes | XEN | N/A | 2025-04-11 | 2025-04-28 | Yes | Yes | 54/G/33 14-05-2025 | M/s Guru Kirpa & Co | 22.54 | not started | 3 months | - |  | Naresh kumar JE and Harkesh kumar JE, Jatinder Sodhi SDO, Randeep SIngh Xen | N/A | N/A | - |  | - | Not Started |  | Notice Issued
190 | MCL-0502 | O&M | D | D4 | West | Gen. | Water Supply | NA | Purchase of Wate Tankerof 15 no. of S.S. for west constituency, Municipal Corporation Ludhiana. (15th Finance Commmission Drinking Water Head). |  | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 44.6 | -23.7% | 2503 23-08-2024 | Yes | Yes | XEN | N/A | 2024-06-12 | 2024-07-01 | Yes | Yes | 43/G/33 26-11-2024 | M/s Kakar Fabricators, Ludhiana | 34.02 | 2024-11-30 | 3 months | 2026-04-07 | 2026-08-14 | Sh. Gurdeep SIngh JE, Sh. Anshul Garcha SDO | N/A | N/A | 75% |  | 25.52 | In Progress |  | Work in Progress
191 | MCL-0503 | O&M | D | D3 | West | West | Water Supply | NA | Annual rate contract of Prov. and installation of 25 HP & 12.5 HP Tubewells for West Constituency. (G.Q) |  | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 80.34 | -8.6% | 2585 11-02-2026 | Yes | Yes | SE | N/A | 2025-04-30 | 2025-05-09 | Yes | Yes | 114/G/33 20-02-2026 | M/s ESS Elechmech Enterprises | 68.67 | 2026-02-25 | 12 months | 2027-10-02 | 2027-10-02 | Sh. Karan Kumar JE, Smt. Harpreet Kaur, JE, Sh. Arjun Sikka SDO | N/A | N/A | 80% |  | 54.94 | In Progress |  | Work in Progress
192 | MCL-0504 | O&M | D | D4 | West | 53 | Water Supply | NA | Rough Cost Estimate For Prov. & Laying of 4” DIK-7 Water Supply line,8” & 10”UPVC Sewer lines at A-Block, Model Town Extension in ward No-53. | 8"Sewer line(722 Mtr & 4"Water Supply Line 871 Mtr,& 10"Sewer line 137 Mtr) | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 61.25 | -24.99 | 3279 25-02-2026 | Yes | Yes | SE | N/A | 2025-04-30 | 2025-06-27 | Yes | Yes | 125/g/33 10-03-2026 | M/S Rajdeep Enterprises | 45.94 | 2026-03-15 | 3 months | 2026-07-15 | 2026-08-15 | Sh. Kulseep Singh JE, Sh. Arjun Sikka SDO | N/A | N/A | 70% |  | 32.16 | In Progress |  | Work in Progress
193 | MCL-0505 | O&M | D | D4 | West | 65 | Water Supply | 398855 | Providing & Installation of 12.5 HP. Submersible Tubewell at St. No. 13, Jain Colony in Ward No-65(E.Comp. No 398855) |  | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 6.37 | -12.29 | 2025-06-12 | Yes | Yes | SDO | N/A | 2025-04-11 | 2025-04-28 | Yes | Yes | 11/g/33 15-06-2026 | Ess Elecmech Enterprises | 5.58 | 2026-06-16 | 2 months | 2026-08-15 | 2026-08-15 | Sh. Karan Kumar JE, Smt. Harpreet Kaur, JE, Sh. Arjun Sikka SDO | N/A | N/A | 25 |  | - | In Progress |  | Work in Progress
194 | MCL-0506 | O&M | D | D3 | West | D4 | Sewerage | 384878 | Estimate for P/I of 12" i/d SN-8 Sewer Line at Hambran Road, MC limit to B&R Store (right side) and Hambran Road, Onkar Autos to outside World Diabetes (left side), sub zone-D4. (E Comp No. 384878) | 8" Sewerline 347 Mtr, 10" Sewer line 215 Mtr,12" Sewer line 457 Mtr | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 62.37 | .35.06 | 04-0 5-02026 | Yes | Yes | XEN | N/A | 2025-04-11 | 2025-04-28 | Yes | Yes | 10/g/33 11-05-2026 | M/s Bedi Pump Store, | 40.49 | 2026-05-15 | 3 months | 2026-08-14 | 2026-08-14 | Sh. Karan Kumar JE, Smt. Harpreet Kaur, JE, Sh. Arjun Sikka SDO | N/A | N/A | 75% |  | 30.37 | In Progress |  | Work in Progress
|  | O&M | A | A2 | Central | 83 | Water Supply | 385468 | Providing & Installation of 25 HP Straight Bore T/Well in Bhanot wali gali, Ward no.83. | NA | NA | 1 |  |  | Proposed | 12.7 |  |  |  |  | SDO | N/A | [11 empty] | Sachin JE Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | [5 empty] | On Tender Process
|  | O&M | A | A2 | Central | 83 | Water Supply | 385457 | Providing & Installation of 12.5HP Straight Bore T/Well aft in Ram Gali , Ward no.83. | NA | NA | 1 | Councillor Quota (CQ) |  | Proposed | 6.72 |  |  |  |  | SDO | N/A | [11 empty] | Sachin JE Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | [5 empty] | On Tender Process
|  | O&M | A | A2 | Central | 83 | Water Supply | 381235 | Providing & Installation of 25HP Straight Bore T/Well Shamshan Ghat, Kalyan Nagar , Ward no.83. | NA | NA | 1 | Councillor Quota (CQ) |  | Proposed | 12.7 |  |  |  |  | SDO | N/A | [11 empty] | Sachin JE Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | [5 empty] | Send to Proforma for Tendering process
|  | O&M | A | A2 | Central | 83 | Sewerage | 384991 | Rough Cost Estimate Prov. Laying of Water Supply Line Bhanot wali Gali Ward No.83 | 146.33 | NA | 1 | MC Funds / General Quota |  | Proposed | 13 |  |  |  |  | SDO | N/A | [11 empty] | Sachin JE Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | [5 empty] | On Tender Process
|  | O&M | A | A2 | Central | 90 | Sewerage | 381579 | Rough Cost Estimate Prov. Laying of Water Supply Line Mata Rani Chowk to Meena Bazar Ward No.90 | 546.05 | NA | 1 | Councillor Quota (CQ) |  | Proposed | 21.9 |  |  |  |  | SDO | N/A | [11 empty] | Sachin JE Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | [5 empty] | On Tender Process
|  | O&M | A | A2 | Central | 90 | Sewerage | 381591 | Rough Cost Estimate Prov. Laying of Water Supply Line Kache Bhande to Prem Gali, Ward No.90 | 396.34 | NA | 1 | Councillor Quota (CQ) |  | Proposed | 26.7 |  |  |  |  | XEN | N/A | [11 empty] | Sachin JE Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | [5 empty] | On Tender Process
|  | O&M | A | A2 | Central |  | Sewerage | 384976 | Rough Cost Estimate Prov. Laying of Water Supply Line in different localities in central ward | 1036.59 | NA | 1 | MC Funds / General Quota |  | Proposed | 48.8 |  |  |  |  | XEN | N/A | [11 empty] | Sachin JE Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | [5 empty] | On Tender Process
|  | O&M | A | A2 | Central | 83 | Water Supply | 385568 | Providing & Installation of new Straight Bore T/Well at Arovansh Dharamshala, Ward no.83. | NA | NA | 1 | Councillor Quota (CQ) |  | Proposed | 8.18 |  |  |  |  | SDO | N/A | [11 empty] | Sachin JE Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | [5 empty] | File already generated, approval pending
|  | O&M | A | A2 | Central | 90 | Sewerage | 385589 | Rough Cost Estimate Prov. Laying of s/w + Water Supply Line Sikha wali gali, Kucha Harnamdas, Ward No.90 | 705.83 |  | 1 | MC Funds / General Quota |  | Proposed | 20.2 |  |  |  |  | SDO | N/A | [11 empty] | Sachin JE Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | [5 empty] | On Tender Process
|  | O&M | A | A1 | Central | 83 | Water Supply | 385551 | Providing & Installation of new Straight Bore T/Well at Saida Mohalla, Ward no.83. | NA | NA | 1 | Councillor Quota (CQ) |  | Proposed | 8.18 |  |  |  |  | SDO | N/A | [11 empty] | Rajneesh Kumar JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | [5 empty] | On Tender Process
|  | O&M | A | A1 | Central | 84 | Water Supply | 385483 | Providing & Installation of 25HP Straight 200 mtr Bore T/Well AFT Roopa Mistri wali gali, Ward no.84. | NA | NA | 1 | MC Funds / General Quota |  | Proposed | 12.74 |  |  |  |  | SDO | N/A | [11 empty] | Rajneesh Kumar JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | [5 empty] | On Tender Process
|  | O&M | A | A2 | Central | 77 |  | 385229 | ਸਬਜ਼ੋਨ ਏ 2 ਵਾਰਡ ਨੰ:77 ਵਿੱਚ 4 ਸੀਵਰਮੈਨ ਆਉਟਸੋਰਸ ਰੱਖਣ ਸਬੰਧੀ | NA | NA | 1 | MC Funds / General Quota |  | Proposed | 7.44 |  |  |  |  | SDO | N/A | [11 empty] | Sachin JE Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | [5 empty] | file on hold
|  | O&M | A | A2 | Central | 78 |  | 375427 | Annual Rate - m+c work of different localities of ward no.78 | NA | NA | 1 | MC Funds / General Quota |  | Proposed | 9.93 |  |  |  |  | SDO | N/A | [11 empty] | Sachin JE Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | [5 empty] | On Tender Process
|  | O&M | A | A | Central |  | Water Supply | 375494 | Annual rate contract of prov/installation of 5 nos.12.5HP and 5 nos. 25HP against failed (emergency) t/well in central constituency Zone-A | NA | NA | 1 | Gen Quota |  | Proposed | 97.46 |  |  |  |  | SDO | N/A | [12 empty] | n/A | N/A | [5 empty] | estimate send for approval for tender procsess
|  | O&M | A | A2 | Central |  | Sewerage | 384439 | ਢੋਕਾਂ ਮੁਹੱਲਾ ਵਿਖੇ ਸਲੁਜ ਗੇਟ ਲ਼ਗਾਉਣ ਸਬੰਧੀ | NA | NA | 1 |  |  | Proposed | 5.97 |  |  |  |  | SDO | N/A | [11 empty] | Sachin JE Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | [5 empty] | On Tender Process
|  | O&M | A | A2 | Central | 82 | Sewerage | 386216 | ips ਗਊਸ਼ਾਲਾ ਨੇੜੇ ਗੁਰਦਵਾਰਾ ਵਿਖੇ ਸੰਤ ਬਾਬਾ ਸੀਚੇਵਾਲ ਵੱਲੋਂ ਬਣਾਏ ਨਵੇ ਡਿਸਪੋਸਲ ਉੱਪਰ 500 kva 25% ਵਾਧਾ ਕਰਨ ਸਬੰਧੀ | NA | NA | 1 |  |  | Proposed | 10.62 |  |  |  |  | SDO | N/A | [11 empty] | Sachin JE Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | [5 empty] | file sent for approval
|  | O&M | A | A2 | Central | 82 | Sewerage | 386226 | ਜ਼ੋਨ ਏ ਅਧੀਨ ਪੈਂਦੇ ਏਰੀਆ ਗਊਸ਼ਾਲਾ (ਟੈਂਪਰੇਰੀ ਡਿਸਪੋਸਲ 500 kva Kirloskar ਜੇਨਰਟੋਰ ਦੀ ਖਰੀਦ ਕਰਨ ਸਬੰਧੀ | NA | NA | 1 |  |  | Proposed | 74.49 |  |  |  |  | SE | N/A | [11 empty] | Sachin JE Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | [5 empty] | On Tender Process
|  | O&M | A | A2 | Central | 90 |  | 388023 | ਸਬਜ਼ੋਨ ਏ 2 ਅਧੀਨ ਪੈਂਦੇ ਵਾਰਡ ਨੰ:90 ਵਿੱਚ 10 ਸਿਵਰਮੈਨ ਦਾ ਵਾਧਾ ਕਰਨ ਸਬੰਧੀ | NA | NA | 1 |  |  | Proposed | 19.09 |  |  |  |  | SDO | N/A | [11 empty] | Sachin JE Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | [5 empty] | put up to next F&CC meeting
|  | O&M | A | A2 | Central | 82 | Water Supply | 388818 | Providing & Installation of 25HP Straight Bore T/Well Harbanspura Ward no.82 (MP lad.) | NA | NA | 1 |  |  | Proposed | [5 empty] | SDO | N/A | [11 empty] | Sachin JE Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | [5 empty] | metrer pending for under process
|  | O&M | A | A1 | Central |  | Water Supply | 391614 | ਜ਼ੋਨ ਏ ਦੇ ਵਿੱਚ ਤੀਸਰੀ ਮੰਜ਼ਿਲ ਤੇ ਪਾਣੀ ਦਾ ਪ੍ਰਬੰਧ ਕਰਵਾਉਣ ਸਬੰਧੀ | NA | NA | 1 |  |  | Proposed | 3.27 |  |  |  |  | JE | N/A | [11 empty] | Sachin JE Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | [5 empty] | On Tender Process
|  | O&M | A | A | Central |  | Sewerage | 391705 | ਮੇਰੇ ਸੈਂਟ੍ਰਲ ਹਲਕੇ ਅਧੀਨ ਪੈਂਦੇ ਵਾਰਡਾ ਦੇ ਸੀਵਰ ਦੇ ਢੱਕਣਾ ਦੀ ਰਿਪੇਅਰ ਕਰਨ ਸਬੰਧੀ | NA | NA | 1 | Gen Quota |  | Proposed | 9.98 |  |  |  |  | SDO | N/A | [11 empty] | Sachin JE Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | [5 empty] | put uoto to next F&CC meeting
|  | O&M | A | A2 | Central | 90 | Water Supply | 392642 | Providing & Installation of 25HP Straight Bore T/Well at 1000 Gaj near lakkad bazar Ward no.90 (MP lad.) | NA | NA | 1 | MP LAD |  | Proposed | 13.5 |  |  |  |  | SDO | N/A | [11 empty] | Sachin JE Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | [5 empty] | file on hold for F&CC meeting
|  | O&M | A | A2 | Central | 84 | Water Supply | 396254 | ਨਗਰ ਨਿਗਮ ਵੱਲੋਂ ਵਾਰਡ ਨੰ: New/84 (Old/56) ਡਾਕਟਰ ਖੇੜਾ ਲਬੋਰਟਰੀ, ਗੁਲਚਮਨ ਗਲੀ, ਲੁਧਿਆਣਾ ਵਿਖੇ 12.5 ਐਚ.ਪੀ ਦਾ ਟਿਊਬਵੈਲ ਲਗਾਇਆ ਗਿਆ ਹੈ, ਜਿਸ ਸਬੰਧੀ ਬਿਜਲੀ ਵਿਭਾਗ ਨੂੰ ਸਕਿਊਰਟੀ ਫੀਸ ਅਤੇ ਡਿਮਾਂਡ ਨੋਟਿਸ ਦੀ ਫੀਸ ਜਮ੍ਹਾਂ ਕਰਵਾਉਣ ਸਬੰਧੀ। | NA | NA | 1 |  |  | Proposed | [5 empty] | SDO | N/A | [11 empty] | Sachin JE Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | [5 empty] | pending for approval
|  | O&M | A | A2 | Central | 82 | Water Supply | 400532 | ਵਾਰਡ ਨੰ:82 ਵਿੱਚ ਬੇਂਜਾਮਿਨ ਰੋਡ ਨੇੜੇ ਸ਼ਾਂਤੀ ਨਿਕੇਤਨ ਵਿਖੇ ਲੱਗਾ ਟਿਊਬਵੈਲ ਫੈਲ ਸਬੰਧੀ | NA | NA | 1 | Councillor Quota (CQ) |  | Proposed | 12.74 |  |  |  |  | SDO | N/A | [11 empty] | Sachin JE Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | [5 empty] | file under process
|  | O&M | A | A2 | Central |  | Sewerage | 408116 | Rough Cost Estimate Prov. Laying of s/w + Water Supply at Mahanta wali gali , Ward No.77 |  | NA | 1 |  |  | Proposed | 5.77 |  |  |  |  | SDO | N/A | [11 empty] | Sachin JE Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | [5 empty] | pending estimate approval
|  | O&M | A | A1 | Central |  | Sewerage | 409317 | Rough Cost Estimate for 500nm dia RCC NP3 sewer line Basti Chowk near Gurdwara , Ward No.9 |  | NA | 1 |  |  | Proposed | [5 empty] | SDO | N/A | [11 empty] | Rajneesh Kumar JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | [5 empty] | pending estimate approval
|  | O&M | A |  | Central |  |  | 379731 | ਓ ਐਂਡ ਐਮ ਸ਼ਾਖਾ ਸਬਜ਼ੋਨ ਏ 2 ਅਧੀਨ ਗਊਸ਼ਾਲਾ ਵਿਖੇ ਬਣੇ ਟੈਂਪਰੇਰੀ ਡਿਸਪੋਸਲ ਨੂੰ ਚਲਾਉਣ ਲਈ ਆਉਟਸੋਰਸ ਸਟਾਫ਼ ਰੱਖਣ ਸਬੰਧੀ |  | NA | 1 |  |  | Proposed | 16.33 |  |  |  |  | SDO | N/A | [11 empty] | Sachin JE Eisha Teji JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | [5 empty] | file on hold
|  | O&M | A | A1 | Central | 10 |  | 380029 | ਓ ਐਂਡ ਐਮ ਸ਼ਾਖਾ ਅਧੀਨ ਪੈਂਦੇ ਸਬਜ਼ੋਨ ਏ 2 ਵਿੱਚ 5 ਸੀਵਰਮੈਨ ਆਉਟਸੋਰਸ ਰੱਖਣ ਸਬੰਧੀ |  | NA | 1 |  |  | Proposed | 8.87 |  |  |  |  | SDO | N/A | [11 empty] | Rajneesh Kumar JE Sandeep Sharma SDO Kamal Ram XEN | n/A | N/A | [5 empty] | put upto next F&CC meeting
|  | O&M | B | B1 | Central | 30 | Sewerage | __ | Prov & laying of Raising of slab of machine hole chamber upto road level in Transport Nagar in W. No. 30 (G-Quota) | NA | NA | 1 | MC Funds / General Quota | GQ | Awarded | 7.06 | 23.02 | 2187 21-11-2025 | YES | YES | XEN | N/A | 2025-08-04 | 2025-08-12 | YES | YES | 88/G33 24-11-2025 | Glisten | 81.93 |  | 4 |  |  | Rajinder Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | n/A | N/A | 100 |  |  | Completed
|  | O&M | B | B1 | Central | 76 | Water Supply | 373937 | Estimate for Prov/Installation of (200 mm) 25HP Deep Straight Bore Tubewell at Near Ramu sabji wala, Islam ganj in Ward No. 76 (Against Failed T/w) (Central Constituency (Councillor Quota) | NA | NA | 1 | MC Funds / General Quota | CQ | Proposed | 12.45 | __ | __ | YES | YES | XEN | N/A | 2026-05-08 | 2026-06-01 | No | No | __ | __ | __ | __ | __ |  |  | Rajinder Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [5 empty] | Tender recall on 01-06-2026 but no tender received.
|  | O&M | B | B1 | Central | 75 | Water Supply | 374166 | Estimate for Prov/ Installation of (200 mm) 2 No 25HP Deep Straight Bore Tubewell at Near Madan Medical store & Near Shanti pardhan wali gali Islam ganj in Ward No. 75 (Against Failed 1/w) (Central Constituency) (G.Q) | NA | NA | 1 | MC Funds / General Quota | GQ | Proposed | 25.15 | __ | __ | YES | YES | XEN | N/A | 2026-05-08 | 2026-06-01 | No | No | __ | __ | __ | __ | __ |  |  | Rajinder Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [5 empty] | Tender recall on 01-06-2026 but no tender received.
|  | O&M | B | B1 | Central | 75 | Water Supply | 381712 | Prov. & Laying of 4" DI-K7 line at Are wali gali to shanti pardhan wali gali, Islam Ganj, Ward No.75 (G-Quota). | 361 | NA | 1 | MC Funds / General Quota | GQ | Proposed | 11.37 | __ | __ | YES | YES | XEN | N/A | 2026-06-09 | 2026-06-25 | Yes | Yes | __ | __ | __ | __ | __ |  |  | Rajinder Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [5 empty] | Financial bid open and file will be sent for allotment approval.
|  | O&M | B | B1 | Central | 76 | Water Supply | 395299 | Prov/Installation of (200 mm) 25HP Deep Straight Bore Tubewell at Nr. Khurana chaki, Prem Nagar in Ward No. 76 (Against Failed T/w) (Central Constituency) (G-Quota). | NA | NA | 1 | MC Funds / General Quota | GQ | Proposed | 12.57 | __ | __ | YES | YES | XEN | N/A | 2026-06-09 | 2026-06-25 | Yes | Yes | __ | __ | __ | __ | __ |  |  | Rajinder Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [5 empty] | Financial bid open and file will be sent for allotment approval.
|  | O&M | B | B1 | Central | 30 | Sewerage | 373722 | Prov Laying of 24 inch dia NP3 Storm Sewer line at Maria Steel wali line in W. No. 30 (GQ). | 579 | NA | 1 | MC Funds / General Quota | GQ | Proposed | 63.85 | __ | __ | YES | YES | XEN | N/A | 2026-05-08 | 2026-06-01 | No | No | __ | __ | __ | __ | __ |  |  | Rajinder Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [5 empty] | Tender recall on 01-06-2026 but no tender received.
|  | O&M | B | B1 | Central | 75 | Sewerage | __ | Prov & Laying of 8" Dia UPVC Sewer Line at various streets in Islam ganj ward No 75 (G-Quota) | 609.6 | NA | 1 | MC Funds / General Quota | GQ | Proposed | 38.68 | __ | __ | YES | YES | XEN | N/A | 2026-04-30 | 2026-05-15 | No | No | __ | __ | __ | __ | __ |  |  | Rajinder Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [5 empty] | File sent for Estimate Approval.
|  | O&M | B | B1 | Central | 80 | Sewerage | 373774 | Rough Cost Estimate of Prov & Laying of additional machine hole chamber in Ward No 80 (G-Quota) | NA | NA | 1 | MC Funds / General Quota | GQ | Proposed | 4.85 | __ | __ | YES | YES | XEN | N/A | 2026-06-09 | 2026-06-25 | Yes | Yes | __ | __ | __ | __ | __ |  |  | Rajinder Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [5 empty] | Financial bid open and file will be sent for allotment approval.
|  | O&M | D | D3 | West | D3 | Water Supply | NA | Annual rate contract regarding maintenance of tubewells in Sub Zone- D3. |  | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 64.07 | -50.15 | 2025-07-02 | Yes | Yes | SE | N/A | 2025-04-11 | 2025-04-28 | Yes | Yes | 74/G/33 02-07-2025 | M/s Bedi Pump Store | 31.93 | 2025-07-20 | 12 months | 2026-06-30 | 2026-06-30 | Naresh kumar JE and Harkesh kumar JE, Jatinder Sodhi SDO, Randeep SIngh Xen | N/A | N/A | work in progress |  |  | In Progress |  | Work in Progress
|  | O&M | D | D3 | West | D3 | Water Supply | NA | Supply of Water & sewer mateiral as per CSR & NS rate in sub zone-D3 (General Quota) |  | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 9.75 | -27.78 | 2635 11.02.2026 | Yes | Yes | SDO | N/A | 2025-04-30 | 2025-06-27 | Yes | Yes | 113/G/33 20-02-2026 | M/S Rajdeep Enterprises | 7.04 | 2026-02-28 | 2 months | 2026-04-01 | 2026-07-15 | Naresh kumar JE and Harkesh kumar JE, Jatinder Sodhi SDO, Randeep SIngh Xen | N/A | N/A | work in progress |  |  | In Progress |  | Work in Progress
|  | O&M | D | D4 | West | 69 | Water Supply | 374175 | P/I of 25 HP Straight Bore Submersible Tubewell at Postal Colony, Wd. No.-69 (G.Q.)(E.Comp. No 374175) |  | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 12.47 | -20.87 | 3799 15-06-2026 | Yes | Yes | SDO | N/A | 2025-04-11 | 2025-04-28 | Yes | Yes | 16/g/33 08-07-2026 | M/S Bedi Pump Store, Ludhiana. | 9.94 | 2026-07-10 | 3 months | 2026-10-10 | 2026-10-10 | Sh. Kulseep Singh JE, Sh. Arjun Sikka SDO | N/A | N/A | just issued |  |  | In Progress |  | Work in Progress
|  | O&M | D | D3 | West | D3 | Sewerage | NA | De-Silting and Cleaning of Sewerlines in different areas of ward No.-57, 58, 59, 60 & 72 of West Constituency |  | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 76.89 | - | 483 09-042025 | Yes | Yes | SE | N/A | 2025-04-11 | 2025-04-28 | Yes | Yes | 49/G/33 25-04-2025 | M/s. Inderjit Bajaj & Associates. | 76.89 | 2025-05-05 | 3 months | 2025-08-06 | 2026-08-14 | Naresh kumar JE and Harkesh kumar JE, Jatinder Sodhi SDO, Randeep SIngh Xen | N/A | N/A | 75% completed |  |  | In Progress |  | Work in Progress
|  | O&M | D | D4 | West | 64 | Sewerage | 384892 | P/L of 8" S.N.8 Sewer Line at Diary Complex, Backside Rehan Basera, near Dog Sanctuary Ward No-64. (G.Q.)(E.Comp. No 384892) | 8" Sewerline 167 Mtr | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 6.15 | -28.04 | 3785 15-06-2026 | Yes | Yes | SDO | N/A | 2025-04-11 | 2025-04-28 | Yes | Yes | 14/g/33 08-07-2026 | Ess Elecmech Enterprises | 4.42 | 2026-07-15 | 2 months | 2026-10-15 | 2026-08-14 | Sh. Karan Kumar JE, Smt. Harpreet Kaur, JE, Sh. Arjun Sikka SDO | N/A | N/A | 50% |  |  | In Progress |  | Work in Progress
|  | O&M | D | D4 | West | 64 | Water Supply | 396210 | Upgradaion of 4" DIK7 Water Supply Line at Kapil Park Wd. No.-64 (C.Q.)(E.Comp. No 396210) | 4" Water Supply Line 2397 Mtr | NA | 1 | Councillor Quota (CQ) | CQ | Awarded | 59.01 | -16..67 | 2026-06-19 | Yes | Yes | SE | N/A | 2025-04-11 | 2025-04-28 | Yes | Yes | 12/g/33 26-06-2026 | M/s Friends and Company | 49.17 | 2026-06-30 | 2 months | 2026-09-01 | 2026-09-01 | Sh. Karan Kumar JE, Smt. Harpreet Kaur, JE, Sh. Arjun Sikka SDO | N/A | N/A | 15% |  |  | In Progress |  | Work in Progress
|  | O&M | D | D4 | West | 64 | Water Supply | 396205 | Upgradation of 4 inch DIK7 Water Supply Line at Shere Punjab Nagar, Wd.No.-64 (C.Q.)(E.Comp. No 396205) | 4" Water Supply Line 725 Mtr | NA | 1 | Councillor Quota (CQ) | CQ | Awarded | 17.16 | -15.95 | 2026-06-19 | Yes | Yes | XEN | N/A | 2025-04-11 | 2025-04-28 | Yes | Yes | 13/g/33 26-06-2026 | M/s Tarsem Chand Singla Govt. Contractor | 14 | 2026-07-01 | 2 months | 2026-09-01 | 2026-09-01 | Sh. Karan Kumar JE, Smt. Harpreet Kaur, JE, Sh. Arjun Sikka SDO | N/A | N/A | 30% |  |  | In Progress |  | Work in Progress
|  | O&M | D | D3 | West | 56 | Sewerage | 373758 | Upgradation & P/Layingh of Sewer line City Enclave New BRS Nagar Ward No-56. | 230 Mtr | NA |  | Councillor Quota (CQ) | CQ | Sent to agenda Branch for . Approval on 20-04-2026 | 9.82 |  |  |  |  | SDO | [12 empty] | Naresh kumar JE and Harkesh kumar JE, Jatinder Sodhi SDO, Randeep SIngh Xen
|  | O&M | D | D3 | West | 55 | Sewerage |  | Rough Cost Estimate Prov. Laying Up-gradation and mtr. of Sewer Line at Different Localities of Ward No-55.(C.Q) |  | NA |  | Councillor Quota (CQ) | CQ | Estimated Approved and tender will be called | 9.75 |  |  |  |  | SDO | [12 empty] | Naresh kumar JE and Harkesh kumar JE, Jatinder Sodhi SDO, Randeep SIngh Xen
|  | O&M | D | D3 | West | 54 | Sewerage |  | Rough Cost Estimate Prov. Laying/Up-gradation and mtc. of Sewer Line at Different Localities of Ward No-54. (C.Q) |  | NA |  | Councillor Quota (CQ) | CQ | Estimated Approved and tender will be called | 9.69 |  |  |  |  | SDO | [12 empty] | Naresh kumar JE and Harkesh kumar JE, Jatinder Sodhi SDO, Randeep SIngh Xen
|  | O&M | D | D3 | West | 59 | Sewerage | 382348 | Rough Cost Estimate Prov. Laying/Up-gradarion and mtc.of Sewer Line and Raising of slabs at Sawami Narayan Mandir, Parksh Colony, Near Baklavi Hotel, Main Road Barewal, New Ashapuri & Sua Road in Ward No-59. | 8" 60 Mtr/Slabs | NA |  | MC Funds / General Quota | G.Q | sent to agenda branch for Est. Approval | 9.36 |  |  |  |  | SDO | [12 empty] | Naresh kumar JE and Harkesh kumar JE, Jatinder Sodhi SDO, Randeep SIngh Xen
|  | O&M | D | D3 | West | 56 | Sewerage | 388616 | ਵਾਰਡ ਨੰ.-56 ਬਲਾਕ-ਐਚ ਸ਼ਹੀਦ ਭਗਤ ਸਿੰਘ ਨਗਰ ਵਿੱਚ ਨਵੀਂ ਸੀਵਰ ਲਾਈਨ ਪਾਉਣ ਬਾਰੇ। |  | NA |  | MC Funds / General Quota | G.Q | estimate should be presented in the next meeting | 6.69 |  |  |  |  | SDO | [12 empty] | Naresh kumar JE and Harkesh kumar JE, Jatinder Sodhi SDO, Randeep SIngh Xen
|  | O&M | D | D4 | West | Gen |  |  | ਸਬ ਜੋਨ-ਡੀ4 ਵਿਖੇ ਟਰਾਲੀਆਂ ਦੀ ਖਰੀਦ ਕਰਨ ਬਾਰੇ। |  | NA | 1 | MC Funds / General Quota | GQ | Send To Xen For Work Proposed | 15 |  |  |  |  | SDO | [12 empty] | Sh. Karan Kumar JE, Smt. Harpreet Kaur, JE, Sh. Arjun Sikka SDO
|  | O&M | D | D4 | West | 61 | Sewerage |  | P/L of 200mm UPVC Sewer Line at Ghumer Mundi, Babu Ram Juice street in ward no 61. |  | NA | 1 | MC Funds / General Quota | GQ | F.B opened and sent to E Office next process | 12.79 |  |  |  |  | SDO | [6 empty] | Rajdeep Enterprises | [5 empty] | Sh. Karan Kumar JE, Smt. Harpreet Kaur, JE, Sh. Arjun Sikka SDO
|  | O&M | D | D4 | West | 61 | Sewerage |  | Additional manhole and 8” SN-8 Sewer Line at the different area of Ward No -61. | 8" Sewer line 128 Mtr | NA | 1 | Councillor Quota (CQ) | CQ | F.B opened and sent to E Office next process | 8.23 |  |  |  |  | SDO | [6 empty] | Bedi Pump Store | [5 empty] | Sh. Karan Kumar JE, Smt. Harpreet Kaur, JE, Sh. Arjun Sikka SDO
|  | O&M | D | D4 | West | 65 | Water Supply | 409205 | P/l of 8” SN-8 Sewer and 4” Water Supply Lines missing link at Inderprasth Nagar Ward No.-65 | 8" Sewer line 122 Mtr & 4" Water Supply line 36 Mtr | NA | 1 | MC Funds / General Quota | GQ | Send To Xen For Work Proposed | 6.54 |  |  |  |  | SDO | [12 empty] | Sh. Karan Kumar JE, Smt. Harpreet Kaur, JE, Sh. Arjun Sikka SDO
|  | O&M | D | D4 | West | 64 | Sewerage | 383347 | P/l of 8” SN-8 Sewer and 4” Water Supply Lines at Haibowal Khurd, St. No.-5 Ward No 64 | 8" Sewerline 115 Mtr & 4" Water suplly line 91 Mtr | NA | 1 | Councillor Quota (CQ) | CQ | Estimated Approved and tender will be called | 9.37 |  |  |  |  | SDO | [12 empty] | Sh. Karan Kumar JE, Smt. Harpreet Kaur, JE, Sh. Arjun Sikka SDO
|  | O&M | D | D4 | West | 62 | Sewerage | 372130 | P/l of 12” SN-8 Storm Sewerline & 8” SN-8 Sewerline at Amrit Colony, St. No.-2, Panj Peer Road, Opp. Corporation Colony Park, Raman Enclave via Gupta Sweet Shop and Outside Raman Enclave Panj Peer Road, Wd. No.-62. | 12" Sewer line 350 Mtr& 8" Sewer line 301 Mtr | NA |  | MC Funds / General Quota | GQ | estimate should be presented in the next meeting | 34.57 |  |  |  |  | SDO | [12 empty] | Sh. Karan Kumar JE, Smt. Harpreet Kaur, JE, Sh. Arjun Sikka SDO
|  | O&M | D | D4 | West | 62 | Sewerage | 372160 | ਵਾਰਡ ਨੰ.- 62 ਅਧੀਨ ਪੈਂਦੇ ਇਲਾਕੇ ਅਮ੍ਰਿਤ ਕਲੋਨੀ ਗਲੀ ਨੰ.2 ਅਤੇ ਪੰਜ ਪੀਰ ਰੋਡ, ਨੇੜੇ ਗੁਰੂਦੁਆਰਾ ਗਲੀ ਨੰ.-8 ਵਿਖੇ 4” DIK7 ਵਾਟਰ ਸਪਲਾਈ ਲਾਈਨ ਦਾ ਮੀਸਿੰਗ ਲਿੰਕ ਪਾਉਣ ਸਬੰਧੀ। (E.Comp. No 372160) | 4" Water Supply Line 381 Mtr | NA |  | MC Funds / General Quota | GQ | estimate should be presented in the next meeting | 8.48 |  |  |  |  | SDO | [12 empty] | Sh. Karan Kumar JE, Smt. Harpreet Kaur, JE, Sh. Arjun Sikka SDO
|  | O&M | D | D4 | West | 60 | Sewerage | 397848 | P/L of missing link 8" i/d SN-8 sewer line near Navrang Saree Centre, Ghumar Mandi, Ward No. 60. .(C.Q) | 8" Sewer line 131 Mtr | NA |  | Councillor Quota (CQ) | CQ | Estimated Approved and tender will be called | 5.45 |  |  |  |  | SDO | [12 empty] | Sh. Karan Kumar JE, Smt. Harpreet Kaur, JE, Sh. Arjun Sikka SDO
|  | O&M | D | D4 | West | 59 | Water Supply | 373110 | Rough Cost Estimate For Prov. & Laying of 4” & 6” DIK-7 Water Supply Line at Adarsh colony Barewal Road, (Zone-D) Ward No 59 |  | NA |  | MC Funds / General Quota | GQ | FB Opened | 37.89 |  |  |  |  | XEN | [12 empty] | Sh. Karan Kumar JE, Smt. Harpreet Kaur, JE, Sh. Arjun Sikka SDO
|  | O&M | D | D3 | West | 58 | Water Supply | 374977 | Rough Cost Estimate For Prov. & Laying of 4” DIK-7 Water Supply line & 8” UPVC Sewer lines at BRS Nagar Block-J Opp. Lodhi Club Wd no 58 |  | NA |  | MC Funds / General Quota | GQ | estimate approved but first take report from LIT | 17.5 |  |  |  |  | SDO | [12 empty] | Naresh kumar JE and Harkesh kumar JE, Jatinder Sodhi SDO, Randeep SIngh Xen
|  | O&M | D | D3 | West | 57 | Water Supply | 373738 | P/I of a new 12.5 HP Tube Well instead of the failed 5 HP Tube Well at Block-L, BRS Nagar, Ward No. 57 (C.Q.). |  | NA |  | Councillor Quota (CQ) | CQ | Estimated Approved and tender will be called | 6.75 |  |  |  |  | SDO | [12 empty] | Naresh kumar JE and Harkesh kumar JE, Jatinder Sodhi SDO, Randeep SIngh Xen
|  | O&M | D | D3 | West | 56 | Water Supply | 377268 | Rough Cost Estimate For Prov. & Laying of 4” DIK-7 Water Supply Line at Different localities of Ward No-56. |  | NA |  | MC Funds / General Quota | GQ | FB Opened | 5.6 |  |  |  |  | SDO | [12 empty] | Naresh kumar JE and Harkesh kumar JE, Jatinder Sodhi SDO, Randeep SIngh Xen
|  | O&M | D | D3 | West | D3 | Water Supply | 385455 | Annual rate contract of Prov. and Installation of 2Nos.-12.5 HP, 5 Nos.-25 HP, Against failed (Emergency) Tubewell in West Constituency, Zone-D-3.(G.Q) |  | NA |  | MC Funds / General Quota | GQ | Estimated Approved and tender will be called | 77.2 |  |  |  |  | SE | [12 empty] | Naresh kumar JE and Harkesh kumar JE, Jatinder Sodhi SDO, Randeep SIngh Xen
|  | O&M | D | D3 | West | 58 | Water Supply | 394276 | Prov./Installation of 25 HP Tubewell at Rajguru Nagar (Against Failed 40 HP T/Well) Ward No.-58 |  | NA |  | MC Funds / General Quota | GQ | estimate should be presented in the next meeting But Anticipation soTechnical Opned | 12.74 |  |  |  |  | SDO | [12 empty] | Naresh kumar JE and Harkesh kumar JE, Jatinder Sodhi SDO, Randeep SIngh Xen
|  | O&M | D | D4 | West | 73 | Water Supply | 372520 | Providing and Installation of 25 HP Straight Bore Submersible Tubewell at Manohar Nagar, Ludhiana Ward No 73 |  | NA |  | MC Funds / General Quota | GQ | file sent to Agenda branch for W.O | 10.03 |  |  |  |  | SDO | [12 empty] | Sh. Karan Kumar JE, Smt. Harpreet Kaur, JE, Sh. Arjun Sikka SDO
|  | O&M | D | D4 | West | 62 | Water Supply |  | ਵਾਰਡ ਨੰ.-62 ਅਧੀਨ ਪੈਂਦੇ ਇਲਾਕੇ ਅਮਰਿਤ ਕਲੋਨੀ ਵਿਖੇ 12.5 ਐਚ.ਪੀ. ਦਾ ਨਵਾਂ ਟਿਊਬਵੈਲ ਲਗਾਉਣ ਸਬੰਧੀ। |  | NA |  | MC Funds / General Quota | GQ | Send To Xen For Work Proposed | 6.37 |  |  |  |  | SDO | [12 empty] | Sh. Karan Kumar JE, Smt. Harpreet Kaur, JE, Sh. Arjun Sikka SDO
|  | O&M | D | D4 | West | 71 | Water Supply | 380066 | ਵਾਰਡ ਨੰ.-71 ਅਧੀਨ ਪੈਂਦੇ ਇਲਾਕੇ ਵਿਡਿਓ ਮਾਰਕਿਟ ਅਤੇ ਪਾਰਕ ਲੇਨ ਵਿਖੇ 25 ਐਚ.ਪੀ. ਦੇ ਦੋ ਨਵੇਂ ਟਿਊਬਵੈਲ ਲਗਾਉਣ ਸਬੰਧੀ। |  | NA |  | MC Funds / General Quota | GQ | file sent to agenda branch for Est. approval for 19-06-2026 | 24.95 |  |  |  |  | SDO | [12 empty] | Sh. Karan Kumar JE, Smt. Harpreet Kaur, JE, Sh. Arjun Sikka SDO
|  | O&M | D | D4 | West | Gen | Water Supply |  | Annual rate contract of Prov. and installation of 2 No.s of 12.5 HP and 3 No.s of 25 HP Tubewells ( against failed tubewells) for West Constituency. |  | NA |  | MC Funds / General Quota | GQ | Send To Xen For Work Proposed | 44.08 |  |  |  |  | XEN | [12 empty] | Sh. Karan Kumar JE, Smt. Harpreet Kaur, JE, Sh. Arjun Sikka SDO
|  | O&M | D | D4 | West | 63 | Water Supply | 401734 | P/L P/L of 4” DIK 7 Water Supply Line at Kitchlu Nagar , at the area of Block –F in Ward no -63. |  | NA |  | MC Funds / General Quota | GQ | F.B opened | 10.88 |  |  |  |  | SDO | [12 empty] | Sh. Karan Kumar JE, Smt. Harpreet Kaur, JE, Sh. Arjun Sikka SDO
|  | O&M | D | D4 | West | 62 | Water Supply | 380054 | ਵਾਰਡ ਨੰ.- 62 ਅਧੀਨ ਵੱਖ-ਵੱਖ ਇਲਾਕਿਆਂ ਵਿਖੇ 4” DIK7 ਵਾਟਰ ਸਪਲਾਈ ਲਾਈਨ ਦਾ ਮੀਸਿੰਗ ਲਿੰਕ ਪਾਉਣ ਸਬੰਧੀ। |  | NA |  | MC Funds / General Quota | GQ | Send To Xen For Work Proposed | 8.48 |  |  |  |  | SDO | [12 empty] | Sh. Karan Kumar JE, Smt. Harpreet Kaur, JE, Sh. Arjun Sikka SDO
|  | O&M | D | D4 | West | 71 | Water Supply | 398066 | P/l of 8” SN-8 Sewer and 4” Water Supply Lines missing link at Sangat Road and Construction of Additional Machineholes in Rupali Street & Raja Ram Park, Ward No.-71 |  | NA |  | MC Funds / General Quota | GQ | file sent to agenda branch for Est. approval for 19-06-2026 | 7.76 |  |  |  |  | SDO | [12 empty] | Sh. Karan Kumar JE, Smt. Harpreet Kaur, JE, Sh. Arjun Sikka SDO
|  | O&M | D | D4 | West | 65 | Water Supply | 402200 | P/I of new tubewell of 25 HP at Ranjodh Park and 12.5 HP Liyar Valley in the area under wd. no.-65(E.Comp. No 398066) |  | NA |  | MC Funds / General Quota | GQ | Agenda Sent to FCC for W.O.Approval on 19-06-2026 | 16.36 |  |  |  |  | SDO | [12 empty] | Sh. Karan Kumar JE, Smt. Harpreet Kaur, JE, Sh. Arjun Sikka SDO
|  | O&M | D | D4 | West | 64 | Water Supply | 406899 | P/l of 25HP Submercible t/w at Radhe Shyam colony and 12.5HP Submercible t/w at X-Block Rishi Nagar ward no-64 |  | NA | 1 | Councillor Quota (CQ) | CQ | EOFFICE sent To XEN | 18.85 |  |  |  |  | SDO | [12 empty] | Sh. Karan Kumar JE, Smt. Harpreet Kaur, JE, Sh. Arjun Sikka SDO
|  | O&M | D | D4 | West | 64 | Sewerage | 406902 | Upgradation of 8" SN-8 Sewerline at X-Block,Rishi Nagar,wd.no-64 | 8" Sewer line 1125 Mtr | NA | 1 | Councillor Quota (CQ) | CQ | EOFFICE sent To XEN | 42.19 |  |  |  |  | XEN | [12 empty] | Sh. Karan Kumar JE, Smt. Harpreet Kaur, JE, Sh. Arjun Sikka SDO
|  | O&M | D | D4 | West | 64 | Sewerage | 406621 | Upgradation of 12" and 8" Sewerline at X-block,Rishi Nagar ,wd.no-64 | 8" Sewer line 2275 Mtr & 12" Sewer line 452 mtr | NA | 1 | Councillor Quota (CQ) | CQ | EOFFICE sent To XEN | 116.37 |  |  |  |  | SE | [12 empty] | Sh. Karan Kumar JE, Smt. Harpreet Kaur, JE, Sh. Arjun Sikka SDO
|  | O&M | D | D4 | West | GEN | Sewerage | 406616 | Estiamate for supply of Water & sewer material as per CSR & Ns rates in SubZoen-D4 |  | NA | 1 | MC Funds / General Quota | GQ | EOFFICE sent To XEN | 9.91 |  |  |  |  | SDO | [12 empty] | Sh. Karan Kumar JE, Smt. Harpreet Kaur, JE, Sh. Arjun Sikka SDO
|  | O&M | D | D4 | West | GEN | Water Supply | 406616 | ਜੋਨ-ਡੀ ਅਧੀਨ ਪੈਂਦੇ 430 ਟਿਊਬਵੈਲਾਂ ਲਈ ਆਟੋਮੈਟਿਕ ਟਾਈਮਰ ਅਤੇ ਸਬੰਧਿਤ ਸਮਾਨ ਦੀ ਖਰੀਦ ਕਰਨ ਸਬਧੀ |  | NA | 1 | MC Funds / General Quota | GQ | EOFFICE sent To XEN | 7.61 |  |  |  |  | SDO | [12 empty] | Sh. Karan Kumar JE, Smt. Harpreet Kaur, JE, Sh. Arjun Sikka SDO
|  | O&M | D | D2 | Atam Nagar | 47 | Water supply |  | Providing and Laying 4"dia DIK-7 water supply line at the area of Kartar Singh Nagar in Ward No-49. | 5710 MTR | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 37.7 | -1.49%% | 239 26-03-2025 | Yes | Yes | XEN | NA | 2024-12-03 | 2024-12-20 | YES | Yes | 1/G/33 11-04-2025 | M/S ESS Elecmech Enterprices, Ludhiana.. | 37.13 | 2025-04-15 | 3 months | 2026-07-14 | 2026-08-05 | Gokaran Kumar JE/Baljeet Singh SDO/Randeep Singh Xen | NA | NA | 95% |  |  | 95%
|  | O&M | D | D2 | Atam Nagar | 47 | Water Supply | 382525 | Prov. and Inst. of 25 HP Deep Straight Bore Tubewell (against failed tubewell) at Ramleela Park of Ambedkar Nagar, Ward No-47 (G.Q) (E Comp No. 382825) |  | NA | 1 | MC Funds / General Quota | C.Q | Just issued | 12.66 |  |  | YES | Yes | SDO | NS |  |  | YES | Yes | 17/g/33 08-07-2026 | M/S Bedi Pump Store, Ludhiana. | 10.01 |  | 3 months |  |  | Harjotpal Singh JE/Baljeet Singh SDO/Randeep Singh Xen | [7 empty] | Just issued
|  | O&M | D | D2 | Atam Nagar | 49&50 | Sewerage | 375918 | Repair of Dat Sewer Line at various area in Ward No. 49 and 50, Sub Zone -D2(G.Q) (E Comp No. 375918) |  | NA | 1 | MC Funds / General Quota | G.Q | 50% | 9.88 |  |  | YES | YES | SDO |  |  |  | YES | Yes | 3/g/33 11-05-2026 | M/s Rajdeep Enterprises, Ludhiana | 6.9 | 2026-05-15 | 2 months | 2026-08-14 | 2026-08-14 | Gokaran kumar JE/Harjotpal Singh JE/Baljeet Singh SDO/Randeep Singh Xen |  |  | 50%
|  | O&M | D | D2 | Atam Nagar | D2 | Water Supply | 385391 | Purchase of material for resolving water and sewerage complaints in Sub Zone-D2.(C.Q) (E Comp No. 385391) |  | NA | 1 | MC Funds / General Quota | C.Q | Just issued | 9.91 |  |  | YES | YES | SDO |  |  |  | YES | Yes | 18/g/33 08-07-2026 | M/S K.B Builder, Ludhiana | 6.75 |  | 2 months |  |  | Kuldeep singh JE/Gokaran kumar JE/Harjotpal Singh JE/Baljeet Singh SDO/Randeep Singh Xen | [7 empty] | Just issued
|  | O&M | D | D2 | Atam Nagar | 51 | Sewerage | 375969 | Repair of Additional Machinehole Chamber & Dat Sewer Line at various area in Ward No. 51, Sub Zone -D2 |  | NA | 1 | MC Funds / General Quota |  | Finacial opened and sent to Worthy mayor for alloted | [5 empty] | SDO | [7 empty] | 6.75 |  |  |  |  | Harjotpal Singh JE/Baljeet Singh SDO/Randeep Singh Xen | [7 empty] | Finacial opened and sent to Worthy mayor for alloted
|  | O&M | D | D2 | Atam Nagar | 51 | Sewerage | 385602 | P/L of 8" sewer line at Street No. 1/3, Dr. Ambedkar Nagar and Pritam Nagar, Ward No. 51.(C.Q) | 373 MTR | NA | 1 | MC Funds / General Quota | C.Q | Estimated Approved and tender will be called | 34.54 |  |  |  |  | XEN | [7 empty] | 34.54 |  |  |  |  | Harjotpal Singh JE/Baljeet Singh SDO/Randeep Singh Xen | [7 empty] | Estimated Approved and tender will be called
|  | O&M | D | D2 | Atam Nagar | 48 | Sewerage | 386004 | P/L of storm sewer line at Block Urban Estate, Phase-1, Dugri, Ward No. 49.(G.Q) | 110 MTR | NA | 1 | MC Funds / General Quota | G.Q | Estimated Approved and tender will be called | 9.16 |  |  |  |  | SDO | [7 empty] | 9.16 |  |  |  |  | Gokaran Kumar JE/Baljeet Singh SDO/Randeep Singh Xen | [7 empty] | Estimated Approved and tender will be called
|  | O&M | D | D2 | Atam Nagar | 50 | Sewerage | 382559 | Repair of machineholes and laying of sewer line (missing link) from Street No. 1 to Street No. 7, Chhoti Jawaddi under Ward No. 50 (M.L.A Q) | 110 MTR | NA | 1 | MC Funds / General Quota | G.Q | Estimated Approved and tender will be called | 39.19 |  |  |  |  | XEN | [7 empty] | 39.19 |  |  |  |  | Harjotpal Singh JE/Baljeet Singh SDO/Randeep Singh Xen | [7 empty] | Estimated Approved and tender will be called
|  | O&M | D | D2 | Atam Nagar | 47 | Water Supply | 375459 | Prov. and Inst. of 40 HP Deep Straight Bore Tubewell (against failed tubewell) at Guru Nanak Park, Ward No-47. |  | NA | 1 | MC Funds / General Quota | C.Q | Finacial opened and sent to signed for alloted | 24.53 |  |  |  |  | SDO | [6 empty] | M/s Bedi Pump Store | 20.62 |  |  |  |  | Harjotpal Singh JE/Baljeet Singh SDO/Randeep Singh Xen | [7 empty] | Finacial opened and sent to signed for alloted
|  | O&M | D | D2 | Atam Nagar | 47 | Water Supply | 375447 | Prov. and Inst. of 40 HP Deep Straight Bore Tubewell (against failed tubewell)at Puri Nursing Home, Ward No-47. |  | NA | 1 | MC Funds / General Quota | C.Q | Finacial opened and sent to signed for alloted | 24.53 |  |  |  |  | SDO | [6 empty] | M/s Bedi Pump Store | 20.62 |  |  |  |  | Harjotpal Singh JE/Baljeet Singh SDO/Randeep Singh Xen | [7 empty] | Finacial opened and sent to signed for alloted
|  | O&M | D | D2 | Atam Nagar | 47 | Water Supply | 375418 | P/I of 25 HP Deep Straight Bore Tubewell at Ambedkar Nagar, Ward No-47. |  | NA | 1 | MC Funds / General Quota | C.Q | Finacial opened and sent to signed for alloted | 12.66 |  |  |  |  | SDO | [6 empty] | M/s Bedi Pump Store | 10.73 |  |  |  |  | Harjotpal Singh JE/Baljeet Singh SDO/Randeep Singh Xen | [7 empty] | Finacial opened and sent to signed for alloted
|  | O&M | D | D2 | Atam Nagar | 52 | Water Supply | 378678 | P/I of 12.5 HP new Tube Well near Manocha Chakki, Azad Nagar, Ward No. 52, Atam Nagar Constituency.(MP Land) |  | NA | 1 | MC Funds / General Quota | MP.LAND | Estimated Approved and tender will be called | 6.75 |  |  |  |  | SDO | [7 empty] | 6.75 |  |  |  |  | Kuldeep Singh JE/Baljeet Singh SDO/Randeep Singh Xen | [7 empty] | Estimated Approved and tender will be called
|  | O&M | D | D2 | Atam Nagar | D2 | Water Supply | 385999 | ਹਲਕਾ ਆਤਮ ਨਗਰ ਅਧੀਨ ਪੈਂਦੇ ਸਬਜੋਨ-ਡੀ2 ਵਿੱਚ ਪੁਰਾਣੇ ਫੇਲ ਹੋਏ ਟਿਊਬਵੈੱਲਾਂ ਦੀ ਜਗ੍ਹਾ ਨਵੇਂ ਟਿਊਬਵੈੱਲ ਲਗਾਉਣ ਸੰਬੰਧੀ। |  | NA | 1 | MC Funds / General Quota | G.Q | estimate should be presented in the next meeting | 90.12 |  |  |  |  | SE | [7 empty] | 90.12 |  |  |  |  | Kuldeep singh JE/Gokaran kumar JE/Harjotpal Singh JE/Baljeet Singh SDO/Randeep Singh Xen | [7 empty] | estimate should be presented in the next meeting
|  | O&M | D | D2 | Atam Nagar | D2 | Water Supply | 390085 | Purchase of motors, starter panels, cables, and timers for various tube wells under Sub-Zone D2. .(G.Q) |  | NA | 1 | MC Funds / General Quota | G.Q | Estimated Approved and tender will be called | 10.73 |  |  |  |  | SDO | [7 empty] | 10.73 |  |  |  |  | Kuldeep singh JE/Gokaran kumar JE/Harjotpal Singh JE/Baljeet Singh SDO/Randeep Singh Xen | [7 empty] | Estimated Approved and tender will be called
|  | O&M | A | A3 | East | 2 | Sewerage/Water supply | 375858 | Providing, Laying /Upgradation of 10" dia., 12" dia. UPVC SN-8 Pipe Sewer Line and 4" dia. DI K7 water supply Line at Ekjot Nagar | S/W : 188 W/S: 539.63 | NA | 1 | MC Funds / General Quota | GQ | For Tender Procedure | 46.85 |  |  |  |  | SE | [12 empty] | Er. Parwinder Singh (JE) Er. Sukhdeep Singh(SDO) Er. Kamal Ram (XEN)
|  | O&M | A | A3 | East | East | Sewerage | 375872 | Construction & Raising of Manhole Chambers and P/F Manhole Cover i.e. EHD, HD, MD sets in various localities of Subzone A3 at East Constituency | - | NA | 1 | MC Funds / General Quota | GQ | For Tender Procedure | 37.68 |  |  |  |  | XEN | [12 empty] | Er. Parwinder Singh (JE) Er. Sukhdeep Singh(SDO) Er. Kamal Ram (XEN)
|  | O&M | A | A3 | East | 6 | Sewerage | 375883 | Providing, Laying of 4" dia. DI-K7 water supply line & 10" dia., 12" dia. UPVC SN-8 pipe Sewer Line at Guru Vihar Hoisery complex Ward No. 6 | S/W : 2128.04 W/S: 353.66 | NA | 1 | MC Funds / General Quota | GQ | For Tender Procedure | 149.65 |  |  |  |  | SE | [12 empty] | Er. Parwinder Singh (JE) Er. Sukhdeep Singh(SDO) Er. Kamal Ram (XEN)
|  | O&M | A | A3 | East | 6 | Water Supply | 375900 | Providing, Laying /Upgradation of 4" dia. DI K7 water supply Line at Kuldeep Nagar Near Trikoni park at East Constituency | W/S: 1525.61 | NA | 1 | Councillor Quota (CQ) | CQ | For Tender Procedure | 44.06 |  |  |  |  | XEN | [12 empty] | Er. Parwinder Singh (JE) Er. Sukhdeep Singh(SDO) Er. Kamal Ram (XEN)
|  | O&M | A | A3 | East | 3 | Water Supply | 376015 | Providing, Laying /Upgradation of 10" dia. UPVC SN-8 Pipe Sewer Line at Sartaj Nagar & New Anandpuri and 4" dia. DI K7 water supply Line at New Inder Vihar, Anandpuri | S/W:382.62 W/S: 518.29 | NA | 1 | Councillor Quota (CQ) | CQ | Currently with Sukhdeep singh For attach the performa as per order no .59 | 47.79 |  |  |  |  | XEN | [12 empty] | Er. Parwinder Singh (JE) Er. Sukhdeep Singh(SDO) Er. Kamal Ram (XEN)
|  | O&M | A | A3 | East | 2 | Tubewell | 380058 | Providing and Installation of 12.5HP Straight Bore Tubewell at Sanyas Nagar & Dhanraj Nagar, Ward no. 02 (ਕੌਂਸਲਰ ਕੋਟਾ) | - | NA | 1 | Councillor Quota (CQ) | CQ | For Tender Procedure | 12.95 |  |  |  |  | SDO | [12 empty] | Er. Parwinder Singh (JE) Er. Sukhdeep Singh(SDO) Er. Kamal Ram (XEN)
|  | O&M | A | A3 | East | 2 | Tubewell | 390088 | Providing & Installation of 25HP Straight Bore Tubewell (3.Nos) at Deep Vihar, Khajur Colony & Inder Vihar at East Constituency | - | NA | 1 | MC Funds / General Quota | GQ | Agenda Has been attached | 44.7 |  |  |  |  | XEN | [12 empty] | Er. Parwinder Singh (JE) Er. Sukhdeep Singh(SDO) Er. Kamal Ram (XEN)
|  | O&M | A | A3 | East | 3,4 | Water Supply | 390884 | Providing, Laying /Upgradation of 10" dia. UPVC SN-8 Sewer line and 6" dia. & 4" dia. DI K7 water supply Line at Guru Gobind Singh Nagar and Vivek Dham at East Constituency | S/W :112.78W/S: 1329.27 | NA | 1 | MC Funds / General Quota | GQ | Currently with Parwinder singh For attach the performa as per order no .59 | 49.83 |  |  |  |  | XEN | [12 empty] | Er. Parwinder Singh (JE) Er. Sukhdeep Singh(SDO) Er. Kamal Ram (XEN)
|  | O&M | A | A3 | East | 4 |  | 392227 | Prov/ Inst. of 2500 ltr. Water Tanker and 25HP Tractor in Ward No - 4 Under MP Lad Scheme | - | NA | 1 | MPLAD | MPLAD |  | 5.6 |  |  |  |  | SDO | [12 empty] | Er. Parwinder Singh (JE) Er. Sukhdeep Singh(SDO) Er. Kamal Ram (XEN)
|  | O&M | A | A3 | East | 2 |  | 392228 | Prov/ Inst. of 2500 ltr. Water Tanker and 25HP Tractor in Ward No - 2 Under MP Lad Scheme | - | NA | 1 | MPLAD | MPLAD |  | 5.6 |  |  |  |  | SDO | [12 empty] | Er. Parwinder Singh (JE) Er. Sukhdeep Singh(SDO) Er. Kamal Ram (XEN)
|  | O&M | A | A3 | East | East | Tubewell | 395039 | Providing and Installation of 12.50HP(02 nos.) , 25HP(04 nos.) against failed (Emergency) Tubewell in East Constituency, Zone A | - | NA | 1 | MC Funds / General Quota | GQ | Currently with Sukhdeep singh For attach the performa as per order no .59 | 64.32 |  |  |  |  | SDO | [12 empty] | Er. Parwinder Singh (JE) Er. Sukhdeep Singh(SDO) Er. Kamal Ram (XEN)
|  | O&M | A | A3 | East | 4 | Water Supply | 399134 | Providing, Laying /Upgradation of 10" dia And 12" dia. UPVC SN-8 supply Line Vishal colony And 4" dia.DIK7 water supply at Grewal Colony and Amrit Vihar at East Constituency. | S/W : 375 W/S: 3100.91 | NA | 1 | MC Funds / General Quota | GQ | Currently with Sukhdeep singh For attach the performa as per order no .59 | 121 |  |  |  |  | SE | [12 empty] | Er. Parwinder Singh (JE) Er. Sukhdeep Singh(SDO) Er. Kamal Ram (XEN)
|  | O&M | A | A3 | East | 5 | Tubewell | 402986 | Providing & Installation of 25HP Straight Bore Tubewell at Shimla Colony, St, No. 02, Near Gurudwara Sahib, Gagandeep Colony, St. No 17 & Golden Enclave, Near Park, Ward No 5 at East Constituency. | - | NA | 1 | MC Funds / General Quota | GQ | Currently with Sukhdeep singh For attach the performa as per order no .59 | 38.11 |  |  |  |  | XEN | [12 empty] | Er. Parwinder Singh (JE) Er. Sukhdeep Singh(SDO) Er. Kamal Ram (XEN)
|  | O&M | A | A3 | East | 2 | Sewer | 408461 | Providing, Laying /Upgradation of 12" dia. UPVC SN-8 Pipe Sewer Line at Koore wala Dump. | S/W : 89.94 | NA | 1 |  |  | Currently with Sukhdeep singh For attach the performa as per order no .59 | [18 empty] | Er. Parwinder Singh (JE) Er. Sukhdeep Singh(SDO) Er. Kamal Ram (XEN)
|  | O&M | A | A3 | East | East | Sewer | 408569 | ਹਲਕਾ ਪੂਰਬੀ ਅਧੀਨ ਪੈਂਦੇ ਇਲਾਕਿਆਂ ਵਿੱਚ ਸੀਵਰ ਲਾਈਨਾਂ ਦੀ ਸੁਪਰ ਸਕਸ਼ਨ ਮਸ਼ੀਨਾਂ ਨਾਲ ਸਫਾਈ ਕਰਵਾਉਣ ਲਈ ਫਰਮ ਨੂੰ ਵਰਕ ਆਰਡਰ ਕਰਨ ਸਬੰਧੀ। | - | NA | 1 | MC Funds / General Quota | GQ | Currently with Sukhdeep singh For attach the performa as per order no .59 | [18 empty] | Er. Parwinder Singh (JE) Er. Sukhdeep Singh(SDO) Er. Kamal Ram (XEN)
|  | O&M | A | A3 | East | 2 | Sewer | 381860 | Providing Laying of 10" dia UPVC SN-8 pipe sewer line at different areas near Bahadurke Road, Ward No 2. | S/W : 193.60 | NA | 1 | Councillor Quota (CQ) | GQ | For Tender Procedure | 20.91 |  |  |  |  | SDO | [12 empty] | Er. Parwinder Singh (JE) Er. Sukhdeep Singh(SDO) Er. Kamal Ram (XEN)
|  | O&M | A | A3 | East | 6 | Water Supply | 375928 | Providing, Laying /Upgradation of 4" dia. DI K7 water supply Line at Kiran Vihar & Kuldeep nagar branch streets at East Constituency | W/S: 1459.15 | NA | 1 | Councillor Quota (CQ) | CQ | For Tender Procedure | 45.6 |  |  |  |  | XEN | [12 empty] | Er. Parwinder Singh (JE) Er. Sukhdeep Singh(SDO) Er. Kamal Ram (XEN)
|  | O&M | C | C4 | Atam Nagar | 40 | WATER | 389654 | Prov./Installation of 25 hp New Submersible T/well at street no. 10-B New Shimlapuri Chimney road. Ward no.40 |  | NA | 1 | MC Funds / General Quota | MCL | Awarded | 12.7 | 18.75% | 3742/15.06.2026 | Yes | Yes |  | N/A | 01.04.2026 | 20.04.2026 | Yes | Yes | 1273/G/33 Dated 08.07.2026 | JCS Electric works | 10.32 |  | - |  |  | Sunpreet Singh JE- Amandeep Singh Grewal SDO Manpreet Singh XEN | NO |  |  |  |  | Not Started |  | Work will start after monsoon
|  | O&M | C | C4 | Atam Nagar | 40 | WATER | 389510 | Prov./Installation of 25 hp New Submersible T/well at street no. 7 Shimlapuri near Sajan Bakery. Ward no.40 |  | NA | 1 | MC Funds / General Quota | MCL | Awarded | 12.7 | 21.8% | 3750/15.06.2026 | Yes | Yes |  | N/A | 01.04.2026 | 20.04.2026 | Yes | Yes | 1274/G/33 Dated 08.07.2026 | ESS ELECMECH ENTERPRISES | 9.93 |  | - |  |  | Sunpreet Singh JE- Amandeep Singh Grewal SDO Manpreet Singh XEN | NO |  |  |  |  | Not Started |  | Work will start after monsoon
|  | O&M | C | C4 | Atam Nagar | 40 | WATER | 389543 | Prov./Installation of 25 hp New Submersible T/well at street no. 1 Shimlapuri Ward no.40 |  | NA | 1 | MC Funds / General Quota | MCL | Awarded | 12.7 | 21.8% | 3751/15.06.2026 | Yes | Yes |  | N/A | 01.04.2026 | 20.04.2026 | Yes | Yes | 1275/G/33 Dated 08.07.2026 | ESS ELECMECH ENTERPRISES | 9.93 |  | - |  |  | Sunpreet Singh JE- Amandeep Singh Grewal SDO Manpreet Singh XEN | NO |  |  |  |  | Not Started |  | Work will start after monsoon
|  | O&M | C | C4 | Atam Nagar | 42 | Sewerage | N/A | Upgradation of 18" id dia RCC NP3 HDPE lining pipe sewer line at Daba road from Gill road to Labour chowk ward no. 42 (Atam nagar constituency) |  | NA | 1 | MC Funds / General Quota | MCL | Estimate Approved | 79.97/- |  |  |  |  | SE | N/A | [11 empty] | Sunpreet Singh JE- Amandeep Singh Grewal SDO Manpreet Singh XEN | NO | [6 empty] | Estimate Approved
|  | O&M | C | C4 | Atam Nagar | 46 | WATER | 394689 | Prov./Installation of 25 hp Submersible t/well at Janta nagar street no. 14 ward no. 46 |  | NA | 1 | MC Funds / General Quota | MCL | Reso. No. 3845/15.06.2026 Put up Next meeting | 12.7 |  | 3845/15.06.2026 |  |  | SDO | N/A | [11 empty] | Sunpreet Singh JE- Amandeep Singh Grewal SDO Manpreet Singh XEN | NO | [6 empty] | Put up Next meeting
|  | O&M | C | c-1 | Atam Nagar | 31 | WATER | N/A | Prov./Installation of 12.5 hp Deep bore t/well at Parbhat nagar street no. 4-A ward no. 31 (MP LAD) |  | NA | 1 | MPLAD Funds | MP Lad | Reso. No. 3606/15.06.2026 Tender Calling | 6.75 |  | 3306/15.06.2026 |  |  | SDO | N/A | [11 empty] | Iqbal Singh JE - Manpreet Singh XEN | NO | [6 empty] | Tender Calling
|  | O&M | C | c-1 | Atam Nagar | 41 | WATER | 381346 | Purchase of water tanker capacity 3000 litre fro ward no. 41 |  | NA | 1 | MC Funds / General Quota | MCL | Reso no. 3604/15.06.2026 (Tender Recall) | 2.11 |  | 3304/15.06.2026 |  |  | JE | N/A | [11 empty] | Sunpreet Singh JE- Amandeep Singh Grewal SDO Manpreet Singh XEN | NO | [6 empty] | (Tender Recall)
|  | O&M | C | C4 | Atam Nagar | 46 | WATER | N/A | Pro./Installation of 3000 litre water tanker in ward no. 46 (MP LAD) |  | NA | 1 | MPLAD Funds | MP Lad | Reso no. 3592/15.06.2026 (Tender Calling) | 2.11 |  | 3392/15.06.2026 |  |  | JE | N/A | [11 empty] | Sunpreet Singh JE- Amandeep Singh Grewal SDO Manpreet Singh XEN | NO | [6 empty] | (Tender Calling)
|  | O&M | C | C-2 | South | 38 | WATER | 382974/16.04.2026 | Prov./Installation of 25 hp New Submersible T/well at Isher Nagar near Bilkhu Fectory.ward no. 38 (CQ) |  | NA | 1 | COUNCILLOR QUOTA | MCL | Proposed | 12.7 |  |  |  |  | SDO | N/A | [11 empty] | Dilpreet Singh JE Harbir Singh SDO Manpreeet Singh XEN | NO | [6 empty] | Technical Bid Opened
|  | O&M | C | C-2 | South | 38 | WATER | 382985/16.04.2026 | Prov./Installation of 25 hp New Submersible T/well at Moh. Begoana. ward no. 38 (CQ) |  | NA | 1 | COUNCILLOR QUOTA | CQ | Proposed | 12.7 |  |  |  |  | SDO | N/A | [11 empty] | Dilpreet Singh JE Harbir Singh SDO Manpreeet Singh XEN | NO | [6 empty] | Technical Bid Opened
|  | O&M | C | C-2 | South | 39 | WATER | 397355/02.06.2026 | Prov./Installation of 25 hp New Submersible T/well at st.no.1 Harkrishan Nagar ward no. 39 (GQ) |  | NA | 1 | MC Funds / General Quota | MCL | Proposed | 12.7 |  |  |  |  | SDO | N/A | [11 empty] | Dilpreet Singh JE Harbir Singh SDO Manpreeet Singh XEN | NO | [6 empty] | File Sent for Estimate Approval
|  | O&M | C | C-2 | South | 35 | WATER | 399036/05.06.2026 | Prov./Installation of 12.5 hp New straight bore T/well at Maan Colony ward no. 35 (CQ) |  | NA | 1 | COUNCILLOR QUOTA | CQ | Proposed | 6.75 |  |  |  |  | SDO | N/A | [11 empty] | Sunpreet Singh JE Harbir Singh SDO Manpreeet Singh XEN | NO | [6 empty] | File Sent for Estimate Approval
|  | O&M | C | C-2 | South | 35 | WATER | 404503/30.06.2026 | Prov./Installation of 12.5 hp New straight bore T/well at Fateh Singh Nagar st no 5 ward no. 35 (CQ) |  | NA | 1 | COUNCILLOR QUOTA | CQ | Proposed | 6.75 |  |  |  |  | SDO | N/A | [11 empty] | Sunpreet Singh JE Harbir Singh SDO Manpreeet Singh XEN | NO | [6 empty] | File Sent for Estimate Approval
|  | O&M | C | C-2 | South | 38 | WATER | 402798/17.06.2026 | Prov./Layiing of 4" id DIK-7 water supply line and 10" id UPVC sewer line at Dalwara Colony ward no. 38 (CQ) |  | NA | 1 | COUNCILLOR QUOTA | CQ | Proposed | 65.75 |  |  |  |  | SE | N/A | [11 empty] | Dilpreet Singh JE Harbir Singh SDO Manpreeet Singh XEN | NO | [6 empty] | File Sent for Estimate Approval
|  | O&M | C | Z-C | South | C | MTC | 408882/9.07.2026 | No?eNo Bzpo PB FF 5386 ns/ PB 10 FH 3078 d/ ;ko/ NkfJo pdbtkT[D ns/ ;oft; eotkT[D ;pzXh. |  | NA | 1 | Gen. | MCL | Proposed | [5 empty] | SDO | N/A | [12 empty] | NO | [6 empty] | File Sent for Estimate Approval
|  | O&M | C | C-1 | South | 33 | WATER | N/A | Prov./Installation of 25 hp new Submersible T/well at Prem nagar street no. 2 ward no.33 MC fund |  | NA | 1 | MC Funds / General Quota | MCL | Reso. No. 3796/15.06.2026 (Tender Calling) | 12.7 |  | 3796/15.06.2026 |  |  | SDO | N/A | [11 empty] | Avneet Singh JE JAgroop Singh SDO Manpreet Singh XEN | NO | [6 empty] | Reso. No. 3796/15.06.2026 (Tender Calling)
|  | O&M | C | C-3 | South | 34 | WATER | N/A | Prov./Installation of 25 hp new Submersible T/well at Harkrishan Nagar ward no.34 MC fund |  | NA | 1 | MC Funds / General Quota | MCL | Reso. No. 3777/15.06.2026 (Tender Calling) | 12.7 |  | 3777/15.06.2026 |  |  | SDO | N/A | [11 empty] | Avneet Singh JE JAgroop Singh SDO Manpreet Singh XEN | NO | [6 empty] | Reso. No. 3777/15.06.2026 (Tender Calling)
|  | O&M | C | South | South | SOUTH | WATER | 388874 | Prov./Installation of 8 No 25 hp & 2 No. 12.5 Hp Emergency Submersible T/wells (AFT) at South Constituency |  | NA | 1 | MC Funds / General Quota | MCL | Reso. No. 3959/15.06.2026 (Put Up Next Meeting) | 115.12 |  | 3959/15.06.2026 |  |  | SE | N/A | [11 empty] | Avneet Singh JE JAgroop Singh SDO Manpreet Singh XEN | NO | [6 empty] | Reso. No. 3959/15.06.2026 (Put Up Next Meeting)
|  | O&M | C | South | South | C-1 |  | N/A | Purchase of new pipes for Jetting machines in Zone-C |  | NA | 1 | MC Funds / General Quota | MCL | Approved from F&CC for work order | 9.91 |  |  |  |  | SDO | N/A | [11 empty] | Avneet Singh JE JAgroop Singh SDO Manpreet Singh XEN | NO | [6 empty] | Approved from F&CC for work order
|  | O&M | C | C | South | C |  | N/A | Intergrated Rain water Run off management system at Dholewal chowk to Vishkarma chowk manju cinema side Zone-C |  | NA | 1 | MC Funds / General Quota | MCL | Tender Calling | 129.78 |  |  |  |  | SE | N/A | [11 empty] | Avneet Singh JE JAgroop Singh SDO Manpreet Singh XEN | NO | [6 empty] | Tender Calling
|  | O&M | C | C | South | C |  | N/A | Intergrated Rain water Run off management system at Gurudwara Pheruman Sahib, Millerganj Dholewal Zone-C |  | NA | 1 | MC Funds / General Quota | MCL | Tender Calling | 149.74 |  |  |  |  | SE | N/A | [11 empty] | Avneet Singh JE JAgroop Singh SDO Manpreet Singh XEN | NO | [6 empty] | Tender Calling
|  | O&M | C | C-4 | South | 43 | WATER | 394692 | Prov./Installation of 25 hp new Submersible T/well at street no.8 Kabir Nagar ward no.43 |  | NA | 1 | MC Funds / General Quota | MCL | Reso. No. 3949/15.06.2026 (Put Up Next Meeting) | 12.7 |  | 3949/15.06.2026 |  |  | SDO | N/A | [11 empty] | Sunpreet Singh JE- Amandeep Singh Grewal SDO Manpreet Singh XEN | NO | [6 empty] | Reso. No. 3949/15.06.2026 (Put Up Next Meeting)
|  | O&M | C | C-4 | South | 43 | WATER | 394695 | Prov./Installation of 25 hp new Submersible T/well at street no.10 Guru Angad Dev Colony ward no.43 |  | NA | 1 | MC Funds / General Quota | MCL | Reso. No. 3948/15.06.2026 (Put Up Next Meeting) | 12.7 |  | 3948/15.06.2026 |  |  | SDO | N/A | [11 empty] | Sunpreet Singh JE- Amandeep Singh Grewal SDO Manpreet Singh XEN | NO | [6 empty] | Reso. No. 3948/15.06.2026 (Put Up Next Meeting)
|  | O&M | C | C | South | 33 | WATER | N/A | Upgradation of 4" id DIK-7 water supply line & 10" id UPVC sewer line at Pritam Colony 33' road ward no. 33 (MLA Quota) |  | NA | 1 | MLA QUOTA | MLA QUOTA | Estimate Pending for Approval | 106 |  |  |  |  | SE | N/A | [11 empty] | Avneet Singh JE JAgroop Singh SDO Manpreet Singh XEN | NO | [6 empty] | Estimate Pending for Approval
|  | O&M | C | C-3 | South | 33 | Sewerage | N/A | Prov./Laying 24" RCC Np3 HDPE sewer line from Jasvir Building Material store to Eastman Chowk Sua road ward no. 33 |  | NA | 1 | MC Funds / General Quota | MCL | Estimate Pending for Work order Approval | 99.5 |  |  |  |  | SE | N/A | [11 empty] | Avneet Singh JE JAgroop Singh SDO Manpreet Singh XEN | NO | [6 empty] | Estimate Pending for Work order Approval
|  | O&M | C | C-3 | South | 33 | WATER | N/A | Prov./Installation of 25 hp new Submersible T/well at Surjit Nagar ward no.33 |  | NA | 1 | MC Funds / General Quota | MCL | Estimate Pending for Approval | 12.7 |  |  |  |  | SDO | N/A | [11 empty] | Avneet Singh JE JAgroop Singh SDO Manpreet Singh XEN | NO | [6 empty] | Estimate Pending for Approval
|  | O&M | C | C-3 | South | 35 | WATER | N/A | Prov./Installation of 12.5 hp New straight bore T/well at st no 10 Maha Singh Nagar ward no. 35 |  | NA | 1 | MC Funds / General Quota | MCL | Estimate Pending for Approval | 6.75 |  |  |  |  | SDO | N/A | [11 empty] | Sunpreet Singh JE Harbir Singh SDO Manpreeet Singh XEN | NO | [6 empty] | Estimate Pending for Approval
|  | O&M | C | C-3 | South | 35 | WATER | N/A | Prov./Installation of 12.5 hp New straight bore T/well at st no 6 Maha Singh Nagar ward no. 35 |  | NA | 1 | MC Funds / General Quota | MCL | Estimate Pending for Approval | 6.75 |  |  |  |  | SDO | N/A | [11 empty] | Sunpreet Singh JE Harbir Singh SDO Manpreeet Singh XEN | NO | [6 empty] | Estimate Pending for Approval
|  | O&M | C | C-2 | South | 35 | water | N/A | Prov./Installation of 12.5 hp Submersible T/well at Village Daba near Gurudwara Guru Ravidas ji. (AFT 12.5 hp T/well)ward no. 35 |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 6.03 | 18.06% | 2417/05.01.2026 | Yes | Yes | SDO | N/A |  |  | Yes | Yes | 1271/G/33 Dated 08.07.2026 | Bedi pump store | 4.91 |  |  |  |  | Sunpreet Singh JE Harbir Singh SDO Manpreet Singh XEN | NO | N/A | 50% |  |  | Work in Progress |  | Work in Progress
|  | O&M | C | C4 | South | 43 | water | N/A | Prov./Installation of 25 hp Submersible T/well at street no. 6 New Amar nagar (AFT 12.5 hp T/well Amar nagar street no 6-A) ward no.43 |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 12.51 | 21.22% | 2416/05.01.2026 | Yes | Yes | SDO | N/A |  |  | Yes | Yes | 1272/G/33 Dated 08.07.2026 | Amarpal Singh Bawa | 9.85 |  |  |  |  | Sunpreet JE Amandeep Singh Grewal SDO Manpreet Singh XEN | NO | N/A | 50% |  |  | Work in Progress |  | Work in Progress
|  | O&M | C | C-2 | South | 37 | water | N/A | Prov./Installation of 25 hp New Submersible T/well at Basant nagar street no.7 ward no. 37 |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 12.7 | 16.71% | 2536/05.2.2026 | Yes | Yes | SDO | N/A |  |  | Yes | Yes | 1279/G/33 Dated 22.07.2026 | Bedi pump Store | 10.58 |  |  |  |  | Dilpreet Singh JE Harbir Singh SDO Manpreet Singh XEN | NO | N/A |  |  |  | Work in Progress |  | Work in Progress
|  | O&M | D | D1 | North | 93 | SEWERAGE |  | Rehabiletation of Sewer Line at Kesari Enclave in Ward No.93. (G.Q) | 1175 | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 49.88 | -26.1% | 2628 11-02-2026 | Yes | Yes | XEN | NA | 2025-04-30 | 2025-06-27 | Yes | yes | 109/g/33 20-02-2026 | M/s Sushil Kumar Contractor | 36.86 | 2026-03-01 | 3 months | 2026-05-19 | 2026-07-30 | Sh. Gurdeep Singh JE, Sh. Anshul Garcha SDO, Sh. RAndeep SIngh XEN | NA | NA | 95%
|  | O&M | D | D1 | North | 93 | WATER Supply &SEWERAGE |  | Rehablition of water supply & Sewer line at Smart City in Ward no-93 | sewer line 1220 water 1160 | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 72.64 | -24% | 3206 25-02-2026 | Yes | Yes | SE | NA | 2025-04-30 | 2025-06-27 | Yes | yes | 124/G/33 10-03-26 | M/S Apex Developers | 55.21 | 2026-03-20 | 3 months | 2026-06-09 |  | Sh. Gurdeep Singh JE, Sh. Anshul Garcha SDO, Sh. RAndeep SIngh XEN | NA | NA | 98%
|  | O&M | D | D1 | North | 66 | TUBEWELL |  | 12.5 HP T/w in New Deep Nagar ward No. 66.(M.P Land) | NA | NA | 1 | MP lLand | MP lLand | Awarded | 6.75 | -19.1% | 3784 15-06-2026 | Yes | Yes | SDO | NA | 2025-04-11 | 2025-04-28 | Yes | yes | 19/G/33 08-07-2026 | M/s JCS Electric Works | 5.46 | 2026-07-15 | 2 months | 2026-09-07 |  | Sh. Gurdeep Singh JE, Sh. Anshul Garcha SDO, Sh. RAndeep SIngh XEN | NA | NA |  |  |  | Not Started
|  | O&M | D | D1 | North | 68 | WATER Supply &SEWERAGE | 385798 | Rehabilitation/Laying of Water Supply Line & Sewer Line in Civil City Road ward No. 68.(G.Q) (E Comp No. 385798) |  | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 36.72 | -25% | 3787,15-06-2026 | Yes | Yes | XEN | NA | 2025-04-11 | 2025-04-28 | Yes | yes | 20/G/33,08-07-2026 | M/s Sushil Kumar Contractor | 27.54 | 2026-07-15 | 2 months | 2026-09-07 |  | Sh. Gurdeep Singh JE, Sh. Anshul Garcha SDO, Sh. RAndeep SIngh XEN | NA | NA
|  | O&M | D | D1 | North | 93 | WATER Supply | 386408 | Rough Cost Estimate Prov. Laying of Water Pipe Line in Jagat Nagar & Tarsem Nagar in Ward No. 93..(C.Q) (E Comp No. 386408) |  | NA | 1 | COUNCILLOR QUOTA | CQ | Awarded | 49.95 |  |  | Yes | Yes | XEN | NA |  |  | Yes | yes | 21/g/33 08-07-2026 | M/S Sushil Kumar Contractor, Ludhiana | 41.9 | Not started | 3 months |  |  | Sh. Gurdeep Singh JE, Sh. Anshul Garcha SDO, Sh. RAndeep SIngh XEN | NA | NA | [5 empty] | Workorder Just Issued
|  | O&M | D | D1 | North | 70 | WATER Supply | 376707 | Providing & Installation of 25 HP submersible T/Well at Deep Nagar Champa Street in Ward No. 70 (MC Funds). (G.Q) (E Comp No. 376707) |  | NA | 1 | MC Funds / General Quota | G.Q | Awarded | 12.49 |  |  | Yes | Yes | SDO | NA |  |  | Yes | yes | 22/g/33 08-07-2026 | M/S JCS Electric Works, Ludhiana | 10.09 | - | 3 months |  |  | Sh. Gurdeep Singh JE, Sh. Anshul Garcha SDO, Sh. RAndeep SIngh XEN | NA | NA
|  | O&M | D | D1 | North | 70 | SEWERAGE |  | Rehablitation/Laying of Sewer Line at Upkar Nagar ward no.70 (General Quota) |  | NA | 1 | MC Funds / General Quota | G.Q | F.B opened | 61.53 |  |  |  |  | SE | [6 empty] | S K Contractor | [5 empty] | Sh. Gurdeep Singh JE Sh. ANshul Garcha SDO sh. Randeep SIngh Xen.
|  | O&M | D | D1 | North | 91 | WATER Supply | 374742 | upgrading kundan puri moti vala disposal ward no 91 |  | NA | 1 | COUNCILLOR QUOTA | CQ | Estimate approved but before deduction disposal | 27.23 |  |  |  |  | XEN | [12 empty] | Sh. Gurdeep Singh JE Sh. ANshul Garcha SDO sh. Randeep SIngh Xen.
|  | O&M | D | D1 | North | 91 | SEWERAGE | 372368 | Construction of new additional manhole chambers in various areas of Ward No. 91 and laying of new sewer and water supply lines in New Kundanpuri .(C.Q) |  | NA | 1 | COUNCILLOR QUOTA | CQ | Estimated Approved and tender will be called | 23.28 |  |  |  |  | SDO | [12 empty] | Sh. Gurdeep Singh JE Sh. ANshul Garcha SDO sh. Randeep SIngh Xen.
|  | O&M | D | D1 | North | 67 | SEWERAGE | 372073 | missing sewage chamber and damaged chamber at ward 67 |  | NA | 1 | MC Funds / General Quota | G.Q | F.B opened and sent to E Office From JE | 7.07 |  |  |  |  | SDO | [6 empty] | Sushil Kumar Contractor | [5 empty] | Sh. Gurdeep Singh JE Sh. ANshul Garcha SDO sh. Randeep SIngh Xen.
|  | O&M | D | D1 | North | 68 | SEWERAGE | 383507 | P/L of storm sewer line and construction of sump near Line Puli, New Chander Nagar in Ward No. 68 (General Quota) |  | NA | 1 | MC Funds / General Quota | G.Q | Estimated Approved and tender will be called | 8.03 |  |  |  |  | SDO | [12 empty] | Sh. Gurdeep Singh JE Sh. ANshul Garcha SDO sh. Randeep SIngh Xen.
|  | O&M | D | D1 | North | D1 | WATER Supply | 397318 | ਬਰਸਾਤਾਂ ਦੇ ਮੌਸਮ ਨੂੰ ਮੁੱਖ ਰੱਖਦੇ ਹੋਏ ਸਬ-ਜ਼ੋਨ-ਡੀ/1 ਦੇ ਇੰਜਣਾਂ ਦੀ ਸਰਵਿਸ ਕਰਵਾਉਣ ਅਤੇ ਬਰਸਾਤਾਂ ਦੇ ਮੌਸਮ ਤੋਂ ਪਹਿਲਾਂ ਪ੍ਰਬੰਧਾਂ ਸਬੰਧੀ ।(E.Comp. No 397318) |  | NA | 1 | MC Funds / General Quota | G.Q | estimate should be presented in the next meeting | 10.57 |  |  |  |  | SDO | [12 empty] | Sh. Gurdeep Singh JE Sh. ANshul Garcha SDO sh. Randeep SIngh Xen.
|  | O&M | D | D1 | North | 93 | WATER Supply | 372470 | Purchase of 5 Tankers in Ward No 93. .(MP Land) |  | NA | 1 | MP lLand | MP lLand | Estimated Approved and tender will be called | 10.55 |  |  |  |  | SDO | [12 empty] | Sh. Gurdeep Singh JE Sh. ANshul Garcha SDO sh. Randeep SIngh Xen.
|  | O&M | D | D1 | North | - | WATER Supply | 372024 | rehabiliation/lay of W/S line in Bajwa Colony, Gurdev Nagar, and PWD colony |  | NA | 1 | MC Funds / General Quota | G.Q | file back to Xen for Map report | 23.71 |  |  |  |  | SDO | [12 empty] | Sh. Gurdeep Singh JE Sh. ANshul Garcha SDO sh. Randeep SIngh Xen.
|  | O&M | D | D1 | North | - | WATER Supply | 401522 | Annual Rate Contract of P/I of 2 no of 12.5 HP and 3. no of 25 HP and 1 no of 40 HP T/well (against failed tubewell ) for sub-zone -d1. |  | NA | 1 | MC Funds / General Quota | G.Q | account branch check for fund in E Office | 76.51 |  |  |  |  | SE | [12 empty] | Sh. Gurdeep Singh JE Sh. ANshul Garcha SDO sh. Randeep SIngh Xen.
|  | O&M | B | B2 | Sahnewal | B2 | Tubewell | __ | Providing & Installing of 40 HP Rig Bore Tubewell at Mundian Village Ward No.27 (Constituency Sahnewal). | NA |  | 1 | MC Funds / General Quota | GQ | Awarded | 24 | 9.99% | 286 26-03-2025 | YES | YES | XEN | N/A | 2024-11-14 | 2024-12-02 | Yes | Yes | 17/G33 11-04-2025 | CNC Precision Engineering | 21.6 |  | 3 |  |  | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN |  |  | 70
|  | O&M | B | B2 | Sahnewal | B2 | Tubewell | __ | Providing & Installing of 40 HP Rig Bore Tubewell at Phase-VIII Focal Point Near Punjab Kesari Press Ward No.27 (Against Failed Tubewell) | NA |  | 1 | MC Funds / General Quota | GQ | Awarded | 23.97 | 10.49% | 283 26-03-2025 | YES | YES | XEN | N/A | 2024-12-03 | 2024-12-19 | Yes | Yes | 18/G33 11-04-2025 | Bedi Pump Store | 21.46 |  | 3 |  |  | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN |  |  | 95
|  | O&M | B | B2 | Sahnewal | B2 | Water Supply | __ | Water Contamination For 4",6",8" & 12" dia DIK-7 water supply at Different Areas Of Sub Zone-B2. | 3000 |  | 1 | MC Funds / General Quota | GQ | Awarded | 76.11 | 3.33% | 285 26-03-2025 | YES | YES | XEN | N/A | 2024-11-14 | 2024-12-02 | Yes | Yes | 12/G33 11-04-2025 | CNC Precision Engineering | 73.58 |  | 4 |  |  | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN |  |  | 70
|  | O&M | B | B2 | Sahnewal | B2 | Tubewell | __ | Providing & Installing of 40 HP deep straight bore tubewell at sec-38 park BH H no.3180 in ward no.21 | NA |  | 1 | MC Funds / General Quota | GQ | Awarded | 24.48 | 14.48% | Approved in anticipation of F&CC your rates vide order dated 30-04-2026 | YES | YES | XEN | N/A | 2025-11-07 | 2025-12-02 | Yes | Yes | 148/G33 07-05-2026 | A.B Construction | 20.93 |  | 3 |  |  | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN
|  | O&M | B | B2 | Sahnewal | B2 | Sewer | __ | Upgradation of Sewer line in Ward No. 28, Sub Zone-B2. | 1541.46 |  | 1 |  | GQ | Awarded | 97.1 | 21.33% | 174 26-03-2025 | YES | YES | XEN | N/A | 2024-11-14 | 2024-12-02 | Yes | Yes | 09/G33 11-04-2025 | CNC Precision Engineering | 76.39 |  | 4 |  |  | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN |  |  | 100
|  | O&M | B | B2 | Sahnewal | B2 | Sewerage | __ | Upgradation for Prov/Laying of 18" & 16" RCC NP3 Sewer line at Devgan Kanda to Near Wine Shop (Gulabi Vedha) W. No. 28. | 763.62 |  | 1 |  | GQ | Awarded | 66.98 | 23.2% | 281 26-03-2025 | YES | YES | XEN | N/A | 2024-03-07 | 2024-03-26 | Yes | Yes | 13/G33 11-04-2025 | Bharat Bhushan | 51.44 |  | 4 |  |  | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN |  |  | 100
|  | O&M | B | B2 | Sahnewal | 23 | Tubewell | 400259 | Prov./Inst of (200 mtr.) 25HP Deep straight Bore Tubewell at Adarsh Colony in ward no. 23 | NA |  | 1 | MC Funds / General Quota | GQ | Proposed | 12.71 | __ | __ | YES | YES | XEN | N/A | 2026-04-01 | 2026-04-13 | [9 empty] | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN
|  | O&M | B | B2 | Sahnewal | 23 | Tubewell | 400107 | Prov./Inst of (200 mtr.) 25HP Deep straight Bore Tubewell at Ramandeep Colony in ward no. 23 | NA |  | 1 | MC Funds / General Quota | GQ | Proposed | 12.71 | __ | __ | YES | YES | XEN | N/A | 2026-04-01 | 2026-04-13 | [9 empty] | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN
|  | O&M | B | B2 | Sahnewal | 22 | Tubewell | 373901 | Rough Cost Estimate Providing & Installing of 25 HP Deep Straight Bore Tubewell At Dream park In Ward No.22 (Against Failed Tubewelt).GQ). | NA |  | 1 | MC Funds / General Quota | GQ | Proposed | 12.71 | __ | __ | YES | YES | XEN | N/A | 2026-05-08 | 2026-06-01 | [9 empty] | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN
|  | O&M | B | B2 | Sahnewal | 22 | Tubewell | 373884 | Rough Cost Estimate for Providing & Installing of 40 HP Rig Bore Tubewell At Rasila Nagar/ Gobind Colony In Ward No.22 (Against Failed Tubewell 40HP). (GQ). | NA |  | 1 | MC Funds / General Quota | GQ | Proposed | 17.77 | __ | __ | YES | YES | XEN | N/A | [11 empty] | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | [7 empty] | File sent for Estimate Approval.
|  | O&M | B | B2 | Sahnewal | 25 | Tubewell | 384555 | Rough Cost Estimate for prov./inst of 40HP Rig Bore Tubewell at D-62 Phase-V focal point. (Against Failed Tubewell). | NA |  | 1 | Councillor Quota (CQ) | CQ | Proposed | 18.35 | __ | __ | YES | YES | XEN | N/A | [11 empty] | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | [7 empty] | File sent for Estimate Approval.
|  | O&M | B | B2 | Sahnewal | 23 | Water supply | 378091 | ਵਾਰਡ ਨੰ.23 ਅਧੀਨ ਪੈਂਦੇ ਇਲਾਕੇ ਰਾਮ ਨਗਰ ਗਲੀ ਨੰ.01 ਅਤੇ 02 ਵਿੱਚ ਪਾਣੀ ਦੀ ਲਾਈਨ ਪਾਉਣ ਸਬੰਧੀ। | 600 |  | 1 | Councillor Quota (CQ) | CQ | Proposed | 13.33 | __ | __ | YES | YES | XEN | N/A | 2026-05-08 | 2026-06-01 | [9 empty] | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN
|  | O&M | B | B2 | Sahnewal | 24 | Tubewell | 391782 | Rough cost estimate for prov./inst. of (200mtr.) 25HP Deep Straight bore tubewell at opp House no.614, G.K Estate chd road. ward no.24 (G.Q). | NA |  | 1 | MC Funds / General Quota | GQ | Proposed | 12.71 | __ | __ | YES | YES | XEN | N/A | [11 empty] | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | [7 empty] | File sent for Estimate Approval.
|  | O&M | B | B2 | Sahnewal | 21 | Water supply | 374079 | ਵਾਰਡ ਨੰ.21 ਅਧੀਨ ਪੈਂਦੇ ਇਲਾਕੇ ਵਿੱਚ ਪੀਣ ਵਾਲੇ ਪਾਣੀ ਦੀਆਂ ਲਾਈਨਾਂ ਅਪਗ੍ਰੇਡ ਕਰਨ ਸਬੰਧੀ। (CQ) | 395 |  | 1 | Councillor Quota (CQ) | CQ | Proposed | 10.48 | __ | __ | YES | YES | XEN | N/A | [11 empty] | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | [7 empty] | File sent for Estimate Approval.
|  | O&M | B | B2 | Sahnewal | 25 | Water supply | 411838 | ਸਬਜੋਨ-ਬੀ2 ਅਧੀਨ ਪੈਂਦੇ ਵਾਰਡ ਨੰ.25 ਦੇ ਇਲਾਕੇ ਬਲਾਲਾ ਕਲੋਨੀ, ਇਸ਼ਵਰ ਕਲੋਨੀ ਅਤੇ ਹਾਥੀ ਕਲੋਨੀ ਵਿੱਚ ਪਾਣੀ ਦੀ ਲਾਈਨ ਪਾਉਣ/ਅਪਗ੍ਰੇਡ ਕਰਨ ਸਬੰਧੀ। | 488 |  | 1 | MC Funds / General Quota | GQ | Proposed | 13.26 | __ | __ | YES | YES | XEN | N/A | [11 empty] | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | [7 empty] | File sent for Estimate Approval.
|  | O&M | B | B2 | Sahnewal | 21 | Sewerage | 373918 | ਸਬਜੋਨ-ਬੀ2 ਅਧੀਨ ਪੈਂਦੇ ਇਲਾਕੇ ਪੀ.ਐਸ.ਆਈ.ਈ.ਸੀ ਰਿਹਾਇਸ਼ੀ ਕਲੋਨੀ, ਜੀਵਨ ਨਗਰ ਵਾਰਡ ਨੰ.21 ਵਿਖੇ ਪਾਣੀ ਅਤੇ ਸੀਵਰੇਜ ਦੀ ਲਾਈਨ ਪਾਉਣ ਸਬੰपी। | 613.28 |  | 1 | Councillor Quota (CQ) | CQ | Proposed | 19.02 | __ | __ | YES | YES | XEN | N/A | 2026-05-08 | 2026-06-01 | [9 empty] | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN
|  | O&M | B | B2 | Sahnewal | 23 | Sewerage | 374038 | ਵਾਰਡ ਨੰ.23 ਵਿੱਚ ਸੀਵਰੇਜ ਦੀਆਂ ਲਾਈਨਾਂ ਅਪਗ੍ਰੇਡ ਕਰਨ ਸਬੰਧੀ। | 600.46 |  | 1 | Councillor Quota (CQ) | CQ | Proposed | 27.94 | __ | __ | YES | YES | XEN | N/A | [11 empty] | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | [7 empty] | File sent for Estimate Approval.
|  | O&M | B | B2 | Sahnewal | 25 | Sewerage | 378046 | Ugradation of 16" HDPE RCC NP-3 Sewer Line in front of D-210 to D-228, Phase-VII, Focal Point Ludhiana in ward no.25. | 736.4 |  | 1 | MC Funds / General Quota | GQ | Proposed | 55.95 | __ | __ | YES | YES | XEN | N/A | 2026-06-09 | 2026-06-25 | [9 empty] | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN
|  | O&M | B | B2 | Sahnewal | 21,22,23,24 & 25 | Sewerage | 389830 | Purchase Of Manhole Sets For Various Wards In O & M Cell, Subzone- B2 | NA |  | 1 | MC Funds / General Quota | GQ | Proposed | 7.41 | __ | __ | YES | YES | XEN | N/A | 2026-06-09 | 2026-06-25 | [9 empty] | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN
|  | O&M | B | B2 | Sahnewal | 23 | Sewerage | 378367 | ਵਾਰਡ ਨੰ.23 ਅਧੀਨ ਪੈਂਦੇ ਇਲਾਕਿਆਂ ਵਿੱਚ ਹੋਰ ਅਡੀਸ਼ਨਲ ਮੇਨਹੋਲ ਬਣਾਉਣ ਅਤੇ ਪਹਿਲਾ ਬਣੇ ਮੇਨਹੋਲਾਂ ਨੂੰ ਰੋਡ ਲੇਵਲ ਤੱਕ ਉੱਚਾ ਚੁੱਕਣ ਸਬੰਧੀ। | NA |  | 1 | Councillor Quota (CQ) | CQ | Proposed | 17.35 | __ | __ | YES | YES | XEN | N/A | 2026-06-09 | 2026-06-25 | [9 empty] | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN
|  | O&M | B | B2 | Sahnewal | 21 | Sewerage | 374075 | ਵਾਰਡ ਨੰ,21 ਅਧੀਨ ਪੈਂਦੇ ਇਲਾਕੇ ਵਿੱਚ ਸੀਵਰੇਜ ਦੀਆਂ ਲਾਈਨਾਂ ਅਪਗ੍ਰੇਡ ਕਰਨ ਸਬੰਧੀ। | 417.58 |  | 1 | Councillor Quota (CQ) | CQ | Proposed | 26.7 | __ | __ | YES | YES | XEN | N/A | [11 empty] | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | [7 empty] | File sent for Estimate Approval.
|  | O&M | B | B2 | Sahnewal | 22 | Sewerage | 400563 | ਵਾਰਡ ਨੰ.22 ਅਧੀਨ ਪੈਂਦੇ ਇਲਾਕੇ ਅੰਸਲ ਇਨਕਲੇਵ ਵਿਖੇ ਸੀਵਰ ਅਪਗ੍ਰੇਡ ਕਰਨ ਸਬੰਧੀ। | 3746.56 |  | 1 | Councillor Quota (CQ) | CQ | Proposed | 210.76 | __ | __ | YES | YES | XEN | N/A | [11 empty] | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | [7 empty] | File sent for Estimate Approval.
|  | O&M | B | B2 | Sahnewal | 24 | Sewerage | 412001 | ਵਾਰਡ ਨੰ.24 ਅਧੀਨ ਪੈਂਦੇ ਇਲਾਕੇ ਮੁੰਡੀਆਂ ਨੇੜੇ ਗੁਰੂਦੁਆਰਾ ਸਾਹਿਬ ਵਿਖੇ ਸੀਵਰ ਲਾਈਨ ਅਪਗ੍ਰੇਡ ਕਰਨ ਸਬੰਧੀ। | 740.5 |  | 1 | MC Funds / General Quota | GQ | Proposed | 81.43 | __ | __ | YES | YES | XEN | N/A | [11 empty] | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | [7 empty] | File sent for Estimate Approval.
|  | O&M | B | B2 | Sahnewal | 25 | Sewerage | 411998 | ਸਬਜੋਨ-ਬੀ2 ਅਧੀਨ ਪੈਂਦੇ ਵਾਰਡ ਨੰ.25 ਦੇ ਇਲਾਕੇ ਬਲਾਲਾ ਕਲੋਨੀ, ਇਸ਼ਵਰ ਕਲੋਨੀ ਅਤੇ ਹਾਥੀ ਕਲੋਨੀ ਵਿੱਚ ਸੀਵਰੇਜ ਦੀ ਲਾਈਨ ਪਾਉਣ/ਅਪਗ੍ਰੇਡ ਕਰਨ ਸਬੰਧੀ। | 1324.36 |  | 1 | MC Funds / General Quota | GQ | Proposed | 91.79 | __ | __ | YES | YES | XEN | N/A | [11 empty] | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | [7 empty] | File sent for Estimate Approval.
|  | O&M | B | B2 | Sahnewal | 21,22,23,24 & 25 | Water & Sewerage | 405962 | ਸਬਜੋਨ-ਬੀ2 ਅਧੀਨ ਪੈਂਦੇ ਵਾਰਡਾਂ (21, 22, 23, 24 ਅਤੇ 25) ਲਈ ਵਾਟਰ ਸਪਲਾਈ ਅਤੇ ਸੀਵਰੇਜ ਦੇ ਕੰਮ ਲਈ ਮਟੀਰਿਅਲ ਦੀ ਖਰੀਦ ਕਰਨ ਸਬੰਧੀ। | NA |  | 1 | MC Funds / General Quota | GQ | Proposed | 45.84 | __ | __ | YES | YES | XEN | N/A | [11 empty] | Davinderpal Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | [7 empty] | File sent for Estimate Approval.
|  | O&M | B | B4 | South | 27 | Sewerage |  | Upgradation of Providing & Laying of 4" Dia DIK-7 Water Supply Line & 12" UPVC Sewer line at New Town Colony, Sherpur Khurd ward no-27. | S/W 382 W/S 382 | NA | 1 | MC Funds / General Quota | GQ | Awarded | 32.61 | -29.13% | 3362 Dt 21/04/2026 | YES | YES | XEN | N/A | 2026-02-05 | 2026-02-16 | Yes | Yes | 134/G33 07-05-2026 | Bedi Pump Store | 23.11 | 2026-05-07 | 3 | 2026-08-07 |  | Harinder Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | 100% |  |  | Completed |  | Completed
|  | O&M | B | B4 | East | 26 | T/Well |  | Providing & Installing of 25 HP Deep straight Bore Tubewell at Phase-1, Park Opp.House No 35,36 & 37 in Ward No. 26. | NA | NA | 1 | MC Funds / General Quota | GQ | Awarded | 12.64 | -18.5% | 2853 Dt 19-02-2026 | YES | YES | XEN | N/A | 2025-11-07 | 2025-12-02 | Yes | Yes | 104/G33 06-03-2026 | Bedi Pump Store | 10.3 | 2026-03-06 | 2 | 2026-05-06 |  | Harinder Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | 100% |  |  | Completed |  | Completed
|  | O&M | B | B4 | South | 27 | Water Supply |  | Prov/Laying of DIK7 4" Water Supply line at Kabaddi Market near 100 ft Road in W. No. 27. | W/S 350.6 | NA | 1 | Councillor Quota (CQ) | CQ | Awarded | 6.74 | -15.86% | 2881 Dt 19-02-2026 | YES | YES | XEN | N/A | 2025-11-07 | 2025-12-02 | Yes | Yes | 118/G33 06-03-2026 | G.K Contractor | 5.67 | 2026-03-06 | 2 | 2026-05-06 |  | Harinder Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | 100% |  |  | Completed |  | Completed
|  | O&M | B | B4 | South | 32 | Water Supply/ Sewer |  | Providing & Laying of 4" Dia DIK-7 Water Supply Line & 12" UPVC Sewer line at Phase-5, Adjoining Dhandary Bridge, ward no-32. | S/W 1210 W/S 1210 | NA | 1 | MC Funds / General Quota | GQ | Awarded | 99.56 | -31.33% | 3359 Dt 21-04-2026 | YES | YES | XEN | N/A | 2026-02-05 | 2026-02-16 | Yes | Yes | 139/G33 07-05-2026 | Bedi Pump Store | 68.37 | 2026-05-07 | 4 | 2026-11-30 |  | Harinder Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | 40% |  |  | In Progress |  | Work Stop Due to Mansoon
|  | O&M | B | B4 | South | 27 | Strom Sewer |  | providing and Laying of 400 MM & 250 MM RCC NP3 Classs Strom line at Kailash Nagar Street no 3, Springdale School road to Cancer Road in ward No 27. | S/W 1048 | NA | 1 | MC Funds / General Quota | GQ | Awarded | 68.41 | -29.75% | 3358 Dt 21-04-2026 | YES | YES | XEN | N/A | 2026-02-05 | 2026-02-16 | Yes | Yes | 138/G33 07-05-2026 | Rajdeep Enterprises | 48.05 | 2026-05-07 | 4 | 2026-11-30 |  | Harinder Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | - |  | - | Not Started |  | Work will start after monsoon
|  | O&M | B | B4 | East | 19 | T/Well | 401586 | Prov/Installation of New 25 HP Straight Bore Tubewell & 5 HP Shallow Submersible Tubewell at Sec-39, Near Sacred Heart School, Ward No- 19 in East Constituency (Against Failed T/Well). | NA | NA | 1 | Councillor Quota (CQ) | CQ | Proposed | 15.27 | __ | __ | YES | YES | XEN | N/A | [11 empty] | Harinder Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | [7 empty] | file sent for approval
|  | O&M | B | B4 | East | 26 | Sewerage | 397475 | Pro/Laying of 12” UPVC Pipe at Metro Road (Pinki Bakery to Phase-1, Goal Market) Ward No-26 in East Constituency .( Upgradation). | Sw 320 | NA | 1 | MC Funds / General Quota | GQ | Proposed | 19.63 | __ | __ | YES | YES | XEN | N/A | [11 empty] | Harinder Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | [7 empty] | file sent for approval
|  | O&M | B | B4 | East | 19 | T/Well | 397425 | Prov/Installation of 25 HP Straight Bore Tubewell at Sec-39, Near Sacred Heart School, Ward No- 19 in East Constituency (Against Failed T/Well). | NA | NA | 1 | Councillor Quota (CQ) | CQ | Proposed | 12.64 | __ | __ | YES | YES | XEN | N/A | [11 empty] | Harinder Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | [7 empty] | file sent for approval
|  | O&M | B | B4 | East | 28 | Sewerage | 405220 | Pro/Laying of 12” UPVC Pipe at New Moti Nagar, St No. 1, 3, 8 & Market, Ward No. 28 in East Constituency.( Upgradation). | SW 850 | NA | 1 | Councillor Quota (CQ) | CQ | Proposed | 51.67 | __ | __ | YES | YES | XEN | N/A | [11 empty] | Harinder Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | [7 empty] | file sent for approval
|  | O&M | B | B4 | South | 32 | T/Well | 1192155 | Installation of New 12.50 HP water Borewell pump in Sherpur Khurd ward No. 32 (M.P LAD Scheme) in South Constituency | NA | NA | 1 | MPLAD Funds | MP LAD | Proposed | 6.56 | __ | __ | Yes | Yes | SDO | N/A |  |  | Yes | Yes | [7 empty] | Harinder Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | - |  |  |  |  | file sent for approval
|  | O&M | B | B4 | South | 27 | Water Supply | 387194 | Upgradation of 3” GI Pipe Water Supply Line at old Sherpur Village, serpur Kalan, Ward No- 22 in South Constituency. (General Quata). | ws 1708 | NA | 1 | MC Funds / General Quota | GQ | Proposed | 30.63 | __ | __ | Yes | Yes | SDO | N/A |  |  | Yes | Yes | [7 empty] | Harinder Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | - |  |  |  |  | file sent for approval
|  | O&M | B | B4 | South | 27 | Sewerage | 377998 | Pro/Laying of 10” UPVC Pipe at 100’ Road Opp. Compactor Sherpur, Ward No-27 in South Constituency.( Upgradation). (General Quota) | sw 122 | NA | 1 | MC Funds / General Quota | GQ | Proposed | 6.12 | __ | __ | Yes | Yes | SDO | N/A |  |  | Yes | Yes | [7 empty] | Harinder Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | - |  |  |  |  | file sent for approval
|  | O&M | B | B4 | East | 28 | T/Well & water supply | 378010 | Upgradation DIK-7 4” &6” Water Supply Line &Installation of New 25 HP Deep Straight Bore Tubewell at Baba Deep Singh Nagar, Ward No- 28 in East Constituency. |  | NA | 1 | Councillor Quota (CQ) | CQ | Proposed | 46.25 | __ | __ | Yes | Yes | SDO | N/A | 2026-06-09 | 2026-06-25 | Yes | Yes | [7 empty] | Harinder Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | - |  |  |  |  | File send for allotment approval
|  | O&M | B | B4 | East | 28 | Water Supply |  | Upgradation DIK-7 4” &6” Water Supply Line at New Moti Nagar, Ward No- 28 in East Constituency (General Quota). |  | NA | 1 | MC Funds / General Quota | GQ | Proposed | 97.88 | __ | __ | Yes | Yes | XEN | N/A | 2026-06-09 | 2026-06-25 | Yes | Yes | [7 empty] | Harinder Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | - |  |  |  |  | File send for allotment approval
|  | O&M | B | B4 | East | 28 | T/Well |  | Prov/Installation of New 25 HP Deep Straight Bore Tubewell at Heera Nagar, Street no. 2 in Ward No- 28 in East Constituency. |  | NA | 1 | MC Funds / General Quota | GQ | Proposed | 12.64 | __ | __ | Yes | Yes | SDO | N/A | 2026-06-09 | 2026-06-25 | Yes | Yes | [7 empty] | Harinder Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | - |  |  |  |  | File send for allotment approval
|  | O&M | B | B4 | East | 28 | Sewerage |  | Prov/Laying of 400 mm dia RCC NP3 Sewer line from Vishwanath Mandir to Aarti Steel (Metro Road). |  | NA | 1 | MC Funds / General Quota | GQ | Proposed | 76.34 | __ | __ | Yes | Yes | SDO | N/A | 2025-11-24 | 2025-12-09 | Yes | Yes |  |  | 57.26 |  |  |  |  | Harinder Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | [5 empty] | File send for allotment approval
|  | O&M | B | B4 | East | 19,26, 27,28 | Sewerage |  | Desilting and cleaning of sewage line in various wards of sub zone-B4 (sanatan mandir road, Vishkarma Colony & labour colony, Kirti Nagar & New Kirti Nagar, Sector-39, Opp. DCM Presidency School, Kailash Nagar, Street No. 0 to 3, Sherpur firni and Samral chowk to vardhman chowk etc.) |  | NA | 1 | MC Funds / General Quota | GQ | Proposed | 171.3 | __ | __ | Yes | Yes | XEN | N/A | [11 empty] | Harinder Singh-J.E Summerbir Singh-SDO Baljinder Singh-XEN | N/A | N/A | [5 empty] | Files sent to F&CC for Estimate Approval.
|  | O&M | A | A4 | North | 87 | sewerage | 382719 | Prov. And laying/upgradation of 16" and 20" RCC NP3 HDPE lining sewer link nanak nagar, main road ward number 87 | 1002 | - |  | Councillor Quota (CQ) | CQ | In progress | 60.81 | 27.27% | in anticipation 12/05/2026 |  |  | SE | [5 empty] | 07/G-33 Dt. 15/06/2026 | Surya Construction | 44.22 | 2026-06-16 | 3 | 2026-09-15 |  | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN
|  | O&M | A | A4 | North | 1 | sewerage | 384350 | Upgradation of sewer line at main Bharti colony road in ward no. 1 | 845 |  |  | Councillor Quota (CQ) | CQ | In progress | 81.27 | 32.82% | in anticipation 15/06/2026 |  |  | SE | [5 empty] | 06/G-33 Dt. 15/06/2026 | Rajdeep Enterprises | 54.59 | 2026-06-18 | 3 | 2026-09-15 |  | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN
|  | O&M | A | A4 | North | 89 | Strom water Drainage | 374778 | Making of Disposal Well at Chand Cinema pully Near Bholi Mahant Dera in Ward no.89 | 69 |  |  | MC Funds / General Quota | GQ | allotment stage | 28.73 |  |  |  |  | XEN | [6 empty] | ESS Elecmech Enterprises | [5 empty] | Amarjit juneja JE anshul garcha sdo kamal ram xen
|  | O&M | A | A4 | North | 8 | sewerage | 374815 | Rough Cost Estimate Prov. Laying of Sewer Line and Water Supply Line in Vishkarma Colony Ward No. 8 | 503 |  |  | MC Funds / General Quota | GQ | allotment stage | 47.79 |  |  |  |  | XEN | [6 empty] | M/s Kohinoor Builders | [5 empty] | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN
|  | O&M | A | A4 | North | 89 | sewerage | 374844 | Rehabilitation of Sewer line at different Area in ward No. 89 | 698 |  |  | Councillor Quota (CQ) | CQ | allotment stage | 44.77 |  |  |  |  | XEN | [6 empty] | Bedi Pump Store | [5 empty] | Amarjit juneja JE anshul garcha sdo kamal ram xen
|  | O&M | A | A4 | North | 1 | sewerage |  | Raising of manhole slab, additional manhole & repair of manhole on different areas of ward no 1 | - |  |  | Councillor Quota (CQ) | CQ | allotment stage | 9.71 |  |  |  |  | SDO | [6 empty] | M/s Bharat Nirman Infracon | [5 empty] | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN
|  | O&M | A | A4 | North | 94 | sewerage | 374622 | Raising of slab, Making Of Scaver Point, Repair Of Manhole in Different Loacalities Of Ward no.94 | - |  |  | Councillor Quota (CQ) | CQ | allotment stage | 6.57 |  |  |  |  | SDO | [6 empty] | G.K Contractor | [5 empty] | Balwinder je Anshul Garch sdo kamal ram xen
|  | O&M | A | A4 | North | 86 | sewerage | 404387 | Rough Cost Estimate Prov. Laying of Water supply line and Sewer Line in Bindra Colony ( Jaswant Nagar) And Vishnupuri of Ward No.86 | 644 |  |  | MC Funds / General Quota | GQ | allotment stage | 38.95 |  |  |  |  | XEN | [6 empty] | Surya Construction | [5 empty] | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN
|  | O&M | A | A4 | North | 86 | sewerage | 413242 | Rough Cost Estimate Prov. Laying of Water supply line and Sewer Line in St.no. 0,Vishnupuri Ward No.86 | 536 |  |  | Councillor Quota (CQ) | CQ | allotment stage | 44.65 |  |  |  |  | XEN | [6 empty] | Bedi Pump Store | [5 empty] | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN
|  | O&M | A | A4 | North | 94 | sewerage | 401665 | Rough Cost Estimate Prov. Laying of Water supply line(4”) and Sewer Line (8”&10”) in Kartar Nagar, Neta Ji Nagar, Punjabi Bagh & other Areas of Ward No.94 ( MC Quota). | 724 |  |  | Councillor Quota (CQ) | CQ | allotment stage | 48.6 |  |  |  |  | XEN | [6 empty] | Surya Construction | [5 empty] | Balwinder je Anshul Garch sdo kamal ram xen
|  | O&M | A | A4 | North | - | sewerage | 401623 | E.AYNf.AYm sYl dy sb jon-ey4 qy qhsIl bxn kwrn sb jon-ey4 nvW dPqr bxwaux sbMDI[ | - |  |  | MC Funds / General Quota | GQ | allotment stage | 31.23 |  |  |  |  | XEN | [6 empty] | ESS Elecmech Enterprises | [5 empty] | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN
|  | O&M | A | A4 | North | 88 | water supply | 413244 | Providing and Laying of DIK 7 Water supply line along with 25 HP tubewell at krishna gali ward no 88 | 515 |  |  | Councillor Quota (CQ) | CQ | allotment stage | 24.85 |  |  |  |  | SDO | [6 empty] | ESS Elecmech Enterprises | [5 empty] | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN
|  | O&M | A | A4 | North | - | sewerage |  | Supply of M/Hole set 's Cove complete/Cover's i. s EHD, HD & MD under Sub Zone-A4 |  |  |  | MC Funds / General Quota | GQ | Tender stage | 9.35 |  |  |  |  | SDO | [12 empty] | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN
|  | O&M | A | A4 | North | - | Strom water Drainage | 378022 | Repair of engines and service of genset for rainy season in sub zone A4 |  |  |  | MC Funds / General Quota | GQ | Tender stage | 8.11 |  |  |  |  | SDO | [12 empty] | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN
|  | O&M | A | A4 | North | 89 | water supply | 379222 | Providing and installation of 25 HP straight bore tubewell against failed at Arya mohalla ward no 89 (MC QUOTA) |  |  |  | Councillor Quota (CQ) | CQ | Tender stage | 12.71 |  |  |  |  | SDO | [12 empty] | Amarjit juneja JE anshul garcha sdo kamal ram xen
|  | O&M | A | A4 | North | - | water supply | 378035 | Annual rate contract of Prov. and Installation of 2 Nos. 12.5 HP, 5 Nos. of 25HP, 03 Nos. of 40HP, Against (Emergency) failed T/well in North Constituency, Zone-A. |  |  |  | MC Funds / General Quota | GQ | Tender stage | 146.63 |  |  |  |  | SE | [12 empty] | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN
|  | O&M | A | A4 | North | 89 | water supply | 379206 | Providing and installation of 25 HP straight bore tubewell against failed at new krishan halwai old sabzi mandi chownk ward no 89 (MC QUOTA) |  |  |  | Councillor Quota (CQ) | CQ | Tender stage | 15.05 |  |  |  |  | SDO | [12 empty] | Amarjit juneja JE anshul garcha sdo kamal ram xen
|  | O&M | A | A4 | North | 88 | sewerage | 378017 | Rough Cost Estimate of Providing laying of 10" UPVC and 12" UPVC Sewer line at Jain Nagar and FatehgarhMohalla Ward NO. 88 | 792 |  |  | Councillor Quota (CQ) | CQ | For Approval | 49.48 |  |  |  |  | XEN | [12 empty] | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN
|  | O&M | A | A4 | North | 8 | sewerage | 378020 | Rough Cost Estimate of Providing laying of 10" UPVC and 12" UPVC Sewer line at Bal Singh Nagar Ward NO. 8 | 790 |  |  | MC Funds / General Quota | GQ | For Approval | 49.8 |  |  |  |  | XEN | [12 empty] | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN
|  | O&M | A | A4 | North | 87 | sewerage | 381545 | Rehablitation/prov.laying /upgradation of 12'' and 8'' sewerline at arjan nagar , karabara basti , opposite cc cold store and 4'' water supply at bindra colony ward no 87 |  |  |  | Councillor Quota (CQ) | CQ | For Approval | 85.02 |  |  |  |  | SE | [12 empty] | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN
|  | O&M | B | B3 | East | 7 | Sewerage |  | Providing, Laying / Up-Gradation of 10" dia. UPVC pipe at Subhash Nagar, Atal Nagar, Chanderlok Colony Street No. 5/5 and 6 of Sub in Wardno. 7 East Constituency |  |  | 1 | MC Funds / General Quota | GQ | Proposed | 49.24 | __ | __ | Yes | Yes | XEN | N/A | 2026-06-09 | 2026-06-25 | Yes | Yes |  |  | 34.31 |  |  |  |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [7 empty] | Financial bid open and file will be sent for allotment approval.
|  | O&M | B | B3 | East | 11 | Water Supply |  | Providing & Installing of 25 HP Deep straight Bore Tubewell at Shakti Nagar, St. No. 7 in Ward No. 11. |  |  | 1 | MC Funds / General Quota | GQ | Proposed | 12.62 | __ | __ | Yes | Yes | XEN | N/A | 2025-11-07 | 2025-12-02 | Yes | Yes |  |  | 10.32 |  |  |  |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [7 empty] | File sent for Allotment Approval.
|  | O&M | B | B3 | East | 11 | Water Supply |  | Rough Cost Estimate for Upgradation of 4” DIK-7 Water supply & 8” UPVC sewer line at Shastri Nagar St. No. 8 & Mayapuri, St. No. 5, Meena Masjid Tibba Road, Shakti Nagar Nr. Longia steel in Ward No. 11 (G.Q). |  |  | 1 | MC Funds / General Quota | GQ | Proposed | 46.21 | __ | __ | Yes | Yes | XEN | N/A | 2026-06-09 | 2026-06-25 | Yes | Yes |  |  | 34.61 |  |  |  |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [7 empty] | Financial bid open and file will be sent for allotment approval.
|  | O&M | B | B3 | East | 11 | Water Supply |  | Prov and Laying of 4 inch dia DIK7 water supply line at Manjeet Nagar in W. No. 11 (GQ). |  |  | 1 | MC Funds / General Quota | GQ | Proposed | 48.39 | __ | __ | Yes | Yes | XEN | N/A | 2026-04-30 | 2026-05-15 | Yes | Yes |  |  | 46.52 |  |  |  |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [7 empty] | File sent for Allotment Approval.
|  | O&M | B | B3 | East | 11 | Water Supply |  | Prov and laying of 4 inch dia DIK7 water supply line at Shakti Nagar near Dada Bajaj in W. No. 11 |  |  | 1 | MC Funds / General Quota | GQ | Proposed | 49.84 | __ | __ | Yes | Yes | XEN | N/A | 2026-04-30 | 2026-05-15 | Yes | Yes |  |  | 48.23 |  |  |  |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [7 empty] | File sent for Allotment Approval.
|  | O&M | B | B3 | East | 11 | Water Supply |  | Prov and laying of 4 inch dia DIK7 water supply line at Shakti Nagar in W. No. 11. |  |  | 1 | MC Funds / General Quota | GQ | Proposed | 47.73 | __ | __ | Yes | Yes | XEN | N/A | 2026-04-01 | 2026-04-13 | Yes | Yes |  |  | 39.67 |  |  |  |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [7 empty] | File sent for Allotment Approval.
|  | O&M | B | B3 | East | 11 | Water Supply |  | Prov and laying of 4 inch dia DIK7 water supply line at Mayapuri near Rehman Chicken Biryani in W. No. 11 |  |  | 1 | MC Funds / General Quota | GQ | Proposed | 31.48 | __ | __ | Yes | Yes | XEN | N/A | 2026-04-30 | 2026-05-15 | Yes | Yes |  |  | 30.04 |  |  |  |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [7 empty] | File sent for Allotment Approval.
|  | O&M | B | B3 | East | 11 | Water Supply |  | Prov & laying of 4 inch dia DIK7 water supply line at Mayapuri Chowk to Shakti Nagar Disposal in W. No. 11 (GQ). |  |  | 1 | MC Funds / General Quota | GQ | Proposed | 40.16 | __ | __ | Yes | Yes | XEN | N/A | 2026-04-30 | 2026-05-15 | Yes | Yes |  |  | 39.33 |  |  |  |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [7 empty] | File sent for Allotment Approval.
|  | O&M | B | B3 | East | 11 | Water Supply |  | Prov and laying of 4 inch dia DIK7 water supply line at New Shakti Nagar in W. No. 11 (GQ). |  |  | 1 | MC Funds / General Quota | GQ | Proposed | 32.62 | __ | __ | Yes | Yes | XEN | N/A | 2026-04-30 | 2026-05-15 | Yes | Yes |  |  | 31.25 |  |  |  |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [7 empty] | File sent for Allotment Approval.
|  | O&M | B | B3 | East | 16 | Water Supply |  | Upgradation of 4” dia DIK7 water supply line and 8” UPVC Sewer line at Tibba Road B/s MLA Office, Gurmail Park, Hingraj Dyeing, Tajpur Road in W. No. 16. |  |  | 1 | MC Funds / General Quota | GQ | Proposed | 17.38 | __ | __ | Yes | Yes | XEN | N/A | [11 empty] | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [7 empty] | File sent for Estimate Approval.
|  | O&M | B | B3 | East | 18 | Water Supply |  | Upgradation of 4 inch dia DIK7 water supply line at M.I.G Flat in W. No. 18 (GQ). |  |  | 1 | MC Funds / General Quota | GQ | Proposed | 59.3 | __ | __ | Yes | Yes | XEN | N/A | 2026-05-08 | 2026-06-01 | Yes | Yes |  |  | 47.55 |  |  |  |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [7 empty] | E-Office No. File sent for Allotment Approval.
|  | O&M | B | B3 | East | 29 | Water Supply |  | P/L of 6" dia DIK7 water supply line at Guru Arjun Dev Nagar (Vishkarma Atta Chaki to Krishna Steel) National Highway in Ward No. 29 (Missing Link). |  |  | 1 | MC Funds / General Quota | GQ | Proposed | 9.36 | __ | __ | Yes | Yes | XEN | N/A | 2026-06-09 | 2026-06-25 | Yes | Yes |  |  | 8.55 |  |  |  |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [7 empty] | Financial bid open and file will be sent for allotment approval.
|  | O&M | B | B3 | East | 17 | Water Supply |  | Providing /laying of 4" DIK 7 water supply line and 8" UPVC sewer line at National Colony, St. No. 2 and Shankar Colony in W. No. 17 (GQ). |  |  | 1 | MC Funds / General Quota | GQ | Proposed | 21.51 | __ | __ | Yes | Yes | XEN | N/A | [11 empty] | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [7 empty] | E-Office No. 406102 File sent for Estimate Approval.
|  | O&M | B | B3 | East | 17 | Water Supply |  | Providing & Installing of 25 HP Deep straight Bore Tubewell at G.K. Estate, Block-B in Ward No. 17. |  |  | 1 | MC Funds / General Quota | GQ | Proposed | 12.62 | __ | __ | Yes | Yes | XEN | N/A | 2026-11-07 | 2026-12-02 | Yes | Yes |  |  | 10.45 |  |  |  |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [7 empty] | E-Office No. 374518 File sent for Allotment Approval.
|  | O&M | B | B3 | East | 17 | Water Supply |  | providing & Installing of 25 HP Deep straight Bore Tubewell at Bharpur Nagar, St. No. 5 in Ward No. 17. |  |  | 1 | MC Funds / General Quota | GQ | Proposed | 12.62 | __ | __ | Yes | Yes | XEN | N/A | [11 empty] | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [7 empty] | E-Office No. 406112 File sent for Estimate Approval.
|  | O&M | B | B3 | East | 13 | Sewerage |  | Prov & laying of sewer line and construction & raising of machine hole chambers & slabs in W. No. 13. |  |  | 1 | MC Funds / General Quota | GQ | Proposed | 49.93 | __ | __ | Yes | Yes | XEN | N/A | 2026-06-09 | 2026-06-25 | Yes | Yes |  |  | 36.69 |  |  |  |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [7 empty] | Financial bid opened and file will be sent for allotment approval.
|  | O&M | B | B3 | East | 14&17 | Sewerage |  | Upgradation of 8” UPVC Sewer line at Gopal Nagar and Shankar Colony in W. No. 14 &17 (GQ). |  |  | 1 | MC Funds / General Quota | GQ | Proposed | 21.25 | __ | __ | Yes | Yes | XEN | N/A | [11 empty] | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [7 empty] | File sent for Estimate Approval.
|  | O&M | B | B3 | East | 16 | Water Supply |  | Rough Cost Estimate for Upgradation of 4” dia DIK-7 water supply line at G.K Estate Block-C W. No. 16 (G.Q). |  |  | 1 | MC Funds / General Quota | GQ | Proposed | 29.17 | __ | __ | Yes | Yes | XEN | N/A | 2026-04-01 | 2026-04-13 | Yes | Yes |  |  | 24.5 |  |  |  |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [7 empty] | E-Office No. 397651 File sent for Allotment Approval.
|  | O&M | B | B3 | East | 18 | Sewerage |  | Upgradation of 8” UPVC sewer line at G.K Estate Block-C in Ward No.16 (G.Q). |  |  | 1 | MC Funds / General Quota | GQ | Proposed | 60.5 | __ | __ | Yes | Yes | XEN | N/A | 2026-04-01 | 2026-04-13 | Yes | Yes |  |  | 41.81 |  |  |  |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [7 empty] | E-Office No. 397644 File sent for Allotment Approval.
|  | O&M | B | B3 | East | 17 | Sewerage |  | Rough Cost Estimate for Upgradation of 8” UPVC sewer line at G.K Estate Block-B in Ward No. 17 (G.Q). |  |  | 1 | MC Funds / General Quota | GQ | Proposed | 76.01 | __ | __ | Yes | Yes | XEN | N/A | 2026-04-01 | 2026-04-13 | Yes | Yes |  |  | 52.53 |  |  |  |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [7 empty] | E-Office No. File sent for Allotment Approval.
|  | O&M | B | B3 | East | 18 | Water Supply |  | Upgradation of 4” dia DIK-7 water supply line at M.I.G Flat in W. No. 18 (G.Q). |  |  | 1 | MC Funds / General Quota | GQ | Proposed | 59.3 | __ | __ | Yes | Yes | XEN | N/A | 2026-04-01 | 2026-04-13 | Yes | Yes |  |  | 47.55 |  |  |  |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [7 empty] | E-Office No. 404254 File sent for Allotment Approval.
|  | O&M | B | B3 | East | 18 | Sewerage |  | Upgradation of 8” & 10” UPVC Sewer line at M.I.G Flat in W. No. 18 (GQ). |  |  | 1 | MC Funds / General Quota | GQ | Proposed | 102.04 | __ | __ | Yes | Yes | SE | N/A | [11 empty] | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [7 empty] | E-Office No. 394016 File sent for Estimate Approval.
|  | O&M | B | B3 | East | 20 | Water Supply & Sewerage |  | Rough Cost Estimate for Upgradation of 4” dia DIK-7 water supply line and 8” UPVC Sewer line at Baba Jeewan Singh Nagar & Mahajan Vihar in W. No. 20. (G.Q). |  |  | 2 | MC Funds / General Quota | GQ | Proposed | 33.76 | __ | __ | Yes | Yes | XEN | N/A | 2026-04-30 | 2026-05-15 | Yes | Yes |  |  | 30.98 |  |  |  |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [7 empty] | E-Office No. 404243 File sent to F&CC for Allotment Approval.
|  | O&M | B | B3 | East |  | Sewerage |  | Prov/Laying of 400 mm dia RCC NP3 Sewer line from Vishwanath Mandir to Aarti Steel (Metro Road). |  |  | 1 | MC Funds / General Quota | GQ | Proposed | 76.34 | __ | __ | Yes | Yes | SE | N/A | 2025-11-24 | 2025-12-09 | Yes | Yes |  |  | 57.26 |  |  |  |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [7 empty] | E-Office No. 378004 File sent for Allotment Approval.
|  | O&M | B | B3 | East | 29 | Sewerage |  | Rough Cost Estimate for Prov & Laying of 8” UPVC Sewer line and 4” dia DIK7 water supply line missing link at various streets of G.A.D Nagar in W. No. 29. |  |  | 1 | MC Funds / General Quota | GQ | Proposed | 7.02 | __ | __ | Yes | Yes | SDO | N/A | 2025-11-07 | 2025-12-02 | Yes | Yes |  |  | 5.27 |  |  |  |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [7 empty] | File sent for Allotment Approval.
|  | O&M | B | B3 | East | 29 | Sewerage |  | Upgradation of 8” UPVC sewer line at Kishore Nagar in Ward No. 29 (G.Q). |  |  | 1 | MC Funds / General Quota | GQ | Proposed | 7.04 | __ | __ | Yes | Yes | SDO | N/A | 2026-04-01 | 2026-04-13 | Yes | Yes |  |  | 5.28 |  |  |  |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [7 empty] | E-Office No. 397626 File sent for Allotment Approval.
|  | O&M | B | B3 | East |  | Storm Sewer |  | P/L of 600mm & 250mm Storm Sewer (1990 mtr.) line Rahon Road (Nayra Petrol Pump to main G.T. Road Disposal) |  |  | 1 | MC Funds / General Quota | GQ | Proposed | 237.74 | __ | __ | Yes | Yes | CE | N/A | [11 empty] | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [7 empty] | Survey and Hydraulic design pending by Dean Testing & Consultancy Cell
|  | O&M | B | B3 | East |  | Sewerage |  | P/L of 600mm, 400mm & 250mm RCC NP3 Class Sewer (1520 mtr.) line at Tirkona Park to main G.T. Road Disposal. |  |  | 1 | MC Funds / General Quota | GQ | Proposed | 137.38 | __ | __ | Yes | Yes | CE | N/A | [11 empty] | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [7 empty] | Survey and Hydraulic design pending by Dean Testing & Consultancy Cell
|  | O&M | B | B3 | East |  | Storm Sewer |  | P/L of 600mm & 250mm storm Sewer (1850 mtr.) line at Nayra Petol Pump to main G.T. Road Basti Chowk. |  |  | 1 | MC Funds / General Quota | GQ | Proposed | 196.97 | __ | __ | Yes | Yes | CE | N/A | [11 empty] | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [7 empty] | Survey and Hydraulic design pending by Dean Testing & Consultancy Cell
|  | O&M | B | B3 | East |  | Sewerage |  | Providing, Laying /Upgradation of 10" dia. UPVC SN-8 Sewer line Grewal colony, Simarjit Nagar and Raju Colony at East Constituency |  |  | 1 | MC Funds / General Quota | GQ | Proposed | 170.04 | __ | __ | Yes | Yes | CE | N/A | [11 empty] | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [7 empty] | File sent to CE for Vetting.
|  | O&M | B | B3 | East |  | Storm Sewer |  | Prov. and Laying of Storm Sewer at Rahon Road (East Constituency). |  |  | 1 | MC Funds / General Quota | GQ | Proposed | 770.51 | __ | __ | Yes | Yes | CE | N/A | [11 empty] | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [7 empty] | File sent to CE for Vetting.
|  | O&M | B | B3 | East |  | Storm Sewer |  | Prov/Laying of 36” Storm Sewer Line and Road Jalli at Green Land Convert School to Budha Dariya in W. No.29. |  |  | 1 | MC Funds / General Quota | GQ | Proposed | 146.07 | __ | __ | Yes | Yes | CE | N/A | [11 empty] | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [7 empty] | Tender recall on 10-08-2026.
|  | O&M | B | B3 | East |  | Sewerage | 385285 | Providing & Laying of 1000 mm RCC pipe with HDPE Lining NP3 class sewer line at vardhman chowk (chandigarh road) to MPS tajpur road |  |  | 1 | MC Funds / General Quota | GQ | Proposed | 256.39 | 30.6% | in anticipation of F&CC vide dated 21-01-2026 | Yes | Yes | CE | N/A | 2025-12-26 | 2026-01-21 | Yes | Yes |  | Ludhiana Construction Company | 177.93 |  | 6 |  |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | [7 empty] | File sent to CE for vetting
|  | O&M | B | B3 | East | 11 | T/well | 382358 | Prov./Inst. of New 25 HP Deep Straight bore tubewell at Shakti Nagar in W. No. 11 (CQ). |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 12.62 | 18.25% | 3863 15-06-2026 | Yes | Yes | XEN | N/A | 2025-11-07 | 2025-12-02 | Yes | Yes | 152/G33 28-07-2026 | M/s Rana Electrical Works | 10.32 |  | 3 |  |  | Gurjeet Singh-J.E Amritpal Singh-SDO Baljinder Singh-XEN | NA
|  | O&M | A | [5 empty] | Allotment of work for Preventive Maintenance of Sewerage System for 26 wards of Ludhiana City for two Years, Municipal Corporation, Ludhiana. |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 34.93 | - | - | Yes | Yes | XEN | N/A |  |  | Yes | Yes | 01/G-33 Dt. 06/05/2026 | M/S Inderjeet Bajaj | 34.93 |  | 12 |  |  |  | NA | [7 empty] | M/S Inderjeet Bajaj
|  | O&M | A | A4 | North | 88 | water supply | 374762 | Divert upgradation of water supply line in shivpuri pully opposite fish market word no. 88 |  |  | 1 | Councillor Quota (CQ) | CQ | Awarded | 5.33 | -17.1% | 3478 21-04-2026 | Yes | Yes | JE | N/A |  |  | Yes | Yes | 02/G-33 Dt. 06/05/2026 | m/s Sushil kumar | 4.41 |  | 2 |  |  | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN | NA | [7 empty] | m/s Sushil kumar |  | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN
|  | O&M | A | A3 | EAST |  | water supply | 375952 | Providing Laying 16" dia NP-3 HDPE sewer line in Green City and 4" dia DIK-7 water supply line at Jaswal colony & constructions of new manholes at East Constituency. |  |  | 1 | Councillor Quota (CQ) | CQ | Awarded | 43.38 | -28.56% | 3457 21-04-2026 | Yes | Yes | XEN | N/A |  |  | Yes | Yes | 04/G-33 Dt. 09/05/2026 | ESS Elecmech Enterprises | 34.56 |  | 3 |  |  | Er. Parwinder Singh (JE) Er. Sukhdeep Singh(SDO) Er. Kamal Ram (XEN) | NA | [7 empty] | ESS Elecmech Enterprises
|  | O&M | A | A4 | North | 87 | sewerage | 382719 | Providing laying/Up-gradation of 16" and 20" RCC NP3 HDPE lining Sewer Line Nanak Nagar main Road in Ward No. 87 |  |  | 1 | Councillor Quota (CQ) | CQ | Awarded | 60.81 | -27.27% | 3444 21-04-2026 | Yes | Yes | SE | N/A |  |  | Yes | Yes | 06/G-33 Dt. 01/06/2026 | Surya Construction | 44.23 |  | 2 |  |  | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN | NA | [7 empty] | Surya Construction |  | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN
|  | O&M | A | A4 | North | 1 | water supply | 382080 | Up-Gradation of Sewer Line At Main Bharti Colony Road in Ward No.1 |  |  | 1 | Councillor Quota (CQ) |  | Awarded | 81.27 | -32.82% | 2026-06-13 | Yes | Yes | XEN | N/A |  |  | Yes | Yes | 07/G-33 Dt. 15/06/2026 | Rajdeep Enterprises | 54.6 |  | 2 |  |  | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN | NA | [7 empty] | Rajdeep Enterprises |  | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN
|  | O&M | A | A4 | North |  | water supply | 400593 | Providing of poclane machine for cleaning of budha dariya on hiring basis. |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 47.29 | -1% | 2026-07-03 | Yes | Yes | XEN | N/A |  |  | Yes | Yes | 08/G-33 Dt. 06/07/2026 | Manmohan Singh Contractor | 46.81 |  | 2 |  |  | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN | NA | [7 empty] | Manmohan Singh Contractor |  | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN
|  | O&M | A | A4 | North | 4 | T/Well | 377871 | Providing & Installation of 25HP Straight Bore Tubewell against failed Tubewell of 12.5 HP Near Bapu Labh Singh Gurudwara Sahib, Kakowal Road, Ward No. 4, Ludhiana. |  |  | 1 | Councillor Quota (CQ) | CQ | Awarded | 12.07 | -0.5% | 3835 15-06-2026 | Yes | Yes | SDO | N/A |  |  | Yes | Yes | 09/G-33 Dt. 15/07/2026 | M/s Rana Electrical works | 12.06 |  | 2 |  |  | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN | NA | [7 empty] | M/s Rana Electrical works |  | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN
|  | O&M | A | A4 | North | 1 | sewerage | 374828 | Raising of manhole slab, additional manhole & repair of manhole in different areas of ward no 1 |  |  | 1 | MC Funds / General Quota | GQ | Awarded | 9.71 | -25% | 3865 15-06-2026 | Yes | Yes | SDO | N/A |  |  | Yes | Yes | 10/G-33 Dt. 27/07/2026 | M/s Bharat Nirman Infracon | 7.28 |  | 3 |  |  | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN | NA | [7 empty] | M/s Bharat Nirman Infracon |  | Himanshu sharma JE Anshul Garcha SDO KamalRam XEN

## SASCI-MDF
Sr. No. | Name of Road | Type of Roads | Source of Funding | Constituency Name | Total Execution Cost (Crores) | Total Length (KM) | Total length completed as on 29th july | % length completed as on 29th july | Total length completed as on 4h Aug. | % length completed as on 4th Aug. | White Line Target (km) | White Line Completion (km) | Date of Completion along with Remarks (if any) | Meeting Dt. 07/08 | Meeting Dt. 20/08 (Physical Progress)
1 | Upgradation of RMC Roads in various wards of Central Constituency. | RMC | MDF 2026-27 | Central | 7.42 | 10.68 | 10.35 | 96.91% | 10.35 | 96.91% | 0 | 0 | Work will be completed by 31-07-2026 |  | 100%
2 | Upgradation of Elevated Road from Jagraon Bridge to Chand Cinema by laying Mastic Asphalt. | Bitumen | MDF 2026-27 | North | 5.68 | 4.88 | 3.1 | 63.52% | 3.1 | 63.52% | 4.88 | 0 | Work will be completed by 15-08-2026. Delayed due to rainy season. | Mastic layer pending, RMC DONE. 50% WORK COMPLETED, updated target date 25/08 | 63.52%
3 | Upgradation of various Roads with RMC in Ward No.1, Ludhiana | RMC | MDF 2026-27 | North | 6.96 | 7.25 | 3.8 | 52.41% | 3.8 | 52.41% | 0 | 0 | Work will be completed by 15-08-2026. Delayed due to rainy season. |  | 55.17%
4 | Upgradation of Roads with RMC in Area Bharti Colony, Akash Nagar adjoining Jalandhar Byepass, Ludhiana | RMC | MDF 2026-27 | North | 5.71 | 7.46 | 3.45 | 46.25% | 3.45 | 46.25% | 0 | 0 | Work will be completed by 15-08-2026. Delayed due to rainy season. |  | 53.62%
5 | Upgradation of Various Main Roads with RMC in North Constituency Zone- A Ludhiana. | RMC | MDF 2026-27 | North | 8.58 | 7.01 | 3.85 | 54.92% | 3.85 | 54.92% | 0 | 0 | Work will be completed by 15-08-2026. Delayed due to rainy season. |  | 64.19%
6 | Upgradation of various Roads with RMC in Ward No.95, Ludhiana | RMC | MDF 2026-27 | North | 6.35 | 7.44 | 6.75 | 90.73% | 6.75 | 90.73% | 0 | 0 | Work will be completed by 31-07-2026 |  | 96.1%
7 | Construction of Various Roads in Industrial Area C & Focal Point in South Constituency Zone-C Ludhiana. | RMC | MDF 2026-27 | South | 4.79 | 3.35 | 1.5 | 44.78% | 1.5 | 44.78% | 0 | 0 | Work will be completed by 30-09-2026 except the road where 24x7 water supply line is to be laid and storm sewer is proposed |  | 52.24%
8 | Upgradation of various road of Atam Nagar Constituency Zone C. (RMC) | RMC | MDF 2026-27 | Atam Nagar | 4.35 | 1.82 | 0.67 | 36.81% | 0.7 | 38.46% | 0 | 0 | RMC work is in progress which will be completed by 15.08.2026 |  | 57.69%
9 | Upgradation of various roads in different wards with RMC & Bitumen in sub zone D1 North Constituency. | RMC & Bitumen | MDF 2026-27 | North | 4.45 | 9.11 | 4.25 | 46.65% | 4.38 | 48.08% | 5.3 | 0 | RMC Work is in progress which will be completed by 31.07.2026 . Bitumen work delay due to rainy season, will be completed by 15.08.2026 |  | 82.99%
10 | Upgradation of various road of Atam Nagar Constituency Zone C. (Bituminous) | Bitumen | MDF 2026-27 | Atam Nagar | 4.98 | 3 | 1.4 | 46.67% | 1.42 | 47.33% | 3 | 0 | Work is in progress which will be completed by 15.08.2026. Bitumen work delay due to rainy season |  | 50%
11 | Construction of Various Roads in South Constituency Zone-C Ludhiana. | RMC | SASCI 2026-27 | South | 5.37 | 4 | 1.58 | 39.5% | 1.68 | 42% | 0 | 0 | RMC work is in progress which will be completed by 15.08.2026 subject to laying of 24x7 W/S project |  | 42%
12 | Upgradation of road from shamshan ghat pully and malhi pully backside New Deep nagar ward no. 91 | Bitumen & RCC wall | SASCI 2026-27 | North | 6.22 | 1.5 | 1.45 | 96.67% | 1.5 | 100% | 0 | 0 | RMC work is in progress which will be completed by 31.07.2026. Completion of bituminous work is delay due to rainy season. |  | 100%
13 | Upgradation of Roads with RMC in Area Guru Har Rai Nagar, Nagesh Hosiery Road adjoining Jalandhar Byepass, Ludhiana | RMC | SASCI 2026-27 | North | 5.01 | 3.68 | 1.9 | 51.63% | 1.9 | 51.63% | 0 | 0 | RMC work is in progress which will be completed by 15.08.2026 |  | 57.07%
14 | Upgradation of Main Metro Road from Jamalpur Chowk to Kangaroo Industry, Jaswant Singh Dental College to Delhi road via Sethi Sweets, Internal Roads of Sec-39,Road from Primary Govt School to NRI Police Station in Sec-39, Main Jain Colony road from Rahon Road to Swastik Enclave and Main Road of Guru Arjun Dev Nagar from GT Road upto Greenland School, Sabji Mandi Road from Chd road to Puda road, EWS colony main road from Jacha Bacha Hospital upto Tajpur road. | Bitumen | SASCI 2026-27 | East | 6.87 | 13.52 | 4.09 | 30.25% | 4.09 | 30.25% | 13.52 | 0 | Work will be completed by 30-09-2026 except the road where 24x7 water supply line is to be laid and storm sewer is proposed |  | 30.25%
15 | Upgradation of Gurudwara road urban estate phase 1&2 from Metro road to Jeewan Nagar chowk, Road along budha nallah from NHAI to MC limit ,Main Bhadur Ke Road from Sabji Mandi upto MC Limit, Main New Azad Nagar 30' Road from Kainth Property Dealer upto Gaur Property Dealer and Roads of Onkar Vihar. | Bitumen | SASCI 2026-27 | East | 5.17 | 7.46 | 0.75 | 10.05% | 0.75 | 10.05% | 7.46 | 0 | Work will be completed by 30-09-2026 except the road where 24x7 water supply line is to be laid and storm sewer is proposed |  | 16,62%
16 | Upgradation and development of various roads in different ward of West Constituency | Bitumen | SASCI 2026-27 | West | 13.14 | 0 | 0 | 0% | 0 | 0% | 0 | 0 | Under Litigation
17 | Upgradation of Various Bitumen Main Roads in North Constituency Zone-A Ludhiana | Bitumen | SASCI 2026-27 | North | 7.82 | 0 | 0 | 0% | 0 | 0% | 0 | 0 | Under Litigation
18 | Laying BM and SDBC on road in Sub Zone D2 Atam Nagar Halka | Bitumen | SASCI 2026-27 | Atam Nagar | 6.8 | 0 | 0 | 0% | 0 | 0% | 0 | 0 | Under Litigation
19 | Upgradation of Bituminious Roads in various wards of Central Constituency. | Bitumen | SASCI 2026-27 | Central | 6.48 | 0 | 0 | 0% | 0 | 0% | 0 | 0 | Under Litigation
20 | Upgradation of Main Bhamian Road from Chandigarh road to upto MC Limit, Main Phirni of Village Mundian Kalan from Chd road to Sunder Nagar 33' Road and from Chd Road to Rasila Nagar Back side Blind School. | Bitumen | SASCI 2026-27 | Sahnewal | 5.2 | 0 | 0 | 0% | 0 | 0% | 0 | 0 | Under Litigation
|  |  | Total |  | 127.35 | 92.16 | 48.89 | 53.05% | 49.22 | 53.41% | 34.16

## Rangla Punjab Dashboard
RANGLA PUNJAB VIKAS SCHEME
Municipal Corporation, Ludhiana — Commissioner’s Dashboard
1. MUNICIPAL CORPORATION LUDHIANA — OVERALL SNAPSHOT (PHASE 1 + PHASE 2)
TOTAL WORKS |  |  | SANCTIONED AMOUNT |  | WORKS ALLOTTED |  | WORKS COMPLETED | YET TO START
86 |  |  | 22.4178 |  | 26 |  | 2 | 62
Rs. Crore
2. PHASE-WISE PROGRESS — MUNICIPAL CORPORATION LUDHIANA
| Metric |  | Phase 1 |  |  | Phase 2 |  | Combined
| No. of Works |  | 39 |  |  | 47 |  | 86
| Sanctioned Amount (Rs. Cr.) |  | 13.5626 |  |  | 8.8552 |  | 22.4178
| Tenders Floated |  | 37 |  |  | 28 |  | 65
| Works Allotted |  | 26 |  |  | 0 |  | 26
| Works Completed (100%) |  | 2 |  |  | 0 |  | 2
| Works In Progress |  | 22 |  |  | 0 |  | 22
| Yet to Start |  | 15 |  |  | 47 |  | 62
| % Physical Completion |  | 5.128% |  |  | 0% |  | 2.326%
3. WORK STATUS BREAKDOWN BY PHASE
| Status | Phase 1 | Phase 2
| Completed | 2 | 0
| In Progress | 22 | 0
| Yet to Start | 15 | 47
4. MUNICIPAL CORPORATION LUDHIANA — SHARE OF DISTRICT-WIDE SCHEME
| Metric |  | District-wide Total |  |  | MC Ludhiana |  | MC Share
| Total Works (Phase 1 + 2) |  | 836 |  |  | 86 |  | 10.29%
| Sanctioned Amount (Rs. Cr.) |  | 221.0961 |  |  | 22.4178 |  | 10.14%
| Segment | Sanctioned Amount (Rs. Cr.)
| MC Ludhiana | 22.4178
| Rest of District | 198.6783
5. PRIORITY ATTENTION — TOP 10 HIGH-VALUE WORKS NOT YET STARTED
# | Phase | Constituency |  | Ward | Name of Work |  |  | Amount (Rs. Cr.) | Remarks
1 | Phase 1 | 60-Ldh East |  | 20 | Construction of playground and stadium ward no. 20 Ludhiana |  |  | 0.856 | Total Amount 373.23 Lacs out of which 250.00 Lacs funds used from Rangla Punjab Grant Phase-I File sent to F&CC for approval of Estimate
2 | Phase 1 | 60-Ldh East |  | 20 | Infrastructure for promotion of sports with indoor stadium (volleyball court) and redevelopment of basketball court |  |  | 0.855
3 | Phase 1 | 60-Ldh East |  | 20 | Infrastructure for promotion of sports with indoor stadium (badminton court) |  |  | 0.789
4 | Phase 2 | 63-Ldh Central |  | 76 | Laying RMC M-30 in link Streets of Kusht Ashram Road in ward no.76. |  |  | 0.728 | Tender called.
5 | Phase 2 | 61-Ldh South |  | 27 | P/F 60mm I/Tiles in various streets of Fauzi colony, Deep Nagar & Ranjit nagar in W.no. 27 |  |  | 0.66 | File sent to F&CC for work allotment. Work in progress
6 | Phase 2 | 63-Ldh Central |  | 79 | Laying RMC M-30 in Street No.1,2,3 & Links Hari Kartar Colony in ward no.79. |  |  | 0.534 | Tender called.
7 | Phase 1 | 64-Ldh West |  | ward no. 72 | Total (143 Benificary per 0.35 lacs) |  |  | 0.5005
8 | Phase 2 | 64-Ldh West |  | 54 | Repair and Renovation of Jawaddi Dharamshalla ward no 54. |  |  | 0.5 | Tender to be Opened on 29.05.2026
9 | Phase 2 | 63-Ldh Central |  | 76 | Laying RMC M-30 in Different Streets of Prem Nagar Part-II in ward no.76. |  |  | 0.498 | Tender called.
10 | Phase 2 | 61-Ldh South |  | 38 | P/F 60mm I/Tiles in various streets of Isher Nagar in W.no. 38 |  |  | 0.49 | File sent to F&CC for work allotment. Work in progress

## Phase 1 - MC Ludhiana
Sr. No. | Name of constituency | Ward No. | Name of Work | Total number of streets | Length (in km) | Administrative Approval (Y/N) | Financial Approval (Y/N) | Sanction Amount (Rs.) In Cr. | Tender Floated (Yes/No) | Work Allotted (Yes/No) | Agency | Work Start Date | Date of Completion | Progress (%) | Ongoing Streets | Completed Streets | Geotagged photos | Remarks | 2026-07-13
1 | 63-Ldh Central | 85 | Laying RMC M-30 in street of Mohalla Shankar Puri, Veer Nagar & SDP College Quilla Mohalla in w.no.85. |  |  | Yes | Yes | 0.859 | Yes | Yes | Maa Chintpurni construcions | 2026-05-15 | 2026-08-04 | 45 |  |  |  | Work in Progress. Should be completed within timeline.
2 | 63-Ldh Central | 82 | Laying RMC M-30 in Shanti Niketen School St & Links Streets of Mohalla Fateh Ganj in Ward No-82 | 8 |  | Yes | Yes | 0.432 | Yes | Yes | LRY | 2026-06-01 | 2026-08-04 | 25 | 4 |  |  | Work in Progress. Road Gullies work in progress
3 | 63-Ldh Central | 82 | Laying RMC M-30 in streets near Gajja Jain Mandir in Tilak Nagar w.no.82. |  |  | Yes | Yes | 0.279 | Yes | Yes | LRY | 2026-06-01 | 2026-08-04 | 15 |  |  |  | Work in Progress
4 | 63-Ldh Central | 79 | Laying RMC M-30 in Hargobind Nagar & its adjoining streets of w.no.79. |  |  | Yes | Yes | 0.531 | Yes | Yes | CAPITAL | 2026-06-01 | 2026-08-30 | 10 |  |  |  | Work in Progress
5 | 63-Ldh Central | 80 | Laying RMC M-30 in streets of New Kidwai Nagar in w.no. 80. |  |  | Yes | Yes | 0.398 | Yes | Yes | Godwyn Infra | 2026-06-01 | 2026-08-04 | 10 |  |  |  | Work in Progress
6 | 65-Ldh North | 66 | Construction of Playground/ Joy box Opposite Bhatia School, Bank Colony, Ward No. 66 |  |  | Yes | Yes | 0.25 | Yes | Yes | Subodh Batish | 2026-07-11 | 2026-08-15 | 5% |  |  |  | Work in progress
7 | 65-Ldh North | 70 | Rejuvenation of Urban Community Health Centre in Ludhiana North Constituency |  |  | Yes | Yes | 0.2 | Yes | No | [7 empty] | 4th time Tender recalled date of invitation Tender 21.07.2026
8 | 65-Ldh North | 88 | Construction of Swimming Pool, Changing Rooms, Attendent Room on Vacant Land opposite Baba Ghori Dargah in Ward No.88 |  |  | Yes | Yes | 0.4 | Yes | No | [7 empty] | Tender opening on Next Monday i.e 20-08-26
9 | 65-Ldh North | General | Installation of Security Camera's at Various locations of North Constituency, Under Safe City Project. |  |  | Yes | Yes | 0.35 | Yes | No | [7 empty] | Tender to be opened, work order expected by next Monday, 20-06-26 agenda to be prepared by Wed, 15-07-26
10 | 60-Ldh East | 20 | Construction of playground and stadium ward no. 20 Ludhiana |  |  | Yes | Yes | 0.856 | Yes | No | [7 empty] | Total Amount 373.23 Lacs out of which 250.00 Lacs funds used from Rangla Punjab Grant Phase-I File sent to F&CC for approval of Estimate. Tender | Tender to be opened by 17-07-26, Financial to be opened by 20-07-26,agenda to be prepared by 22-07-26
11 | 60-Ldh East | 20 | Infrastructure for promotion of sports with indoor stadium (volleyball court) and redevelopment of basketball court |  |  | Yes | Yes | 0.855 | Yes | No | [8 empty] | Tender to be opened by 17-07-26, Financial to be opened by 20-07-26,agenda to be prepared by 22-07-27
12 | 60-Ldh East | 20 | Infrastructure for promotion of sports with indoor stadium (badminton court) |  |  | Yes | Yes | 0.789 | Yes | No | [8 empty] | Tender to be opened by 17-07-26, Financial to be opened by 20-07-26,agenda to be prepared by 22-07-28
13 | 61-Ldh South | 38 | Construction of Dispensary on Shamshan Ghat road Lohara W. NO. 38 |  |  | Yes | Yes | 0.1499 | Yes | Yes |  | 2026-06-22 | 2026-08-30 | 10% |  |  |  | Work in progress
14 | 61-Ldh South | 32 | Construction of Dispensary in Dhandari Kalan Village W. no.32 |  |  | Yes | Yes | 0.1499 | Yes | No | [7 empty] | Technical bids to be opened. | Tender to be opened today , i.e 13-08-36 and financial to be opened by 14-07-26
15 | 61-Ldh South | 27 | Construction of Indoor stadium opposite Baba Dental college W. no. 27 |  |  | Yes | Yes | 0.12 | No | No | [7 empty] | Tender to be called. | Tender to be opened today , i.e 13-08-36 and financial to be opened by 14-07-27
16 | 61-Ldh South | 32 | Providing and Installation of Open air Gym Equipments Dhandari Kalan W.no. 32 |  |  | Yes | Yes | 0.08 | Yes | Yes |  | 2026-04-30 | 2026-08-25 | 50 |  |  |  | Work in progress | Supply received of the equipments
17 | 61-Ldh South | 31,32 | Construction of Two no. Bus Shelters in south constituency W. no. 31 & 32 |  |  | Yes | Yes | 0.05 | Yes | No | [7 empty] | Technical bids to be opened. | Tender to be opened today , i.e 13-08-36 and financial to be opened by 14-07-26
18 | 61-Ldh South | 35 | Construction of RCC road from Mair Di Chakki Chowk to Near Daba Village W. No. 35 |  |  | Yes | Yes | 0.6102 | Yes | Yes |  | 2026-06-22 | 2026-07-30 | 30 |  |  |  | Work in progress | Exavation done, road gullies done
19 | 61-Ldh South | 32 | Reconstruction of community centre on Campa Cola road in village Dhandari kalan. W. no. 32 |  |  | Yes | Yes | 0.25 | Yes | Yes |  | 2026-06-22 | 2026-08-15 | 10 |  |  |  | Work in progress
20 | 61-Ldh South | 37 | Laying RMC in street no. 8 of Guru Gobind Singh Nagar W. no. 37 |  |  | Yes | Yes | 0.3243 | Yes | Yes |  | 2026-04-30 | 2026-08-11 | 100 |  |  |  | COMPLETED
21 | 61-Ldh South | 33 | Laying RMC in various streets odf Satguru Nagar & Karamjit Nagar Halka South W. no. 33 | 5 |  | Yes | Yes | 0.7657 | Yes | Yes | sobti contractor | 2026-04-30 | 2026-07-31 | 40
22 | 62-Atam Nagar |  | Construction of Road by Laying RMC from Jeet Sweet Shop to Itta Wala Chowk Halka Atam Nagar. (Rangla Punjab Vikas Scheme). |  |  | Yes | Yes | 0.6095 | Yes | Yes | Apex Contractor | 2026-04-30 | 2026-08-15 | 10 |  |  |  | Work in progress | Reason for delay- Sewer was clogged, issue resolved now
23 | 62-Atam Nagar | 44 | Laying RMC in Street No.6 ,7 & Links of Janta Nagar Near Bhagwan Chowk, W.No.44 (Rangla Punjab Vikas Scheme) |  |  | Yes | Yes | 0.2504 | Yes | Yes | sobti contractor | 2026-04-30 |  | 100 |  |  |  | COMPLETED
24 | 64-Ldh West | 72 | Construction of Additional Rooms at Ayurvedic Dispensary Jawahar Nagar Camp near Bus Stand in Ward no 72 |  |  | Yes | Yes | 0.15 | Yes | Yes |  | 2026-05-13 | 2026-08-05 | 45% |  |  |  | Work in Progress
25 | 64-Ldh West | 72 | Providing Mobile Water tankers in Ward no. 72 |  |  | Yes | Yes | 0.05 | Yes | [9 empty] | TENDER TO BE OPENED TODAY 13-07-26, AGENDA TO BE PREPARED BY 15-07-26
26 | 64-Ldh West | 60 | Construction of Public Library in Gurdev Nagar in Ward No 60 |  |  | Yes | Yes | 0.12 | Yes | Yes |  | 2026-05-13 | [5 empty] | Pending for site selection
27 | 64-Ldh West | 60 | Providing CCTV Camera system for security Purpose in Gurdev Nagar Ward no. 60 |  |  | Yes | Yes | 0.03 | Yes | [8 empty] | To be recalled 4th time. | TENDER TO BE OPENED TODAY 13-07-26, AGENDA TO BE PREPARED BY 15-07-26
28 | 64-Ldh West | 60 | Construction of Cricket Playground in Gurdev Nagar Ward no 60. |  |  | Yes | Yes | 0.05 | Yes | Yes |  | 2026-05-13 |  | 4 |  |  |  | Pending for site selection
29 | 64-Ldh West | 64 | Construction of park in Dairy Complex, Block A, Ward no. 64. |  |  | Yes | Yes | 0.15 | Yes | [8 empty] | Tenders under technical Evaluation | TENDER TO BE OPENED TODAY 13-07-26, AGENDA TO BE PREPARED BY 15-07-26
30 | 64-Ldh West | 63 | Construction of Joybox or Playground in Ward no 63. |  |  | Yes | Yes | 0.2723 | Yes | Yes |  | 2026-05-13 | 2026-08-15 | 10 |  |  |  | Work in progress
31 | 64-Ldh West | 59 | Repair & renovation by Laying 80mm thick I/tiles in streets of Sajha Sahib Gurudwara to Village Barewal T point ward no. 59 | 1 | 0.2 | Yes | Yes | 0.1 | Yes | Yes |  | 2026-05-13 | 2026-07-25 | 75% |  |  |  | Work in progress
32 | 64-Ldh West | 55 | Repair & renovation of various Parks and sprikler system in parks of ward no 55 |  |  | Yes | Yes | 0.2 | Yes | Yes |  | 2026-05-13 | 2026-07-25 | 30 |  |  |  | Work in progress
33 | 64-Ldh West | 63 | Provision of High Mast 12.5 Mtr. Lighting arrangement in Ward no 63 |  |  | Yes | Yes | 0.1406 | Yes | Yes |  | 2026-06-09 | 2026-07-30 | 5 |  |  |  | Work in progress
34 | 64-Ldh West | 65 | Installation of new LED lights on ward no 65 |  |  | Yes | Yes | 0.188 | Yes | Yes |  | 2026-06-20 | 2026-08-15 | 5 |  |  |  | Work in progress
35 | 64-Ldh West | 65 | Provision of Semi High Mast Lighting arrangement in Ward no 65 |  |  | Yes | Yes | 0.0513 | Yes | Yes |  | 2026-06-20 |  | 5 |  |  |  | Work in progress
36 | 64-Ldh West | 58 | Provision of High Mast 12.5 Mtr. Lighting arrangement in Ward no 58 |  |  | Yes | Yes | 0.2938 | Yes | Yes |  | 2026-06-20 |  | 5 |  |  |  | Work in progress
37 | 64-Ldh West | 71 | Provision of Online Cloud connected Surveillance system at various locations of ward no 71 |  |  | Yes | Yes | 0.2 | Yes | [8 empty] | To be recalled 4th time. | TENDER TO BE OPENED TODAY 13-07-26, AGENDA TO BE PREPARED BY 15-07-26
38 | 62-Atam Nagar | 50 | P/Laying Bm & Pc in Various Streets of Guru Gian Vihar ward no.50 | 12 |  | Yes | Yes | 1.5072 | Yes | Yes |  | 2026-05-20 | 2026-07-31 | 90 |  | 12 |  | Bitumenous work in progress at site. | Road furniture left
39 | 64-Ldh West | 72 | Total (143 Benificary per 0.35 lacs) |  |  | Yes | Yes | 0.5005 |  | Yes |  | 2026-06-01
TOTAL (Municipal Corporation, Ludhiana) | [7 empty] | 13.5626 | 37 | 26

## Phase 2 - MC Ludhiana
RANGLA PUNJAB VIKAS SCHEME — PHASE 2 — MUNICIPAL CORPORATION, LUDHIANA
Sr. No. | Name of constituency | Panchayat Name/ Ward No. | Name of Work | Proposal Received (Yes/No) | Administrative Approval (F&CC/House) | Financial Approval (Y/N) | Sanction Amount (Rs.) In Cr. | Tender Floated (Yes/No) | Work Allotted (Yes/No) | Work Start Date | Date of Completion | Progress (%) | Remarks | 2026-07-14
1 | 63-Ldh Central | 79 | Laying RMC M-30 in Street No.1,2,3 & Links Hari Kartar Colony in ward no.79. | Yes | Yes |  | 0.534 | No | No |  |  |  | Tender called. | Tender to be opened on 24/07/26
2 | 63-Ldh Central | 76 | Laying RMC M-30 in link Streets of Kusht Ashram Road in ward no.76. | Yes | Yes |  | 0.728 | No | No |  |  |  | Tender called. | Tender to be opened on 24/07/27
3 | 63-Ldh Central | 76 | Laying RMC M-30 in Different Streets of Prem Nagar Part-II in ward no.76. | Yes | Yes |  | 0.498 | No | No |  |  |  | Tender called. | Tender to be opened on 24/07/28
4 | 63-Ldh Central | 30 | Laying RMC M-30 in Various Streets of Bihari Colony in ward no.30. | Yes | Yes |  | 0.7382 | No | No |  |  |  | Tender called. | Tender to be opened on 24/07/29
5 | 65-Ldh North | 68 | Construction of Road with RMC from Lala Jagat Narain chowk to B.K Building Material store w.no. 68 | Yes | Yes |  | 0.3 | Yes | No | 2026-07-21 | 2026-07-30 |  | 2nd time tender recalled dt 21.07.2026 | Tender recalled due to single bid. To be opened on 21/07
6 | 65-Ldh North | Gen | Construction of road with RMC from karanvir Hospital to Jassian Chowk,22 footi Road, Ludhiana. | Yes | Yes |  | 0.35 | Yes | No |  | 2026-07-30 |  | File sent to F&CC for tender approval | Was approved in anticipation. To be put in F&CC for approval of tender. Work has been completed.
7 | 65-Ldh North | Gen | Providing & Installation of New Street Lights (30 watt & 60 watt) at various Locations of North Constituency, Ludhiana | Yes | Yes |  | 0.35 | No | No | 2026-07-25 | 2026-07-30 |  |  | Tender to be opened on 24/07
8 | 60-Ldh East | 20 | Upgradation of Play Ground on Main Bhamian Road W. No. 20 | Yes | Yes |  |  | No | No |  |  |  | Total Amount 373.23 Lacs out of which 250.00 Lacs funds used from Rangla Punjab Grant Phase-I and balance amount 123.23 lacs will be utilised from Rangla Punjab Grant Phase-II Proposal sent to DESA | Tender to be opened on 16/07/26. WO by 20/07 in anticipation.
9 | 60-Ldh East | 15 | Development and construction of sports area & Library in ward no. 15 | Yes | Yes |  |  | No | No |  |  |  | Proposal sent to DESA | Tender to be opened on 21/07/26. WO by 23/07 in anticipation.
10 | 60-Ldh East | 20 | Construction of Library in W No.20 (East Constituency) | Yes | Yes |  |  | No | No |  |  |  | Proposal sent to DESA | Tender to be opened on 21/07/26. WO by 23/07 in anticipation.
11 | 61-Ldh South | 32 | Construction of rooms in Govt. Primary School, Jugiana W.no. 32 | Yes | Yes |  | 0.3 | Yes | No |  | 2026-08-30 |  | Tender Stage | Single bid, second time, SE to prepare justification, In ancticipation approval. WO by 17/07
12 | 61-Ldh South | 32 | Construction of box cricket court in Jugiana Park W. no. 32 | Yes | Yes |  | 0.27 | Yes | No |  | 2026-07-30 |  | File sent to F&CC for work allotment | To be put up for in anticipation approval. WO by 17/07
13 | 61-Ldh South | 32,38 | Construction of 3 nos. of Labour Sheds in Kunti Nagar, near Gillz garden and Sherpur of South Constituency | Yes | Yes |  | 0.1 | Yes | No |  | 2026-08-15 |  | Tender Stage | Single bid, second time, SE to prepare justification, In ancticipation approval. WO by 17/07
14 | 61-Ldh South | 27 | P/F 60mm I/Tiles in various streets of Fauzi colony, Deep Nagar & Ranjit nagar in W.no. 27 | Yes | Yes |  | 0.66 | Yes | No |  |  |  | File sent to F&CC for work allotment. Work in progress | To be put up for in anticipation approval. WO by 17/07
15 | 61-Ldh South | 27 | P/F 60mm I/Tiles in various streets near Noori Masjid in W.no. 27 | Yes | Yes |  | 0.35 | Yes | No |  |  |  | File sent to F&CC for work allotment. Work in progress | To be put up for in anticipation approval. WO by 17/07
16 | 61-Ldh South | 38 | P/F 60mm I/Tiles in various streets of Isher Nagar in W.no. 38 | Yes | Yes |  | 0.49 | Yes | NO |  |  |  | File sent to F&CC for work allotment. Work in progress | To be put up for in anticipation approval. WO by 17/07
17 | 61-Ldh South | 31 | P/F 60mm I/Tiles in various streets of Bhagwan Nagar in W.no. 31 | Yes | Yes |  | 0.33 | Yes | NO |  |  |  | File sent to F&CC for work allotment. Work in progress | To be put up for in anticipation approval. WO by 17/07
18 | 62-Atam Nagar |  | Supply of 1 nos. of T1 AMB (SHELL) 3350 Fabricated Type C (Force Motor Ltd) include Equipments (Scoop, Stretcher, Spine Board, Head Immobilizer, Wheel Chair) include Registration & Insurance Ambulance for various Area's of Atam nagar constituency | Yes | Yes |  |  | No |  |  |  |  | Proposal sent to DESA
19 | 62-Atam Nagar |  | Box cricket and Renovation of Golden park | Yes | Yes |  |  | No | No |  |  |  | File sent to F&CC for work allotment | Tender to be floated. WO by 30/07/26
20 | 62-Atam Nagar |  | Repair and Renovation of Basant park | Yes | Yes |  |  | Yes | No |  |  |  | Tender stage | WO by 17/07 in anticipation
21 | 62-Atam Nagar |  | Repair and Renovation of Ravidasia Dharamshala | Yes | Yes |  |  | No | No |  | 2026-08-15 |  | Tender to be recalled | No bid received. to be recalled again. WO by 26/7 in anticipation
22 | 62-Atam Nagar |  | Repair and Renovation of Valmiki Dharamshala | Yes | Yes |  |  | No |  |  | 2026-08-15 |  | Tender to be recalled | No bid received. to be recalled again. WO by 26/7 in anticipation
23 | 62-Atam Nagar |  | Repair and Renovation of Dr. Ambedkar nagar Dharamshala | Yes | Yes |  | 0.14 | Yes | No |  | 2026-08-30 |  | At Tender Stage. | Tender to be opened by 16/07/26. WO by 20/07 in anticipation
24 | 62-Atam Nagar |  | Repair and Renovation of community centre Shaheed karnail singh nagar Phase 3 | Yes | Yes |  | 0.13 | No |  |  | 2026-08-30 |  | At Tender Stage. | Tender to be opened by 16/07/26. WO by 20/07 in anticipation
25 | 62-Atam Nagar |  | Supplying and Fixing Solar lights at Various Dark Zone of Atam Nagar Constituency. | Yes | Yes |  | 0.177 | No |  |  |  |  | Proposal sent to DESA | Tender to be floated on 16/07. WO by 5 Aug
26 | 62-Atam Nagar |  | Repair and Renovation of Vikas Dharamshala and manjit nagar Dharamshala | Yes | Yes |  | 0.23 | No |  |  |  |  | At Tender Stage. | Tender to be opened on 15/07. WO by 17/07 in anticipation.
27 | 62-Atam Nagar |  | Providing and fixing of CCTV's Camera in Different locations of Atam Nagar. | Yes | Yes |  | 0.39 | No | No |  |  |  | Proposal sent to DESA | Tender to be floated on 16/07. WO by 5 Aug
28 | 62-Atam Nagar |  | Construction of Walkway Foothpath at ITI Gill road Ludhiana | Yes | Yes |  |  | No | No |  |  |  | At Tender Stage. | Tender to be floated. WO by 30/07/26
29 | 64-Ldh West | 54 | Repair and Renovation of Jawaddi Dharamshalla ward no 54. | Yes | Yes |  | 0.5 | Yes | No |  | 2026-08-30 |  | Tender to be Opened on 29.05.2026 | Tender opened on 13/07/26. Work Order to be given by 17/07 in anticipation
30 | 64-Ldh West | 55 | Installation of High Mast Light at Gurunanak Public School Chowk. W.No.55 | Yes | Yes |  | 0.05 | Yes | No |  | 2026-07-30 |  | Tender to be Opened on 29.05.2026 | SIngle bid received third time, To prepare justification and issue WO in anticipation
31 | 64-Ldh West | 55 | Installation of High Mast Lights I Block Park Sarabha Nagar.W.No.55 | Yes | Yes |  | 0.05 | Yes | No |  | 2026-07-30 |  | Tender to be Opened on 29.05.2026 | SIngle bid received third time, To prepare justification and issue WO in anticipation
32 | 64-Ldh West | 55 | Repair & Renovation of H Block Park Sarabha Nagar W.No.55 | Yes | Yes |  | 0.05 | Yes | No |  | 2026-07-30 |  | Tender to be Opened on 29.05.2026 | Double bids, same price. to be approved in anticipation
33 | 64-Ldh West | 56 | Installation of CCTV Cameras in Ward no 56. | Yes | Yes |  | 0.05 | Yes | No |  | 2026-07-30 |  | Tender to be Opened on 29.05.2026 | Dual bids, to be approved in anticipation
34 | 64-Ldh West | 57 | Installation of CCTV Cameras in I block Ward no 57 | Yes | Yes |  | 0.03 | Yes | No |  | 2026-07-30 |  | Tender to be Opened on 29.05.2026 | Dual bids, to be approved in anticipation
35 | 64-Ldh West | 57 | Repair and Renovation of Alla Lallu pati Dhramshalla ward no 57 | Yes | Yes |  | 0.03 | Yes | No |  | 2026-08-05 |  | Tender to be Opened on 29.05.2026 | Double bids, same price. to be approved in anticipation
36 | 64-Ldh West | 58 | CCTV Camera in J & HJ block W.No.58 | Yes | Yes |  | 0.05 | Yes | No |  |  |  | Tender to be Opened on 29.05.2026 | Dual bids, to be approved in anticipation Financial evaluation to complete by 16/07/26
37 | 64-Ldh West | 59 | Construction and Renovation of Fathepur playing Ground W.No.59 | Yes | Yes |  | 0.25 | No | No |  |  |  | Tender to be Opened on 29.05.2026 | No bids. Call for tender again
38 | 64-Ldh West | 60 | Installation of CCTV Cameras W.No.60 | Yes | Yes |  | 0.05 | Yes | No |  | 2026-07-30 |  | Tender to be Opened on 29.05.2026 | Dual bids, to be approved in anticipation
39 | 64-Ldh West | 62 | High Mast Light in Ward no 62 | Yes | Yes |  | 0.05 | Yes | No |  | 2026-07-30 |  | Tender to be Opened on 29.05.2026 | SIngle bid received third time, To prepare justification and issue WO in anticipation
40 | 64-Ldh West | 63 | Installation of CCTV Cameras in Kitchlu Nagar W.No.63 | Yes | Yes |  | 0.05 | Yes | No |  | 2026-07-30 |  | Tender to be Opened on 29.05.2026 | Dual bids, to be approved in anticipation. WO by 17/07
41 | 64-Ldh West | 64 | Beautification of 2 nos chowk of Ward no 64 | Yes | Yes |  | 0.05 | Yes | No |  | 2026-07-30 |  | Tender to be Opened on 29.05.2026 | SIngle bid received third time, To prepare justification and issue WO in anticipation
42 | 64-Ldh West | 65 | Repair and Maintenance of Satguru Ravidass Dharamshalla Satguru Nagar W.No.65 | Yes | Yes |  | 0.15 | Yes | No |  |  |  | Tender to be Opened on 29.05.2026 | No bids. Call for tender again. Bid to open on 25/07/26
43 | 64-Ldh West | 65 | Installation of CCTV Cameras at Social and Public place of Ward no 65 | Yes | Yes |  | 0.03 | Yes | No |  | 2026-07-30 |  | Tender to be Opened on 29.05.2026 | Dual bids, WO by 17/07 in anticipation
44 | 64-Ldh West | 69 | Providing infrastructure for Badminton Court and Renovation of Canopy in 2 nos park at Kitchlu Nagar W.No.69 | Yes | Yes |  | 0.2 | Yes | No |  | 2026-08-15 |  | Tender to be Opened on 29.05.2026 | Two bids, WO by 17/07 in anticipation
45 | 64-Ldh West | 71 | Beautification of 2 nos chowk of Ward no 71 | Yes | Yes |  | 0.05 | Yes | No |  | 2026-08-15 |  | Tender to be Opened on 29.05.2026 | SIngle bid received third time, To prepare justification and issue WO in anticipation by 17/07
46 | 64-Ldh West | 72 | Installation of CCTV Cameras at New Model town, Gandhi Colony, Social and Public Place of Ward no 72 | Yes | Yes |  | 0.05 | Yes | No |  | 2026-07-30 |  | Tender to be Opened on 29.05.2026 | Two bids, WO by 17/07 in anticipation
47 | 64-Ldh West | 73 | Installation of CCTV Cameras at Social and public place of ward no 73 | Yes | Yes |  | 0.05 | Yes | No |  | 2026-07-30 |  | Tender to be Opened on 29.05.2026 | Two bids, WO by 17/07 in anticipation
TOTAL (Municipal Corporation, Ludhiana) | [6 empty] | 8.8552 | 28 | 0

## Lists (hidden)
BRANCH | ZONE | SUBZONE | AC | NATURE | FUND | YN | TSLEVEL | TENDERSTATUS
B&R | A | A1 | Atam Nagar | Roads - Bituminous | MC Funds / General Quota | Yes | JE | Not Floated
O&M | B | A2 | Central | Roads - Interlocking Tiles | Councillor Quota (CQ) | No | SDO | Floated
Horticulture | C | A3 | East | Roads - RMC / Cement Concrete | MDF / SASCI | N/A | XEN | Under Evaluation
Building | D | A4 | North | Parks & Green Belts | MPLAD Funds |  | SE | Awarded
Public Health |  | B1 | Sahnewal | Street Lighting | Rangla Punjab |  | Chief Engineer | Re-tendered
|  | B2 | South | Water Supply | SIDBI |  | Commissioner
|  | B3 | West | Sewerage | Viveki Funds
|  | B4 |  | Storm Water Drainage | N-CAP
|  | C1 |  | Building / Community Centre | CSAG
|  | C2 |  | Public Health & Sanitation | SBM (Swachh Bharat Mission)
|  | C3 |  | Horticulture | RPVS
|  | C4 |  | Others | Other / Unspecified
D1
D2
D3
D4

## Master - Legacy (Archive) (hidden)
Project ID | Zone | Constituency | Ward | Branch | Fund / Quota Type | Quota (as recorded) | Nature of Work | Name of Work | Est./Vetted Cost (Lacs) | Tender Cost (Lacs) | Allocated Amount (Lacs) | OAS % | Reso No. & Date | Work Order No. & Date | Agency | Start Date | Time Limit (Months) | End Date | Physical Progress % | Financial Progress % | Expenditure/Payment (Lacs) | Remarks / Status Notes | Status | Issues
MCL-0001 | B4 | East | 19 | B&R | MC Funds / General Quota | General | Park | Repair & Renovation of various parks in LIG W No.19 | 62.03 | 37.22 |  |  | 3189 22.11.2024 | 82 dt 04.12.2024 | M/s Prince Sharma | 04.12.2024 | 6 | 03.06.2025 | 80 |  | 24.61 | Work is in Progress | In Progress
MCL-0002 | B3 | East | 12 | B&R | MC Funds / General Quota | General | I/tiles | P/F I/tiles in various streets of W No.12 | 93.51 | 53.31 |  |  | 3190 22.11.2024 | 83 dt 04.12.2024 | M/s Apex Developers | 04.12.2024 | 5 | 03.05.2025 | 60 |  | 30.00 | Work was held up due to non-laying of W/s line in Guru Nanak Estate . Now same has been laid. Work is in progress | Delayed/Held Up
MCL-0003 | B2 | East | 17 & 19 | B&R | MC Funds / General Quota | General | I/tiles | P/F I/tiles in streets of Guru Arjun Dev Nagar, Jaswant Nagar and Indrapuri St No.4 W No.17 & 19 | 20.81 | 12.14 |  |  | 3141 22.11.2024 | 86 dt 04.12.2024 | Capital Const Co. | 04.12.2024 | 3 | 03.03.2025 | 25 |  | 5.00 | Heldup due to Dispute at site for the balance work | Delayed/Held Up
MCL-0004 | B2 | East | 16 | B&R | MC Funds / General Quota | General | Park | Const of Park on Bhamian Road Near Football Ground W No.16 | 50 | 34.06 |  |  | 355 dt 26.03.2025 | 01 16.04.2025 | M/s Teg Builders | 16.04.2025 | 6 | 15.10.2025 | 10 |  | 0.0 | Heldup due to construction of water tank by O&M Cell | In Progress
MCL-0005 | B3 | East | 12 | B&R | MC Funds / General Quota | General | I/tiles | P/F I/tiles in streets of Juneja Colony and Karamsar Colony W No.12 | 50 | 29 |  |  | 177 dt 26.03.2025 | 9 16.04.2025 | Apex Developers | 16.04.2025 | 4 | 15.08.2025 | 15 |  | 0 | Work is in Progress | In Progress
MCL-0006 | B3 | East | 10 | B&R | MC Funds / General Quota | General | I/tiles | P/F 80mm thick Interlocking tiles in streets of Mohalla New Subhash Nagar on Towerline No. 2 & 5 and St No.10 & St No.2/10 & 2/11 of Subhash Nagar W No.10 | 29.69 | 17.35 |  |  | 179 dt 26.03.2025 | 10 16.04.2025 | Capital Const Co. | 16.04.2025 | 3 | 15.07.2025 | 30 |  | 0 | Work heldup due to upgradation of W/s lines, Now same has been completed. Work is in progress now. | In Progress
MCL-0007 | B3 | East | 9 | B&R | MC Funds / General Quota | General | I/tiles | P/F I/tiles in remaining streets of Shastri Nagar and link of New Shakti Nagar W No.09 | 34.61 | 19.86 |  |  | 180 dt 26.03.2025 | 11 16.04.2025 | T&G Const Co. | 16.04.2025 | 3 | 15.07.2025 | 70 |  | 8.78 | Work heldup due to upgradation of W/s lines in the balance area | In Progress
MCL-0008 | B4 | East | 21 | B&R | MC Funds / General Quota | General | I/tiles | P/F I/tiles in streets No.2 of Hargobindpura & Links W No.21 | 34.21 | 19.99 |  |  | 185 dt 26.03.2025 | 13 16.04.2025 | Capital Const Co. | 16.04.2025 | 3 | 15.07.2025 | 90 |  | 13.50 | Balance work was heldup due to upgradation of W/S line in the balance area, now same has been laid. Work is in Progress now. | In Progress
MCL-0009 | B3 | East | 11 | B&R | MC Funds / General Quota | General | I/tiles | P/F I/tiles in streets of Sandhu Colony | 145.87 | 81.55 |  |  | 1483 dt 13.10.2025 | 20 11.07.2025 | T&G Const Co. | 11.07.2025 | 6 | 10.01.2026 | 90 |  | 75.64 | Work is in Progress | In Progress
MCL-0010 | B2 | East |  | B&R | MC Funds / General Quota | General | Others | Providing & Fixing of Sign Boards in different areas of Sub Zone B2 | 34.03 | 23.14 |  |  | Approved inanticipation of F&CC | 22 14.08.2025 | Glisten | 14.08.2025 | 3 | 13.11.2025 | 50 |  | 13.62 | Work is in Progress | In Progress
MCL-0011 | B3 | East |  | B&R | MC Funds / General Quota | General | Others | Providing & Fixing of Sign Boards in different areas of Sub Zone B3 | 43.13 | 29.33 |  |  | Approved inanticipation of F&CC, | 23 14.08.2025 | Glisten | 14.08.2025 | 4 | 13.12.2025 | 60 |  | 17.43 | Work is in Progress | In Progress
MCL-0012 | B3 | East | 12 | B&R | MC Funds / General Quota | General | Parks | Development of Green Belt on Towerline No.2 and 5 | 309.16 | 216.44 |  |  | 1787 dt 13.10.2025 | 24 27.08.2025 | RK Const Co. | 27.08.2025 | 6 | 26.02.2026 | 60 |  | 70.00 | Work is in Progress | In Progress
MCL-0013 | B3 | East | 16,18,20 &29 | B&R | MC Funds / General Quota | General | Others | Construction of Central Verge on Tajpur raod . | 217.47 | 186.7 |  |  | 1786 dt 13.10.2025 | 25 27.08.2025 | Navyug Comapany | 27.08.2025 | 6 | 26.02.2026 | 40 |  | 82.88 | Work is in Progress | In Progress
MCL-0014 | B4 | East | 19 | B&R | MC Funds / General Quota | General | Parks | P/F different type of Open garden gym machines in ward no 19. | 16.03 | 10.1 |  |  | 1669 dt 13.10.2025 | 27 15.01.2026 | Khalsa Exports Pvt Ltd. | 15.01.2026 | 2 | 14.03.2026 |  |  | 0 | Inauguration is to be done | Not Started
MCL-0015 | B4 | East | 19 | B&R | MC Funds / General Quota | General | Parks | Repair & Renovation of various Park in Sec 39 Block-I | 36.2 | 25.85 |  |  | 1666 dt 13.10.2025 | 32 15.01.2026 | RK Const Co. | 15.01.2026 | 3 | 14.04.2026 | 75 |  | 14.68 | Work is in Progress | In Progress
MCL-0016 | B4 | East | 19 | B&R | MC Funds / General Quota | General | Parks | Repair & Renovation of various Park in Sec 39 Block-II | 38.85 | 27.74 |  |  | 1667 dt 13.10.2025 | 33 15.01.2026 | RK Const Co. | 15.01.2026 | 3 | 14.04.2026 | 75 |  | 19.77 | Work is in Progress | In Progress
MCL-0017 | B4 | East | 19 | B&R | Councillor Quota (CQ) | Councillor | Others | Renovation of Disposal site and Fixing of Information Board at enterance of Sec-39 near Vardhman Chowk W No.19 | 20.7 | 19.48 |  |  | 2493 dt 05.01.2026 Workorder to be issued | 43 15.01.2026 | Teg Builders | 15.01.2026 | 2 | 14.03.2026 | 80 |  | 10.10 | Work is in Progress | In Progress
MCL-0018 | B3 | East | 16 | B&R | MC Funds / General Quota | General | RMC | Const of Road by laying RMC from Gita Nagar Pully to Vijay Nagar Pully W No.16 | 66.47 | 42.08 |  |  | 2488 dt 05.01.2026 | 44 15.01.2026 | RK Const Co. | 15.01.2026 | 4 | 14.05.2026 | 5 |  | 0 | Work heldup due to upgradation of Sewer line | In Progress
MCL-0019 | B4 | Sahnewal |  | B&R | MC Funds / General Quota | General | Others | Providing & Fixing of Sign Boards in different areas of Sub Zone B4 | 36.92 | 25.11 |  |  | 1571 dt 13.10.2025 | 46 29.01.2026 | Glisten | 46 29.01.2026 | 3 | 28.04.2026 | 50 |  | 2.49 | Work is in Progress | In Progress
MCL-0020 | B4 | East | 19 | B&R | MC Funds / General Quota | General | Parks | P/F of Garden Benches in various park of W No.19 | 7.91 | 6.45 |  |  | 1668 dt 13.10.2025 | 48 29.01.2026 | Glisten | 48 29.01.2026 | 1 | 28.02.2026 |  |  | 0 | Inauguration is to be done | Not Started
MCL-0021 | B4 | East | 28 | B&R | MC Funds / General Quota | General | Parks | P/F Garden Benches, Open Gym Machines & Children Playing Equipments in W No.28 | 12.92 | 10.27 |  |  | 1671 dt 13.10.2025 | 49 16.02.2026 | Glisten | 49 16.02.2026 | 1 | 15.03.2026 |  |  | 0 | Inauguration is to be done | Not Started
MCL-0022 | B3 | East | 13 | B&R | MC Funds / General Quota | General | Others | Development of Badminton Court in Banda Bhadur Colony near Shamshanghat W No.13 | 7.92 | 7.74 |  |  | Approved inanticipation by W/Mayor vide dt 21.01.2026 & Regular approval by F&CC 2779 dt 19.02.2026 | 50 16.02.2026 | Sachdeva Art Gallery | 16.02.2026 | 1 | 15.03.2026 | 70 |  | 4.00 | Work is in Progress | In Progress
MCL-0023 | B4 | East | 21 | B&R | MC Funds / General Quota | General | Bituminous | Const.of bituminous road in GRD colony | 49.88 | 40.38 |  |  | 2522 dt 05.02.2026 | 52 16.02.2026 | Somaya Infrastructure | 16.02.2026 | 5 | 15.07.2026 |  |  | 0 | Work heldup due to upgradation of W/S lines | Not Started
MCL-0024 | B3 | East | 11 | B&R | MC Funds / General Quota | General | Park | Re-devlopment of New Shastri Nagar Park W No.11 | 4.7 | 4.33 |  |  | 2520 dt 05.02.2026 | 54 16.02.2026 | Teg Builders | 16.02.2026 | 3 | 15.05.2026 | 90 |  | 0 | Work is in Progress | In Progress
MCL-0025 | B4 | East | 19 | B&R | Councillor Quota (CQ) | Councillor | I/tiles | P/F Perforated I/tiles on side berms of GRD Colony W NO.19 | 24.53 | 17.08 |  |  | 2518 dt 05.02.2026 | 55 16.02.2026 | Navyug Company | 16.02.2026 | 3 | 15.05.2026 | 5 |  | 0 | Work heldup due to upgradation of sewerline. | In Progress
MCL-0026 |  | East |  | B&R | MDF / SASCI | Special Assistance Scheme | Bituminous | Upgradation of Gurudwara road urban estate phase 1&2 from Metro road to Jeewan Nagar chowk, Road along budha nallah from NHAI to MC limit , Main Bhadur Ke Road from Sabji Mandi upto MC Limit, Main New Azad Nagar 30' Road from Kainth Property Dealer upto Gaur Property Dealer and Roads of Onkar Vihar. | 535.05 | 517.66 |  |  | 2675 dt 11.02.2026 | 60 18.02.2026 | CH Builders Pvt. Ltd. | 18.02.2026 | 3 | 17.05.2026 | 10 |  | 0 | Work is in Progress | In Progress
MCL-0027 |  | East |  | B&R | MDF / SASCI | Special Assistance Scheme | Bituminous | Upgradation of Main Metro Road from Jamalpur Chowk to Kangaroo Industry, Jaswant Singh Dental College to Delhi road via Sethi Sweets, Internal Roads of Sec-39, Road from Primary Govt School to NRI Police Station in Sec-39, Main Jain Colony road from Rahon Road to Swastik Enclave and Main Road of Guru Arjun Dev Nagar from GT Road upto Greenland School, Sabji Mandi Road from Chd road to Puda road, EWS colony main road from Jacha Bacha Hospital upto Tajpur road. | 718.12 | 687.6 |  |  | 2873 dt 19.02.2026 | 61 20.02.2026 | Kabir Infra Pvt. Ltd. | 20.02.2026 | 3 | 19.05.2026 | 25 |  | 0 | Work is in Progress | In Progress
MCL-0028 | B2 | East | 20 | B&R | MC Funds / General Quota | General | Bituminous | Const.of bituminous road in Sukhdev Nagar | 49.95 | 40.43 |  |  | 2769 dt 19.02.2026 | 66 09.03.2026 | Somaya Infrastructure | 09.03.2026 | 5 | 08.08.2026 | 0 |  | 0 | Heldup due to non avaiability of Bitumen | Not Started
MCL-0029 | B3 | East | 7 | B&R | MC Funds / General Quota | General | I/tiles | P/F I/tiles in street No.5/1 to 5/6 & Links of New Subhash Nagar on Towerline No.5 W No.7 | 78.55 | 50.75 |  |  | 2771 dt 19.02.2026 | 67 09.03.2026 | Navyug Company | 09.03.2026 | 5 | 08.08.2026 | 50 |  | 0 | Work is in Progress | In Progress
MCL-0030 | B4 | East | 19 | B&R | Councillor Quota (CQ) | Councillor | Park | Renovation of remaining Parks in Sec-39 Block- II W No.19 | 97.59 | 67.67 |  |  | 2761 dt 19.02.2026 | 71 09.03.2026 | Apex Developers | 09.03.2026 | 5 | 08.08.2026 | 5 |  | 0 | Work is in Progress | In Progress
MCL-0031 | B3 | East | 12 | B&R | MC Funds / General Quota | General | Parks | Repair & Renovation of Sawtantar Nagar Park in W No.12 | 18.99 | 16.35 |  |  | 2878 dt 19.02.2026 | 72 09.03.2026 | Teg Builders & Varinder Singh Govt Contractor | 09.03.2026 | 3 | 08.06.2026 | 70 |  | 9.00 | Work is in Progress | In Progress
MCL-0032 | B3 | East | 13 | B&R | MC Funds / General Quota | General | Others | Development of Box Cricket in Banda Bhadur Colony near Shamshanghat W No.13 | 30.16 | 28.38 |  |  | 2760 dt 19.02.2026 | 75 09.03.2026 | Teg Builders & Varinder Singh Govt Contractor | 09.03.2026 | 4 | 08.07.2026 | 50 |  | 15.00 | Work is in Progress | In Progress
MCL-0033 | B3 | East | 13 | B&R | MC Funds / General Quota | General | Others | Construction of Entrance Gates for Karamsar Colony & Sutantar Nagar in w no.13. | 26.34 | 25.58 |  |  | 2791dt 19.02.2026 | 76 09.03.2026 | Teg Builders & Varinder Singh Govt Contractor | 09.03.2026 | 4 | 08.07.2026 |  |  | 0 | Inauguration is to be done | Not Started
MCL-0034 | B3 | East | 13 | B&R | Councillor Quota (CQ) | Councillor | I/tiles | P/Fixing I/tiles in Karamsar Colony & Nalwa Coloiny W No.13 | 83.89 | 52.86 |  |  | 2770 dt 19.02.2026 | 77 12.03.2026 | Apex Developers | 12.03.2026 | 4 | 11.07.2026 | 20 |  | 0 | Work is in Progress | In Progress
MCL-0035 | B3 | East | 13 | B&R | Councillor Quota (CQ) | Councillor | I/tiles | P/Fixing I/tiles in streets of Grewal Colony & Raju Colony W No.13 | 49.53 | 43.64 |  |  | 3436 dt 21.04.2026 | 09 13.05.2026 | Teg Builders | 13.05.2026 | 4 | 12.09.2026 |  |  | 0 | Inauguration is to be done | Not Started
MCL-0036 | B3 | East | 13 | B&R | Councillor Quota (CQ) | Councillor | I/tiles | P/Fixing I/tiles in streets of Heera Vihar & Sutantar Nagar W No.13 | 49.8 | 43.88 |  |  | 3435 dt 21.04.2026 | 10 13.05.2026 | Varinder Singh Govt Contractor | 13.05.2026 | 4 | 12.09.2026 | 25 |  | 0 | Work is in Progress | In Progress
MCL-0037 | B4 | East | 19 | B&R | MC Funds / General Quota | General | RMC | Laying RMC in streets of New Kirti Nagar W No.19 | 18.07 | 15.2 |  |  | 3434 dt 21.04.2026 | 11 13.05.2026 | Teg Builders | 13.05.2026 | 3 | 12.08.2026 | 25 |  | 0 | Work is in Progress | In Progress
MCL-0038 | B4 | East | 28 | B&R | Councillor Quota (CQ) | Councillor | I/tiles | P/F I/tiles in street of Saini Colony W No.28 | 88.68 | 63.06 |  |  | 3433 dt 21.04.2026 | 12 13.05.2026 | Teg Builders | 13.05.2026 | 5 | 12.10.2026 |  |  | 0 | Work heldup due to W/s Line | Not Started
MCL-0039 | B4 | East | 19 | B&R | MC Funds / General Quota | General | Others | Const of RCC Boundary wall adj GRD Colony Sec-39 W No.19 | 24.65 | 23.5 |  |  | 3432 dt 21.04.2026 | 13 13.05.2026 | Varinder Singh Govt Contractor | 13.05.2026 | 3 | 12.08.2026 | 10 |  | 0 | Work is in Progress | In Progress
MCL-0040 | B4 | East | 28 | B&R | Councillor Quota (CQ) | Councillor | Bituminous | Const.of bituminous road of Moti Nagar Block-C W No.28 | 65.52 | 62.24 |  |  | 3431 dt 21.04.2026 | 14 13.05.2026 | Shiva Construction | 13.05.2026 | 5 | 12.10.2026 |  |  | 0 | Inauguration is to be done | Not Started
MCL-0041 | B3 | East | 13 | B&R | MC Funds / General Quota | General | I/tiles | P/Fixing I/tiles in left side streets of Banda Singh Bhadur Colony W No.13 | 88.4 | 53.05 |  |  | 3429 dt 21.04.2026 | 16 13.05.2026 | Varinder Singh Govt Contractor | 13.05.2026 | 6 | 12.11.2026 | 10 |  | 0 | Work is in Progress | In Progress
MCL-0042 | B3 | East | 13 | B&R | MC Funds / General Quota | General | I/tiles | P/Fixing I/tiles in right side streets of Banda Singh Bhadur Colony W No.13 | 68.69 | 41.22 |  |  | 3428 dt 21.04.2026 | 17 13.05.2026 | Varinder Singh Govt Contractor | 13.05.2026 | 5 | 12.10.2026 |  |  | 0 | Inauguration is to be done | Not Started
MCL-0043 | B3 | East | 13 | B&R | MC Funds / General Quota | General | I/tiles | P/Fixing I/tiles in various Streets of juneja colony W No.13 | 76.4 | 54.52 |  |  | 3427 dt 21.04.2026 | 18 13.05.2026 | Varinder Singh Govt Contractor | 13.05.2026 | 5 | 12.10.2026 |  |  | 0 | Inauguration is to be done | Not Started
MCL-0044 | B2 | East | 20 | B&R | MC Funds / General Quota | General | Bituminous | Const.of bituminous road Guru Nanak Nagar Bhamian 27' Road | 35.74 | 32.76 |  |  | Approved by W/Mayor dt 14.05.2026 inanticipation of F&CC, | 23 27.05.2026 | Shiva Construction | 27.05.2026 | 5 | 26.10.2026 | 80 |  | 0 | Work is in Progress | In Progress
MCL-0045 | B4 | Sahnewal | 28 | B&R | MC Funds / General Quota | General | RMC | Const of road by laying RMC (M-30) in Ishwar colony W No.28 | 52 | 30.34 |  |  | 3205 29.11.2024 | 75 dt 04.12.2024 | Capital Const Co. | 04.12.2024 | 4 | 03.05.2025 | 0 |  | 0 | Heldup due to non laying of Sewerline | Not Started
MCL-0046 | B4 | Sahnewal | 28 | B&R | MC Funds / General Quota | General | I/tiles | P/F 80mm thick I/Tiles in Balance streets of Prem Nagar & New Durga Colony W No.28 | 71.89 | 41.06 |  |  | 361 dt 26.03.2025 | 15 16.04.2025 | T&G Const Co. | 16.04.2025 | 5 | 15.09.2025 | 50 |  | 20.66 | Work was heldup due to upgradation of W/S Line, now same has been laid. Work is in Progress | In Progress
MCL-0047 | B4 | Sahnewal | 24 | B&R | MC Funds / General Quota | General | Park | Re-Development of Main Jeevan Nagar Park W No.24 | 26.72 | 18.6 |  |  | 186 dt 26.03.2025 | 16 16.04.2025 | Asis Builders | 16.04.2025 | 3 | 15.07.2025 | 80 |  | 17.46 | Work is in Progress | In Progress
MCL-0048 | B4 | Sahnewal | 28 | B&R | MC Funds / General Quota | General | Park | Re-Development of Park Backside Gov.Sen.Sec School Dhandari Khurd Ludhiana W No.28 | 25.74 | 16.99 |  |  | 188 dt 26.03.2025 | 17 16.04.2025 | Apex Developers | 16.04.2025 | 3 | 15.07.2025 | 70 |  | 8.77 | Work is in Progress | In Progress
MCL-0049 | B2 | Sahnewal | 22 | B&R | MC Funds / General Quota | General | I/tiles | P/F I/tiles in streets of Jyoti Colony | 23.07 | 15 |  |  | 1670 dt 13.10.2025 | 26 15.01.2026 | Capital Const Co. | 15.01.2026 | 2 | 14.03.2026 | 5 |  | 0 | Work is in Progress | In Progress
MCL-0050 | B2 | Sahnewal | 22 | B&R | MC Funds / General Quota | General | Park | Renovation of Tikoni park | 15.02 | 11.27 |  |  | 2524 dt 05.02.2026 | 57 16.02.2026 | Varinder Singh Govt Contractor and Maa Chintpurni Const | 16.02.2026 | 3 | 15.05.2026 |  |  | 0 | Inauguration is to be done | Not Started
MCL-0051 | B4 | Sahnewal | 21 | B&R | MC Funds / General Quota | General | Park | Renovation of park in Urban Estate Phase-II on Chd Road | 105.91 | 69.79 |  |  | 2582 dt 11.02.2026 | 59 16.02.2026 | Ram Parkash Kakkar | 16.02.2026 | 6 | 15.08.2026 | 30 |  | 0 | Work is in Progress | In Progress
MCL-0052 | B2 | Sahnewal | 22 | B&R | Councillor Quota (CQ) | Councillor | RMC | Laying RMC in streets of Village Kuliewal W No.22 | 86.8 | 53.21 |  |  | 2763 dt 19.02.2026 | 74 09.03.2026 | KS Constructions | 09.03.2026 | 5 | 08.08.2026 | 30 |  | 0 | Heldup due to non laying of W/s line | In Progress
MCL-0053 | B2 | Sahnewal | 22 | B&R | Councillor Quota (CQ) | Councillor | RMC | Laying RMC in streets of Jamalpur Awana W No.22 | 69.91 | 41.95 |  |  | 2762 dt 19.02.2026 | 78 12.03.2026 | Apex Developers | 12.03.2026 | 5 | 11.08.2026 | 45 |  | 0 | Work is in Progress | In Progress
MCL-0054 | B2 | Sahnewal | 24 | B&R | MC Funds / General Quota | General | Bituminous | Const of Bituminous roads in GK Estate main Road | 117.76 | 111.87 |  |  | 3309, dt 25.02.2026 | 80 20.03.2026 | CH Builders Pvt. Ltd. | 20.03.2026 | 6 | 19.09.2026 | 15 |  | 0 | Work is in Progress | In Progress
MCL-0055 | B4 | Sahnewal | 25 | B&R | MC Funds / General Quota | General | I/tiles | P/F 80mm thick I/Tiles in Shiv colony | 112.48 | 65.55 |  |  | 3324 dt 25.02.2026 | 85 24.03.2026 | T&G Const Co. | 24.03.2026 | 6 | 23.09.2026 | 40 |  | 26.2 | Work is in Progress | In Progress
MCL-0056 | B4 | Sahnewal | 21 | B&R | MC Funds / General Quota | General | Bituminous | Const of Bituminous Road of Jeewan Nagar & Guru Bag Colony Main Road of W No.21 | 48.52 | 45.95 |  |  | 3438 dt 21.04.2026 | 20 13.05.2026 | Maruti Const Co. | 13.05.2026 | 4 | 12.09.2026 |  |  | 0 | Inauguration to be done | Not Started
MCL-0057 | B4 | Sahnewal | 21 | B&R | Councillor Quota (CQ) | Councillor | Parks | Renovation and Development of various parks Urban Estate Phase-II, Jamalpur of W No.21 | 78.46 | 58.92 |  |  | 3437 dt 21.04.2026 | 21 13.05.2026 | Ram Parkash Kakkar | 13.05.2026 | 5 | 12.10.2026 |  |  | 0 | Inauguration to be done | Not Started
MCL-0058 | B2 | Sahnewal | 24 | B&R | MC Funds / General Quota | General | Bituminous | Const of Bituminous Road from Chandigarh Road to GTB Nagar Near Jassal Factory | 15.02 | 13.77 |  |  | Approved by W/Mayor dt 14.05.2026 inanticipation of F&CC, workorder to be issued | 24 27.05.2026 | Shiva Construction | 27.05.2026 | 3 | 26.08.2026 | 10 |  | 0 | Work is in Progress | In Progress
MCL-0059 | B2 | Sahnewal | 22 | B&R | MC Funds / General Quota | General | RMC | P/L RMC(M-30) in Streets of Bank Colony W. No. 22 | 65.95 | 40.43 |  |  | Approved by W/Mayor dt 14.05.2026 inanticipation of F&CC, | 25 27.05.2026 | LRY Labour Contractor | 27.05.2026 | 6 | 26.11.2026 |  |  | 0 | Inauguration to be done | Not Started
MCL-0060 | B4 | Sahnewal | 21 | B&R | MC Funds / General Quota | General | Bituminous | Const of Bituminous Road of Guru Bag Colony W No.21 | 99.8 | 82.56 |  |  | Approved by W/ Mayor dt 28.05.2026 inanticipation approval by F&CC | 26 01.06.2026 | Rajesh Kumar Sood | 01.06.2026 | 5 | 30.11.2026 | 5 |  | 0 | Just Started | In Progress
MCL-0061 | B3 | East | 17 | B&R | MC Funds / General Quota | General | RMC | Laying RMC from Main Tibba road upto Mahavir Jain Colony W No.17 | 114.55 | 76.75 |  |  | Inanticipation approval by W Mayor dt 16.06.2026 | 27 19.06.2026 | Capital const Co. | 19.06.2026 | 6 | 18.12.2026 |  |  | 0 | Heldup due to laying of Sewerline | Not Started
MCL-0062 | B4 | Sahnewal | 28 | B&R | MDF / SASCI | MDF | RMC | Const of Road by laying RMC in Prem Nagar W No.28 | 191.52 | 128.57 |  |  | 1005 13.10.2023 | 23 dt 20.10.2023 | M/s Capital Const Co. | 20.10.2023 | 6 | 19.04.2024 | 55 |  | 45.64 | Work heldup due to upgradation of W/s & Sewer lines in the balance streets | In Progress
MCL-0063 | B4 | Sahnewal | 28 | B&R | MDF / SASCI | MDF | RMC | Laying RMC in street of New Durga Colony W No.28 | 196.63 | 180.8 |  |  | 1321 20.11.2023 | 44A & 44B dt 20.11.2023 | M/s Glisten and Ashok Kumar Sobti (50%-50% allotted) | 20.11.2023 | 6 | 19.05.2024 | 55 |  | 40.48 | Work heldup due to upgradation of W/s lines in the balance streets | In Progress
MCL-0064 | B3 | East | 15 | B&R | MDF / SASCI | MDF | Bitumionus | Const of Bituminous Road on Mata Karam Kaur Road W No.15 | 25 | 24.62 |  |  | 1324 20.11.2023 | 47 dt 20.11.2023 | Shiva Construction | 20.11.2023 | 3 | 19.02.2024 | 20 |  | 0 | Work is in Progress | In Progress
MCL-0065 | B4 | East | Focal Point | B&R | MDF / SASCI | 50%MDF &50%MC | Parks | Development of Green Belt along Surpal cycle Road Phase-I Focal Point | 146.06 | 119.48 |  |  | 3307, dt 25.02.2026 | 01 10.04.2026 | Navyug Company | 10.04.2026 | 6 | 9.10.2026 | 10 |  | 0 | Work is in Progress | In Progress
MCL-0066 | B4 | East | Focal Point | B&R | MDF / SASCI | 50%MDF &50%MC | Parks | Const of Green Belt on Sanatan Dharam Mandir Road Phase-III Focal Point Ludhiana | 79.02 | 53.58 |  |  | 2481 dt 05.01.2026 | 40 15.01.2026 | Ram Parkash Kakkar | 15.01.2026 | 4 | 14.07.2026 | 20 |  | 0 | Work is in Progress | In Progress
MCL-0067 | B4 | East | Focal Point | B&R | MDF / SASCI | 50%MDF &50%MC | Parks | Re-Development of Green Belts & Parks near E-76 to E-92, E-93 to E-106, E-107 to E-145 & E-21, E-173 & E-190 in Phase-IV Focal Point Ludhiana | 99.85 | 71.9 |  |  | 2482 dt 05.01.2026 | 41 15.01.2026 | Apex Developers | 15.01.2026 | 5 | 14.07.2026 | 5 |  | 0 | Work is in Progress | In Progress
MCL-0068 | B4 | East | Focal Point | B&R | MDF / SASCI | 50%MDF &50%MC | RMC | Laying RMC along Kangaroo Industry & Upgradation of Junction Near BJ Computer Kanda on Metro Road Phase-IV Focal Point Ludhiana | 117.69 | 73.2 |  |  | 2773 dt 19.02.2026 | 02 10.04.2026 | LRY Labour Contractor | 10.04.2026 | 5 | 09.10.2026 | 80 |  | 0 | Work is in Progress | In Progress
MCL-0069 | B4 | Sahnewal | Focal Point | B&R | MDF / SASCI | 50%MDF &50%MC | RMC | Const of road by laying RMC from Rishi Raj D-40 to Udehra Mechanical Works and other various locations in Focal Point Phase V, Ludhiana . | 151.9 | 94.48 |  |  | 2775 dt 19.02.2026 | 03 10.04.2026 | LRY Labour Contractor | 10.04.2026 | 6 | 09.10.2026 | 10 |  | 0 | Work is in Progress | In Progress
MCL-0070 | B4 | Sahnewal | Focal Point | B&R | MDF / SASCI | 50%MDF &50%MC | Bituminous | Widening of Road from Jeewan Nagar Chowk upto Junction of Akal Spring Road, Phase-V and laying RMC in links between C-215 & C-216 near Dainik Jagran Road and Rectification of level at various Junctions in Focal Point, Ludhiana. | 169.46 | 105.4 |  |  | 2772 dt 19.02.2026 | 04 10.04.2026 | LRY Labour Contractor | 10.04.2026 | 6 | 09.10.2026 | 20 |  | 0 | Work is in Progress | In Progress
MCL-0071 | B4 | Sahnewal | Focal Point | B&R | MDF / SASCI | 50%MDF &50%MC | Parks | Development of Green Belt From Jeewan Nagar Road to Rotar Kanda Phase-V Focal Point Ludhiana (Park No.1,2,3, 4,5 & 6) | 173.65 | 135.64 |  |  | 2774 dt 19.02.2026 | 62 09.03.2026 | Navyug Co. | 09.03.2026 | 7 | 08.10.2026 | 5 |  | 0 | Work is in Progress | In Progress
MCL-0072 | B4 | Sahnewal | Focal Point | B&R | MDF / SASCI | 50%MDF &50%MC | Parks | Re-Development of Green Belts & Parks near D-119, C-207 C-82, B-37, D-42 D-51 & D-70 in Phase-V Focal Point Ludhiana (Park No.12,13,15,18,21 & 22) | 215.85 | 175.21 |  |  | 3305, dt 25.02.2026 | 05 10.04.2026 | Navyug Company | 10.04.2026 | 6 | 09.10.2026 | 5 |  | 0 | Work is in Progress | In Progress
MCL-0073 | B4 | Sahnewal | Focal Point | B&R | MDF / SASCI | 50%MDF &50%MC | Parks | Re-Development of Green Belts & Parks near D-190d, E-362 & E-393 in Phase-VI Focal Point Ludhiana (Park No.9,10,11 & 12) | 99.41 | 68 |  |  | 2483 dt 05.01.2026 | 42 15.01.2026 | Ram Parkash Kakkar | 15.01.2026 | 4 | 14.07.2026 | 5 |  | 0 | Work is in Progress | In Progress
MCL-0074 | B4 | Sahnewal | Focal Point | B&R | MDF / SASCI | 50%MDF &50%MC | Parks | Re-Development of Green Belts & Parks near E-581, E-626 & C-202A in Phase-VII Focal Point Ludhiana (Park No.2 & 3) | 198.84 | 159.89 |  |  | 2777 dt 19.02.2026 | 79 12.03.2026 | RK Const Co. | 12.03.2026 | 8 | 11.10.2026 | 65 |  | 66.25 | Work is in Progress | In Progress
MCL-0075 | B4 | Sahnewal | Focal Point | B&R | MDF / SASCI | 50%MDF &50%MC | Bituminous | Const of mettaled Road Opp ESI Dispensery Phase - V and Residential pocket Phase VIII Focal Point, Ludhiana. | 147.05 | 103.67 |  |  | 2776 dt 19.02.2026 | 06 10.04.2026 | Somaya Infrastructures | 10.04.2026 | 6 | 09.10.2026 | 80 |  | 73.46 | Work is in Progress | In Progress
MCL-0076 | B4 | Sahnewal | Focal Point | B&R | MDF / SASCI | 50%MDF &50%MC | Parks | Re-Development of Parks near C-246, C-256, 164 & 241 & Residential Pocket in Phase-VIII (Park No.2,3,6 & 9) & Parks in 34 Acre Scheme Focal Point Ludhiana (Park No.2) | 113.02 | 102.85 |  |  | 3308, dt 25.02.2026 | 07 10.04.2026 | Ashok Kumar Sobti | 10.04.2026 | 8 | 09.10.2026 | 5 |  | 0 | Work is in Progress | In Progress
MCL-0077 | B4 | Sahnewal | Focal Point | B&R | SIDBI | SIDBI | Bitumen | Const of Various Bituminous Roads in Phase - V & VII Focal Point Ludhiana (Roter Kanda towards Jiwan Nagar Chown, Disposal Rd.and E-654) & (E-773 to E-778 and Roter Kanda Rd to Fortis Hospital Chd Rd) | 158.55 | 147.15 |  |  | 3439 dt 21.04.2026 | 08 13.05.2026 | Maruti Const Co. | 08 13.05.2026 | 6 |  | 15 |  | 0 | Work is in Progress | In Progress
MCL-0078 | B4 | Sahnewal | Focal Point | B&R | SIDBI | SIDBI | RMC | Const of Various Roads by laying RMC(M-40) in Phase-V,VI,VII & VIII Focal Point Ludhiana (Satya Industry Phase 5, D-51 to D-58 )(A13E & A13A) (Opp. RCJ Auto Forge E-756 and C-202 A to C-203 C(E-701 to E-706 | 136.09 | 78.95 |  |  | 1484 dt 13.10.2025 | 30 15.01.2026 | Apex Developers | 30 15.01.2026 | 6 | 14.07.2026 | 45 |  | 34.43 | Work is in Progress | In Progress
MCL-0079 | B4 | East | Focal Point | B&R | SIDBI | SIDBI | Parks | Development of various Parks in Phase-I Focal Point (OPP Kay Jay Forjing and Opp E-2) | 53.25 | 37.87 |  |  | 2486 dt 05.01.2026 | 34 15.01.2026 | Teg Builders | 34 15.01.2026 | 5 | 14.06.2026 | 60 |  | 0 | Work is in Progress | In Progress
MCL-0080 | B4 | East | Focal Point | B&R | SIDBI | SIDBI | Parks | Development of various Parks in Phase-IV Focal Point (OPP E-90 and Opp E-132) | 78.08 | 55.52 |  |  | 2485 dt 05.01.2026 | 35 15.01.2026 | Teg Builders | 35 15.01.2026 | 5 | 14.06.2026 | 90 |  | 40.34 | Work is in Progress | In Progress
MCL-0081 | B4 | East | Focal Point | B&R | SIDBI | SIDBI | Parks | Development of various Parks in Phase-IVA Focal Point (Opp D-145, Opp D-148 and Opp D-152) | 8.05 | 6.34 |  |  | 2263, dt 21.11.2025 | 29 15.01.2026 | Varinder Singh Contractor | 29 15.01.2026 | 3 | 14.05.2026 | 80 |  | 0 | Work is in Progress | In Progress
MCL-0082 | B4 | Sahnewal | Focal Point | B&R | SIDBI | SIDBI | Parks | Construction of Various Parks of Focal Point Phase-V , Ludhiana (D-114, C-86,B-37, C-115, D-130) | 217.72 | 156.54 |  |  | 2484 dt 05.01.2026 | 36 15.01.2026 | RK Const Co. | 36 15.01.2026 | 6 | 14.07.2026 | 30 |  | 35.75 | Work is in Progress | In Progress
MCL-0083 | B4 | Sahnewal | Focal Point | B&R | SIDBI | SIDBI | Parks | Construction of Various Parks of Focal Point Phase-VI , Ludhiana (Park No.1,2,4,6,7 & 8) | 348.82 | 285.33 |  |  | 2487 dt 05.01.2026 | 37 15.01.2026 | Navyug Company | 37 15.01.2026 | 6 | 14.07.2026 | 5 |  | 0 | Work is in Progress | In Progress
MCL-0084 | B4 | Sahnewal | Focal Point | B&R | SIDBI | SIDBI | Parks | Construction of Various Parks of Focal Point Phase-VII Ludhiana (Park No.2,3,4,5 & 6) | 123.11 | 87.42 |  |  | 2492 dt 05.01.2026 | 38 15.01.2026 | RK Const Co. | 38 15.01.2026 | 6 | 14.07.2026 | 25 |  | 19.95 | Work is in Progress | In Progress
MCL-0085 | B4 | Sahnewal | Focal Point | B&R | SIDBI | SIDBI | Parks | Development of various Parks in Phase-VIII Focal Point (Adj F-170 & F171,Adj F-155 & F156 , Adj F-179 & F176, Adj F-194 & F195 and Opp F-251) | 168.7 | 129.04 |  |  | 2489 dt 05.01.2026 | 39 15.01.2026 | KS Constructions | 39 15.01.2026 | 6 | 14.07.2026 | 30 |  | 0 | Work is in Progress | In Progress
MCL-0086 | B4 | Sahnewal | Focal Point | B&R | SIDBI | SIDBI | Parks | Repair & Renovation of various Parks in 34 Acre Scheme Focal Point (Park Opp F-309, Opp K-312) | 25.32 | 17.4 |  |  | 2172 dt 13.10.2025 | 31 15.01.2026 | Varinder Singh Contractor | 31 15.01.2026 | 4 | 14.05.2026 | 90 |  | 15.99 | Work is in Progress | In Progress
MCL-0087 | A1 | Central | 83 | B&R | MC Funds / General Quota | MC Funds |  | Construction Of Retaining Wall And Road Along Budha Nallah From Madhopuri Pulli To Sunder Nagar Pulli, Ludhiana. | 366.48 | 301.02 | 301.02 |  | 931 dt. 06-05-2025 | 88/EEA dt. 15-05-2025 | Gaaneshkartikey Construction Pvt. Ltd. | 15-05-2025 | 18 months | 14-11-2026 | 60 |  | 90 | Work delayed due to shortage of bitumen. Notice issue to Contractor | Delayed/Held Up
MCL-0088 | A1 | Central | 9 & 10 | B&R | MC Funds / General Quota | MC Funds |  | Construction of Main 70' Road Sunder Nagar in w.no.8 & 58. | 57.19 | 42.89 | 42.89 |  | 102 dt. 26-03-2025 | 83/EEA dt. 21-04-2025 | M/s C.H Builders Pvt. Ltd. | 21-04-2025 | 6 months | 22-10-2025 | 0 |  | NIL | Work delayed due to shortage of bitumen. Final Notice issued to Contractor | Delayed/Held Up
MCL-0089 | B1 | Central | 81 | B&R | MC Funds / General Quota | MC Funds |  | Repair and Maintenance of Zone-B Main Building of Municipal Corporation Ludhiana. | 123.69 | 97.55 | 97.55 |  | 124 dt. 26-03-2025 | 91/EEA dt. 15-05-2025 | Teg Builders (Govt. Contractor) | 15-05-2025 | 6 months | 16-10-2025 | 95 |  | 86.12 | Revised est. has been prepared due to increase of electrical item, sanitation items. | In Progress
MCL-0090 | A1 | Central | 83 & 85 | B&R | MC Funds / General Quota | MC Funds |  | Laying RMC M-30 in various streets in vakilla Mohalla & Krishana Gali in ward no.59 & 61.(New w.no. 83 & 85) | 25.19 | 13.96 | 13.96 |  | Tender F&CC Reso.no. 97 dt. 26-03-2025 | 94/EEA dt. 01-08-2025 | Capital Construction Co. | 01-08-2025 | 6 months | 02-01-2026 | 75 |  | 8.36 | Work in progress | In Progress
MCL-0091 | B1 | Central | 76 | B&R | MC Funds / General Quota | MC Funds |  | Laying 30mm thick SDBC Kucha no.16 adjoining Janj Ghar w.no.63. (New w.no.76) | 20.32 | 13.18 | 13.18 |  | Tender F&CC Reso.no. 100 dt. 26-03-2025 | 95/EEA dt. 01-08-2025 | Capital Construction Co. | 01-08-2025 | 6 months | 02-01-2026 | 10 |  | NIL | Work delayed due to shortage of bitumen. | Delayed/Held Up
MCL-0092 | C | Central | 74 | B&R | MC Funds / General Quota | MC Funds |  | Laying BM&PC on various streets of Industrial Area B adjoining overlock road in w.no.51. | 175.23 | 110.39 | 110.39 |  | Tender F&CC Reso.no. 761 dt. 09-04-2025 | 101/EEA dt. 01-08-2025 | Hitesh Aggarwal Cont. | 01-08-2025 | 6 months | 02-01-2026 | 10 |  | NIL | Work delayed due to shortage of bitumen. | Delayed/Held Up
MCL-0093 | A2 | Central | 78 | B&R | MC Funds / General Quota | MC Funds |  | Renovation of various parks in ward no. 78, Ludhiana. | 37.41 | 29.55 | 29.55 |  | Tender F&CC reso.no. 1821 dt. 13-10-2025 | 103/EEA dt. 19-11-2025 | M/s Dynamic tiles | 19-11-2025 | 6 months | 20-06-2026 | 50 |  | NIL | The work of one park has been completed balance work in progress Notice issued to contractor | In Progress
MCL-0094 | B1 | Central | 80 | B&R | MC Funds / General Quota | MC Funds |  | Laying SDBC in streets of Janakpuri Part-I in w.no.80. | 39.89 | 36.81 | 36.81 |  | Tender F&CC reso.no. 2147 dt. 13-10-2025 | 105/EEA dt. 19-11-2025 | M/s Soham Construction Company | 19-11-2025 | 6 months | 20-06-2026 | 0 |  | NIL | Work delayed due to shortage of bitumen. | Delayed/Held Up
MCL-0095 | A1 | Central | 9 | B&R | MC Funds / General Quota | MC Funds |  | Construction of New Toilets and Repair & Renovation of Sunder Nagar Fire Station. | 24.33 | 19.32 | 19.32 |  | Tender F&CC reso.no. 1811 dt. 13-10-2025 | 106/EEA dt. 19-11-2025 | M/s Prince Sharma | 19-11-2025 | 6 months | 20-06-2026 | 60 |  | 12.61 | Work will be completed 30-07-2026 Work in progress | In Progress
MCL-0096 | A2 | Central | 78 | B&R | MC Funds / General Quota | MC Funds |  | Laying RMC M30 In Streets No.1,2,3,4 & Links of Mohar Singh Nagar, W.No.78, Ludhiana. | 93.11 | 53.35 | 53.35 |  | Tender F&CC reso.no. 1823 dt. 13-10-2025 | 108/EEA dt. 19-11-2025 | K.S Constructions | 19-11-2025 | 6 months | 20-06-2026 | 80 |  | 50.7 | Work delayed due to laying Water supply line by O&M Cell. | Delayed/Held Up
MCL-0097 | A1 | Central | 10 | B&R | MC Funds / General Quota | MC Funds |  | Laying RMC in street of Mohalla New Madho Puri in w.no.58 (New w.no.10) Part-II. | 83.72 | 47.97 | 47.97 |  | Tender F&CC reso.no. 1819 dt. 13-10-2025 | 110/EEA dt. 19-11-2025 | K.S Constructions | 19-11-2025 | 7 months | 20-05-2026 | 60 |  | 18.75 | Work in progress | In Progress
MCL-0098 | A1 | Central | 83 | B&R | MC Funds / General Quota | GQ |  | Laying RMC M-30 in street of Mohalla Mehmoodpura in w.no.61. (New w.no.83) | 71.84 | 41.16 | 41.16 |  | Tender F&CC reso.no. 1814 dt. 13-10-2025 | 111/EEA dt. 19-11-2025 | K.S. Constructions | 19-11-2025 | 6 months | 20-05-2026 | 30 |  | 7.89 | Work in progress | In Progress
MCL-0099 | B1 | Central | 81 | B&R | MC Funds / General Quota | MC Funds |  | Laying RMC M-30 in streets of Harcharan Nagar in w.no.57. | 56.74 | 30.88 | 30.88 |  | Tender F&CC reso.no.758 dt. 09-04-2025 | 114/EEA dt.19-11-2025 | Varinder Singh Govt. Contractor | 19-11-2025 | 4 months | 20-02-2026 | 10 |  | NIL | Work stopped due to upgradation of water supply line. | Delayed/Held Up
MCL-0100 | A2 | Central | 82 | B&R | MC Funds / General Quota | MC Funds |  | P/F 60/80mm I/Tiles on RMC in Streets of Dhoka Mohalla, Ludhiana. (Rs. 33,89,445.15 Only (1/2 of total Tender Cost: 67,78,890.30) ) | 121.03 | 67.78 | 67.78 |  | Tender F&CC reso.no. 1795 dt. 13-10-2025 | 115/EEA dt.19-11-2025 & 116/EEA dt.19-11-2025 | M/s Apex Devlopers & M/s K.S. Constructions | 19-11-2025 | 7 months | 20-05-2026 | 40 |  | 13.72 | Work delayed due to laying Water supply line by O&M Cell. | Delayed/Held Up
MCL-0101 | A1 | Central | 83 | B&R | MC Funds / General Quota | MC Funds |  | Laying RMC M-30 in street of Bharam Puri in w.no.83. | 24.93 | 14.19 | 14.19 |  | Tender F&CC reso.no. 2153 dt. 13-10-2025 | 124/EEA dt.18-02-2026 | Godwyn Infra | 18-02-2026 | 6 months | 17-07-2026 | 0 |  | NIL | Work not started Notice issued | Not Started
MCL-0102 | A2 | Central | 78 | B&R | MC Funds / General Quota | GQ |  | Laying RMC M30 In Streets No. 5,6 & Links of Mohar Singh Nagar, W.No.78, Ludhiana. | 73.03 | 42.13 | 42.13 |  | Tender F&CC reso.no. 1809 dt. 13-10-2025 | 127/EEA dt.18-02-2026 | LRY Labour Contractor | 18-02-2026 | 6 months | 17-07-2026 | 40 |  | NIL | Work delayed due to laying Water supply line by O&M Cell. | Delayed/Held Up
MCL-0103 | A2 | Central | 78 | B&R | Councillor Quota (CQ) | CQ |  | Laying RMC M30 In Streets No.7, 8 & Links of Mohar Singh Nagar, W.No.78, Ludhiana. | 99.68 | 57.51 | 57.51 |  | Tender F&CC reso.no. 1890 dt. 13-10-2025 | 128/EEA dt.18-02-2026 | LRY Labour Contractor | 18-02-2026 | 6 months | 17-07-2026 | 20 |  | NIL | Work delayed due to laying Water supply line by O&M Cell. | Delayed/Held Up
MCL-0104 | A1 | Central | 85 | B&R | MC Funds / General Quota | GQ |  | Repair & Renovation of Sub Zone-A1 Office at Daresi. W. No. 85. | 35.53 | 28.42 | 28.42 |  | Tender F&CC reso.no. 3266 dt. 25-02-2026 | 131/EEA dt.18-03-2026 & 132/EEA dt.18-03-2026 | The Sobha Gram Co Operative Labour and Construction Society Ltd. & Apex Devlopers | 18-03-2026 | 7 months | 17-09-2026 | 10 |  | NIL | Work in progress | In Progress
MCL-0105 | B1 | Central | 75 | B&R | MC Funds / General Quota | GQ |  | Laying 30mm thick SDBC on Kidwai Nagar Main Road & Road from Suffian Chowk to Janakpuri in w.no.75. | 38.33 | 34.11 | 34.11 |  | Tender F&CC reso.no. 3263 dt. 25-02-2026 | 133/EEA dt. 18-03-2026 | Capital Construction Co. | 18-03-2026 | 6 months | 17-08-2026 | 10 |  | NIL | Work delayed due to shortage of bitumen. | Delayed/Held Up
MCL-0106 | A1 | Central | 83 | B&R | MC Funds / General Quota | GQ |  | Laying RMC M-30 in St.no.1 Madhopuri & Links in w.no.83. | 46.89 | 25.79 | 25.79 |  | Tender F&CC reso.no. 3267 dt. 25-02-2026 | 135/EEA dt. 18-03-2026 | N.S. Infra | 18-03-2026 | 6 months | 17-08-2026 | 0 |  | NIL | Inaguration pending | Delayed/Held Up
MCL-0107 | A1 | Central | 83 | B&R | Councillor Quota (CQ) | CQ |  | Laying RMC M-30 in street of Ghati Mohalla in ward no. 83. | 11.4 | 6.72 | 6.72 |  | Tender F&CC reso.no. 3265 dt. 25-02-2026 | 137/EEA dt. 18-03-2026 | K.S. Constructions | 18-03-2026 | 6 months | 17-08-2026 | 10 |  | NIL | Work stopped due to laying of water supply line. | Delayed/Held Up
MCL-0108 | A2 | Central | 82 | B&R | Councillor Quota (CQ) | CQ |  | Laying RMC M-30 in street of Mohalla Taj Ganj in ward no.82. | 24.65 | 13.97 | 13.97 |  | Tender F&CC reso.no. 3264 dt. 25-02-2026 | 139/EEA dt. 18-03-2026 | K.S. Constructions | 18-03-2026 | 3 months | 17-05-2026 | 20 |  | NIL | Work in progress Work will be completed within 20 days. | In Progress
MCL-0109 | A2 | Central | 75 | B&R | Councillor Quota (CQ) | CQ |  | Laying RMC (M-30) in various streets of ward no.75. | 63.32 | 34.74 | 34.74 |  | Tender F&CC reso.no. 3268 dt. 25-02-2026 | 141/EEA dt. 18-03-2026 | K.S. Constructions | 18-03-2026 | 6 months | 17-08-2026 | 65 |  | 14.62 | Work in progress | In Progress
MCL-0110 | A2 | Central | 78 | B&R | MC Funds / General Quota | GQ |  | Re-Development of Children Friendly Park on Old Jail Road, Ludhiana. | 66.68 | 42.68 | 42.68 |  | Tender F&CC reso.no. 2788 dt. 19-02-2026 | 142/EEA dt. 18-03-2026 | Navdeep Gupta and Company | 18-03-2026 | 6 months | 17-08-2026 | 40 |  | NIL | Repair work of Satpal prasher park has been completed work in progress. | In Progress
MCL-0111 | B1 | Central | 80 | B&R | MC Funds / General Quota | GQ |  | Laying RMC M-30 in St.no.1,2,3 & 4 of Janakpuri w.no.80. | 69.55 | 37.89 | 37.89 |  | Tender F&CC reso.no. 2794 dt. 19-02-2026 | 143/EEA dt. 18-03-2026 | Vansh Engineers | 18-03-2026 | 7 months | 17-09-2026 | 0 |  | NIL | Inaguration pending | Delayed/Held Up
MCL-0112 | A2 | Central | 77 | B&R | MDF / SASCI | Under Special Central Assistance Scheme |  | Laying RMC streets in internal streets of Mochpura Bazar. | 26.98 | 14.84 | 14.84 |  | Tender F&CC reso.no. 2574 dt. 11-02-2026 | 144/EEA dt. 20-03-2026 | Maa Chintpurni Construction | 20-03-2026 | 3 months | 21-05-2026 | 45 |  | 14.51 | Work delayed due to core area. Work in progress. | Delayed/Held Up
MCL-0113 | B1 | Central | 80 | B&R | MC Funds / General Quota | GQ/MLA |  | Laying SDBC in streets of Janakpuri Part-II in w.no.80. | 24.15 | 18.93 | 18.93 |  | Tender F&CC reso.no. 3578 dt. 21-04-2026 | 151/EEA dt. 06-05-2026 | Capital Construction Co. | 06-05-2026 | 6 months | 07-10-2026 | 10 |  | NIL | Work delayed due to shortage of bitumen. Notice issue | Delayed/Held Up
MCL-0114 | A1 | Central | 85 | B&R | Rangla Punjab | Under Rangla Punjab Vikas Scheme Ph-I |  | Laying RMC M-30 in street of Mohalla Shankar Puri, Veer Nagar & SDP College Quilla Mohalla in w.no.85. |  | 46.39 | 46.39 |  | 3196 dt. 25-02-2026 | 150/EEA dt. 05-05-2026 | Maa Chintpurni Construction | 05-05-2026 | 7 months | 06-11-2026 | 45 |  | NIL | Work in progress. Work will be completed upto 15-07-2026 | In Progress
MCL-0115 | A2 | Central | 82 | B&R | Rangla Punjab | Under Rangla Punjab Vikas Scheme Ph-I |  | Laying RMC M-30 in Shanti Niketen School St & Links Streets of Mohalla Fateh Ganj in Ward No-82. |  | 26.49 | 26.49 |  | 3271 dt. 25-02-2026 | 148/EEA dt. 05-05-2026 | LRY Labour Contractor | 05-05-2026 | 3 months | 06-07-2026 | 10 |  | NIL | Work in progress. Work will be completed upto 15-07-2026 | In Progress
MCL-0116 | A2 | Central | 82 | B&R | Rangla Punjab | Under Rangla Punjab Vikas Scheme Ph-I |  | Laying RMC M-30 in streets near Gajja Jain Mandir in Tilak Nagar w.no.82. |  | 17.1 | 17.1 |  | 3274 dt. 25-02-2026 | 147/EEA dt. 05-05-2026 | LRY Labour Contractor | 05-05-2026 | 4 months | 06-08-2026 | 25 |  | NIL | Work in progress. Work will be completed upto 15-07-2026 | In Progress
MCL-0117 | B1 | Central | 79 | B&R | Rangla Punjab | Under Rangla Punjab Vikas Scheme Ph-I |  | Laying RMC M-30 in Hargobind Nagar & its adjoining streets of w.no.79. |  | 30.2 | 30.2 |  | 3273 dt. 25-02-2026 | 149/EEA dt. 05-05-2026 | Capital Construction Co. | 05-05-2026 | 4 months | 06-08-2026 | 10 |  | NIL | Work in progress. Work will be completed upto 15-07-2026 | In Progress
MCL-0118 | B1 | Central | 80 | B&R | Rangla Punjab | Under Rangla Punjab Vikas Scheme Ph-I |  | Laying RMC M-30 in streets of New Kidwai Nagar in w.no. 80. |  | 22.61 | 22.61 |  | 3272 dt. 25-02-2026 | 146/EEA dt. 05-05-2026 | Godwyn Infra | 05-05-2026 | 7 months | 06-11-2026 | 10 |  | NIL | Work in progress. Work will be completed upto 15-07-2026 | In Progress
MCL-0119 | Gen. | Central | Gen. | B&R | MC Funds / General Quota | PUEIP Ph-III |  | Remodeling of Nallah & Constructions of roads from Shingar Cinema Bridge to Shamshan Ghat Bridge. |  | 939.21 | 939.21 |  | 26-11-2021 | 153/EEA/LOA dt. 13-12-2021 | M/s Kabir Infra | 13-12-2021 | 12 months | 14-12-2021 | 60 |  | 300.62 | Work delayed because of pending IPS construction work causing obstruction at the site. Work in progress (Amt. approved from under PUEIP PH-III 600 lacs) but Orginal Est. Cost is 948.70 & vetted Est. amt. 942.05 lacs | Delayed/Held Up
MCL-0120 |  |  |  |  | MC Funds / General Quota |  |  | Total |  | 2359.73 | 2359.73 | [9 empty] | 617.9 |  | Not Started
MCL-0121 | A | Central | Gen. | B&R | MDF / SASCI | MDF Funds |  | Laying SDBC Links between Vijay Nagar Road & Suffian Chowk Road, Links Nearby Night Shelter Moti Nagar, Main Road from Basti Jodhewal to Sunder Nagar Pulley Both Sides, Gaushalla Main Road, Ghora Colony & Links and Links between RK Road & Kabir Road in central Constituency. | 877.87 | [12 empty] | Under technical evaluation | Not Started
MCL-0122 | A | Central | Gen. | B&R | MDF / SASCI | MDF Funds |  | Laying RMC M-30 in streets of Old Madho Puri Part-I & II, Janakpuri, Hargobind Nagar Road, Ambedkar Nagar & Ram Nagar, Industrial area, Basti Sheikh Mohamadh, Mohalla Vijay Nagar & New Shiva Ji Nagar of Central Constituency. | 601.4 | [12 empty] | Under technical evaluation | Not Started
MCL-0123 | A | Central | Gen. | B&R | MDF / SASCI | MDF Funds |  | Laying RMC M-40 in Various Streets of Transport Nagar Part-II Ward No.30. | 701.92 | [12 empty] | Under technical evaluation | Not Started
MCL-0124 | A | Central | Gen. | B&R | MDF / SASCI | MDF Funds |  | Laying BM & SDBC on Guru Nanak Dev Market, Main Hargobind Marg, Main Textile Colony Road and Brown Road & Islamia School Road and Main Road from 3 No. Division to CMC Chowk. | 553.56 | [12 empty] | Under technical evaluation | Not Started
MCL-0125 | A | Central | Gen. | B&R | MDF / SASCI | MDF Funds |  | Laying RMC M-30 in streets of Mohalla Islam Ganj, Mustak Ganj and Ucha Tibba in w.no.75, Various Kuchas in w.no.76, Various Streets of Shivaji Nagar in w.no.79, Streets of Kashmir Nagar & Narinder Nagar in w.no.81 and Main Road of Dal Bazar, Hindi Bazar & Chawal Bazar and Main Hosiery Road. | 652.17 | [12 empty] | Under technical evaluation | Not Started
MCL-0126 | B1 | Central | 30 | B&R | Rangla Punjab | Rangla Punjab-II |  | Laying RMC M-30 in Various Streets of Bihari Colony in ward no.30. | 73.82 | [12 empty] | F&CC approved in anticipation Tender to be called | Not Started
MCL-0127 | B1 | Central | 79 | B&R | Rangla Punjab | Rangla Punjab-II |  | Laying RMC M-30 in Street No.1,2,3 & Links Hari Kartar Colony in ward no.79. | 53.46 | [12 empty] | F&CC approved in anticipation Tender to be called | Not Started
MCL-0128 | B1 | Central | 76 | B&R | Rangla Punjab | Rangla Punjab-II |  | Laying RMC M-30 in link Streets of Kusht Ashram Road in ward no.76. | 72.81 | [12 empty] | F&CC approved in anticipation Tender to be called | Not Started
MCL-0129 | B1 | Central | 76 | B&R | Rangla Punjab | Rangla Punjab-II |  | Laying RMC M-30 in Different Streets of Prem Nagar Part-II in ward no.76. | 49.81 | [12 empty] | F&CC approved in anticipation Tender to be called | Not Started
MCL-0130 | Gen. | Central | Gen. | B&R | MDF / SASCI | Special Central Assistance Scheme |  | Upgradation of RMC Roads in various wards of Central Constituency. |  | 741.93 | 741.93 |  | 2676 dt. 11-02-2026 | 123/EEA dt. 18-02-2026 | M/s J.K.Infocon Pvt. Ltd | 18-02-2026 |  |  | 90 |  | NIL | Work will be completed upto 30-06-2026 | In Progress
MCL-0131 |  |  |  |  | MDF / SASCI |  |  | Total |  | 741.93 | 741.93 | [9 empty] | 0 |  | Not Started
MCL-0132 | D | North | 68 | Subzone D1 B&R | MC Funds / General Quota | MC Funds |  | P/Laying RMC M-30 in streets of Chander nagar & Jagan nath puram road ward no. 68. |  | 31.78 | 31.78 |  | 2639 dt 11.02.2026 | 29/EED dt 23.02.2026 | M/s Prince Sharma | 23.02.2026 | 4 | 30.07.2026 | 50 |  | NiL | Work in Progress | In Progress
MCL-0133 | D | North | 70 | Subzone D1 B&R | Councillor Quota (CQ) | CQ |  | P/Laying RMC M-30 in streets of Wadhwa street, Gandhi street , Prem nagar & kundanpuri ward no. 70. |  | 32.75 | 32.75 |  | 2648 dt 11.02.2026 | 27/EED dt 23.02.2026 | M/s Navdeep Gupta & Company | 23.02.2026 | 4 | 30.06.2026 | 70 |  | 21.24 | Work in Progress. balance 2 no.st which is pending will be completed by 30.06.2026 | Delayed/Held Up
MCL-0134 | D | North | 70 | Subzone D1 B&R | MC Funds / General Quota | MC Funds |  | P/L 60mm thick Perforated tiles on side berms of Pavillion chowk to Kailash chowk , Petrol pump street w.no.70. |  | 11.42 | 11.42 |  | 2641 dt 11.02.2026 | 25/EED dt 23.02.2026 | M/s Navdeep Gupta & Company |  | 2 | 30.07.2026 |  |  | NiL | Inauguration pending | Delayed/Held Up
MCL-0135 | D | North | 70 | Subzone D1 B&R | Councillor Quota (CQ) | CQ |  | Repair & Renovation of Tanki wala park (prem nagar), Park lane & Gol park in ward no. 70. |  | 18.64 | 18.64 |  | 2640 dt 11.02.2026 | 26/EED dt 23.02.2026 | M/s Deepak Madaan | 23.02.2026 | 3 | 30.07.2026 | 30 |  | NiL | Work in Progress | In Progress
MCL-0136 | D | North | 66 | Subzone D1 B&R | MC Funds / General Quota | GQ |  | P/Laying Bm & Pc from Lal Kothi chowk to Sheller road, main road Bank colony w.no. 66. |  | 39.59 | 39.59 |  | 2643 dt 11.02.2026 | 23/EED dt 23.02.2026 | M/s Soham Construction Co. |  | 3 | 30.07.2026 |  |  | NiL | Inauguration pending & bitumen work delay due to non-avalibility of bitumen | Delayed/Held Up
MCL-0137 | D | North | 91 | Subzone D1 B&R | Councillor Quota (CQ) | CQ |  | P/Laying RMC M-30 in streets of Guru Nanak pura ward no. 91. |  | 18.71 | 18.71 |  | 2647 dt 11.02.2026 | 28/EED dt 23.02.2026 | M/s Navdeep Gupta & Company | 23.02.2026 | 3 | 15.07.2026 | 70 |  | 14.3 | Work in progress | In Progress
MCL-0138 | D | North | 66 | Subzone D1 B&R | MC Funds / General Quota | MC Funds |  | P/Laying RMC M-30 in New Deep Nagar ward no. 66. |  | 6.77 | 6.77 |  | 2644 dt 11.02.2026 | 21/EED dt 23.02.2026 | M/s Prince Sharma |  | 2 | 30.07.2026 |  |  | NiL | Inauguration pending (council. Quota) | Delayed/Held Up
MCL-0139 | D | North | 66 | Subzone D1 B&R | MC Funds / General Quota | GQ |  | P/Laying RMC M-30 in streets of Om Park Part -I ward no. 66. |  | 28.38 | 28.38 |  | 2642 dt 11.02.2026 | 22/EED dt 23.02.2026 | M/s Navdeep Gupta & Company |  | 4 | 30.07.2026 |  |  | NiL | Inauguration pending | Delayed/Held Up
MCL-0140 | D | North | 66 | Subzone D1 B&R | MC Funds / General Quota | GQ |  | P/Laying RMC M-30 in streets of Om Park Part -II ward no. 66. |  | 29.42 | 29.42 |  | 2646 dt 11.02.2026 | 24/EED dt 23.02.2026 | M/s Prince Sharma | 23.02.2026 | 4 | 10.07.2026 | 95 |  | 29.41 | only 300 feet length of sts. pending due to W/S supply Work in Progress | Delayed/Held Up
MCL-0141 | D | North | 70 | Subzone D1 B&R | Councillor Quota (CQ) | CQ |  | P/Laying RMC M-30 in Bhandari street ward no. 70. |  | 15.95 | 15.95 |  | 2645 dt 11.02.2026 | 30/EED dt 23.02.2026 | M/s Navdeep Gupta & Company |  | 3 | 30.07.2026 |  |  | NiL | Inauguration pending (Council. Quota) | Delayed/Held Up
MCL-0142 | D | North | 68 | Subzone D1 B&R | MC Funds / General Quota | MC Funds |  | P/Laying RMC M-30 in streets of Jagannath puram ward no. 68. |  | 22.22 | 22.22 |  | 1876 dt 13.10.2025 | 15/EED dt 23.12.2025 | M/s Prince Sharma | 23.12.2025 | 3 | 30.07.2026 | 30 |  | NiL | Work in progress | In Progress
MCL-0143 | D | North | 68 | Subzone D1 B&R | MC Funds / General Quota | MC Funds |  | P/L 60mm thick Perforated tiles on both side berms of Malhi road ward no. 68. |  | 30.47 | 30.47 |  | 1877 dt 13.10.2025 | 14/EED dt 23.12.2025 | M/s Navdeep Gupta & Company |  | 3 | 30.07.2026 |  |  | NiL | Inauguration pending | Delayed/Held Up
MCL-0144 | D | North | 92 | Subzone D1 B&R | MC Funds / General Quota | MC Funds |  | Repair & Renovation of Parks in Pritam Nagar ward no. 92. |  | 13.41 | 13.41 |  | 172 dt | 19/EED dt 16.01.2026 | M/s Dynamic tiles | 16.01.2026 | 3 | 15.07.2026 | 50 |  | NiL | Work in Progress | In Progress
MCL-0145 | D | North | 68 | Subzone D1 B&R | MC Funds / General Quota | MC Funds |  | PROVIDING AND FIXING M.S.SIGN BOARDS IN WARD NO 68 LUDHIANA |  | 10.78 | 10.78 |  | 161 dt | 18/EED dt 16.01.2026 | M/s Dynamic tiles | 16.01.2026 | 3 | 30.07.2026 | 10 |  | NiL | Work in Progress | In Progress
MCL-0146 | D | North | 70 | Subzone D1 B&R | Viveki Funds | Un-tied/ Viveki Funds |  | Repair & Renovation of Govt. Primary school, kundan puri ward no. 70. |  | 8.62 | 8.62 |  | 298 dt 26-03-2025 | 9/EED/D1-N dt 25/04/2025 | M/s Prince Sharma | 25.04.2025 | 2 | 10.07.2026 | 40 |  | NiL | ਇਹ ਕੰਮ ਵਿਵੇਕੀ ਫੰਡ ਅਧੀਨ ਅਲਾਟ ਕੀਤਾ ਗਿਆ ਸੀ । ਪਰੰਤੂ ਮੌਕੇ ਤੇ ਪਰਾਇਵੇਟ ਲੋਕਾਂ ਵੱਲੋ ਇਸਦਾ ਮਾਲਕੀ ਦਾ ਹੱਕ ਜਤਾਇਆ ਜਾ ਰਿਹਾ ਹੈ ਅਤੇ ਕੋਰਟ ਕੇਸ ਦਾ ਸਟੇ ਹੋਣ ਕਰਕੇ ਇਹ ਕੰਮ ਬੰਦ ਕੀਤਾ ਗਿਆ ਹੈ । | In Progress
MCL-0147 | D | North | 91 | Subzone D1 B&R | MC Funds / General Quota | MC Funds |  | Construction of Retainnig wall from Budha Nallah towards Baba Balak Nath Mandir in New Kundanpuri ward no. 91. |  | 94.21 | 94.21 |  | 843 dt 06-05-2025 | 11/EED dt 22.05.2025 | M/S LRY Contractor | 22.05.2025 | 6 | 15.07.2026 | 85 |  | 77.37 | 300 ft length pending which will be completed | Delayed/Held Up
MCL-0148 | D | North | 91 | Subzone D1 B&R | MC Funds / General Quota | General quota |  | Construction of Volleyball Ground in Dusshera ground Upkar nagar ward no. 91. |  | 15.53 | 15.53 |  | 2823 dt 19.02.2026 | 33/EED dt 15.03.2026 | M/s Subodh Batish |  | 3 | 30.07.2026 |  |  | NiL | Inauguration pending | Delayed/Held Up
MCL-0149 | D | North | 93 | Subzone D1 B&R | MC Funds / General Quota | MC funds |  | Prov. and laying of RMC M-30 in L.H.S streets of Mohalla Smart City in ward no. 94.(site change P//L of RMC M-30 at Main Haibowal puli upto MLA Office via Bhuriwala Gurudwara road & streets of Pahalwan colony ) |  | 43.56 | 43.56 |  | 3094 dt 22-11-2024 | 35/EEA dt 27-11-2024 | Navdeep Gupta & Company | 27.11.2024 | 6 | 10.07.2026 | 90 |  | 27.67 | Work held up due to world bank project | Delayed/Held Up
MCL-0150 | D | North | 93 | Subzone D1 B&R | MC Funds / General Quota | MC funds |  | Prov. and laying of RMC M-30 in streets of Sunil Nagar and balance streets of New Friends colony in ward no. 93. |  | 53.4 | 53.4 |  |  | 66/EEA dt 05-12-2024 | Neeraj Joshi | 05.12.2024 |  | 30.07.2026 | 30 |  | NiL | work held up due to water & sewerage line pending & Now work started | Delayed/Held Up
MCL-0151 | D | North | 93 | Subzone D1 B&R | MC Funds / General Quota | MC funds |  | Prov. and laying of RMC M-30 in R.H.S streets of Mohalla Smart City in ward no. 93. |  | 40.62 | 40.62 |  | 3093 dt 22-11-2024 | 34/EEA dt 27-11-2024 | Navdeep Gupta & Company | 27.11.2024 | 6 | 30.07.2026 | 0 |  | NiL | work held up due to water & sewerage line , Now sewerage line work just completed. | Delayed/Held Up
MCL-0152 | D | North | 68 | Subzone D1 B&R | MC Funds / General Quota | MC Funds |  | P/Laying RMC M-30 in various streets of Hargobind nagar w.no 68. |  | 22.62 | 22.62 |  | 3328 dt 21.04.2026 | 03/EED dt 07.05.2026 | R.K Construction |  | 4 | 07.09.2026 |  |  | NiL | Inauguration pending | Delayed/Held Up
MCL-0153 | D | North | 68 | Subzone D1 B&R | Councillor Quota (CQ) | CQ |  | P/Laying RMC M-30 in remaining streets of Chander nagar ward no. 68. |  | 79.16 | 79.16 |  | 3329 dt 21.04.2026 | 04/EED dt 07.05.2026 | Neeraj Joshi |  | 6 | 07.11.2026 |  |  | NiL | Inauguration pending | Delayed/Held Up
MCL-0154 | D | North | 68 | Subzone D1 B&R | MC Funds / General Quota | GQ |  | Construction of Retaining wall at Malhi puli existing bitumen road side. |  | 20.13 | 20.13 |  | 3326 dt 21.04.2026 | 06/EED dt 07.05.2026 | Rajesh Kumar Sood |  | 3 | 07.08.2026 |  |  | NiL | Inauguration pending | Delayed/Held Up
MCL-0155 | D | North | 67 | Subzone D1 B&R | MC Funds / General Quota | GQ |  | Construction of Retainnig wall at Main haibowal puli to life line puli existing bitumen road side. |  | 24.55 | 24.55 |  | 3333 dt 21.04.2026 | 05/EED dt 07.05.2026 | Rajesh Kumar Sood |  | 2 | 07.07.2026 |  |  | NiL | Inauguration pending | Delayed/Held Up
MCL-0156 | D | North | 70 | Subzone D1 B&R | MC Funds / General Quota | GQ |  | Repair & Renovation of Shahi Mohalla park in ward no. 70. |  | 18.52 | 18.52 |  | 3330 dt 21.04.2026 | 10/EED dt 07.05.2026 | Navdeep Gupta & Company | 07.05.2026 | 3 | 07.08.2026 | 60 |  | 14.96 | Work in Progress | In Progress
MCL-0157 | D | North | 91 | Subzone D1 B&R | Councillor Quota (CQ) | CQ |  | Repair & Renovation of Park 1 & Park 2 in New Deep Nagar ward no. 91. |  | 12.88 | 12.88 |  | 3335 dt 21.04.2026 | 08/EED dt 07.05.2026 | Navdeep Gupta & Company | 07.05.2026 | 3 | 07.08.2026 | 90 |  | 8.57 | Work in Progress | In Progress
MCL-0158 | D | North | 91 | Subzone D1 B&R | Councillor Quota (CQ) | CQ |  | Repair & renovation of Parks along with Road Dusshera ground to damoria chowk in ward no. 91. |  | 28.56 | 28.56 |  | 3336 dt 21.04.2026 | 09/EED dt 07.05.2026 | M/s Prince Sharma | 07.05.2026 | 4 | 07.09.2026 | 5 |  | NiL | Work just started | In Progress
MCL-0159 | D | North | D1 | Subzone D1 B&R | MC Funds / General Quota | MC Funds |  | Scrapping by Cold Milling Machine and P/L BM & SDBC in Haibowal Main road (hambran road to churpur road ) |  | 117 | 117 |  | 3334 dt 21.04.2026 | 07/EED dt 07.05.2026 | Vansh Engineers |  | 6 | 07.11.2026 |  |  | NiL | Work held up due to world bank project | Delayed/Held Up
MCL-0160 | D | North | 91 | Subzone D1 B&R | MDF / SASCI | Special Assistenace scheme |  | Upgradation of Road From Shamshan Ghat Puli & Malhi Pulli backside New Deep nagar ward no. 91. |  | 622.32 | 622.32 |  | 2674 dt 11.02.2026 | 35/EED dt 25.03.2026 | M/s J.K Infcon Pvt. Ltd | 25.03.2026 | 6 | Completion of work depends on the availabilty of bitumen material. | 55 |  | 150.03 | RMC work is in progress which will be completed by 30.06.2026. Bituminious work is getting delayed due to non-availability of bitumen VG-30. | Delayed/Held Up
MCL-0161 | D | North | D1 | Subzone D1 B&R | MDF / SASCI | MDF |  | Upgradation of various roads in different wards with RMC & Bitumen roads in sub zone D1 North Constituency. |  | 445.29 | 445.29 |  | 3288 dt 25.02.2026 | 36/EED dt 25.03.2026 | M/s Dass Builders Pvt. Ltd | 25.03.2026 | 6 | Completion of work depends on the availabilty of bitumen material. | 30 |  | 80.06 | RMC work is in progress which will be completed by 30.06.2026. Bituminious work is getting delayed due to non-availability of bitumen VG-30. | Delayed/Held Up
MCL-0162 | D | North | 93,67&92,91 | Subzone D1 B&R | MDF / SASCI | MDF-3 |  | P/Laying 40mm BC at Sangam chowk towards Jassian road, Dusshera ground to shahi mohalla park road, Luxmi nagar main road in subzone D1 North Constituency. | 171.24 | [12 empty] | Estimate approval in anticipation. Tender has been called which is under Technical Evalution. | Not Started
MCL-0163 | D | North | 93,92,66,70, 91,68 | Subzone D1 B&R | MDF / SASCI | MDF-3 |  | P/Laying RMC in streets of Kesari Enclave, Mohalla Smart City, Jagat Nagar, Luxmi nagar st no. 5,7,9 & Links & st.s of Kehar singh nagar road, Durgapuri st no. 8,9,10 & Mandir st, Piara singh chakki main road & Links, Mohini resort road to damoria chowk along dusshera ground, st no. 10 & Links & Garg optical shop humbran road to shamshanghat chowk,Bassi hospital to Lifeline puli road, Chander nagar councillor off to shakti nagar roads in subzone D1 North Constituency. | 672.05 | [12 empty] | Estimate approval in anticipation. Tender has been called which is under Technical Evalution. | Not Started
MCL-0164 | D | North | 66 | Subzone D1 B&R | Rangla Punjab | Rangla punjab Ph-I |  | Construction of Playground/JoyBox opp. Bhatia School, Bank Colony ward no. 66. |  | 21.96 | 21.96 |  | Approved in anticipation |  | M/s Subodh Batish |  | 3 |  |  |  |  | Work order just issued | Not Started
MCL-0165 | D | North | 70 | Subzone D1 B&R | Rangla Punjab | Rangla punjab Ph-I |  | Construction of Room & Shed in Community Health Center in North Consitutency. Ward no. 70. | [8 empty] | 3 |  |  |  |  | Tender Re-Called. | Not Started
MCL-0166 | D | North | 67 | Subzone D1 B&R | Rangla Punjab | Rangla punjab Ph-II |  | Construction of Road with RMC from Karanvir hospital to Jassian chowk (22 ft road) w.no. 67. |  | 33.01 | 33.01 |  | 3331 dt 21.04.2026 |  | M/S Apex Developers |  | 3 |  |  |  |  | Tender rece. Allotment pending by F&CC | Delayed/Held Up
MCL-0167 | D | North | 68 | Subzone D1 B&R | Rangla Punjab | Rangla punjab Ph-II |  | Construction of Road with RMC from Lala Jagat Narain chowk to B.K Building Material store w.no. 68 | [8 empty] | 3 |  |  |  |  | Tender to be Recalled. | Not Started
MCL-0168 | A3 | East | 5 | B&R | MC Funds / General Quota | GQ |  | Laying RMC M-30 in roads between from Kakowal Road via MD Factory to Kailash Nagar Main Road w.no.5. |  | 32.85 | 59.25 |  | 2709 dt.24-09-2024 | 3 16.04.2025 | Capital Const Co. | 16-04-2025 | 5 |  | 50 |  | 12.85 | Work was heldup due to non upgradation of Water supply lines, now same has been laid by 30/04/26 & work is in progress now. | In Progress
MCL-0169 | A3 | East | 3 & 4 | B&R | MC Funds / General Quota | GQ |  | Laying RMC M-30 in Mohalla Inder Vihar, New Basant Vihar, Basant Vihar Ext., Anand Puri in w.no.3 & 4. |  | 20.57 | 37.09 |  | 2708 dt. 24-09-2024 | 4 16.04.2025 | Capital Const Co. | 16-04-2025 | 4 |  | 85 |  | 4.58 | The work of streets of new basant vihar,Basant vihar ext. is completed and inder vihar and anandpuri streets work in process which is delayed due to water supply line now balance work will be completed by 10/07/26 | Delayed/Held Up
MCL-0170 | A3 | East | 5 | B&R | MC Funds / General Quota | GQ |  | P/Fixing I/tiles in Mohalla Royal Estate, Green City W No.5 |  | 61.31 | 99.88 |  | 1518 dt. 13-10-2025 | 51 16.02.2026 | M/s T&G Const Co. | 16-02-2026 | 6 |  | 15 |  | NIL | Initally work was stopped by area councillor due to upgradation of sewer line but now work is in progress which will be completed within time limit upto 15/8/26 | Delayed/Held Up
MCL-0171 | A3 | East | 2 | B&R | Councillor Quota (CQ) | CQ |  | P/Fixing I/tiles in Golden Vihar W.No.02. |  | 23.33 | 37.62 |  | 1624 dt. 13-10-2025 | 53 16.02.2026 | Varinder Singh Govt Contractor | 16-02-2026 | 4 |  | 0 |  | NIL | Work was delayed due to inauguration pending by worthy MLA .Now worthy MLA has directed to start the work. | Delayed/Held Up
MCL-0172 | A3 | East | 5 | B&R | Councillor Quota (CQ) | CQ |  | Laying RMC in street of Mohalla New Shimla Colony and Jaiswal Colony in W No.05 |  | 27.42 | 44.22 |  | 1946 dt. 13-10-2025 | 56 16.02.2026 | NS Infra | 16-02-2026 | 5 |  | 0 |  | NIL | Work is held up due to pending of laying W/S lines to be laid by o&m cell street has been katcha at site. | Delayed/Held Up
MCL-0173 | A3 | East | 2 | B&R | MC Funds / General Quota | GQ |  | P/Fixing I/tiles in Ekjot Nagar & Banda Bahadur Nagar in W No.02 |  | 43.64 | 70.15 |  | 3268 dt. 29-11-2024 | 58 16.02.2026 | Varinder Singh Govt Contractor | 16-02-2026 | 6 |  | 0 |  | NIL | Work was delayed due to inauguration pending by worthy MLA .Now worthy MLA has directed to start the work. | Delayed/Held Up
MCL-0174 | A3 | East | 2 | B&R | Councillor Quota (CQ) | CQ |  | P/Fixing I/tiles in Banda Bhadur Colony, New Azad Nagar & Masjid Wali Gali Ward No.02. |  | 53.83 | 85.43 |  | 1663 dt. 13-10-2025 | 68 09.03.2026 | Apex Developers | 09-03-2026 | 5 |  | 0 |  | NIL | Work was delayed due to inauguration pending by worthy MLA .Now worthy MLA has directed to start the work. | Delayed/Held Up
MCL-0175 | A3 | East | 3 | B&R | Councillor Quota (CQ) | CQ |  | P/F of I/tiles in Guru Gobind Singh Nagar, Panchsheel Colony & Basant Valley W No.03 |  | 44.37 | 71.71 |  | 1893 dt. 13-10-2025 | 69 09.03.2026 | Varinder Singh Govt Contractor | 09-03-2026 | 5 |  | 60 |  | 12.75 | The panchsheel colony streets completed and basant balley streets is in progress and the work of the work of guru gobind nagar streests will be started after completion of water supply lines to be laid by O&M cell | In Progress
MCL-0176 | A3 | East | 5 | B&R | Councillor Quota (CQ) | CQ |  | P/fixing I/tiles in Amrit Vihar in ward no.5. |  | 40.39 | 65.29 |  | 1936 dt. 13-10-2025 | 70 09.03.2026 | Varinder Singh Govt Contractor | 09-03-2026 | 4 |  | 80 |  | 24.46 | Work is in Progress | In Progress
MCL-0177 | A3 | East | 3&4 | B&R | MC Funds / General Quota | GQ |  | Construction of bituminious roads between Main Noorwala Road & Kakowal Road via Raghunath Mandir & DVM School Road |  | 33.18 | 40.42 |  | 2710 dt. 24-09-2024 | 73 09.03.2026 | Maruti Const Co. | 09-03-2026 | 3 |  | 20 |  |  | Road gully work completed bitumen work pending due to shortage of bitumen | Delayed/Held Up
MCL-0178 | A3 | East | 4&5 | B&R | MC Funds / General Quota | GQ |  | Construction of Main Kakowal Road w.no.4& 5 |  | 76.19 | 80.2 |  | 813 dt. 09-04-2025 | 85 10.04.2026 | Apex Builders | 10-04-2026 | 4 |  |  |  | NIL | Work heldup due to upgradation of w/s Lines , (24/7) | Not Started
MCL-0179 | A3 | East | 3&4 | B&R | MC Funds / General Quota | GQ |  | Construction of Main Noorwala Road |  | 69.16 | 72.8 |  | 814 dt. 09-04-2025 | 86 10.04.2026 | VKBS Constructions Pvt. Ltd. | 10-04-2026 | 4 |  |  |  | NIL | Work heldup due to upgradation of & sewerage lines now same has been completed and work will start after rainy season | Not Started
MCL-0180 | A3 | East | 3 | B&R | MC Funds / General Quota | GQ |  | Beautification of Lajpat Nagar Entry Point on Noorwala Road. |  | 6.36 | 6.62 |  | 1973 dt. 13-10-2025 | 87 10.04.2026 | Teg Builders | 10-04-2026 | 2 |  | 80 |  | NIL | Work is in Progress | In Progress
MCL-0181 | A3 | East | 4 | B&R | Councillor Quota (CQ) | CQ |  | P/Fixing I/tiles in Prem Vihar, Pink City, Vivek Dham & Sant Singh Cheema Nagar W No.04 |  | 55.39 | 77.89 |  | 1958 dt. 13-10-2025 | 87 10.04.2026 | Varinder Singh Govt Contractor | 10-04-2026 |  |  | 20 |  | NIL | Work is in Progress | In Progress
MCL-0182 | A3 | East | 5&6 | B&R | MC Funds / General Quota | GQ |  | Construction of Main Kailash Nagar Road w.no.5 |  | 73.3 | 102.73 |  | 463 dt. 09-04-2025 | 15 13.05.2026 | Somaya Infrastructure | 13-05-2026 | 6 |  | 25 |  | NIL | R/G work completed & bituminious work is pending due to shortage of Bitumen. | Delayed/Held Up
MCL-0183 |  |  |  |  | Other / Unspecified |  |  | Total |  | 949.49 | 1421.06 | [9 empty] | 54.64 |  | Not Started
MCL-0184 | C | Atam Nagar | 48 | B&R | MC Funds / General Quota | MC |  | Laying SDBC on various roads of W.No.43 | 106.79 | 75.83 |  |  | 2269 dt 24.07.24 | 140/EEC DT 11.10.24 | Rajesh Kumar Sood |  | 6 |  | 65 |  |  | Work stopped due to 24X7 W/S | Delayed/Held Up
MCL-0185 | C | Atam Nagar | 46 | B&R | MC Funds / General Quota | MC |  | Development of Green Belt Dhuri Line to Gill Bridge along Sidhwan Canal | 137.66 | 95.09 |  |  | 1452 dt 22.02.23 | 116/EEC DT 15.02.24 | Glisten |  | 6 |  | 70 |  |  | Work not completed due to enchroachment at site. | In Progress
MCL-0186 | C | Atam Nagar | 45 | B&R | MC Funds / General Quota | MC |  | Renovation of Municipal Corporation Ludhiana Zone C Main Office Gill Road. | 45.56 | 34.17 |  |  | 1664 dt 14.02.24 | 124/EEC DT 20.02.24 | The Gill Co Op Diploma Holder Society Ltd |  | 6 |  | 80 |  |  | Work in progress. | In Progress
MCL-0187 | C | Atam Nagar | 41& 42 | B&R | MC Funds / General Quota | MC |  | Construction of RCC road from Labour chowk to Harkrishan Sahib School. | 118.84 | 84.78 |  |  | 721 dt 09.04.25 | 169/EEC dt 28.04.25 | M/S Ashok Kumar Sobti |  | 6 |  | 55 |  |  | Work held up due to upgradation of s/w line. | Delayed/Held Up
MCL-0188 | C | Atam Nagar | 40 | B&R | MC Funds / General Quota | MC |  | Laying RMC in link of Kwality Road & Link of Maya Soap. | 43.73 | 25.07 |  |  | 1982 dt 13.10.25 | 196/EEC dt 11.11.25 | N.S.Infra |  | 3 |  | 0 |  |  | Work held up due to upgradation of w/s line. | Delayed/Held Up
MCL-0189 | C | Atam Nagar | 40 | B&R | MC Funds / General Quota | MC |  | P/F of Informatory Sign Board in various streets of W.No.40 | 4.06 | 3.57 |  |  | 1839 dt 13.10.25 | 197/EEC dt 11.11.25 | Glisten |  | 1 |  | 10 |  |  | work stopped due to dispute | Delayed/Held Up
MCL-0190 | C | Atam Nagar | 45 | B&R | MC Funds / General Quota | MC |  | Laying RMC in main street Ram nagar market ,mohalla parbhat nagar and labour colony ward no.45 | 64.56 | 37.83 |  |  | 1840 dt 13.10.25 | 199/EEC dt 11.11.25 | K.S.Constructions |  | 3 |  | 25 |  |  | work stopped due to dispute | Delayed/Held Up
MCL-0191 | C | Atam Nagar | 42 | B&R | MC Funds / General Quota | MC |  | P/F of Informatory Sign Board in various streets of W.No.42 | 7.6 | 5.42 |  |  | 1951 dt 13.10.25 | 200/EEC dt 11.11.25 | Ram Parkash Kakar |  | 1 |  | 0 |  |  | Not Started | Not Started
MCL-0192 | C | Atam Nagar | 41 | B&R | MC Funds / General Quota | MC |  | Laying RMC in Streets of daba colony and new janta nagar ward no.41 | 88.55 | 51.36 |  |  | 1802 dt 13.10.25 | 203/EEC dt 11.11.25 | Apex Devlopers |  | 4 |  | 80 |  |  | Work in progress. | In Progress
MCL-0193 | C | Atam Nagar | 40 | B&R | MC Funds / General Quota | MC |  | Laying RMC in Main Streets of Maya Soap W.No.40 | 76.67 | 44.92 |  |  | 1801 dt 13.10.25 | 204/EEC dt 11.11.25 | K.S.Constructions |  | 3 |  | 0 |  |  | Work held up due to upgradation of water supply. | Delayed/Held Up
MCL-0194 | C | Atam Nagar | 45 | B&R | MC Funds / General Quota | MC |  | Laying RMC in streets of mohalla parbhat nagar and vishvakarma colony ward no.45 | 29.51 | 18.07 |  |  | 1804 dt 13.10.25 | 206/EEC dt 11.11.25 | R.K.Construction Co. |  | 3 |  | 50 |  |  | Work in progress. | In Progress
MCL-0195 | C | Atam Nagar | 40 | B&R | MC Funds / General Quota | MC |  | Laying BM&PC on Seerat Hospital Road upto Gurudwara Sahib. Site Change Lappar Paint Main Street & Links. | 57.13 | 36.07 |  |  | 2085 dt 13.10.25 | 208/EEC dt 21.11.25 | Apex Builders |  | 5 |  |  |  |  | Inaugration pending | Delayed/Held Up
MCL-0196 | C | Atam Nagar |  | B&R | CSAG | CSAG | Bitumen | Upgradation of various roads of Atam Nagar constituency Zone C. | 522.08 | 498.58 |  |  | 2683 dt 11.02.2026 | 03/EEC dt 20.02.26 | M/S VKBS Construction Pvt Ltd. |  | 3 |  | 30 |  |  | Work in progress. | In Progress
MCL-0197 | C | Atam Nagar |  | B&R | CSAG | CSAG | RMC | Upgradation of various roads of Atam Nagar constituency Zone C. | 511.6 | 434.66 |  |  | 2865 dt 19.02.2026 | 04/EEC dt 20.02.26 | M/S Dass Builders |  | 3 |  | 30 |  |  | Work in progress. | In Progress
MCL-0198 | C | Atam Nagar | 40 | B&R | MC Funds / General Quota | MC |  | Laying RMC from Gill Road to Gurudwara Sahib (Seerat Hospital Road) | 96.65 | 62.73 |  |  | 2423 dt 05.01.2026 | 11/EEC dt 27.02.2026 | LRY Labour Contractor |  | 4 |  | 0 |  |  | Inaugration pending | Delayed/Held Up
MCL-0199 | C | Atam Nagar | 40 | B&R | MC Funds / General Quota | MC |  | P/F of cat eyes & laying Thermoplastic lines in different streets of W.No.40 | 13.9 | 9.93 |  |  | 2352 dt 05.01.26 | 07/EEC dt 27.02.2026 | Anand Sales |  | 2 |  | 0 |  |  | Decision pending | Delayed/Held Up
MCL-0200 | C | Atam Nagar | 40 | B&R | MC Funds / General Quota | MC |  | Laying RMC in Nippy Public School Street W.No.40 | 49.15 | 33.59 |  |  | 2440 dt 05.01.2026 | 08/EEC dt 27.02.2026 | M/S Ashok Kumar Sobti |  | 3 |  | 75 |  |  | Work in progress. | In Progress
MCL-0201 | C | Atam Nagar | 40 | B&R | MC Funds / General Quota | MC |  | Laying RMC in various streets of mohalla Shimlapuri W.No.40. | 84.21 | 57.55 |  |  | 2441 dt 05.01.26 | 09/EEC dt 27.02.2026 | M/S Ashok Kumar Sobti |  | 4 |  | 0 |  |  | Inaugration pending | Delayed/Held Up
MCL-0202 | C | Atam Nagar | 41 | B&R | MC Funds / General Quota | MC Funds(GQ) |  | Construction of Road by Laying RMC from Bedi Chowk to Harkrishan Chowk. (GQ) | 76.1 | 46.64 |  |  | 2842 dt 19.02.2026 | 20/EEC dt 02.03.2026 | The Gill Co Op Diploma Holder Society Ltd |  | 4 |  | 0 |  |  | Work held up due to upgradation of sewer line. | Delayed/Held Up
MCL-0203 | C | Atam Nagar | 42 | B&R | Councillor Quota (CQ) | MC Funds (CQ) |  | Laying RMC in Streets of New Janta Nagar W.No.42 | 98.29 | 57.22 |  |  | 2838 dt 19.02.2026 | 17/EEC dt 02.03.2026 | Capital Const.Co. |  | 5 |  | 5 |  |  | Work in progress. | In Progress
MCL-0204 | C | Atam Nagar | 45 | B&R | Councillor Quota (CQ) | MC Funds (CQ) |  | Providing and Laying Perforated interlocking tiles adjoining Road from Sangeet Cinema to Gabria Office Road, W.No.45 | 14.6 | 9.93 |  |  | 2730 dt 19.02.26 | 21/EEC dt 02.03.2026 | Dynamic Tiles |  | 2 |  | 0 |  |  | Inaugration pending | Delayed/Held Up
MCL-0205 | C | Atam Nagar | 45 | B&R | Councillor Quota (CQ) | MC Funds (CQ) |  | Construction of new park near Partap Chowk, W.No.45. | 64.41 | 44.31 |  |  | 2820 dt 19.02.2026 | 28/EEC dt 02.03.2026 | Ram Parkash Kakar |  | 5 |  | 35 |  |  | Work in progress. | In Progress
MCL-0206 | C | Atam Nagar | 45 | B&R | N-CAP | NCAP Funds |  | Providing and Laying Perforated interlocking tiles adjoining Road Vishkarma Park. | 21.84 | 16.38 |  |  | 2729 dt 19.02.2026 | 23/EEC dt 02.03.2026 | T and G Construction Co. |  | 2 |  | 0 |  |  | Inaugration pending | Delayed/Held Up
MCL-0207 | C | Atam Nagar | 45 | B&R | MC Funds / General Quota | MC Funds |  | Providing and Laying Perforated interlocking tiles adjoining Road Basant Park. | 13.51 | 10.13 |  |  | 2735 dt 19.02.2026 | 19/EEC dt 02.03.2026 & 29/EEC dt 02.03.2026 | Dynamic Tiles & T and G Construction Co. |  | 2 |  | 0 |  |  | Inaugration pending | Delayed/Held Up
MCL-0208 | C | Atam Nagar | 48 | B&R | Councillor Quota (CQ) | CQ |  | Laying RMC in various streets of mohalla Himmat Singh Nagar, Shaheed Karnail Singh Nagar & Guru nanak Colony W No. 48 | 89.41 | 48.28 |  |  | 2863 dt 19.02.2026 | 26/EEC dt 02.03.2026 | V.S.Infra |  | 5 |  | 45 |  |  | work in progress. | In Progress
MCL-0209 | C | Atam Nagar | 42 | B&R | RPVS | RPVS |  | Construction of Road by Laying RMC from Jeet Sweet Shop to Itta Wala Chowk Halka Atam Nagar. (Rangla Punjab Vikas Scheme). | 60.95 | 42.67 |  |  | 3463 dt 21.04.2026 | 54/EEC dt 30.04.2026 | Apex Devlopers |  | 4 |  | 0 |  |  | Inaugration pending | Delayed/Held Up
MCL-0210 | C | Atam Nagar | 46 | B&R | Councillor Quota (CQ) | MC Funds (CQ) |  | P/F of Informatory Sign Board in various streets of W.No.46 | 7.61 | 6.21 |  |  | 3409 dt 21.04.2026 | 58/EEC dt 08.05.2026 | Glisten |  | 2 |  | 0 |  |  | Decision pending | Delayed/Held Up
MCL-0211 | C | Atam Nagar | 44 | B&R | Councillor Quota (CQ) | MC Funds (CQ) |  | Laying RMC in street no 3,4,5 & Links of SAS Nagar W.No.44 | 75.05 | 43.69 |  |  | 3482 dt 21.04.2026 | 60/EEC dt 08.05.2026 | Capital Const.Co. |  | 4 |  | 0 |  |  | Inaugration pending | Delayed/Held Up
MCL-0212 | C | Atam Nagar | 46 | B&R | Councillor Quota (CQ) | MC Funds (CQ) |  | Laying RMC in streets of super cycle market & mohalla chet singh nagar W.No.46 | 41.51 | 24.16 |  |  | 3417 dt 21.04.2026 | 62/EEC dt 08.05.2026 | Capital construction Co. |  | 3 |  | 0 |  |  | Inaugration pending | Delayed/Held Up
MCL-0213 | C | Atam Nagar | 40 | B&R | MC Funds / General Quota | MC Funds(GQ) |  | P/F of Stainless Steel Sign boards in ward no.40 | 12.31 | 10.58 |  |  | 3414 dt 21.04.2026 | 66/EEC dt 08.05.2026 | Glisten |  | 2 |  | 0 |  |  | Decision pending | Delayed/Held Up
MCL-0214 | C | Atam Nagar | 46 | B&R | Councillor Quota (CQ) | MC Funds (CQ) |  | Laying RMC in Streets No 5, 7 New Janta Nagar( Gill Road) , Street No.20 Janta Nagar, W.No 46 | 44.3 | 25.79 |  |  | 3418 dt 21.04.2026 | 71/EEC dt 08.05.2026 | Capital construction Co. |  | 3 |  | 0 |  |  | Inaugration pending | Delayed/Held Up
MCL-0215 | C | Atam Nagar | 46 | B&R | MC Funds / General Quota | GQ |  | Repair & Renovation of Central Verge of Gill Road from Gill Chowk to Gill Canal.(GQ) | 19.76 | 19.18 |  |  | 3410 dt 21.04.2026 | 73/EEC dt 08.05.2026 | Teg Builders |  | 3 |  | 0 |  |  | Inaugration pending | Delayed/Held Up
MCL-0216 | C | Atam Nagar | 40 | B&R | MC Funds / General Quota | MC Funds(GQ) |  | Repair & Renovation of Green belt from gill road to Guru Arjun Dev Gurudwara Sahib and Const. of Canopies in ward no 40 | 39.75 | 37.43 |  |  | 3420 dt 21.04.2026 | 74/EEC dt 08.05.2026 | Teg Builders |  | 5 |  | 0 |  |  | Inaugration pending | Delayed/Held Up
MCL-0217 | C | Atam Nagar | 44 | B&R | Councillor Quota (CQ) | MC Funds (CQ) |  | Laying RMC in street no. 01 & 04 of mohalla Partap Nagar ward no.44. | 25.83 | 15.04 |  |  | 3483 dt 21.04.2026 | 75/EEC dt 08.05.2026 | Capital Const.Co. |  | 2 |  | 0 |  |  | Inaugration pending | Delayed/Held Up
MCL-0218 | C | Atam Nagar | 44 | B&R | Councillor Quota (CQ) | MC Funds (CQ) |  | Laying RMC in streets no.2 & Links of SAS Nagar W.No.44. | 40.88 | 23.8 |  |  | 3481 dt 21.04.2026 | 76/EEC dt 08.05.2026 | Capital Const.Co. |  | 3 |  | 0 |  |  | Inaugration pending | Delayed/Held Up
MCL-0219 |  |  |  | B&R | Other / Unspecified |  |  | TOTAL | 2804.36 | 2090.66 | [12 empty] | Not Started
MCL-0220 | C | South | 35 | B&R | MDF / SASCI | MDF |  | Construction of Stadium at Village Daba | 323.39 | 290.89 |  |  | 931 dt 12.10.23 | 100/EEC dt 13.10.23 | Asis Builders |  | 12 |  | 95 |  |  | File sent for revision of work | In Progress
MCL-0221 | C | South |  | B&R | MC Funds / General Quota | MC |  | Relocation and construction of Lohara Bridge in alignment with the Missing Link-2 Part C with Southern Bye Pass Project Ludhiana | 1194.48 | 1194.48 |  |  | 3333 dt 05.12.24 | 145/EEC DT 26.11.24 | M/s Tarmac Road and Roof Builders. |  | 12 |  | 80 |  |  | Work will start after Canal Closure | In Progress
MCL-0222 | C | South | 43 | B&R | MC Funds / General Quota | MC |  | Laying RMC in st.no.19,20 and link of Mohalla Kot Mangal and St.No.1 Mohalla Gurpal Nagar. | 51.92 | 28.01 |  |  | 3341 dt 05.12.24 | 156/EEC dt 24.12.24 | M/s Capital Construction Co. |  | 4 |  | 90 |  |  | Work held up due to 24X7 W/S line. | Delayed/Held Up
MCL-0223 | C | South | 43 | B&R | MC Funds / General Quota | MC |  | Laying RMC in St.No.2, St.No. 7 ½ and Main street of Mohalla Hargobind Nagar. | 75.15 | 40.54 |  |  | 3335 dt 05.12.24 | 157/EEC dt 24.12.24 | M/s Capital Construction Co. |  | 5 |  | 30 |  |  | Work stopped due to dispute | Delayed/Held Up
MCL-0224 | C | South | 38 | B&R | MC Funds / General Quota | MC |  | Construction of Road from Shamshan Ghat to Bapu market via Radha Swami Satsang Ghar Lohara. | 84.28 | 57.07 |  |  | 720 dt 09.04.25 | 165/EEC dt 28.04.25 | Apex Builders |  | 3 |  | 0 |  |  | Work held up due to 24X7 W/S line. | Delayed/Held Up
MCL-0225 | C | South | 34 | B&R | MC Funds / General Quota | MC |  | Construction of 33' road from Giaspura Park to Pippal Chowk. | 172.89 | 107.19 |  |  | 726 dt 09.04.25 | 166/EEC dt 28.04.25 | M/s Hitesh aggarwal contractor |  | 6 |  | 95 |  |  | File sent for revision of work | In Progress
MCL-0226 | C | South |  | B&R | MC Funds / General Quota | MC |  | Construction of RCC road from wine shop to Giaspura Chowk | 124.53 | 74.73 |  |  | 820 dt 06.05.25 | 181/EEC dt 22.05.25 | Apex Devlopers |  | 8 |  | 85 |  |  | Work in progress | In Progress
MCL-0227 | C | South | 38 | B&R | MC Funds / General Quota | MC |  | Construction of road from Simran palace to Morgan crossing. | 99.94 | 61.96 |  |  | 729 dt 09.04.25 | 182/EEC dt 22.05.25 | Hitesh Aggarwal |  | 8 |  | 30 |  |  | Work held up due to 24X7 W/S line. | Delayed/Held Up
MCL-0228 | C | South | 35 | B&R | MC Funds / General Quota | MC |  | Laying 80mm thick I/tiles balance streets mohalla Maha Singh Nagar. | 67.42 | 38.44 |  |  | 830 dt 06.05.25 | 189/EEC dt 26.06.25 | Apex Devlopers |  | 5 |  | 95 |  |  | Work in progress. | In Progress
MCL-0229 | C | South | 31 | B&R | MC Funds / General Quota | MC |  | Construction of RCC roads from NPC upto Daba road and link on GT road. | 179.36 | 97.84 |  |  | 1021 dt 06.05.25 | 195/EEC dt 20.08.25 | LRY labour Contractor. |  | 8 |  | 20 |  |  | Work in progress. | In Progress
MCL-0230 | C | South | 32 | B&R | MC Funds / General Quota | MC |  | Construction of RCC road from Giaspura Chowk to Eastman Chowk. | 326.57 | 178.14 |  |  | 1020 dt 06.05.25 | 192/EEC dt 20.08.25 | LRY labour Contractor. |  | 12 |  | 60 |  |  | Work in progress. | In Progress
MCL-0231 | C | South | 32 | B&R | Councillor Quota (CQ) | MC Funds (CQ) |  | P/ Fixing 80mm thick I/Tiles in Mohalla Makkar Colony, Dhandari Kalan & Shanti Nagar, W. No. 32. | 76.48 | 42.66 |  |  | 1033 dt 06.05.2025 | 05/EEC dt 27.02.2026 | Navyug Company |  | 3 |  | 30 |  |  | Work in progress | In Progress
MCL-0232 | C | South | 27 | B&R | MC Funds / General Quota | GQ |  | Construction Of Rooms, Boundary wall and I/ Tiles adjoining Sewa Kendra Water Tank Sherpur | 49.73 | 42.82 |  |  | 1027 dt 06.05.25 | 10/EEC dt 27.02.2026 | Teg Builders |  | 6 |  | 25 |  |  | Work in progress | In Progress
MCL-0233 | C | South | 35 | B&R | Councillor Quota (CQ) | MC FUNDS (CQ) |  | Laying RMC in St.No. 2,3 & 5 of Mohalla Fateh Singh Nagar W.No.35 | 19.37 | 11.62 |  |  | 2721 dt 19.02.2026 | 27/EEC dt 02.03.2026 | Varinder Singh Govt. Contractor |  | 2 |  | 10 |  |  | work in progress | In Progress
MCL-0234 | C | South | 36 | B&R | Councillor Quota (CQ) | MC FUNDS (CQ) |  | Laying RMC in various streets of Lohara Village and Basant Nagar W.No.36 | 54.86 | 35.7 |  |  | 2840 dt 19.02.26 | 30/EEC dt 02.03.2026 | T And G Construction Co |  | 3 |  | 30 |  |  | work in progress | In Progress
MCL-0235 | C | South | 38 | B&R | Councillor Quota (CQ) | MC FUNDS (CQ) |  | Laying RMC in various streets of Ishar Nagar W.No-38 | 21.21 | 12.17 |  |  | 2722 dt 19.02.26 | 15/EEC dt 02.03.2026 | Neeraj Joshi |  | 2 |  | 60 |  |  | work in progress | In Progress
MCL-0236 | C | South | 31 | B&R | Councillor Quota (CQ) | MC FUNDS (CQ) |  | Laying RMC in Streets of Mohalla Bhagwan Nagar W. No.31 | 72.79 | 44 |  |  | 2841 dt 19.02.2026 | 18/EEC dt 02.03.2026 | Capital Const.Co. |  | 4 |  | 0 |  |  | inaugration pending. | Delayed/Held Up
MCL-0237 | C | South | 27 | B&R | MC Funds / General Quota | MC |  | Construction of central Verge HP Dharam Kanda, upto Opp Govt.High School Sherpur W.No.27 | 98.83 | 69.19 |  |  | 2727 dt 19.02.2026 | 37/EEC dt 02.03.2026 | M/S Apex Devlopers |  | 5 |  | 10 |  |  | work in progress | In Progress
MCL-0238 | C | South | 27 | B&R | Councillor Quota (CQ) | MC Funds (CQ) |  | Laying RMC in various streets of baba gajjamall Jain Colony & Mohindra Colony, W.No.27 | 16.48 | 9.7 |  |  | 2708 dt 19.02.2026 | 33/EEC dt 02.03.2026 | Asis Builders |  | 2 |  | 20 |  |  | work in progress | In Progress
MCL-0239 | C | South | 37 | B&R | Councillor Quota (CQ) | MC Funds (CQ) |  | Laying RMC Balance Streets of Basant Nagar Halka South, W.No.37 | 24.96 | 14.69 |  |  | 2726 dt 19.02.26 | 34/EEC dt 02.03.2026 | Asis Builders |  | 2 |  | 0 |  |  | inaugration pending. | Delayed/Held Up
MCL-0240 | C | South | 32& 34 | B&R | MC Funds / General Quota | MC Funds (GQ) |  | Laying RMC in Asian Bike Street Dhandari Kalan Sua Road w.no. 32 and various streets of Guru Nanak Nagar W.No. 34 | 63.73 | 36.56 |  |  | 2757 dt 19.02.26 | 36/EEC dt 02.03.2026 | Neeraj Joshi |  | 4 |  | 60 |  |  | work in progress | In Progress
MCL-0241 | C | South | 34 & 35 | B&R | MC Funds / General Quota | MC Funds (GQ) |  | Laying RMC in St. no. 2,3 & links of Captain Sewa Singh Nagar W.No. 34 and various roads of Daba Village adjoining Nanka Darbar Gurudwara Sahib and JB Karyana Store in W. no. 35 | 93.65 | 57.4 |  |  | 2846 dt 19.02.26 | 41/EEC dt 02.03.2026 | The Gill Co op Diploma Holder Society. |  | 5 |  | 0 |  |  | inaugration pending. | Delayed/Held Up
MCL-0242 | C | South | 32 & 39 | B&R | Councillor Quota (CQ) | MC Funds (CQ) |  | Laying RMC in street no. 5 of Guru Gobind Singh Nagar in W.No. 39 and Street near Mini Rose Garden W.No. 32 | 49.87 | 33.67 |  |  | 2724 dt 19.02.26 | 31/EEC dt 02.03.2026 | T And G Construction Co |  | 3 |  | 20 |  |  | work in progress | In Progress
MCL-0243 | C | South | 32 | B&R | MC Funds / General Quota | MC Funds (GQ) |  | Laying RMC in Dhandari Kalan road W.No. 32 | 57.6 | 33.41 |  |  | 2710 dt 19.02.2026 | 40/EEC dt 02.03.2026 | M/S Apex Devlopers |  | 3 |  | 0 |  |  | inaugration pending. | Delayed/Held Up
MCL-0244 | C | South | 33 | B&R | MC Funds / General Quota | MC Funds (GQ) |  | Laying RMC in various streets of Makkar Colony W.No. 33 | 76.08 | 43.64 |  |  | 2758 dt 19.02.26 | 35/EEC dt 02.03.26 | Neeraj Joshi. |  | 4 |  | 20 |  |  | work in progress | In Progress
MCL-0245 | C | South | 32 | B&R | MC Funds / General Quota | MC Funds (GQ) |  | Laying RMC near PSPCL road street and Mohalla Shanti Nagar Link in W.No. 32 | 59.95 | 34.77 |  |  | 2711 dt 19.02.26 | 39/EEC dt 02.03.2026 | M/S Apex Devlopers |  | 3 |  | 40 |  |  | work in progress | In Progress
MCL-0246 | C | South | 32 | B&R | MC Funds / General Quota | MC Funds (GQ) |  | Reconstruction of Road Dhandari Phirni W.No.32.(NCAP Funds). | 94.37 | 70.58 |  |  | 2837 dt 19.02.26 | 38/EEC dt 02.03.2026 | Dugra Construction Co. |  | 5 |  | 10 |  |  | work in progress | In Progress
MCL-0247 | C | South | 38 | B&R | Councillor Quota (CQ) | MC Funds (CQ) |  | Laying RMC in Various street of Captain Nagar W.No. 38, St. no. 9 link and Isher Nagar Block-C streets in w. no. 38 and Various Streets of Mohalla Ishar Nagar And begoana Street | 67.18 | 40.31 |  |  | 2728 dt 19.02.2026 | 50/EEc dt 09.04.2026 | M/S Apex Devlopers |  | 4 |  | 0 |  |  | inaugration pending. | Delayed/Held Up
MCL-0248 | C | South | 37 | B&R | Rangla Punjab | Rangla Punjab |  | Laying RMC in street no. 8 of Guru Gobind Singh Nagar W. no. 37 | 32.43 | 21.37 |  |  | 3448 dt 21.04.2026 | 51/EEC dt 30.04.2026 | K.S. Constructions |  | 3 |  | 40 |  |  | work in progress | In Progress
MCL-0249 | C | South | 32 | B&R | Rangla Punjab | Rangla Punjab |  | Providing and Installation of Open air Gym Equipments Dhandari Kalan W.no. 32 | 8 | 4.64 |  |  | 3455 dt 21.04.26 | 52/EEC dt 30.04.2026 | Aggarwal Builders |  | 2 |  | 20 |  |  | work in progress | In Progress
MCL-0250 | C | South | 33 | B&R | Rangla Punjab | Rangla Punjab |  | Laying RMC in various streets of Satguru Nagar & Karamjit Nagar Halka South W. no. 33 | 76.57 | 49.77 |  |  | 3450 dt 21.04.2026 | 55/EEC dt 30.04.2026 | M/S Ashok Kumar Sobti |  | 4 |  | 20 |  |  | work in progress | In Progress
MCL-0251 | C | South | 35 | B&R | MC Funds / General Quota | MC FUNDS |  | Laying RMC in Streets No-1 & 5 of Mohalla Guru Gobid Singh Nagar w. No-35 | 35.91 | 20.02 |  |  | 3465 dt 21.04.2026 | 56/EEC dt 08.05.2026 | Godwyn |  | 1.5 |  | 0 |  |  | inaugration pending. | Delayed/Held Up
MCL-0252 | C | South | 33 | B&R | MPLAD Funds | MP LAD |  | Construction of Bathrooms in Shamshan Ghat Lohara W.no.33 | 4.5 | 4.39 |  |  | 3461 dt 21.04.2026 | 57/EEC dt 08.05.2026 | Kohinoor Builders |  | 3 |  | 0 |  |  | inaugration pending. | Delayed/Held Up
MCL-0253 | C | South | 35 | B&R | MC Funds / General Quota | MC FUNDS |  | P/F 80MM Thick I/Tiles Streets No-18,1 and Links Mohalla Fateh Singh Nagar W. No-35 | 38.14 | 21.26 |  |  | 3464 dt 21.04.2026 | 59/EEC dt 08.05.2026 | Godwyn |  | 1.5 |  | 0 |  |  | inaugration pending. | Delayed/Held Up
MCL-0254 | C | South | 36 | B&R | Councillor Quota (CQ) | MC FUNDS (CQ) |  | Laying RMC in Streets of Mohalla Gurmail Nagar Dhillon Nagar and Basatn Nagar in W. No-36 | 27.63 | 18.42 |  |  | 3413 dt 21.04.2026 | 61/EEC dt 08.05.2026 | Godwyn infra |  | 2 |  | 0 |  |  | inaugration pending. | Delayed/Held Up
MCL-0255 | C | South | 50 | B&R | MPLAD Funds | MP LAD |  | Construction of Bathrooms in Shamshan Ghat Dholewal W.no.50 | 4.5 | 4.44 |  |  | 3456 dt 21.04.2026 | 63/EEC dt 08.05.2026 | Kohinoor Builders |  | 3 |  | 0 |  |  | inaugration pending. | Delayed/Held Up
MCL-0256 | C | South | 35 | B&R | Councillor Quota (CQ) | MC FUNDS (CQ) |  | P/F of informatory sign board in various streets of W.No.35 | 8.5 | 6.94 |  |  | 3421 dt 21.04.2026 | 64/EEC dt 08.05.2026 | Glisten |  | 2 |  | 0 |  |  | inaugration pending. | Delayed/Held Up
MCL-0257 | C | South | 43 | B&R | MC Funds / General Quota | MC Funds (GQ) |  | Laying RMC in street no. 11/5,11/6 and 11/7 of Kabir Nagar in W.No. 43 | 49.99 | 29.66 |  |  | 3416 dt 21.04.2026 | 65/EEC dt 08.05.2026 | Prince Sharma |  | 3 |  | 0 |  |  | inaugration pending. | Delayed/Held Up
MCL-0258 | C | South | 37 | B&R | MC Funds / General Quota | MC Funds (GQ) |  | P/F 80MM thick I/Tiles in Streets of Mohalla Gobind Nagar and Azad Nagar in W. No-37 | 39.71 | 26.21 |  |  | 3415 dt 21.04.2026 | 67/EEC dt 08.05.2026 | N.S.Infra |  | 3 |  | 0 |  |  | inaugration pending. | Delayed/Held Up
MCL-0259 | C | South | 32 | B&R | Councillor Quota (CQ) | MC Funds (CQ) |  | P/F 80mm thick I/Tiles in various streets Shanti Nagar in W.No. 32 | 48.65 | 31.63 |  |  | 3411 dt 21.04.2026 | 68/EEC dt 08.05.2026 | N.S.Infra |  | 3 |  | 0 |  |  | inaugration pending. | Delayed/Held Up
MCL-0260 | C | South | 38 | B&R | MC Funds / General Quota | MC FUNDS |  | P/F 60MM I/Tiles in Streets 5L, 6L, 13R & Links of Mohalla Isher Nagar W. No.38 | 31.45 | 17.53 |  |  | 3480 dt 21.04.2026 | 70/EEC dt 08.05.2026 | Godwyn |  | 1.5 |  | 0 |  |  | inaugration pending. | Delayed/Held Up
MCL-0261 | C | South | 35 | B&R | MC Funds / General Quota | MC FUNDS |  | P/F 60mm I/Tiles Streets of 6 to 12 & St No. 17 in Mohalla Fateh Singh Nagar W. No. 35 | 87.31 | 50.65 |  |  | 3474 dt 21.04.2026 | 72/EEC dt 08.05.2026 | M/S Apex Devlopers |  | 3 |  | 0 |  |  | inaugration pending. | Delayed/Held Up
MCL-0262 | C | South |  | B&R | MDF / SASCI | SASCI Funds |  | Construction of various roads in South Constituency Zone C. | 564.33 | 537.8 |  |  | 2681 dt 11.02.2026 | 77/EEC dt 08.05.2026 | M/S Hitesh Aggarwal Cont. |  | 3 |  | 25 |  |  | Work in progress. | In Progress
MCL-0263 | C | South | Gen | B&R | MC Funds / General Quota | MC Funds (GQ) |  | Construction of Fire Station at Dhandari Kalan in South Constituency. | 189.77 | 187.68 |  |  | in-anticipation by Worthy Mayor on dt 21.05.2026 | 78/EEC dt 21.05.2026 | M/S Parveen Sehgal |  | 8 |  | 0 |  |  | Dispute at Site | Delayed/Held Up
MCL-0264 | C | South | 35 | B&R | Rangla Punjab | Rangla Punjab |  | Construction of RCC road from Mair Di Chakki Chowk to Near Daba Village W. No. 35 | 61.02 | 51.46 |  |  | 3110 dt 25.02.26 | 79/EEC dt 22.06.26 | Varinder Singh Govt Contractor |  | 4 |  | 20 |  |  | Work in progress. | In Progress
MCL-0265 | C | South | 38 | B&R | Rangla Punjab | Rangla Punjab |  | Construction of Dispensary on Shamshan Ghat road Lohara W. NO. 38 | 14.99 | 13.67 |  |  | in-anticipation by Worthy Mayor on dt 13.06.26 | 80/EEC dt 22.06.26 | Smridhi Construction |  | 4 |  | 5 |  |  | Work in progress. | In Progress
MCL-0266 | C | South | 32 | B&R | Rangla Punjab | Rangla Punjab |  | Reconstruction of community centre on Campa Cola road in village Dhandari kalan. W. no. 32 | 25 | 22.61 |  |  | 3472 dt 21.04.26 | 81/EEC dt 22.06.26 | Smridhi Construction |  | 4 |  | 5 |  |  | Work in progress. | In Progress
MCL-0267 |  |  |  | B&R | Other / Unspecified |  |  | Total | 5045.47 | 3922.33 | [12 empty] | Not Started
MCL-0268 | A | North | 86&88 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | Estimate for Bridge across Budha Naala Near Shivpuri Ludhina |  | 204.76 | 204.76 |  | 03 Dt.26-03-2025 | 72/LOA dt. 28-01-2025 | M/s Hitesh Aggarwal | 02-05-2026 | 9 Months | 27-10-2025 | 95 |  | 252.71 | Work in Progress. | In Progress
MCL-0269 | A | North | Gen | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | Estimate for Bridge across Budha Naala Near Manna Singh Nagar Ludhina |  | 275.94 | 275.94 |  | 04 Dt.26-03-2025 | 73/LOA dt. 28-01-2025 | J.K. Infocon Pvt. Ltd | 18-02-2025 | 9 Months | 27-10-2025 | 85 |  | 214.71 | Work in Progress. | In Progress
MCL-0270 | A | North | 89 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | Construction of Senior Citizen Home cum Community Center in Peeru Banda in Ward No.84. |  | 23.53 | 23.53 |  | 3099 Dt.22-11-2024 | 40/EEA dt. 27-11-2024 | M/s Smridhi Constructions | 13-12-2024 |  |  | 90 |  | 20.93 | Work in Progress. | In Progress
MCL-0271 | A | North | 89 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | Construction of Senior Citizen Home cum Community Center in ward no.84. |  | 18.83 | 18.83 |  | 2645 Dt.24-09-2024 | 168/EEA dt. 23-10-2024 | The Saharan Majra Co-op | 11-11-2024 | 3 Months | 22-01-2025 | 80 |  | 0 | Work in Progress. | In Progress
MCL-0272 | A | North | 95 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | Construction of Badminton Indoor Stadium Backside Duke factory near Jalandhar Byepass Ludhiana. |  | 69.9 | 69.9 |  | 3097 Dt.22-11-2024 | 38/EEA dt. 27-11-2024 | M/s Apurva Inc | 14-12-2025 | 6 Months | 26-05-2025 | 20 |  | 0 | Work in Progress. | In Progress
MCL-0273 | A | North | 87 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | Construction of Metailed Road to Join Missing Link of Service Lane Backside Petrol Pump in Ward No.87. |  | 47.18 | 47.18 |  | 1741 Dt.13-10-2025 | 01/EEA dt 25-08-2025 | M/s Soham Construction Company | 15-09-2025 | 3 Months | 24-11-2025 | 85 |  | 42.08 | Work in Progress. | In Progress
MCL-0274 | A | North | 90 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | Construction of Bijli Market Main Road & Streets Near Lakkar Bazar With RMC in Field Ganj Ward No.90. |  | 49.15 | 49.15 |  | 1747 Dt.13-10-2025 | 06/EEA dt 24-10-2025 | M/S Capital Construction Co. | 15-11-2025 | 6 Months | 23-04-2026 | 40 |  | 27.67 | Work in Progress delayed due to internal city area. | Delayed/Held Up
MCL-0275 | A | North | 90 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | P/F Painting Road Marking & Cat Eyes at Various Main Roads of Ward No.90. |  | 18.13 | 18.13 |  | 1830 Dt.13-10-2025 | 07/EEA dt 24-10-2025 | M/S Capital Construction Co. | 18-11-2025 | 3 Months | 23-01-2026 | 40 |  | 9.96 | Work in Progress delayed due to bitumen Work. | Delayed/Held Up
MCL-0276 | A | North | 90 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | Construction of Lekhi Vehra With RMC in Ward No.90. |  | 13.34 | 13.34 |  | 1744 Dt.13-10-2025 | 08/EEA dt 24-10-2025 | M/s Godwyn Infra | 19-11-2025 | 3 Months | 23-01-2026 | 25 |  | 0 | Work in Progress. | In Progress
MCL-0277 | A | North | 90 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | Construction of Side Berms With RMC of Main Gurudwara Dukhniwaran Sahib Road Ward No.90. |  | 24.81 | 24.81 |  | 1746 Dt.13-10-2025 | 09/EEA dt 24-10-2025 | M/s Godwyn Infra | 11-11-2025 | 3 Months | 23-01-2026 | 50 |  | 9.91 | Work in Progress. | In Progress
MCL-0278 | A | North | 88 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | P/L of RMC M-30 in Damage Streets of Mohalla Shivpuri in Ward No.88. |  | 35.54 | 35.54 |  | 1832 Dt.13-10-2025 | 10/EEA dt 24-10-2025 | M/s Neeraj Joshi | 13-11-2025 | 4 Months | 23-02-2026 | 50 |  | 0 | Work in Progress. | In Progress
MCL-0279 | A | North | 84 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | Laying RMC M-30 in Streets of Near Guru Ravidass Mandir of Main Peeru Banda Ward No 84.(New Ward No.89) |  | 26.83 | 26.83 |  | 1749 Dt.13-10-2025 | 12/EEA dt 24-10- 2025 | M/s Neeraj Joshi | 11-12-2025 | 3 Months | 23-01-2026 | 35 |  | 8.41 | Laying of Water Supply Line Work in Progress. | In Progress
MCL-0280 | A | North | 95 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | P/L of RMC M-30 in Streets of New Ashok Nagar in Ward No.95 |  | 57.6 | 57.6 |  | 1748 Dt.13-10-2025 | 13/EEA dt 24-10-2025 | M/s LRY Labour Constractor | 13-11-2025 | 6 Months | 22-04-2026 | 90 |  | 0 | Work in Progress. | In Progress
MCL-0281 | A | North | 94 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | P/L of RMC M-30 in Streets of Mohalla Saroop Nagar New Janak Puri & Suiyan Wala Hospital Road in Ward No.89. (New Ward no.94) |  | 52.87 | 52.87 |  | 1745 Dt.13-10-2025 | 14/EEA dt 24-10-2025 | M/s LRY Labour Constractor | 11-11-2025 | 6 Months | 22-04-2026 | 35 |  | 0 | Work in Progress. | In Progress
MCL-0282 | A | North | 85 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | Laying RMC M-30 in Streets of Mohalla Gandhi Nagar & Mohalla Basant Nagar St no.6 in Ward No.85. (New Ward No.88) |  | 41.12 | 41.12 |  | 1742 Dt.13-10-2025 | 16/EEA dt 24-10-2025 | M/s Navdeep Gupta & Company | 13-11-2025 | 4 Months | 23-02-2026 | 25 |  | 0 | Delayed due to Water Supply Line. | Delayed/Held Up
MCL-0283 | A | North | Gen | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | Painting of Elevated Road Deck Slab Roof,Jagroan Bridge,Ludhiana. |  | 43.35 | 43.35 |  |  | 18/EEA dt 12-12-2025 | M/s K.S Constructions |  | 3 Months | 03-11-2026 | 0 |  | 0 | Inauguration Pending. Will start after Elevated road work. | Delayed/Held Up
MCL-0284 | A | North | Gen | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | Painting of Kerb Stone Elevated Road Pillars & Walls Below Elevated Road Jagroan Bridge,Ludhiana. |  | 17.15 | 17.15 |  |  | 19/EEA dt 12-12-2025 | M/s N.S Infra | 01-05-2026 | 3 Months | 03-11-2026 | 5 |  | 0 | Work in Progress. | In Progress
MCL-0285 | A | North | 86 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | Laying RMC M-30 in Streets of Farid Nagar in Ward No.86. (New Wrad No.8). |  | 25.07 | 25.07 |  | 2274 DT.21-11-2025 | 20/EEA dt 22-12-2025 | M/s Neeraj Joshi | 13-01-2026 | 3 Months | 21-03-2026 | 60 |  | 19.81 | Work in Progress. | In Progress
MCL-0286 | A | North | 87 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | Laying RMC M-30 in Streets of Arjun Nagar & Vai Kunth Nagar in Ward No.87 |  | 26.39 | 26.39 |  | 2272 Dt.21-11-2025 | 21/EEA dt 22-12-2025 | M/s Neeraj Joshi | 14-01-2026 | 5 Months | 21-05-2026 | 90 |  | 26.03 | Work in Progress. | In Progress
MCL-0287 | A | North | 90 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | Construction of Balance Streets of Shahpur Road With RMC in Ward No.90. |  | 21.65 | 21.65 |  | 2432 DT.05-01-2026 | 23/EEA dt 28-01-2026 | M/s Neeraj Joshi | 02-10-2026 | 3 Months | 27-04-2026 | 0 |  | 0 | Inauguration Pending. | Delayed/Held Up
MCL-0288 | A | North | 90 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | Construction of Streets With RMC Backside JMD Mall in Ward No.90. |  | 25.62 | 25.62 |  | 2434 Dt.05-01-2026 | 24/EEA dt 28-01-2026 | M/s Neeraj Joshi | 02-11-2026 | 3 Months | 27-04-2026 | 50 |  | 0 | Work in Progress. | In Progress
MCL-0289 | A | North | 95 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | Laying RMC M-30 in Streets of New Aman Nagar & Bhagat Singh Colony in Ward No.95. |  | 25.41 | 25.41 |  | 2281 Dt.21-11-2025 | 26/EEA dt 28-01-2026 | M/s Navyug Company | 15-02-2026 | 3 Months | 27-04-2026 | 80 |  | 22.76 | Work in Progress. | In Progress
MCL-0290 | A | North | 88 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | Recarpeting of Road Along Budha Nallah from Chand Cinema Pully to Shivpuri Pully in Ward No. |  | 87.55 | 87.55 |  | 2285 Dt.21-11-2025 | 49/EEA dt 20-02-2026 | M/s Maruti Construction Co. | 03-02-2026 | 6 Months | 19-08-2026 | 50 |  | 48.22 | Work in Progress. | In Progress
MCL-0291 | A | North | 94 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | P/L of RMC M-30 in Streets of Mahavir Homes Colony & Balance Streets of Rajauri Garden Colony in Ward No.94 (new Ward No.93) |  | 52.13 | 52.13 |  | 2273 Dt.21-11-2025 | 50/EEA dt 20-02-2026 | M/s Navyug Company | 03-04-2026 | 6 Months | 19-08-2026 | 0 |  | 0 | Inauguration Pending. | Delayed/Held Up
MCL-0292 | A | North | 88 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | P/L of RMC -30 in Various Streets of Gandhi Nagar in Ward No.88. |  | 59.52 | 59.52 |  | 2469 Dt.05-01-2026 | 51/EEA dt 20-02-2026 | M/s Varinder Singh Contractor | 03-03-2026 | 6 Months | 19-08-2026 | 40 |  | 0 | Delayed due to Water Supply Line. | Delayed/Held Up
MCL-0293 | A | North | 88 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | Construction of Retaining Wall along Budha Darya from Shivpuri Pully to Jain Nagar Pully (LHS) Ward No.88 (Old Ward No.85) |  | 80.68 | 80.68 |  | 2475 Dt.05-01-2026 | 52/EEA dt 20-02-2026 | M/s Varinder Singh Contractor | 03-03-2026 | 9 Months | 19-11-2026 | 90 |  | 76.07 | Work in Progress. | In Progress
MCL-0294 | A | North | 88 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | Construction of Retaining Wall along Budha Darya from Jain Nagar Towards Basant Nagar in Ward No.88 |  | 77.2 | 77.2 |  | 2474 Dt.05-01-2026 | 53/EEA dt 20-02-2026 | M/s Apex Developers | 04-05-2026 | 6 Months | 19-08-2026 | 60 |  | 0 | Work in Progress. | In Progress
MCL-0295 | A | North | 94 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | Laying RMC M-30 in Streets of Model Colony in Ward No.89.(New Ward No.94) |  | 37.93 | 37.93 |  | 2882 Dt.21-11-2025 | 54/EEA dt 20-02-2026 | M/s K.S Constructions | 03-03-2026 | 4 Months | 19-06-2026 | 35 |  | 0 | Work in Progress. | In Progress
MCL-0296 | A | North | 94 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | P/L of RMC M-30 in Streets of Bhagwan Dass Colony in Ward No.89 (New Ward No.94) |  | 56.42 | 56.42 |  | 2284 Dt.21-11-2025 | 55/EEA dt 20-02-2026 | M/s K.S Constructions | 03-07-2026 | 6 Months | 19-08-2026 | 40 |  | 0 | Work in Progress. | In Progress
MCL-0297 | A | North | 86 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | Laying RMC M-30 in Various Streets of Ward No.88 (New Ward No.86) |  | 46.06 | 46.06 |  | 2278 Dt.21-11-2025 | 56/EEA dt 20-02-2026 | M/s Navyug Company | 03-12-2026 | 6 Months | 19-08-2026 | 75 |  | 22.61 | Work in Progress. | In Progress
MCL-0298 | A | North | 1 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | Construction of Metalled Road in adjoining streets of Nagesh Hosiery in Ward No.1. |  | 49.87 | 49.87 |  | 2463 Dt.05-01-2026 | 57/EEA dt 20-02-2026 | M/s Somaya Infrastructures |  | 3 Months | 19-05-2026 | 0 |  | 0 | Inauguration Pending. | Delayed/Held Up
MCL-0299 | A | North | 1 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | Recarpeting of Akash Nagar Main Road in Ward No.1. |  | 41.25 | 41.25 |  | 2466 Dt.05-01-2026 | 58/EEA dt 20-02-2026 | M/s Somaya Infrastructures | 04-04-2026 | 5 Months | 19-07-2026 | 60 |  | 25.34 | Work Held up due to Sewer Line. | Delayed/Held Up
MCL-0300 | A | North | 89 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | P/L of RMC M-30 in Kharbanda Chowk,Bohar Wala Gurudwara Nali Mohalla & Beli Ram Chowk Streets in Ward No.84.(New Ward No.89) |  | 51.35 | 51.35 |  | 2280 Dt.21-11-2025 | 61/EEA dt 20-02-2026 | M/s Asis Builders | 03-09-2026 | 6 Months | 19-08-2026 | 40 |  | 26.31 | Work in Progress. | In Progress
MCL-0301 | A | North | Gen | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | Development of Green Belt along Jalandhar Byepass upto MC Limit. |  | 68.49 | 68.49 |  | 2827 Dt.19-02-2026 | 64/EEA dt 25-02-2026 | M/s Rajeev Enterprises | 03-12-2026 | 6 Months | 24-08-2026 | 95 |  | 67.89 | Work in Progress. | In Progress
MCL-0302 | A | North | 88 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | Construction of Retaining Wall Along Budha Darya From Basant Nagar Towards Gandhi Nagar in Ward No.88 |  | 78.49 | 78.49 |  | 2752 Dt.19-02-2026 | 65/EEA dt 25-02-2026 | M/s Asis Builders | 04-04-2026 | 6 Months | 24-08-2026 | 50 |  | 0 | Work in Progress. | In Progress
MCL-0303 | A | North | 88 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | Construction of Joybox or Playground at Ward No.86 (New Ward No.88) |  | 22.96 | 22.96 |  | 2829 Dt.19-02-2026 | 67/EEA dt 25-02-2026 | M/s Subodh Batish |  | 3 Months | 24-05-2026 | 0 |  | 0 | Held up due to Retaining Wall Work. | Delayed/Held Up
MCL-0304 | A | North | 95 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | Construction of Streets With RMC M-30 in Area Aman Vihar Colony Ward No.95. |  | 27.84 | 27.84 |  | 2739 Dt.19-02-2026 | 68/EEA dt 25-02-2026 | M/s Navyug Company |  | 3 Months | 24-05-2026 | 0 |  | 0 | Inauguration Pending. | Delayed/Held Up
MCL-0305 | A | North | 1 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | Construction of Adjoining Streets of Guru Har Rai Nagar with RMC M-30 in Ward No.1 |  | 34.48 | 34.48 |  | 2740 Dt.19-02-2026 | 71/EEA dt 25-02-2026 | M/s Asis Builders | 03-04-2026 | 3 Months | 24-05-2026 | 25 |  | 0 | Work in Progress. | In Progress
MCL-0306 | A | North | 89 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | P/Laying RMC M-30 in Various Streets of Naali Mohalla in Ward No.89, Ludhiana |  | 43.37 | 43.37 |  | 2849 Dt.19-02-2026 | 72/EEA dt 25-02-2026 | M/s Asis Builders | 17-03-2026 | 3 Months | 24-05-2026 | 40 |  | 0 | Work in Progress. | In Progress
MCL-0307 | A | North | 89 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | Construction of Joybox or Playground at Ward No.89 |  | 22.96 | 22.96 |  | 2828 Dt.19-02-2026 | 73/EEA dt 25-02-2026 | M/s Subodh Batish |  | 3 Months | 24-05-2026 | 0 |  | 0 | Inauguration pending. | Delayed/Held Up
MCL-0308 | A | North | 94 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | Construction of Joybox or Playground at Ward No.94 |  | 22.96 | 22.96 |  | Dt.19-02-2026 | 75/EEA dt 25-02-2026 | M/s Subodh Batish |  | 3 Months | 24-05-2026 | 0 |  | 0 | Inauguration Pending. | Delayed/Held Up
MCL-0309 | A | North | 86 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | P/F of RMC M-30 in Streets B/S Ram Rai School & Sarvanand Colony in Ward No.86 |  | 30.44 | 30.44 |  | 2470 Dt.05-01-2026 | 77/EEA dt 25-02-2026 | M/s Navdeep Gupta & Company | 06-01-2026 | 6 Months | 24-08-2026 | 10 |  | 0 | Work in Progress delayed due to laying of Water Supply & Sewer Lines. | Delayed/Held Up
MCL-0310 | A | North | 90 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | Construction of Main Kesar Ganj Mandi with RMC in Ward No.90, Ludhiana |  | 49.09 | 49.09 |  |  | 94/EEA dt.05-05-2026 | M/S LRY Labour Contrator | 15-05-2026 | 4 Months | 09-04-2026 | 90 |  | 0 | Work in Progress. | In Progress
MCL-0311 | A | North | 87 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | P/L of RMC M-30 on streets of Vaishnu Colony in Ward No.87 |  | 22.71 | 22.71 |  |  | 92/EEA dt.05-05-2026 | M/S GODWYN INFRA | 20-05-2026 | 3 Months | 08-04-2026 | 25 |  | 0 | Work in Progress delayed due to laying of Water Supply line. | Delayed/Held Up
MCL-0312 | A | North | 90 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | P/Laying RMC in adjoining streets of Bagh Wali Gali & Streets of Kutcha no 2-3-4 in Ward No.90, Ludhiana |  | 18.82 | 18.82 |  |  | 88/EEA dt.05-05-2026 | M/S Capital Construction Co. | 18-05-2026 | 3 Months | 08-04-2026 | 30 |  | 0 | Work in Progress. | In Progress
MCL-0313 | A | North | 1 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | Laying RMC M-30 in streets of Gurbaksh Nagar & adjoining area in Ward No. 1 |  | 49.14 | 49.14 |  |  | 90/EEA dt.05-05-2026 | M/S Capital Construction Co. | 24-05-2026 | 6 Months | 11-04-2026 | 60 |  | 23.26 | Work in Progress. | In Progress
MCL-0314 | A | North | 1 | Sub-Zone A4 (B&R) | MC Funds / General Quota | MC |  | P/L of RMC M-30 in different streets of Geeta Colony & adjoining area in ward no 1 |  | 53.38 | 53.38 |  |  | 87/EEA dt.05-05-2026 | M/S Capital Construction Co. | 20-05-2026 | 6 Months | 11-04-2026 | 50 |  | 22.65 | Work in Progress. | In Progress
MCL-0315 | A | North | A4 | Sub-Zone A4 (B&R) | MDF / SASCI | SASCI |  | Upgradation of Road with RMC in Area Guru Har Rai Nagar Nagesh Hosiery Road Adjoining Jalandhar Byepass, Ludhiana |  | 501.26 | 501.26 |  |  | 79/EEA dt 09/03/2026 | M/s NKC Construction Pvt. Ltd. | 20-03-2026 | 3 Months | 06-08-2026 | 20 |  | 83.19 | Delayed due to Payment Pending. | Delayed/Held Up
MCL-0316 | A | North | A4 | Sub-Zone A4 (B&R) | MDF / SASCI | MDF |  | Upgradation of Various Main Roads With RMC in North Constituency Zone-A,Ludhiana. |  | 858.33 | 858.33 |  | 2898 Dt.19-02-2026 | 81/EEA dt 25-03-2026 | M/s Gaanesh Kartikey | 04-04-2026 | 3 Months | 24-06-2026 | 50 |  | 182.88 | Work in progress | In Progress
MCL-0317 | A | North | A4 | Sub-Zone A4 (B&R) | MDF / SASCI | MDF |  | Upgradation of Elevated Road from Jagroan Bridge to Chand Cinema by Laying Mastic Asphalt |  | 568.23 | 568.23 |  | 2678 Dt.11-02-2026 | 82/EEA dt 25-03-2026 | M/s Dass Builders | 26-03-2026 | 3 Months | 24-06-2026 | 60 |  | 119.17 | Work in progress | In Progress
MCL-0318 | A | North | A4 | Sub-Zone A4 (B&R) | MDF / SASCI | MDF |  | Upgradation of Roads with RMC in Area Bharti Colony, Akash Nagar adjoining Jalandhar Byepass, Ludhiana |  | 571.5 | 571.5 |  | 2677 Dt.11-02-2026 | 80/EEA Dt.25-03-2026 | M/s Hitesh Aggarwal Cont | 04-04-2026 |  |  | 35 |  | 195.5 | Held up due to Laying of Sewer Line. | Delayed/Held Up
MCL-0319 | A | North | A4 | Sub-Zone A4 (B&R) | MDF / SASCI | MDF |  | Upgradation of various Roads with RMC in Ward No.95, Ludhiana |  | 635.34 | 635.34 |  | 2679 Dt.11-02-2026 | 84/EEA Dt.25-03-2026 | M/s Ashok Kumar Sobti | 26-03-2026 | 3 Months | 24-06-2026 | 75 |  | 338.54 | Work in progress | In Progress
MCL-0320 | A | North | A4 | Sub-Zone A4 (B&R) | MDF / SASCI | MDF |  | Upgradation of various Roads with RMC in Ward No.1, Ludhiana |  | 696.4 | 696.4 |  |  | 85/EEA Dt.25-03-2026 | M/s Kabir Infra | 26-03-2026 |  |  | 70 |  | 269.52 | Delayed due to Laying of Sewer Line. | Delayed/Held Up
MCL-0321 | A2 | Central | 78 | O&M | Councillor Quota (CQ) | CQ |  | Rough Cost Estimate Pro. Laying of Water Supply Line and Sewer Line in Mohar singh nagar st no 2-4 & 7 Ward No78. |  | 24.08 | 24.08 |  | 1442 Dt. 11/08/2025 | 45/G-33 Dt. 25/09/2025 | M/s Kohinoor Builders | 10-01-2025 | 3 | 07-10-2026 | 80 |  | 19.264 | Work in Progress | In Progress
MCL-0322 | A2 | Central | 84 | O&M | Councillor Quota (CQ) | CQ |  | Rough Cost Estimate Prov. Laying/Up-gradation and mtc. of Water Supply & Sewer Line At Different Localities of Ward No. 84. |  | 8.36 | 8.36 |  |  | 71/G-33 Dt. 22/11/2025 | M/s Brar Brothers | 23/11/2025 | 3 | 07-10-2026 | 85 |  | 7.106 | Work in Progress | In Progress
MCL-0323 | A1 | Central | 10 | O&M | Councillor Quota (CQ) | CQ |  | Rough Cost Estimate Prov. Laying/Up-gradation and mtc. of Water Supply & Sewer Line At Different Localities of Ward No. 10 |  | 7.92 | 7.92 |  | 2622 Dt. 11/02/2026 | 83/G-33 Dt. 24/02/2026 | As Contractor | 24/02/2026 | 3 | 07-10-2026 | 80 |  | 6.336 | Work in Progress | In Progress
MCL-0324 | A1 | Central | 9 | O&M | Councillor Quota (CQ) | CQ |  | Rough Cost Estimate Prov. Laying of Sewer Line and Water Supply Line in Basti Sheikh Mohammad Ward No. 9 |  | 18.39 | 18.39 |  | 2607 Dt.11/02/2026 | 100/G-33 Dt. 24/02/2026 | Surya Construction | 24/02/2026 | 3 | 30/10/2026 | 0 |  | 0 | Narrow Streets work will start after monsoon | Not Started
MCL-0325 | A1 | Central | 83 | O&M | MC Funds / General Quota | GQ |  | Rough Cost Estimate Prov. Laying of Sewer and Water Supply Line Mohalla Balmiki Ghatti Ward No. 83 |  | 25.96 | 25.96 |  | 2608 Dt.11/02/2026 | 97/G-33 Dt. 24/02/2026 | Kohinoor Builders | 24/02/2026 | 3 | 30/8/2026 | 50 |  | 12.98 | Work stop from 15-06-2026 due to reason Local mela now work start after monsoon | In Progress
MCL-0326 | A2 | Central | 62 | O&M | MC Funds / General Quota | GQ |  | Providing & Installation of 25 HP Straight Bore T/Well against failed T/Well in Bangru Mohalla, Ward no. 62. |  | 12.63 | 12.63 |  | 2367 Dt.23/08/2024 | 09/G-33 Dt. 18/09/2024 | The Ananda coop L&C Society Ltd. | 18/09/2024 | 3 | 30/8/2026 | 0 |  | 0 | Notice issue to contrator | Not Started
MCL-0327 | A1 | Central | 60 | O&M | MC Funds / General Quota | GQ |  | Providing and Installation of 12.5 HP Submersible T/well in Mohalla Nau Ghara Ward No. 60 |  | 6.48 | 6.48 |  |  | 17/G-33 Dt. 07/10/2024 | The Ananda coop L&C Society Ltd. | 10-07-2024 | 3 | 30/8/2026 | 100 |  | 0 | The streets at the site are narrow, so the machine couldn't be set up. Now, Mr. Thapar has said that they will open a new route, and the work can start after that | Completed
MCL-0328 | A2 | Central | 84 | O&M | Councillor Quota (CQ) | CQ |  | Providing & Installation of 12.5 HP Straight Bore T/Well Against Failed T/well Ktaira Norian Near Dal Bazar Ward No. 84 |  | 6.38 | 6.38 |  | 1724 Dt.13/10/2025 | 66G-33 Dt. 06/11/2025 | M/s Bedi Pump Store | 11-06-2025 | 2 | 30/7/2026 | 0 |  | 0 | Machinary not entered at proposed site due to narrow streets/ Now contractor will arrange small machine and start the work | Not Started
MCL-0329 | A2 | Central | 82 | O&M | MPLAD Funds | MP LAD |  | Providing and Installation of 25 HP Straight Bore T/Well in Mohalla Harbanspura, Ward No. 82, Ludhiana. (MP Lad) |  | 10.96 | 10.96 |  | 2665 Dt.11/02/2026 | 80/G-33 Dt. 24/02/2026 | JCS Electric Works | 24/02/2026 | 3 | 15/7/2026 | 100 |  | 10.96 | electrical meter pending | Delayed/Held Up
MCL-0330 | A2 | Central | 78 | O&M | MC Funds / General Quota | GQ |  | Providing & Installation of 25 HP Straight Bore T/Well Mohar Singh Nagar,Ward No. 78(new) |  | 10.35 | 10.35 |  | 2614 Dt.11/02/2026 | 79/G-33 Dt. 24/02/2026 | JCS Electric Works | 24/02/2026 | 3 | 30-06-2026 | 0 |  | 0 | Notice issue to contactor | Not Started
MCL-0331 | A2 | Central | 78 | O&M | MC Funds / General Quota | GQ |  | Providing and Installation of 25 HP Straight Bore T/Well Against Failed T/well Sadhu Sundar Singh Colony St No. 4 Issa Nagri Ward No. 78 |  | 10.87 | 10.87 |  | 2786 Dt.19/02/2026 | 103/G-33 Dt. 05/03/2026 | Rajdeep Enterprises | 03-05-2026 | 3 | 07-10-2026 | 80 |  | 8.696 | Work in Progress | In Progress
MCL-0332 | A1 | Central | 83 | O&M | MC Funds / General Quota | GQ |  | Providing & Installation of 25 HP Straight Bore T/Well Mohalla Balmik Ghatti Ward No. 83(new) |  | 11.84 | 11.84 |  | 2785 Dt.19/02/2026 | 104/G-33 Dt. 05/03/2026 | ESS Elechmech Enterprises | 03-05-2026 | 3 | 07-10-2026 | 100 |  | 11.84 | Electrical meter pending | Delayed/Held Up
MCL-0333 | A4 | Central | 59 | O&M | MC Funds / General Quota | GQ |  | Rough Cost Estimate Prov. Laying / Up-Gradation of Water Supply Line, Sewer line in Kohlu Wali Gali Qilla Mohalla Near Dispansary Petrol Pump Wali Gali & Mandir Wali Gali in Ward No. 59 |  | 41.81 | 41.81 |  |  | 61/G-33 Dt. 07/03/2024 | The Dynamic Coop. L&C Society Ltd. | 03-07-2024 | 3 | 30/9/2026 | 20 |  | 8.362 | Machinary not entered at proposed site due to narrow streets/ Now contractor will arrange small machine and start the work | In Progress
MCL-0334 | A2 | Central | 56 | O&M | MC Funds / General Quota | GQ |  | Rough Cost Estimate Prov. Laying / Up-Gradation of Water Supply Line, Sewer line in Dhoka Mohalla Street No. 1 and 2, Near Kalra Hospital, Ward No. 56 |  | 33.24 | 33.24 |  | 351 Dt.26/03/2025 | 05/G-33 Dt. 14/04/2025 | M/s Surya Const. | 14/04/2025 | 3 | 30/9/2026 | 60 |  | 19.944 | Low laying area pending work start to be done after monsoon | Delayed/Held Up
MCL-0335 | A2 | Central | 54 | O&M | MC Funds / General Quota | GQ |  | Rough Cost Estimate Prov. Laying of Water Supply Line and Sewer Line At Fatehganj Shanti Nikaten Wali Gali and Near Gurudwara Sahib Wali Gali, Ward No. 54 |  | 23.12 | 23.12 |  | 558 Dt.09/04/2025 | 15/G-33 Dt. 28/04/2025 | Dynamic Tiles | 28/04/2025 | 3 | 30/9/2026 | 50 |  | 11.56 | Pending Sewer work to be done after monsoon | Delayed/Held Up
MCL-0336 | A2 | Central | 56 | O&M | MC Funds / General Quota | GQ |  | Rough Cost Estimate Prov. Laying of Water Supply Line Gulchaman Gali and Its Branch line in Ward No. 56 |  | 40.17 | 40.17 |  | 560 Dt.09/04/2025 | 16/G-33 Dt. 28/04/2025 | ESS Elechmech Enterprises | 28/04/2025 | 3 | 30/7/2026 | 90 |  | 36.153 | Work in Progress | In Progress
MCL-0337 | A1 | Central | 9 | O&M | MC Funds / General Quota | GQ |  | Rough Cost Estimate Prov. Laying of Water Supply Line and Sewer Line From Sunder Nagar Pully to Bajwa Nagar Pully along Budha Dariya Ward No. 83 (old 61) |  | 26.18 | 26.18 |  | 110 Dt.11/08/2025 | 49/G-33 Dt. 25/09/2025 | Ess Elecmech Enterprises | 25/09/2025 | 3 | 30/9/2026 | 0 |  | 0 | Work hold due to road level issue | Not Started
MCL-0338 | A1 | Central | 84 | O&M | Councillor Quota (CQ) | CQ |  | Rough Cost Estmate Prov. Laying of Water Supply Line and Sewer Line in Maddi Bhature Wali Gali & Dr. Kheda wali Gali Ward No. 84 |  | 17.87 | 17.87 |  | 2623 Dt.11/02/2026 | 84/G-33 Dt. 24/02/2026 | ESS Elechmech Enterprises | 24/02/2026 | 3 | 30/7/2026 | 40 |  | 7.148 | Work in Progress | In Progress
MCL-0339 | A1 | Central | 9 | O&M | Councillor Quota (CQ) | CQ |  | Rough Cost Estimate Prov. Laying of Water Supply and Sewer Line at Basti Mani Singh Ward No. 9 |  | 36.58 | 36.58 |  | 2606 Dt.11/02/2026 | 99/G-33 Dt. 24/02/2026 | Surya Construction | 24/02/2026 | 3 | 30/9/2026 | 30 |  | 10.974 | Work in Progress till 30-06-2026 & balance work will start after monsoon | In Progress
MCL-0340 | A2 | North | 90 | O&M | Councillor Quota (CQ) | CQ |  | Rough Cost Estimate Pro. Laying / Up-Gradation of Water Supply line, sewer line IN Thaper PCO wali gali and Hanuman mandir wali gali Ward No.90 |  | 25.41 | 25.41 |  | 2478 Dt.05/01/2026 | 74/G-33 Dt. 30/01/2026 | Kohinoor Builders | 30/01/2026 | 3 | 30/9/2026 | 50 |  | 12.705 | Work in Progress till 30-06-2026 & balance work will start after monsoon | In Progress
MCL-0341 | A2 | North | 90 | O&M | Councillor Quota (CQ) | CQ |  | Rough Cost Estimate Prov. Laying/Up-gradation and mtc. of Water Supply & Sewer Line At Different Localities of Ward No. 90 |  | 7.9 | 7.9 |  | 3285 Dt.25/02/2026 | 107/G-33 Dt. 27/03/2026 | N.S Infra | 27/03/2026 | 3 | 31/8/2026 | 15 |  | 1.185 | This work as per maintenance work | In Progress
MCL-0342 | A2 | North | 90 | O&M | Councillor Quota (CQ) | CQ |  | Rough Cost Estimate Prov. Laying / Up-Gradation of Water Supply Line, Sewer line (Missing Link) in Kucha No. 5,6,7 Field Ganj, Fish Market, Tyre Market Ward No. 64 |  | 45.71 | 45.71 |  |  | 49/G-33 Dt. 29/02/2024 | The Rajowal Coop. L&C Society Ltd. | 29/02/2024 | 3 | 30-10-2026 | 65 |  | 29.7115 | Work in Progress till 30-06-2026 & balance work will start after monsoon | In Progress
MCL-0343 | A2 | North | 90 | O&M | Councillor Quota (CQ) | CQ |  | Rough Cost Estimate Pro. Laying of Water Supply Line and Sewer Line in Backside Local Adda Streets Ward no. 90 |  | 37.19 | 37.19 |  | 1675 Dt.13/10/2025 | 75/G-33 Dt. 30/01/2026 | Kohinoor Builders | 01-02-2026 | 3 | 30-10-2026 | 50 |  | 18.595 | Work in Progress till 30-06-2026 & balance work will start after monsoon | In Progress
MCL-0344 | A3 | East | 2 | O & M | MC Funds / General Quota | GQ |  | Providing, Laying / Up-Gradation of 16" & 24" dia. NP-3 HDPE pipe Sewer Line from Jivan Jyoti School to Phambran Disposal Ward No. 2 |  | 91.39 | 91.39 |  | 2239 dt.21/11/2025 | 05/G-33/XEN/Z-A dt. 01/06/2026 | M/s Deepak Madaan | 06-01-2026 | 3 | 31.12.2026 | 0 |  | 0 | Work will be done after monsoon | Not Started
MCL-0345 | A3 | East | 2,3 | O & M | MC Funds / General Quota | GQ |  | Providing, Laying /Up-gradation of 20" dia. NP=3 HDPE pipe Sewer Line from Phambran Disposal to Shivpuri Chownk. Ward No. 2 |  | 109.42 | 109.42 |  | 2240 dt. 21/11/2025 | 03/G-33/XEN/Z-A dt. 09/05/2026 | Kohinoor Builders | 05-09-2026 | 3 | 08-08-2026 | 50 |  | 54.71 | Work is in Progress | In Progress
MCL-0346 | A3 | East | 3 | O & M | Councillor Quota (CQ) | CQ |  | Providing, Laying Upgradation of 12'' dia UPVC Sewer Line and 4" dia. DI K7 water supply Line at Near Shani Dev Mandir, Extension Basant Vihar ward 3 |  | 35.89 | 35.89 |  | 955 dt. 06/05/2025 | 19/G-33 Dt. 15/05/2025 | ESS Elechmech Enterprises | 15/05/2025 | 3 | 20/7/2026 | 90 |  | 32.301 | Earlier site issue. Now work start | In Progress
MCL-0347 | A3 | East | 4 | O & M | Councillor Quota (CQ) | CQ |  | Providing, Laying 10'' dia UPVC Sewer Line at Vivek Dham and 4" dia. DI K7 water supply Line at Vivek Dham & Sant Cheema Singh Nagar ward 4 |  | 30.75 | 30.75 |  | 1301 dt. 11/08/2025 | 42/G-33 Dt. 25/09/2025 | Kohinoor Builders | 25/09/2025 | 3 | 30/7/2026 | 65 |  | 19.9875 | Work is in Progress | In Progress
MCL-0348 | A3 | East | 5 | O & M | Councillor Quota (CQ) | CQ |  | Providing Laying 10” UPVC SN-8 Sewer Line and 4” dia. DI K7 water supply Line at Beas Hosiery Complex at East Constituency. Ward 5 |  | 34.1 | 34.1 |  | 2624 dt. 11/02/2026 | 87/G-33/XEN/Z-A dt. 24/02/2026 | Friends & Company | 24/02/2026 | 3 | 20/7/2026 | 50 |  | 17.05 | narrow streets manual work in progress | In Progress
MCL-0349 | A3 | East | 5 | O & M | Councillor Quota (CQ) | CQ |  | Providing , Laying 10”dia. UPVC pipe Sewer Line at Flower Vally and 4” dia. DI K7 water supply Line at Flower Vally & Gagandeep colony at East Constituency. Ward No. 5 |  | 33.02 | 33.02 |  | 2666 dt. 11/02/2026 | 94/G-33/XEN/Z-A dt. 24/02/2026 | Friends & Company | 24/02/2026 | 3 | 30/7/2026 | 80 |  | 26.416 | narrow streets manual work in progress | In Progress
MCL-0350 | A3 | East | 6 | O & M | Councillor Quota (CQ) | CQ |  | Providing, Laying Upgradation of 12" dia. UPVC SN-8 pipe Sewer Line from Kuldeep Nagar St No. 4 to near Mohalla Clinic ward 6 |  | 31.46 | 31.46 |  | 949 dt. 06/05/2025 | 20/G-33 Dt. 15/05/2025 | ESS Elechmech Enterprises | 15/05/2025 | 3 | 30/7/2026 | 75 |  | 23.595 | Work is in Progress | In Progress
MCL-0351 | A3 | East | 6 | O & M | Councillor Quota (CQ) | CQ |  | Providing, Laying ,Upgradation of sewer line NP-3 16'' Shere punjab School to Kailash Nagar Road, 4" dia. DI K7 W/s Line at Janta Colony, 6" dia. DI K7 w/s Line at Lucky Enclave to Basti Jodhewal Chownk ward 6 |  | 39.15 | 39.15 |  | 2027 dt. 13/10/2025 | 55/XEN/Z-A Dt. 13/10/2025 | Kohinoor Builders | 13/10/2025 | 3 | 15.07.2026 | 90 |  | 35.235 | Work is in Progress | In Progress
MCL-0352 | A3 | East | 6 | O & M | MC Funds / General Quota | GQ |  | Providing laying Water Supply Line & Sewer Line at Kailash Nagar to Gehlewal and its Branch lines in East Constituency Zone-A |  | 46.33 | 46.33 |  | 3386 dt. 05/12/2024 | 66/G-33 Dt. 05/12/2024 | M/s Rajdeep Enterprises | 12-05-2024 | 3 |  | 60 |  | 27.798 | Balance work Case sent for site change. E.comp. No. 404820 | In Progress
MCL-0353 | A4 | North | 86 | O&M | Councillor Quota (CQ) | CQ |  | Construction of Storm Water Disposal Well in Near Shani Mandir, Shivpuri Pully Ward No. 86 |  | 29.13 | 29.13 |  |  | 43/G-33 Dt. 25/09/2025 | M/s Kohinoor Builders | 30/09/2025 | 3 | 30/7/2026 | 95 |  | 27.6735 | Work in Progress | In Progress
MCL-0354 | A4 | North | 86 | O&M | Councillor Quota (CQ) | CQ |  | Construction of Storm Water Disposal Well in Near Gandhi Nagar Pully Ward No. 86 |  | 22.76 | 22.76 |  | 1445 11/08/2025 | 46/G-33 Dt. 25/09/2025 | M/s Kohinoor Builders | 30/09/2025 | 3 | 30/6/2026 | 95 |  | 21.622 | Work in Progress | In Progress
MCL-0355 | A4 | North | 88 | O&M | Councillor Quota (CQ) | CQ |  | Making of Dispossal well at Shivpuri Pulli at ward no 88. |  | 24.03 | 24.03 |  |  | 61/G-33 Dt. 03/11/2025 | M/s Kohinoor Builders | 11-08-2025 | 1 | 30/6/2026 | 95 |  | 22.8285 | Work in Progress | In Progress
MCL-0356 | A4 | North | 70,88,89 | O&M | SBM (Swachh Bharat Mission) | SBM |  | Construction of Toilet Set in Ward No. 70,88,89 (under SBM 2.0) |  | 28.7 | 28.7 |  |  | 63/G-33 Dt. 03/11/2025 | M/s Ess Elecmech Enterprises | 11-10-2025 | 2 | 30/7/2026 | 45 |  | 12.915 | site issue | In Progress
MCL-0357 | A4 | North | 89 | O&M | Councillor Quota (CQ) | CQ |  | Rehabilitation/Diversion of Existing Sewer line with Dia 18" RCC HDPE Pipe at Janjh Ghar Road and Manna Singh Nagar to close the Dhakka colony outlet point fall in Buddah Daria in Ward no. 89 |  | 55.86 | 55.86 |  |  | 77/G-33 Dt. 30/01/2026 | M/s Joytee Builders | 02-05-2026 | 3 | 10-01-1900 | 60 |  | 33.516 | balance work will be done after monsoon | In Progress
MCL-0358 | A4 | North | 89 | O&M | MC Funds / General Quota | GQ |  | Prov. & Laying of Sewer Line at Nalli Mohalla Chowani Mohalla Shani Mandir Piru Banda Mohalla Ward No. 89 |  | 30.63 | 30.63 |  |  | 90/G-33 Dt. 24/02/2026 | Surya Construction | 28/02/2026 | 4 | 15/10/2026 | 20 |  | 6.126 | narrow streets manual work in progress | In Progress
MCL-0359 | A4 | North | 88 | O&M | Councillor Quota (CQ) | CQ |  | Rehablitation of sewer line at Surinder Nagar Chand Cinena Adjoining Petrol Pump & Noor Maszid Ward No. 88 |  | 39.63 | 39.63 |  |  | 93/G-33 Dt. 24/02/2026 | ESS Elechmech Enterprises | 28/02/2026 | 4 | 30/10/2026 | 15 |  | 5.9445 | narrow streets manual work in progress | In Progress
MCL-0360 | A4 | North | 8,86 | O&M | Councillor Quota (CQ) | CQ |  | Making of additional manhole scaver points others miscellaneous works in ward no. 8 & 86 |  | 29.03 | 29.03 |  |  | 82/G-33 Dt. 24/02/2026 | Prince Sharma | 30-02-2026 | 3 | 15/7/2026 | 35 |  | 10.1605 | maintenance type work | In Progress
MCL-0361 | A4 | North | 86 | O&M | MC Funds / General Quota | GQ |  | Rough Cost Estimate Prov. Laying/Up-gradation and mtc. of Water Supply & Sewer Line At Different Localities of Ward No. 8 and 86. |  | 23.59 | 23.59 |  |  | 98/G-33 Dt. 24/02/2026 | RS Builders | 03-03-2026 | 3 | 15/7/2026 | 10 |  | 2.359 | Material is reached at site | In Progress
MCL-0362 | A4 | North | 8 | O&M | MC Funds / General Quota | GQ |  | Rough Cost Estimate Prov. Laying of Sewer Line and Water Supply Line in Sarvanand Colony Ward No. 8 |  | 18.7 | 18.7 |  |  | 89/G-33 Dt. 24/02/2026 | Prince Sharma | 28/02/2026 | 3 | 07-05-2026 | 80 |  | 14.96 | Work in Progress | In Progress
MCL-0363 | A4 | North | 88 | O&M | MC Funds / General Quota | GQ |  | Up- Gradartion of Water Supply Line in Fatehgarh Mohalla Near Noori Maszid Ward No. 88 |  | 10.32 | 10.32 |  |  | 102/G-33 Dt. 02/03/2026 | Kohinoor Builders | 03-05-2026 | 3 | 15/11/2026 | 5 |  | 0.516 | Work will be started after rain | In Progress
MCL-0364 | A4 | North | 95 | O&M | MC Funds / General Quota | GQ |  | Providing & Installation of 25 HP Straight Bore T/Well Guru Har Rai Nagar Ward No. 95 |  | 12.09 | 12.09 |  |  | 92/G-33 Dt. 24/02/2026 | Rajdeep Enterprises |  | 3 |  |  |  | 0 | File sent for change of site | Not Started
MCL-0365 | A4 | North | 86 | O&M | MC Funds / General Quota | GQ |  | Providing & Installation of 25 HP Straight Bore Tubewell against failed Tubewell In Dr. Ashwani Clinic Ward No. 86 |  | 10.74 | 10.74 |  |  | 91/G-33 Dt. 24/02/2026 | Rajdeep Enterprises |  | 3 |  |  |  | 0 | site issue | Not Started
MCL-0366 | A4 | North | 87 | O&M | MC Funds / General Quota | GQ |  | Rehabilitation Missing Link of Water Supply line and Sewer line in Ward No. 87 |  | 26.46 | 26.46 |  |  | 58/G-33 Dt. 02/12/2024 | Rajdeep Enterprises | 15/12/2024 | 2 |  | 95 |  | 25.137 | File sent for 25% Enhancement | In Progress
MCL-0367 | A4 | North | 86 | O&M | Councillor Quota (CQ) | CQ |  | Prov. Laying of Water Supply Line and Sewer Line in Bal Singh Nagar Gli No. 8 and Pritampuri, Ward No. 86. |  | 26.24 | 26.24 |  |  | 62/G-33 Dt. 05/12/2024 | surya contractor | 12-08-2024 | 3 |  | 95 |  | 24.928 | File sent for 25% Enhancement | In Progress
MCL-0368 | A4 | North | 85 | O&M | Councillor Quota (CQ) | CQ |  | Providing & Laying 4" Water Supply Line at Gandhi Nagar, ward no.85. |  | 47.42 | 47.42 |  |  | 11/G-33 Dt. 28/04/2025 | Bedi Pump Store | 05-05-2025 | 3 | 15/7/2026 | 85 |  | 40.307 | narrow streets manual work in progress | In Progress
MCL-0369 | A4 | North | 85 | O&M | Councillor Quota (CQ) | CQ |  | Rehablitation of Water Supply line Due to Water Conteminations at Basant Nagar/ Gandhi Nagar, Ward no.85 |  | 47.11 | 47.11 |  |  | 48/G-33 Dt. 25/09/2025 | Bedi Pump Store | 30/09/2025 | 3 | 15/7/2026 | 80 |  | 37.688 | narrow streets manual work in progress | In Progress
MCL-0370 | A4 | North | 1,95 | O&M | Councillor Quota (CQ) | CQ |  | Rehabilitation/Missing link of Water Supply line and Sewer Line in Different Localities Ward No.1 & 95. |  | 26.96 | 26.96 |  |  | 62/G-33 Dt. 03/11/2025 | Dynamic Tiles | 11-08-2025 | 2 | 15/7/2026 | 80 |  | 21.568 | Work in Progress | In Progress
MCL-0371 | A4 | North | 84 | O&M | Councillor Quota (CQ) | CQ |  | Rehablitation of Water Supply line Due to Water Conteminations at Various Areas in North Consitituency Like Dakka Colony, Peeru Mohalla, Karabara Chownk & Badour House |  | 34.08 | 34.08 |  |  | 81/G-33 Dt. 24/02/2026 | Prince Sharma | 28/02/2026 | 3 | 15/7/2026 | 40 |  | 13.632 | Work in Progress | In Progress
MCL-0372 | A4 | North | 88 | O&M | Councillor Quota (CQ) | CQ |  | Rough Cost Estimate Prov. Laying Up-gradation of water supply line and sewer line at Sekhewal 60' Road, Ward No. 88. |  | 30.03 | 30.03 |  |  | 96/G-33 Dt. 24/02/2026 | Sushil Kumar Contractor | 03-07-2026 | 4 | 30/7/2026 | 10 |  | 3.003 | Work in Progress | In Progress
MCL-0373 | B | East | 7 | O&M Cell | MPLAD Funds | MP LAD |  | Providing & Installing of 25 HP Deep straight Bore Tubewell at Atal Nagar in Ward No. 7 (MP LAD Scheme). |  | 10.84 | 10.84 |  |  | 114/G33 06-03-2026 | Rajdeep Enterprises | 11-10-2025 | 3 | 07-10-2026 | 90 |  | 9.756 | Work in progress | In Progress
MCL-0374 | B | East | 7 | O&M Cell | MC Funds / General Quota | GQ |  | Rough Cost Estimate for P/L of 4” dia DIK7 water supply line at Atal Nagar, St. No. 2,3,4 & 5 in W. No. 7. |  | 60.82 | 60.82 |  |  | 66/G33 07-11-2025 | CNC Precision Engineering | 10/11/1015 | 3 | 31/08/2026 | 25 |  | 15.205 | Work in progress | In Progress
MCL-0375 | B | East | 11 | O&M Cell | MC Funds / General Quota | GQ |  | Rough Cost Estimate for Upgradation of 4” dia DIK7 water supply line in various areas of W. No. 9. |  | 37.95 | 37.95 |  |  | 257/G33 17-03-2025 | CNC Precision Engineering | 20/03/2025 | 3 | 07-10-2026 | 80 |  | 30.36 | Work in progress | In Progress
MCL-0376 | B | East | 13 | O&M Cell | MC Funds / General Quota | GQ |  | Rough cost estimate for Up gradation of 4” dia DIK-7 water supply line and missing link of 8” UPVC sewer line in various areas of W. No. 13 |  | 75.93 | 75.93 |  |  | 45/G33 14-05-2025 | A.B. Construction Co. | 15/05/2025 | 4 | 15/7/2026 | 90 |  | 68.337 | Work in progress | In Progress
MCL-0377 | B | East | 13 | O&M Cell | MC Funds / General Quota | GQ |  | Rough cost estimate for Up gradation of 4” & 6” dia DIK-7 water supply line in various areas of W. No. 13 |  | 17.07 | 17.07 |  |  | 39/G33 14-05-2025 | CNC Precision Enginering | 15/05/2025 | 2 | 15/7/2026 | 90 |  | 15.363 | Work in progress | In Progress
MCL-0378 | B | East | 14 | O&M Cell | Councillor Quota (CQ) | CQ |  | Upgradation of 4” dia DIK7 water supply line and 8” & 12” UPVC Sewer line at New Karamsar Colony in W. No. 14. |  | 60.76 | 60.76 |  |  | 146/G33 07-05-2026 | Manmohan Singh Contractor | 05-10-2026 | 4 | 15/11/2026 | 50 |  | 30.38 | Balance work will be done after rainy season | In Progress
MCL-0379 | B | East | 19 | O&M Cell | Councillor Quota (CQ) | CQ |  | Prov/Laying of 12” UPVC pipe at Kirti Nagar, St. No. 3&4, at W. No. 19 in East Constituency (Upgradation). |  | 9.67 | 9.67 |  |  | 119/G33 06-03-2026 | Ess Elechmech Enterprises | 03-07-2026 | 2 | 31/07/2026 | 0 |  | 0 | Material reached at site | Not Started
MCL-0380 | B | East | 14,15,18&29 | O&M Cell | MC Funds / General Quota | GQ |  | Rough Cost Estimate for P/L of 4” dia DIK7 water supply line in various wards of East Constituency (Missing Link). |  | 18.4 | 18.4 |  |  | 269/G33 17-03-2025 | CNC Precision Engineering | 20/3/2026 | 3 | 31/07/2026 | 80 |  | 14.72 | Work in progress | In Progress
MCL-0381 | B | East | 17 | O&M Cell | MC Funds / General Quota | GQ |  | Providing & Installing of 25 HP Deep straight Bore Tubewell at Shiv Shankar Colony in Ward No. 17. |  | 10.08 | 10.08 |  |  | 125/G33 25-03-2026 | Bedi Pimp Store | 26/3/2026 | 3 | 15/7/2026 | 60 |  | 6.048 | Work in progress | In Progress
MCL-0382 | B | East | 19 | O&M Cell | Councillor Quota (CQ) | CQ |  | Pro/Laying of 12” UPVC Pipe at 177 Welfare Society, Sector-39, Ward No-19 in East Constituency. (Upgradation). |  | 6.53 | 6.53 |  |  | 136/G33 07-05-2026 | Bedi Pump Store | 05-09-2026 | 3 | 15/7/2026 | 90 |  | 5.877 | Work in progress | In Progress
MCL-0383 | B | East | 20 | O&M Cell | MC Funds / General Quota | GQ |  | Providing & Installing of 12.5 HP Deep straight Bore Tubewell at Bhola Colony, Nr. Gurdwara Sahib in Ward No. 20. |  | 4.82 | 4.82 |  |  | 99/G33 06-03-2026 | Sai Enterprises | 03-10-2026 | 2 | 31/07/2026 | 0 |  | 0 | Work will start next week | Not Started
MCL-0384 | B | East | 20 | O&M Cell | MC Funds / General Quota | GQ |  | Rough cost Estimate for providing & Installing of 25 HP Deep straight Bore Tubewell at Mahajan Vihar in Ward No. 20. |  | 10.56 | 10.56 |  |  | 101/G33 06-03-2026 | CNC Precision Engineering | 03-06-2026 | 3 | 07-10-2026 | 95 |  | 10.032 | Work in progress | In Progress
MCL-0385 | B | East | 26 | O&M Cell | MC Funds / General Quota | GQ |  | Pro/Laying DIK-7 water supply line 6”, 4” at Focal Point, Phase-4A (Replace of old water supply line) W. No. 26, in East Constituency. |  | 76.33 | 76.33 |  |  | 92/G33 19-01-2026 | Baljit Singh Gill | 20/1/2026 | 3 |  |  |  | 0 | Work stopped by MLA saab | Delayed/Held Up
MCL-0386 | B | East | 26 | O&M Cell | MC Funds / General Quota | GQ |  | Providing & Installing of 25 HP Deep straight Bore Tubewell at Rajiv Gandhi Colony in Ward No. 26. |  | 10.46 | 10.46 |  |  | 105/G33 06-03-2026 | ESS Elechmech Enterprises | 03-06-2026 | 3 | 07-05-2026 | 90 |  | 9.414 | Work in progress | In Progress
MCL-0387 | B | East | 26 | O&M Cell | MPLAD Funds | MP Quota |  | Rough Cost Estimate for Prov/Installation of New 25HP Deep Straight Bore Tubewell at Rajiv Gandhi Colony, HE Colony, Ward No. 26 (M.P Quota) in East Constituency. |  | 9.89 | 9.89 |  |  | 135/G33 07-05-2026 | Rajdeep Enterprises | 05-10-2026 | 3 | 30/8/2026 | 0 |  | 0 | Work will start by 1/7/2026 | Not Started
MCL-0388 | B | East | 29 | O&M Cell | MPLAD Funds | MP LAD |  | Providing & Installing of 25 HP Deep straight Bore Tubewell at L.I.G Flat in Ward No. 29 (MP LAD Scheme). |  | 10.84 | 10.84 |  |  | 102/G33 06-03-2026 | Rajdeep Enterprises | 03-07-2026 | 3 |  | 0 |  | 0 | Delyed due to site dispute | Delayed/Held Up
MCL-0389 | B | East | 29 | O&M Cell | MC Funds / General Quota | GQ |  | Providing & Installing of 25 HP Deep straight Bore Tubewell at Vishkarma Nagar, Nr. Baba Deep Singh Gurdwara in Ward No. 29 (against 25 HP failed tubewell) |  | 9.96 | 9.96 |  |  | 142/G33 07-05-2026 | Bedi Pump Store | 05-10-2026 | 4 | 30/8/2026 | 0 |  | 0 | Work will start by 1/7/2026 | Not Started
MCL-0390 | B | East | 7 | O&M Cell | MC Funds / General Quota | GQ |  | Rough Cost Estimate for Upgradation of 10" & 12” UPVC SN-8 sewer line at Indra Colony & Chanderlok Colony in W. No. 7. |  | 65.92 | 65.92 |  |  | 267/G33 17-03-2025 | CNC Precision Engg. | 20/3/2025 | 3 | 20/7/2026 | 70 |  | 46.144 | Work in progress | In Progress
MCL-0391 | B | East | 7 | O&M Cell | MC Funds / General Quota | GQ |  | Rough Cost Estimate for Upgradation of 8” UPVC SN-8 sewer line at Golden Colony in W. No. 7. |  | 52.58 | 52.58 |  |  | 265/G33 17-03-2025 | CNC Precision Engg. | 20/3/2025 | 3 | 30/09/2026 | 25 |  | 13.145 | Work in progress | In Progress
MCL-0392 | B | East | 17 | O&M Cell | MC Funds / General Quota | GQ |  | Prov/Laying of 6" DIK7 water suplly line at Main Tibba Road Dump Site in W. No. 17 (GQ) |  | 36.49 | 36.49 |  |  | 143/G33 07-05-2026 | Friends and Company | 05-08-2026 | 3 | 15/11/2026 | 0 |  | 0 | Work will start after monsoon | Not Started
MCL-0393 | B | East | 17 | O&M Cell | MC Funds / General Quota | GQ |  | Prov/Laying of 30" RCC NP3 sewer line at Mahavir jain (Puneet Nagar) in W. No. 17 (GQ) |  | 38.35 | 38.35 |  |  | 144/G33 07-05-2026 | Surya Construction | 05-08-2026 | 3 | 15/10/2026 | 0 |  | 0 | Work will start after monsoon | Not Started
MCL-0394 | B | East | 17 | O&M Cell | MC Funds / General Quota | GQ |  | Prov/Laying of 18" RCC NP3 sewer line at Main Tibba Road Dump Site in W. No. 17 (GQ) |  | 43.68 | 43.68 |  |  | 140/G33 07-05-2026 | Surya Construction | 05-08-2026 | 4 | 15/11/2026 | 0 |  | 0 | Work will start after monsoon | Not Started
MCL-0395 | B | East | 19 | O&M Cell | MC Funds / General Quota | GQ |  | Pro/Laying of 12” UPVC pipe at GRD Colony, Sector-39, W. No. 19, in East Constituency. (Upgaddation). |  | 40.23 | 40.23 |  |  | 91/G33 19-01-2026 | Glisten | 20/1/2026 | 3 | 20/7/2026 | 90 |  | 36.207 | Work in progress | In Progress
MCL-0396 | B | East | 19 | O&M Cell | Councillor Quota (CQ) | CQ |  | Prov/Laying of 12” UPVC pipe at Sec-39, Back side Pal Petrol Pump in W. No. 19 in East Constituency (Upgradation). |  | 10.17 | 10.17 |  |  | 106/G33 06-03-2026 | R.S. Builders | 03-09-2026 | 3 | 15/7/2026 | 60 |  | 6.102 | Work in progress | In Progress
MCL-0397 | B | East | 20 | O&M Cell | MC Funds / General Quota | GQ |  | Rough Cost Estimate for Prov/Laying of 8" UPVC Sewer line at New GRD Nagar in Ward No. 16 (Site Changed) |  | 12.95 | 12.95 |  |  | 145/G33 9/18/2024 | The Sutlej Co-Op L&C Society Ltd. | 20/9/2024 | 3 | 30/10/2026 | 50 |  | 6.475 | File Approved in F&CC dated:- 24/06/2026 for change of site now work started again | In Progress
MCL-0398 | B | East | 28 | O&M Cell | MC Funds / General Quota | GQ |  | Pro/Laying of 12” UPVC pipe at Street No. ¼, Heera Nagar, in W. No. 28 in East Constituency. |  | 4.95 | 4.95 |  |  | 84/G33 07-11-2025 | Rajdeep Enterprises | 11-10-2025 | 2 | 20/7/2026 | 20 |  | 0.99 | Work held due to Super Suction work | In Progress
MCL-0399 | B | East | 26 | O&M Cell | Councillor Quota (CQ) | CQ |  | Construction of Additional Machine hole chamber at Vishkarma Colony in W. No. 26. |  | 1.37 | 1.37 |  |  | 147/G33 07-05-2026 | K.B. Builders | 05-09-2026 | 2 | 31/7/2026 | 0 |  | 0 |  | Not Started
MCL-0400 | B | East | 29 | O&M Cell | Councillor Quota (CQ) | CQ |  | Prov/Laying of 8” UPVC Sewer line and 4” dia DIK7 water supply line missing link at various streets of G.A.D Nagar in W. No. 29 (C.Q). |  | 5.27 | 5.27 |  |  | 95/G33 27/1/2026 | Sushil Contractor | 30/1/2026 | 2 | 15/7/2026 | 80 |  | 4.216 | Work in progress | In Progress
MCL-0401 | B | East | B | O&M Cell | MC Funds / General Quota | GQ |  | Upgradation of M/Hole Chamber of main 48” Sewer line at Dump Site (Tibba Road). |  | 18.33 | 18.33 |  |  | 124/G33 25-03-2026 | Kohinoor Builders | 25/3/2026 | 2 | 15/10/2026 | 40 |  | 7.332 | Balance Work will start after monsoon | In Progress
MCL-0402 | B | East | B3 | O&M Cell | MC Funds / General Quota | GQ |  | Construction of Raising of manhole hole chambers and Prov and fixing of manhole cover sets i.e EHD, HD, MD sets in different localities of East Constituency (GQ) |  | 24.64 | 24.64 |  |  | 131/G33 07-05-2026 | Prince Sharma | 05-10-2026 | 3 | 15/11/2026 | 0 |  | 0 | Work will start after monsoon | Not Started
MCL-0403 | B | East | B | O&M Cell | MC Funds / General Quota | GQ |  | Prov.& Laying Of 1100MM RCC NP-3 class Sewer line at Tajpur MPS chowk to Tajpur road Police Chonky Nr. Central Jail (G.Q) |  | 132.75 | 132.75 |  |  | 130/G33 07-05-2026 | Ludhiana Construction Company | 05-10-2026 | 6 | 07-10-2026 | 30 |  | 39.825 | Work in progress | In Progress
MCL-0404 | B | East | B3 | O&M Cell | MC Funds / General Quota | GQ |  | Providing & Laying of 250mm, 300mm, 400mm & 600mm RCC NP3 HDPE Line & UPVC SN-8 Sewer line at Mahavir Jain Textile Colony. |  | 126.57 | 126.57 |  |  | 145/G33 07-05-2026 | Ludhiana Construction Company | 05-07-2026 | 6 | 28/2/2027 | 0 |  | 0 | Work will start after monsoon | Not Started
MCL-0405 | B | East | B | O&M Cell | MC Funds / General Quota | GQ |  | Prov.& Laying Of 1000MM RCC NP-3 class Sewer line at Vardhman Chowk to MPS (Tajpur Road) in Sub Zone-B3. |  | 177.93 | 177.93 |  |  | 149/G33 21-05-2026 | Ludhiana Construction Company | 22/5/2026 | 6 | 31/12/2026 | 0 |  | 0 | Work will start after work order no. 130 | Not Started
MCL-0406 | B | Central | 75 | O&M Cell | MC Funds / General Quota | GQ |  | Providing & Installation of (200 mm) 25 HP Deep Straight Bore Tubewell at Gurdware wali gali in W. No.75 (Against Failed T/W) (Central Constituency) |  | 10.91 | 10.91 |  |  | 77/G33 07-11-2025 | Baljit Singh Gill | 11-10-2025 | 3 |  | 0 |  | 0 | Due to site issue (not adequate space) | Not Started
MCL-0407 | B | Central | 80 | O&M Cell | MC Funds / General Quota | GQ |  | Prov/Inst. of 12.5 HP Straight bore Tubewell at st no 10, Hargobind Nagar in W. No. 53 (Against Failed T/w) (Central Constituency). |  | 5.56 | 5.56 |  |  | 125/G33 9/18/2024 | Rana Electrical Works | 20/9/2024 | 2 |  | 0 |  | 0 | Due to site issue (not adequate space) | Not Started
MCL-0408 | B | Central | 80 | O&M Cell | MC Funds / General Quota | GQ |  | Prov/Inst. of 25 HP Straight bore Tubewell at Gabe wali Gali, Kidwai Nagar in W. No. 53 (Against Failed T/w) (Central Constituency). |  | 10.17 | 10.17 |  |  | 03/G33 11-04-2025 | Bedi Pump Store | 13/4/2025 | 3 |  | 0 |  | 0 | Due to site issue (not adequate space) | Not Started
MCL-0409 | B | Central | B1 | O&M Cell | MC Funds / General Quota | GQ |  | Repair & Upgaradation of Shingar Disposal. |  | 20.2 | 20.2 |  |  | 137/G33 07-05-2026 | G.K. Contractor | 05-10-2026 | 3 | 30/8/2026 | 40 |  | 8.08 | Work in progress | In Progress
MCL-0410 | B | Sahnewal | 25 | O&M Cell | SIDBI | MDF/GQ (SIDBI) |  | Providing & Installing of 40 HP Rig Bore Tubewell at Phase-VII Focal Point Water Tanki Wala Park Near Marshell Kanda Ward No.28 (Against Failed Tubewell). |  | 21.03 | 21.03 |  |  | 19/G33 11-04-2025 | CNC Precision Engineering | 04-11-2025 | 3 | 07-10-2026 | 90 |  | 18.927 | Work in progress | In Progress
MCL-0411 | B | Sahnewal | 25 | O&M Cell | MC Funds / General Quota | GQ |  | Missing Links For 4" dia DIK-7 water supply at Different Areas Of Sub Zone-B2. |  | 71.64 | 71.64 |  |  | 16/G33 11-04-2025 | Friends & Co. | 04-12-2025 | 4 | 07-10-2026 | 85 |  | 60.894 | Work in progress | In Progress
MCL-0412 | B | Sahnewal | 25 | O&M Cell | SIDBI | MDF/GQ (SIDBI) |  | Providing & Installing of 40 HP Rig Bore Tubewell at Phase-VIII Focal Point opp Perfect Dyeing. |  | 19.94 | 19.94 |  |  | 116/G33 06-03-2026 | CNC Precision Engineering | 03-07-2026 | 3 | 07-10-2026 | 90 |  | 17.946 | Work in progress | In Progress
MCL-0413 | B | Sahnewal | 25 | O&M Cell | SIDBI | MDF/GQ (SIDBI) |  | Providing & Installing of 40 HP Rig Bore Tubewell at Tikona park Near Metro Tyre Phase-V. |  | 19.94 | 19.94 |  |  | 123/G33 25-03-2026 | CNC Precision Engineering | 25/3/2026 | 3 | 07-10-2026 | 90 |  | 17.946 | Work in progress | In Progress
MCL-0414 | B | Sahnewal | 21 | O&M Cell | MC Funds / General Quota | GQ |  | Upgradation of sewer line in W. No. 24 and 25 (50% - 50% Work Alloted). |  | 32.9 | 32.9 |  |  | 25/G33 17-04-2025 | Deepak Madaan | 20/4/2025 | 4 | 07-10-2026 | 90 |  | 29.61 | Work in progress | In Progress
MCL-0415 | B | Sahnewal | 23 | O&M Cell | MC Funds / General Quota | GQ |  | Upgradation of sewer line in W. No. 25, 26 and 27. |  | 73.8 | 73.8 |  |  | 11/G33 11-04-2025 | Friends & Co. | 04-11-2025 | 4 | 07-10-2026 | 90 |  | 66.42 | Work in progress | In Progress
MCL-0416 | B | Sahnewal | 25 | O&M Cell | Councillor Quota (CQ) | CQ |  | Upgradation of 18” Sewer line from Shiv Colony to Devgan Kanda Sua Road in Sub Zone-B2 (Sahnewal Constituency). |  | 48.37 | 48.37 |  |  | 122/G33 06-03-2026 | Bharat Bhushan Contractor | 03-10-2026 | 4 | 15/8/2026 | 0 |  | 0 | Material reached at site | Not Started
MCL-0417 | B | Sahnewal | B2 | O&M Cell | MC Funds / General Quota | GQ |  | Prov/Laying of RCC NP3 HDPE Lining UPVC SN-8 & HDPE Pipes of dia 250 MM, 300 MM, 400 MM & 450 MM From M.C Limit G.T Road (Ludhiana To Delhi NH) Near Eastman Cast and Forge Ltd. to UCO Bank Juginan Road Ldh. |  | 130.3 | 130.3 |  |  | 10/G33 11-04-2025 | Deepak Madaan | 04-11-2025 | 6 |  | 0 |  | 0 | NOC Pending from NHAI | Delayed/Held Up
MCL-0418 | B | Sahnewal | B2 | O&M Cell | MC Funds / General Quota | GQ |  | Providing & Laying Of 8",10",12" UPVC SN-8 & 16" RCC NP-3 HDPE Lining Sewer Line Missing Links at different places in sub zone B2. |  | 53.38 | 53.38 |  |  | 14/G33 11-04-2025 | Deepak Madaan | 04-11-2025 | 4 | 15/7/2026 | 90 |  | 48.042 | Work in progress | In Progress
MCL-0419 | B | Sahnewal | B2 | O&M Cell | MC Funds / General Quota | GQ |  | Providing & Laying Of 8",10",12" UPVC SN-8 & 16" RCC NP-3 HDPE Lining Sewer Line Missing Links at different places in sub zone B2. |  | 68.47 | 68.47 |  |  | 15/G33 11-04-2025 | Friends & Co. | 04-11-2025 | 4 | 15/7/2026 | 85 |  | 58.1995 | Work in progress | In Progress
MCL-0420 | B | Sahnewal | B2 | O&M Cell | MC Funds / General Quota | GQ |  | Prov./Laying of 900 mm dia RCC NP3 Sewer line at main chandigarh road near Police Colony Chowk. |  | 64.24 | 64.24 |  |  | 129/G33 07-05-2026 | Rajdeep Enterprises | 20/5/2026 | 4 |  | 0 |  | 0 | NOC Pending from NHAI | Delayed/Held Up
MCL-0421 | B | South | 32 | O&M Cell | MC Funds / General Quota | GQ |  | Rough Cost Estimate For Prov/Installation of 40 HP Straight Bore Tube well at Sherpur Khurd, Backside Kabristaan , Ward No- 22 in South Constituency (Against Failed T/Well Tanki wala). |  | 21.05 | 21.05 |  |  | 48/G33 20/05/2025 | Guru Kirpa & Co. |  | 3 |  |  |  | 0 | Not Started, Notice issued to contractor. | Not Started
MCL-0422 | B | South | 32 | O&M Cell | MDF / SASCI | MDF |  | Prov/Laying of DIK7 4" & 6" Water Supply line in various areas in W. No. 22. |  | 92.1 | 92.1 |  |  | 35/G33 05-05-2025 | Bedi Pump Store | 05-07-2025 | 3 | 15/7/2026 | 75 |  | 69.075 | Work in progress | In Progress
MCL-0423 | B | South | 32 | O&M Cell | MC Funds / General Quota | GQ |  | Upgradation of 3” GI Pipe Water Supply Line at old Sherpur Village, Sherpur Khurd, Ward No-22 in South Constituency. |  | 23.16 | 23.16 |  |  | 32/G33 05-05-2025 | Surya Construction | 05-07-2025 | 3 |  |  |  | 0 | Work Shifted to Zone-A under CBD as funds not received work not started | Not Started
MCL-0424 | B | South | 32 | O&M Cell | MPLAD Funds | MP LAD |  | Prov/Inst. of 3000 ltr. water tanker in Sherpur ward no. 16 (old) 32 (new) under MP LAD Scheme. |  | 1.94 | 1.94 |  |  | 120/G33 06-03-2026 | Ram Parkash Kakar | 03-06-2026 | 2 | 07-05-2026 | 0 |  | 0 | Supply will be provided by 05/7/2026 | Not Started
MCL-0425 | B | South | 27 | O&M Cell | Councillor Quota (CQ) | CQ |  | Prov & Laying of 12” UPVC Pipe at Kailash Nagar, St. No. 3-1/2 (Cancer Road Sherpur) in W. No. 27 in South Constituency. |  | 8.67 | 8.67 |  |  | 117/G33 06-03-2026 | Ess Elechmech Enterprises | 03-07-2026 | 3 | 15/11/2026 | 0 |  | 0 | Work will start after monsoon | Not Started
MCL-0426 | C | Atam Nagar | 44 | O&M | MC Funds / General Quota | MCL |  | Prov./Laying 4” id DIK-7 Water Supply lines at street no.7 Partap Nagar Ward no. 41 old. MC Funds |  | 8.99 | 8.99 |  | 518/09.04.2025 | 1173/G/33 Dated 30-04-2025 | Bedi Pump Store | 30/4/2025 | 2 | 07-10-2026 | 60 |  | 5.394 | Work Has been delayed by Councillor | Delayed/Held Up
MCL-0427 | C | Atam Nagar | 48 | O&M | MC Funds / General Quota | MCL |  | Prov./Laying 4” id Dik-7 water supply lines at Bhai Himmat Singh Nagar (ward no. 48) MC Funds |  | 47.31 | 47.31 |  | 520/09.04.2025 | 1174/G/33 Dated 30-04-2025 | Bedi Pump Store | 30/4/2025 | 3 |  | 60 |  | 28.386 | Work has been stopped by MLA Sir due to approval of road work | Delayed/Held Up
MCL-0428 | C | Atam Nagar | C-1 | O&M | MC Funds / General Quota | MCL |  | Prov./Installation of 3 nos. 25 hp Submersible T/wells and 2 nos. 12.5 hp Submersible T/wells in Sub Zone C-1 (AFT T/well) |  | 40.38 | 40.38 |  | 2812/19.02.2026 | 1243/G/33 Dated 29.04.2026 | Bedi pump Store | 30/4/2025 | 3 |  | 20 |  | 8.076 | T/well to be Installed Against failed as per requirment | In Progress
MCL-0429 | C | Atam Nagar | 40 | O&M | MC Funds / General Quota | MCL |  | Prov./Laying 6" id Dik-7 water supply line at main Maya soap ward no. 40 |  | 26.85 | 26.85 |  | 3390/21.04.2026 | 1258/G/33 Dated 13.05.2026 | Shushil Kumar | 15/05/2026 | 3 | 10-10-2026 | 0 |  | 0 | work to be start after monsoon | Not Started
MCL-0430 | C | Atam Nagar | 40 | O&M | MC Funds / General Quota | MCL |  | Prov./Installation of 25 hp New Submersible T/well at street no. 12 1/2 chimeny road Shimlapuri ward no. 40 |  | 10.26 | 10.26 |  | 2806/19.02.2026 | 1269/G/33 Dated 20.05.2026 | JCS Electric works | 22/05/2026 | 3 | 25/08/2026 | 0 |  | 0 | Notice issued to contractor for delay in start | Delayed/Held Up
MCL-0431 | C | Atam Nagar | 41 | O&M | MC Funds / General Quota | MCL |  | Prov./Installation of 25 hp Submersible T/well at street no. 13 Shimlapuri (AFT 25 hp T/well)ward no. 41 |  | 10.36 | 10.36 |  | 2814/19.02.2026 | 1270/G/33 Dated 20.05.2026 | Ess Elechmec | 22/05/2026 | 3 | 20/08/2026 | 0 |  | 0 | Material reached at site | Not Started
MCL-0432 | C | Atam Nagar | 44 | O&M | MC Funds / General Quota | MCL |  | Upgradation of 10" id UPVC sewer line in SAS Nagar ward no. 44 |  | 16.97 | 16.97 |  | 2808/19.02.2026 | 1233/G/33 Dated 18.03.2026 | Joytee Builedrs |  | 3 |  | 0 |  | 0 | Notice issued to contractor for delay in start | Delayed/Held Up
MCL-0433 | C | Atam Nagar | 44 | O&M | MC Funds / General Quota | MCL |  | Upgradation of 12" id UPVC sewer line in Miltary Camp ward no. 44 |  | 16.42 | 16.42 |  | 2809/19.02.2026 | 1234/G/33 Dated 18.03.2026 | ESS Elechmec | 20/03/2026 | 3 | 31/07/2026 | 60 |  | 9.852 | Work in Progress | In Progress
MCL-0434 | C | Atam Nagar | 41 | O&M | MC Funds / General Quota | MCL |  | Upgradation of 16" id RCC NP3 HDPE sewer line from Waheguru road to Daba road Dhand Palace ward no.41 |  | 68.39 | 68.39 |  | 2781/19.02.2026 | 1266/G/33 Dated 13.05.2026 | Bharat Bhushan | 13/5/2026 | 3 | 15/11/2026 | 60 |  | 41.034 | Work stopped and will start after monsoon | Delayed/Held Up
MCL-0435 | C | South | 31 | O&M | MC Funds / General Quota | MCL |  | Prov./Laying 4" id DIK-7 water supply lines at street no. 9,16,17 Bhagwan nagar ward no. 50 old |  | 9.9 | 9.9 |  | 999/06.05.2025 | 1189/G/33 Dated 14-05-2025 | APEX Developers | 15/05/2025 | 2 | 31/07/2026 | 60 |  | 5.94 | work in progress | In Progress
MCL-0436 | C | South | 32 | O&M | MC Funds / General Quota | MCL |  | Prov./Installation of 25 hp new Submersible T/well at street no.22 Makkar colony Dhandari kalan ward no.32 MC fund |  | 10.61 | 10.61 |  | 2816/19.02.2026 | 1238/G/33 Dated 09.04.2026 | Ess Elechmec | 04-10-2026 | 3 | 15/07/2026 | 40 |  | 4.244 | work in progress | In Progress
MCL-0437 | C | South | C-3 | O&M | MC Funds / General Quota | MCL |  | Prov./Installation of 4 nos. 25 hp submersible T/wells (AFT 25 hp t/wells) in South Constituency (MC funds.) |  | 48.77 | 48.77 |  | 2036/13.10.2025 | 1219/G/33 Dated 04-11-2025 | Bedi pump Store | 11-06-2025 | 3 |  | 75 |  | 36.5775 | T/well to be Installed Against failed as per requirment | In Progress
MCL-0438 | C | South | 29 | O&M | MC Funds / General Quota | MCL |  | Providing Laying 4" i/d DIK-7 water supply line at Makkar Colony Ward No.29 |  | 35.84 | 35.84 |  | 220/11.03.2025 | 1161/G/33 Dated 11-04-2025 | APEX Developers | 15/4/2025 | 3 | 31/07/2026 | 80 |  | 28.672 | Work stopped by MLA, until road estimate to be approved | Delayed/Held Up
MCL-0439 | C | South | 36 | O&M | MC Funds / General Quota | MCL |  | Prov./Installation of 25 hp new Submersible T/well at street no.1 Chahal road Sukhdev Nagar ward no.36 MC fund |  | 10.57 | 10.57 |  | 2538/05.02.2026 | 1240/G/33 Dated 20.04.2026 | Amarpal Singh Bawa | 20/04/2026 | 3 | 20/7/2026 | 85 |  | 8.9845 | Work in progress | In Progress
MCL-0440 | C | South | 37 | O&M | MC Funds / General Quota | MCL |  | Prov./Installation of 25 hp new Submersible T/well at street no. 13 Guru Gobind singh nagar barota road ward no.37 MC fund |  | 10.26 | 10.26 |  | 2810/19.02.2026 | 1235/G/33 Dated 09.04.2026 | JCS Electric works |  | 3 |  | 0 |  | 0 | Notice issued to contractor for delay in start | Delayed/Held Up
MCL-0441 | C | South | 37 | O&M | MC Funds / General Quota | MCL |  | Prov./Installation of 25 hp New Submersible T/well at Guru Gobind singh nagar street no. 10/3 ward no. 37 |  | 10.58 | 10.58 |  | 2540/05.02.2026 | 1236/G/33 Dated 09.04.2026 | Amarpal Singh Bawa | 04-10-2026 | 3 | 07-10-2026 | 85 |  | 8.993 | Work In Progress | In Progress
MCL-0442 | C | South | 37 | O&M | MC Funds / General Quota | MCL |  | Prov./Laying 4" id Dik-7 water supply lines at Barota road and Branch streets of Guru Gobind Singh Nagar ward no. 37 |  | 40.18 | 40.18 |  | 2819/19.02.2026 | 1242/G/33 Dated 27.04.2026 | Sushil Kumar contractor |  | 3 |  | 0 |  | 0 | Work stopped by MLA, until road estimate to be approved | Delayed/Held Up
MCL-0443 | C | South | 43 | O&M | MC Funds / General Quota | MCL |  | Prov./Installation of 25 hp new Submersible t/well at New Amar nagar stret no. 10-B ward no. 43 |  | 10.24 | 10.24 |  | 2818/19.02.2026 | 1237/G/33 Dated 09.04.2026 | Ess Elechmec | 04-10-2026 | 3 | 15/7/2026 | 60 |  | 6.144 | Work In Progress | In Progress
MCL-0444 | C | South | 44 | O&M | MC Funds / General Quota | MCL |  | Prov./Laying 4” id DIK-7 Water Supply lines at street no.4 Kot Mangal Singh Ward no. 41 old. MC Funds |  | 9.73 | 9.73 |  | 517/09.04.2025 | 1168/G/33 Dated 30-04-2025 | The Boha Co.op L&C Society ltd. |  | 2 |  | 0 |  | 0 | Due To road dispute of Public work not started | Delayed/Held Up
MCL-0445 | C | South | 45 | O&M | MC Funds / General Quota | MCL |  | Prov./Laying 4" id Dik-7 water supply lines in street no. 11, 14 & 15 at Vishkarma colony ward no. 50 old |  | 9.37 | 9.37 |  | 516/09.04.2025 | 1169/G/33/30.04.2025 | Bedi pump store | 30/4/2025 | 2 |  | 70 |  | 6.559 | Work Held up due to political dispute | Delayed/Held Up
MCL-0446 | C | South | 31 | O&M | MC Funds / General Quota | MCL |  | Upgradation of 4" id DIK water supply lines & 12" UPVC sewer line at street no 3,4,5,6 Hargobind Nagar ward no. 31 |  | 72.24 | 72.24 |  | 2890/19.02.2026 | 1247/G/33 Dated 11.05.2026 | APEX Developers | 15/05/2026 | 3 | 15/10/2026 | 0 |  | 0 | work to be start after monsoon | Not Started
MCL-0447 | C | South | 34 | O&M | MC Funds / General Quota | MCL |  | Prov./Laying missing links 4" id DIK-7 water supply lines & 10" id UPVC sewer lines at Lachman nagar & Ajit Colony ward no. 34 |  | 6.5 | 6.5 |  | 2811/19.02.2026 | 1250/G/33 Dated 11.05.2026 | GK Contractor | 15/05/2026 | 2 | 08-10-2026 | 25 |  | 1.625 | Work in Progress | In Progress
MCL-0448 | C | South | 33 | O&M | MC Funds / General Quota | MCL |  | Prov./Laying missing links 4" id DIK-7 water supply lines for missing links & 10" id UPVC sewer lines at Mahadev nagar, Samrat Colony & Laxmi Nagar ward no. 33 |  | 14.37 | 14.37 |  | 2807/19.02.2026 | 1251/G/33 Dated 11.05.2026 | NS Infra | 13/05/2026 | 3 | 15/08/2026 | 25 |  | 3.5925 | Work in Progress | In Progress
MCL-0449 | C | South | 36 | O&M | MC Funds / General Quota | MCL |  | Upgradation of 4" id DIK water supply lines & 12" id UPVC sewer line at Gill colony Sappan wala mandir ward no. 36 |  | 67.85 | 67.85 |  | 2891/19.02.2026 | 1249/G/33 Dated 11.05.2026 | Friennds & company | 15/05/2026 | 3 | 31/08/2026 | 20 |  | 13.57 | Work in Progress | In Progress
MCL-0450 | C | South | 32 | O&M | MPLAD Funds | MP Lad |  | Purchase of 3000 litters water tanker for ward no. 16 old new ward no. 32 MP Quota |  | 1.94 | 1.94 |  | 3386/21.04.2026 | 1252/G/33 Dated 13.05.2026 | Ram Parkash Kakkar | 15/05/2026 | 2 | 07-12-2026 | 0 |  | 0 | Manufacturing under process | Not Started
MCL-0451 | C | South | 32 | O&M | MPLAD Funds | MP Lad |  | Purchase of 3000 litters water tanker for ward no. 30 old new ward no. 32 MP Quota |  | 1.94 | 1.94 |  | 3382/21.04.2026 | 1253/G/33 Dated 13.05.2026 | Ram Parkash Kakkar | 15/05/2026 | 2 | 07-12-2026 | 0 |  | 0 | Manufacturing under process | Not Started
MCL-0452 | C | South | 34 | O&M | MC Funds / General Quota | MCL |  | Prov./Installation of 25 hp New Submersible T/well at street no. 8 Gagan Nagar ward no. 34 |  | 10.11 | 10.11 |  | 3524/21.04.2026 | 1254/G/33 Dated 13.05.2026 | Bedi pump Store | 13/05/2026 | 3 | 15/08/2026 | 0 |  | 0 |  | Not Started
MCL-0453 | C | South | 43 | O&M | MC Funds / General Quota | MCL |  | Prov./Installation of 25 hp New Submersible T/well at street no. 33 Kot Mangal Singh Nagar ward no. 43 |  | 10.11 | 10.11 |  | 3388/21.04.2026 | 1256/G/33 Dated 13.05.2026 | Bedi pump Store | 13/05/2026 | 3 | 15/08/2026 | 0 |  | 0 |  | Not Started
MCL-0454 | C | South | 32 & 33 old | O&M | MC Funds / General Quota | MCL |  | Prov./Suction tanker for desilting of sewer in various area of ward no. 32 & 33 old sub Zone C-2 |  | 5.95 | 5.95 |  | 3379/21.04.2026 | 1257/G/33 Dated 13.05.2026 | Sai Enterprises | 13/05/2026 | 3 | 15/08/2026 | 50 |  | 2.975 |  | Not Started
MCL-0455 | C | South | 36 | O&M | MC Funds / General Quota | MCL |  | Prov./Laying 4" id DIK-7 water supply lines & 10" id UPVC sewer lines at Dhillon nagar ward no. 36 |  | 56.03 | 56.03 |  | 2892/19.02.2026 | 1267/G/33 Dated 13.05.2026 | Apex Developers | 13/05/2026 | 3 | 30/11/2026 | 0 |  | 0 | Work will start after monsoon | Not Started
MCL-0456 | C | South | 31 | O&M | MC Funds / General Quota | MCL |  | Upgradation of 10" id UPVC sewer line in Gandhi Nagar Ward no. 50 |  | 29.05 | 29.05 |  | 3408/05.12.2024 | 1143/G/33 Dated 05-12-2024 | M/S Kohinoor Builders | 12-07-2024 | 3 |  | 85 |  | 24.6925 | As per original contract work is completed. File sent for change of site for balance fund. | In Progress
MCL-0457 | C | South | 34 | O&M | MC Funds / General Quota | MCL |  | Providing Laying 10" UPVC Sewer line & 4" i/d DIK-7 water supply line Near BSUP Flats Ward No.31 |  | 7.52 | 7.52 |  | 332/26.03.2025 | 1162/G/33 Dated 11-04-2025 | The Sarabha Co. Op. L&C Society Ltd. | 13/04/2025 | 2 | 31/07/2026 | 70 |  | 5.264 | Work in Progress, delay due to clearance from building branch | Delayed/Held Up
MCL-0458 | C | South | 34 | O&M | MC Funds / General Quota | MCL |  | Upgradation of 4" id DIK water supply lines & 10" UPVC sewer line at City Garden colony ward no. 34 |  | 69.37 | 69.37 |  | 3381/21.04.2026 | 1245/G/33 Dated 11.05.2026 | APEX Developers | 05-12-2026 | 3 | 15/09/2026 | 20 |  | 13.874 | Work in Progress | In Progress
MCL-0459 | C | South | 32 | O&M | MC Funds / General Quota | MCL |  | Upgradation of 24" id RCC NP3 HDPE sewer line at Singla Cycle road ward no. 32 |  | 70.06 | 70.06 |  | 3383/21.04.2026 | 1246/G/33 Dated 11.05.2026 | Rajdeep Enterprises | 20/04/2026 | 4 | 30/09/2026 | 20 |  | 14.012 | Work in Progress | In Progress
MCL-0460 | C | South | 32 | O&M | MC Funds / General Quota | MCL |  | Prov./Laying 12" id UPVC sewer lines at Mittal kanda Dhandari Kalan near Skoda showroom ward no. 32 |  | 19.01 | 19.01 |  | 2813/19.02.2026 | 1248/G/33 Dated 11.05.2026 | Prince Sharma | 14/5/2026 | 3 |  | 0 |  | 0 | Delayed due to earth filling has to done by B&R | Delayed/Held Up
MCL-0461 | C | South | 39 | O&M | MC Funds / General Quota | MCL |  | Upgradation of 12" id UPVC sewer line at street no. 8 Harkrishan nagar ward no. 39 |  | 22.04 | 22.04 |  | 2815/19.02.2026 | 1268/G/33 Dated 13.05.2026 | Prince Sharma | 14/05/2026 | 3 | 15/09/2026 | 0 |  | 0 |  | Not Started
MCL-0462 | C | Central | 74 | O&M | MC Funds / General Quota | MCL |  | Raising & Construction of M/H Slabs & Additional M/H Chambers , Prov./Laying 8" id sewer line for missing links in ward no. 74 |  | 7.66 | 7.66 |  | 3380/21.04.2026 | 1260/G/33 Dated 13.05.2026 | Kohinoor Builders | 14/05/2026 | 3 | 30/07/2026 | 50 |  | 3.83 |  | Not Started
MCL-0463 | C | Central | 74 | O&M | MC Funds / General Quota | MCL |  | Upgradation of 10" id UPVC storm sewer line from Gill road to Loha Mandi Indra market opp. Indra market ward no. 74 |  | 19.86 | 19.86 |  | 3547/21.04.2026 | 1263/G/33 Dated 13.05.2026 | Friennds & company | 14/05/2026 | 3 | 15/11/2026 | 0 |  | 0 | Work will be start after monsoon | Not Started
MCL-0464 | C | Central | 74 | O&M | MC Funds / General Quota | MCL |  | Raising & Constyruction of M/H slabs and construction of add. M/H chambers in Ward no. 74 |  | 5.84 | 5.84 |  | 3387/21.04.2026 | 1264/G/33 Dated 13.05.2026 | Bharat Nirman Infracon | 14/05/2026 | 2 | 30/07/2026 | 20 |  | 1.168 |  | Not Started
MCL-0465 | C | Central | 74 | O&M | MC Funds / General Quota | MCL |  | Upgradation of 10" id UPVC sewer lines in Industrial Estate ward no. 74 |  | 24.9 | 24.9 |  | 3578/21.04.2026 | 1265/G/33 Dated 13.05.2026 | Friennds & company | 14/05/2026 | 3 | 15/11/2026 | 0 |  | 0 | Work will start after monsoon | Not Started
MCL-0466 | D | North | North | O&M | MC Funds / General Quota | G.Q |  | Rehabitation/Missing links of 8" and 12"UPVC Sewer line and 2" G.I & 4" water supply line at Various wards of North Constituency |  | 49.38 | 49.38 |  | 242 26-03-2025 & 2233 21/11/2026 | 03/G-33 Dt. 15/04/2025 & 358/XEN/D 10/09/2025 | M/s Rajdeep Enterprises | 20/04/2025 | (upto 10/11/2025) | 07-10-2026 | 95 |  | 46.911 | Work was delayed due to road work was not approved. now work under progress | Delayed/Held Up
MCL-0467 | D | North | 91 | O&M | MC Funds / General Quota | G.Q |  | P/Laying 12” id storm sewer line at on the road outside the park, near Silver Spoon, New Deep Nagar, Ward No. 91. (G.Q) (E Comp No. 385246) |  | 9.31 | 9.31 |  | 256 26-03-2025 | 6/g/33 11-05-2026 | M/S Sushil Kumar Contractor, Ludhiana | 05-12-2026 | 2 months | 07-11-2026 | 0 |  | 0 |  | Not Started
MCL-0468 | D | North | D1 | O&M | MC Funds / General Quota | G.Q |  | Rehablitation/Missing link of 4" Water Supply line at various wards of Subzone-D1 |  | 69.18 | 69.18 |  | 06-11-2025 | 104/G-33 Dt. 06/11/2025 | M/S ESS Elecmech Enterprises | 10-11-2025 | 3 Months | 15/07/2026 | 95 |  | 65.721 | Work is delayed Due to rehablitation work | Delayed/Held Up
MCL-0469 | D | North | 66 | O&M | MC Funds / General Quota | G.Q |  | Providing & Installation of 12.5 HP submersible T/well at Gaganpreet Vihar in Ward No-66. (G.Q) |  | 4.45 | 4.45 |  | 2627 11-02-2026 | 107/G/33 20-02-2026 | M/s JCS Electric Works | 20-05-2026 | 2 months | 15/07/2026 | 10 |  | 0.445 |  | Not Started
MCL-0470 | D | North | 93 | O&M | MC Funds / General Quota | G.Q |  | Making of Disposal Well at new Kundanpuri (PeeruBanda) Railway bridge Sandhu Showroom in ward no-93 . (G.Q) |  | 25.12 | 25.12 |  | 2615 11-02-2026 | 108/G/33 20-02-2026 | M/s Bedi Pump Srore | 21/02/2026 | 3 months | 30/06/2026 | 86 |  | 21.6032 | Only Gen set pending | Delayed/Held Up
MCL-0471 | D | North | 66,68,92 | O&M | Councillor Quota (CQ) | C.Q |  | Rehablition of water supply & Sewer line at Gokul Vihar, Tersem Colony, Jaganath Purm, Preet Vihar, Civil City, New Sant Nagar in Ward no. 66, 68, 92(C.Q) |  | 27.38 | 27.38 |  | 2625 11-02-2026 | 110/G/33 20-02-2026 | M/s Sushil Kumar Contractor | 15-04-2026 | 3 months | 30/07/2026 | 25 |  | 6.845 |  | Not Started
MCL-0472 | D | North | 93 | O&M | Councillor Quota (CQ) | C.Q |  | Rehablition of water supply line at sunil nagar in ward no 93. |  | 40.33 | 40.33 |  | 2867 19-02-2026 | 123/g/33 26-02-2026 | M/s Sushil Kumar Contractor | 27/02/2026 | 3 months | 07-05-2026 | 95 |  | 38.3135 |  | Not Started
MCL-0473 | D | North | - | O&M | MC Funds / General Quota | G.Q |  | Providing & Installing of 2nos.12.5 HP, 1 nos. 25 HP & 1 nos. 40 HP Tubewells in place of against failed tubewells and water shortage in Emergency Situations in various areas under North Constituency. (G.Q) (E Comp No. 376246) |  | 43.37 | 43.37 |  | 3378 21-04-2026 | 1/g/33 08-05-2026 | M/S Rana Electrical Works, Ludhiana. | 05-11-2026 | 12 months | 05-10-2027 | 90 |  | 39.033 |  | Not Started
MCL-0474 | D | North | 70 | O&M | MC Funds / General Quota | G.Q |  | Providing & Installation of 25 HP submersible T/well in Pahwa dharamshala against failed T/well in Ward no- 70.. (G.Q) (E Comp No. 374186) |  | 8.2 | 8.2 |  | 3346 21-04-2026 | 4/g/33 11-05-2026 | M/S Bharat Nirman Infracon, Ludhiana. | 05-12-2026 | 3 months | 08-10-2026 | 0 |  | 0 | Notice Issued | Not Started
MCL-0475 | D | North | 93 | O&M | Councillor Quota (CQ) | C.Q |  | Rehablition of water supply line at Kehar Singh Nagar in ward no 93. (C.Q) (E Comp No. 377250) |  | 61.12 | 61.12 |  | 3573 21-04-2026 | 7/g/33 11-05-2026 | M/S Friends and Company, Ludhiana.. | 05-12-2026 | 4 months | 09-10-2026 | 0 |  | 0 | Notice Issued | Not Started
MCL-0476 | D | Atam Nagar | 47 | O&M | MC Funds / General Quota | G.Q |  | Providing and Laying 4"dia DIK-7 water supply line at the area of Kartar Nagar in Ward No-49 |  | 31.49 | 31.49 |  | 241 03-12-2024 | 4/G/33 11-04-2025 | M/S ESS Elecmech Enterprices, Ludhiana.. | 20/4/2026 | 3 months |  | 55 |  | 17.3195 | Work stopped by MLA saab and work to be done after road work allotment | Delayed/Held Up
MCL-0477 | D | Atam Nagar | 47 | O&M | MC Funds / General Quota | G.Q |  | Providing and Laying 4"dia DIK-7 water supply line at the area of Ambedker Nagar, street no-9, in Ward No-48 |  | 31.83 | 31.83 |  | 543 09-04-2025 | 40/G/33 25-04-2025 | M/S Bedi Pump Store , Ludhiana | 25/04/2025 | 3 months |  | 0 |  | 0 | Work stopped by MLA saab and work to be done after road work allotment | Delayed/Held Up
MCL-0478 | D | Atam Nagar | 47 | O&M | MC Funds / General Quota | G.Q |  | Providing and Laying 4"dia DIK-7 water supply line at the area of Anbedker Nagar in Ward No-48 |  | 22.06 | 22.06 |  | 540 09-04-2025 | 42/G/33 25-04-2025 | M/S ESS Elecmech Enterprises, Ludhiana | 25/04/2025 | 2 months |  | 0 |  | 0 | Work stopped by MLA saab and work to be done after road work allotment | Delayed/Held Up
MCL-0479 | D | Atam Nagar | 52 | O&M | MC Funds / General Quota | G.Q |  | Providing and Laying 4"dia DIK-7 water supply line at the area of Abdulapur Basti in Ward No-47. |  | 22.95 | 22.95 |  | 541 09-04-2025 | 41/G/33 25-04-2025 | M/S ESS Elecmech Enterprises, Ludhiana | 30-04-2025 | 3 months | 15/7/2026 | 60 |  | 13.77 | Area is conjusted and there was sewer issue due to which excavation was not possible work started after sewer is cleared | In Progress
MCL-0480 | D | Atam Nagar | 52 | O&M | MC Funds / General Quota | G.Q |  | Prov/Inst. of 25 HP Straight bore T/well at Abdulapur basti Vikas dharamshalla in W. No. 52 (against failed t/well 40 HP) |  | 10.06 | 10.06 |  | 1458 13-10-2025 | 97/G/33 03-11-2025 | M/S Rajdeep Enterprises | 11-10-2025 | 3 months | 15/7/2026 | 95 |  | 9.557 |  | Not Started
MCL-0481 | D | Atam Nagar | 51 | O&M | MC Funds / General Quota | G.Q |  | Prov/Inst. of 2 No. New 25 HP Straight bore Tube wells in Ward No. 51. |  | 20.29 | 20.29 |  | 2379 05-01-2026 | 106/G/33 27-01-2026 | M/S Rajdeep Enterprises | 02-04-2026 | 3 months | 15/7/2026 | 90 |  | 18.261 |  | Not Started
MCL-0482 | D | Atam Nagar | 50 | O&M | Councillor Quota (CQ) | C.Q |  | Providing and Installation of 25 HP Straight Bore Submersible Tubewell at 200 ft. road, Urban Estate, Ph-3 in Ward No 50.(C.Q) |  | 10.31 | 10.31 |  | 2631 11-02-2026 | 116/G/33 20-02-2026 | M/s ESS Elechmech Enterprises | 25/2/26 | 3 months | 15/7/2026 | 65 |  | 6.7015 |  | Not Started
MCL-0483 | D | Atam Nagar | 49 | O&M | MC Funds / General Quota | G.Q |  | Providing and Installation of 25 HP Straight Bore Submersible Tubewell at Ph-1, Near Dr. Grewal Park in Ward No 49 (against 12.5HP failed tubewell )(G.Q). |  | 10.31 | 10.31 |  | 2636 110-2-2026 | 117/G/33 20-02-2026 | M/s ESS Elechmech Enterprises | 25-02-2026 | 3 months | 07-05-2026 | 80 |  | 8.248 |  | Not Started
MCL-0484 | D | Atam Nagar | 50 | O&M | Councillor Quota (CQ) | C.Q |  | Providing and Installation of 25 HP Straight Bore Submersible Tubewell at L.I.G Flat, Urban Estate, Ph-3, Near Army Flat in Ward No 50.(C.Q) |  | 10.3 | 10.3 |  | 2633 11-02-2026 | 120/G/33 20-02-2026 | M/s JCS Electric Works | 21/02/2026 | 3 months | 15/7/2026 | 0 |  | 0 | Notice Issued | Not Started
MCL-0485 | D | Atam Nagar | 47 | O&M | MC Funds / General Quota | G.Q |  | Providing and Installation of 25 HP Straight Bore Submersible Tubewell at Kartar Nagar (Apna Park), in Ward No 47 (against 40HP failed tubewell). (G.Q). |  | 10.18 | 10.18 |  | 2637 11-02-2026 | 121/G/33 20-02-2026 | M/s JCS Electric Works | 25/2/26 | 3 months | 15/7/2026 | 95 |  | 9.671 | only electric connection pending | Delayed/Held Up
MCL-0486 | D | Atam Nagar | 50 | O&M | Councillor Quota (CQ) | C.Q |  | Providing and Installation of 25 HP Straight Bore Submersible Tubewell at Chhoti Jawaddi in Ward No 50. (C.Q) |  | 10.17 | 10.17 |  | 2638 11-02-2026 | 122/G/33 20-02-2026 | M/s JCS Electric Works | 25/02/2026 | 3 months | 31/7/2026 | 0 |  | 0 | Notice Issued | Not Started
MCL-0487 | D | Atam Nagar | D2 | O&M | MC Funds / General Quota | G.Q |  | Prepare of Foundation of 100 HP Motor Pump at Water Works Plant, Ph1, Dugri in Sub Zone D2. (C.Q) (E Comp No. 375948) |  | 1.96 | 1.96 |  | 3347 21-4-02026 | 9/g/33 11-05-2026 | M/S G.K Contractor, Ludhiana | 05-12-2026 | 2 months | 07-11-2026 | 0 |  | 0 |  | Not Started
MCL-0488 | D | Atam Nagar | 47 | O&M | MC Funds / General Quota | G.Q |  | Prov/Laying of Sewer line (missing links) in W. No. 47..(C.Q) |  | 7.36 | 7.36 |  | 2632 11-02-2026 | 119/G/33 20-02-2026 | M/s G.K. Contractor | 25/2/2026 | 2 months | 15/7/2026 | 50 |  | 3.68 | Mannual work is being done | In Progress
MCL-0489 | D | West | 59 | O&M | MC Funds / General Quota | G.Q |  | P/I or New Sub. 40 HP Tubewell at Big Park, Chhpar wali park, Ward No-74. |  | 26.62 | 26.62 |  | 255 26-03-2025 | 15/G/33 11-04-2025 | CNC Precision Engineering |  | 3 months |  | 0 |  | 0 | Site issue | Not Started
MCL-0490 | D | West | 60 | O&M | MC Funds / General Quota | G.Q |  | Rough Cost Estimate For Prov. & Laying of 4” DIK-7 Water Supply lines & 8” SN-8 UPVC sewer lines at Sargodha Colony &Gurdev Nagar, Backside Silver Arc Mall in Ward No.60 |  | 29.14 | 29.14 |  | 973 06-05-2025 | 67/G/33 14-05-2025 | M/s Bharat Bhushan Contractor | 20/5/2026 | 3 months | 15/7/2026 | 100 |  | 17.484 |  | Not Started
MCL-0491 | D | West | Gen. | O&M | MC Funds / General Quota | G.Q |  | Rough cost of Estimate For Providing & Installation of 40 HP. Rig Bore Tubewell at against failed T/well) Ward General T/well West |  | 20.54 | 20.54 |  | 961 06-05-2025 | 72/G/33 14-05-2025 | M/s Guru Kirpa & Co |  | 3 months |  | 0 |  | 0 | Notice Issued | Not Started
MCL-0492 | D | West | 72 | O&M | MC Funds / General Quota | G.Q |  | Prov. & Laying of 4” DIK-7 Water Supply Line at Jawahar Nagar Camp Ward No-72. |  | 43.41 | 43.41 |  | 1871 13-10-2025 | 89/G/33 03-11-2025 | M/S Bharat Bhushan Contractor | 11-10-2025 | 3 months | 15/7/2026 | 95 |  | 41.2395 | Only one street pending mannual work in being done | Delayed/Held Up
MCL-0493 | D | West | 72 | O&M | MC Funds / General Quota | G.Q |  | Rough Cost Estimate For 4" DIK-7 Water Supply Line at Bus Stand to Bharat Nagar chowk Ward No-72. |  | 29.16 | 29.16 |  | 1870 13-10-2025 | 90/G/33 03-11-2025 | 1 Apex Devlopers, Ludhiana. 2. M/S Kohinoor Builders, Ludhiana. | 11-08-2025 | 3 months | 15/7/2026 | 50 |  | 14.58 | Not further work required in this file | In Progress
MCL-0494 | D | West | 54 | O&M | MC Funds / General Quota | G.Q |  | Providing & Installation of 25 HP. Submersible new Tubewell at J- Block, Sarabha Nagar (Against Failed Tubewell) Ward No-55. shifted to karnail singh nagar |  | 12.96 | 12.96 |  | 1460 13-10-2025 | 95/G/33 03-11-2025 | M/S Amarpal Singh Bawa | 10-11-2025 | 2 months | 15/7/2026 | 85 |  | 11.016 |  | Not Started
MCL-0495 | D | West | 59 | O&M | MC Funds / General Quota | G.Q |  | Upgradaiton of 4" DIK7 Water Supply line at Indra Colony, Barewal Road, Ward No-59. (C.Q) (E Comp No. 373959) |  | 11.57 | 11.57 |  | 3371 21-04-2026 | 5/g/33 11-05-2026 | M/S Sushil Kumar Contractor, Ludhiana | 05-12-2026 | 3 months | 08-11-2026 | 0 |  | 0 |  | Not Started
MCL-0496 | D | West | 55 | O&M | MC Funds / General Quota | G.Q |  | Estimate For Prov. & Laying of 10” UPVC SN-8 Pipe Sewer Line at H. No.-22 Block-K, Sarabha Nagar in Ward No-75, Ludhiana |  | 5.31 | 5.31 |  | 3250 29-11-2024 | 52/G/33 02-12-2024 | Bharat Bhusan Contractor | not started | 2 months |  |  |  | 0 | New Road constucted | Not Started
MCL-0497 | D | West | 59 | O&M | MC Funds / General Quota | G.Q |  | Rough Cost Estimate For Upgradation of 315mm UPVC SN-8 Pipe Sewer Line at Barewal Shamshan Ghat Road in Ward No-74, Ludhiana. |  | 7.37 | 7.37 |  | 3248 29-11-2024 | 50/G/33 02-12-2024 | Bedi Pump Store., Ludhiana. | not started | 2 months |  |  |  | 0 | New Road constucted | Not Started
MCL-0498 | D | West | 56 | O&M | MC Funds / General Quota | G.Q |  | Up-gradation of 12” SN-8 UPVC Sewer line at House No.-3H to Opp. Key Hotel Wd. No.-71. |  | 29.04 | 29.04 |  | 976 06-05-2026 | 66/G/33 14-05-2025 | M/s Anmol Katyal Contractor | not started | 3 months |  |  |  | 0 | road level issue so hold up. | Not Started
MCL-0499 | D | West | 56 | O&M | Councillor Quota (CQ) | C.Q |  | Providing & Laying of 8” SN-8 UPVC Sewer Line at keys Hotel back side, S.B.S Nagar in Ward No- 56, Ludhiana.(C.Q) |  | 17.21 | 17.21 |  | 2634 11-02-2026 | 112/G/33 20-02-2026 | M/s N.S. Infra | 25/2/2026 | 3 months | 15/7/2026 | 90 |  | 15.489 | Notice Issued | In Progress
MCL-0500 | D | West | 55 | O&M | MC Funds / General Quota | G.Q |  | Providing & Laying 12" UPVC SN-8 Storm Sewer Line at Block-G, B.R.S Nagar in Ward No-55, Ludhiana. (G.Q) (E Comp No. 379488) |  | 58.95 | 58.95 |  | 3408 21-04-2026 | 8/g/33 11-05-2026 | M/S Friends and Company, Ludhiana.. | 15/5/2026 | 4 months | 14/08/2026 | 50 |  | 29.475 |  | Not Started
MCL-0501 | D | West | 61 | O&M | MC Funds / General Quota | G.Q |  | Providing & installation of a new tubewell (against failure) of 40 HP in Rose Garden-2 (inside the park) under Ward No.-61. |  | 22.54 | 22.54 |  | 962 06-05-2025 | 54/G/33 14-05-2025 | M/s Guru Kirpa & Co | not started | 3 months | - |  |  | 0 | Notice Issued | Not Started
MCL-0502 | D | West | Gen. | O&M | MC Funds / General Quota | G.Q |  | Purchase of Wate Tankerof 15 no. of S.S. for west constituency, Municipal Corporation Ludhiana. (15th Finance Commmission Drinking Water Head). |  | 34.02 | 34.02 |  | 2503 23-08-2024 | 43/G/33 26-11-2024 | M/s Kakar Fabricators, Ludhiana | 30/11/2024 | 3 months | 07-04-2026 | 75 |  | 25.515 |  | Not Started
MCL-0503 | D | West | West | O&M | MC Funds / General Quota | G.Q |  | Annual rate contract of Prov. and installation of 25 HP & 12.5 HP Tubewells for West Constituency. (G.Q) |  | 68.67 | 68.67 |  | 2585 11-02-2026 | 114/G/33 20-02-2026 | M/s ESS Elechmech Enterprises | 25/2/2026 | 12 months | 02-10-2027 | 80 |  | 54.936 |  | Not Started
MCL-0504 | D | West | 53 | O&M | MC Funds / General Quota | G.Q |  | Rough Cost Estimate For Prov. & Laying of 4” DIK-7 Water Supply line,8” & 10”UPVC Sewer lines at A-Block, Model Town Extension in ward No-53. |  | 45.94 | 45.94 |  | 3279 25-02-2026 | 125/g/33 10-03-2026 | M/S Rajdeep Enterprises | 15/3/2026 | 3 months | 15/7/2026 | 70 |  | 32.158 |  | Not Started
MCL-0505 | D | West | 65 | O&M | MC Funds / General Quota | G.Q |  | Providing & Installation of 12.5 HP. Submersible Tubewell at St. No. 13, Jain Colony in Ward No-65(E.Comp. No 398855) |  | 5.58 | 5.58 |  | 12-06-2025 | 11/g/33 15-06-2026 | Ess Elecmech Enterprises | 16/06/2026 | 2 months | 15/08/2026 | 0 |  | 0 |  | Not Started
MCL-0506 | D | West | D4 | O&M | MC Funds / General Quota | G.Q |  | Estimate for P/I of 12" i/d SN-8 Sewer Line at Hambran Road, MC limit to B&R Store (right side) and Hambran Road, Onkar Autos to outside World Diabetes (left side), sub zone-D4. (E Comp No. 384878) |  | 40.49 | 40.49 |  | 04-0 5-02026 | 10/g/33 11-05-2026 | M/s Bedi Pump Store, | 15/05/2026 | 3 months | 14/08/2026 | 75 |  | 30.3675 |  | Not Started
MCL-0507 | D | West | 53 | B&R | MC Funds / General Quota | MC Funds |  | Providing Zebra Crossong & Road Marking work at Various Streets of Ward no. 53 | 9.95 | 7.46 |  | 25 | 2090 13-10-2025 | 83/EED 04-11-2025 | M/s Dhindsa Enterprises |  | 2 |  | 10 |  |  | Work in Progress | In Progress
MCL-0508 | D | West | 54 | B&R | MC Funds / General Quota | MC Funds |  | Laying BM & OGPC in various streets of Punjab Mata Nagar | 38.39 | 37.6222 |  | 2 | 1171 15-11-2023 | 123/EED 16-01-2024 | M/s VKBS Const (P) Ltd |  | 3 |  | 85 |  |  | Premix Work Completed, Only road furniture Pending | Delayed/Held Up
MCL-0509 | D | West | 54 | B&R | MC Funds / General Quota | MC Funds |  | Laying BM & OGPC in Various Streets of Karnail Singh Nagar Ph-2 | 153.1 | 98.1677 |  | 35.88 | 2332 23-08-2024 | 01/EED 01-04-2025 | M/s SK Const. Co. |  | 3 |  | 95 |  |  | Premix Work Completed, Only road furniture Pending | Delayed/Held Up
MCL-0510 | D | West | 54 | B&R | MC Funds / General Quota | MC Funds |  | Providing and Laying OGPC in various streets of Punjab Mata Nagar Opposite Dhami Property Dealer | 36.84 | 27.6337 |  | 24.99 | 3496 21-04-2026 | 05/EED 07-05-2026 | M/s Somaya Infrastructures |  | 3 |  | 95 |  |  | Premix Work Completed, Only road furniture Pending | Delayed/Held Up
MCL-0511 | D | West | 55 | B&R | MC Funds / General Quota | MC Funds |  | P/L BM & OGPC in J Block Sarabha Nagar | 83.03 | 59.8646 |  | 27.9 | 2999 Dt. 8-11-2024 | 18/EED 09-04-2025 | M/s IHR Associates |  | 3 |  | 85 |  |  | Work in Progress | In Progress
MCL-0512 | D | West | 55 | B&R | N-CAP | N-CAP |  | Laying SDBC on Main Road from Zone-D Office to FZR Road Ward No.55 | 73.08 | 54.01 |  | 26.09 | 1861 13-10-2025 | 141/EED 25-03-2026 | Maruti Construction Co. |  | 5 |  | 95 |  |  | Work in progress | In Progress
MCL-0513 | D | West | 55 | B&R | MC Funds / General Quota | MC Funds |  | Laying SDBC on Roads of BRS Nagar Block-B W.No.55 | 77.54 | 55.3248 |  | 28.65 | 1772 13-10-2025 | 136/EED 25-03-2026 | M/s Somaya Infrastructure |  | 5 |  | 95 |  |  | Work in progress | In Progress
MCL-0514 | D | West | 55 | B&R | MC Funds / General Quota | MC Funds |  | Laying SDBC on Roads of BRS Nagar Block-C W.No.55 | 90.57 | 67.7464 |  | 25.2 | 1770 13-10-2025 | 142/EED 25-03-2026 | Maruti Construction Co. |  | 5 |  | 90 |  |  | Work in progress | In Progress
MCL-0515 | D | West | 56 | B&R | MC Funds / General Quota | MC Funds |  | Laying OGPC in Various Streets of Gobind Nagar W. No. - 56 | 41.21 | 38.0368 |  | 7.7 | 2602 11-02-2026 | 128/EED 18-03-2026 & 129/EED 18-03-2026 | Soham Construction Company & CH Builders Pvt. Ltd |  | 3 |  | 0 |  |  | Not Started | Not Started
MCL-0516 | D | West | 56 | B&R | MC Funds / General Quota | MC Funds |  | Laying OGPC in Streets of New BRS Nagar, Sham Nagar and New Sham Nagar W. No. - 56 | 71 | 58.6744 |  | 17.36 | 2597 11-02-2026 | 121/EED 18-03-2026 | Ganpati Infra |  | 4 |  | 20 |  |  | Work in progress | In Progress
MCL-0517 | D | West | 57 | B&R | MC Funds / General Quota | MC Funds |  | Laying BM & OGPC in Various Streets of Sunet W.No.72 | 66.04 | 43.8307 |  | 33.63 | 2329 23-08-2024 | 101/EED 12-02-2025 | SK Const. Co. |  | 3 |  | 20 |  |  | Work in Progress | In Progress
MCL-0518 | D | West | 57 | B&R | MC Funds / General Quota | MC Funds |  | Laying OGPC in Streets of Sunet Village W. No. 57 | 47.84 | 44.1563 |  | 7.7 | 2590 11-02-2026 | 130/EED 18-03-2026 & 131/EED 18-03-2026 | Soham Construction Company & CH Builders Pvt. Ltd |  | 3 |  | 0 |  |  | work not started | Not Started
MCL-0519 | D | West | 57 & 55 | B&R | MC Funds / General Quota | MC Funds |  | Laying SDBC on Main Road From Durga Mata Mandir to CFC School W. No. 57 & 55 | 25.34 | 23.3888 |  | 7.7 | 2529 11-02-2026 | 132/EED 18-03-2026 | Soham Construction Company |  | 2 |  | 0 |  |  | work not started | Not Started
MCL-0520 | D | West | 57 | B&R | MC Funds / General Quota | MC Funds |  | Laying OGPC in Streets of E - Block Near Lodhi Club W. No. 57 | 55.77 | 42.084 |  | 24.54 | 2598 11-02-2026 | 117/EED 18-03-2026 | Somaya Infrastructure |  | 3 |  | 95 |  |  | Work in Progress | In Progress
MCL-0521 | D | West | 57 | B&R | MC Funds / General Quota | MC Funds |  | Laying OGPC in Streets of BRS Nagar I - Block Near Cremation Ground W. No. 57 | 80.56 | 65.7692 |  | 18.36 | 2600 11-02-2026 | 120/EED 18-03-2026 | Ganpati Infra |  | 3 |  | 0 |  |  | Work Order Issued | Not Started
MCL-0522 | D | West | 57 | B&R | MC Funds / General Quota | MC Funds |  | Laying OGPC in Streets of BRS Nagar I - Block Near Lodhi Club W. No. 57 | 85.26 | 72.3857 |  | 15.1 | 2599 11-02-2026 | 119/EED 18-03-2026 | Soham Construction Company |  | 3 |  | 0 |  |  | Not started | Not Started
MCL-0523 | D | West | 57 | B&R | MC Funds / General Quota | MC Funds |  | Laying SDBC Main Sunet Road from Orient Market to Post Office Sunet. W. No. 57 | 48.42 | 39.6657 |  | 18.08 | 3221 25-02-2026 | 139/EED 25/03/2026 | Maruti Construction Co. |  | 3 |  | 10 |  |  | Work in Progress | In Progress
MCL-0524 | D | West | 58 | B&R | MC Funds / General Quota | MC Funds |  | Laying OGPC in Various Streets of Rajouri garden and Gill Avenue W.No.58 | 86.85 | 65.5283 |  | 24.55 | 2048 13-10-2025 | 148/EED 25/03/2026 | M/s Somaya Infrastructure |  | 5 |  | 95 |  |  | Work in Progress | In Progress
MCL-0525 | D | West | 58 | B&R | MC Funds / General Quota | MC Funds |  | Milling Laying BM & SDBC on Main Roads of J-Block, HJ Block, Lodhi Club to Namdev Chownk and under bridge side Slipway W.No.58 | 96.89 | 72.4737 |  | 25.2 | 2049 13-10-2025 | 149/EED 25/03/2026 | M/s Durga Construction Company |  | 5 |  | 95 |  |  | Work in Progress | In Progress
MCL-0526 | D | West | 58 | B&R | MC Funds / General Quota | MC Funds |  | Laying OGPC in Various Streets of Flower Dale, Good Friend Colony and Bhai Daya Singh Nagar on Barewal Main Road W.No.58 | 45.79 | 34.2509 |  | 25.2 | 2047 13-10-2025 | 147/EED 25/03/2026 | M/s Durga Construction Company |  | 3 |  | 5 |  |  | Work in Progress | In Progress
MCL-0527 | D | West | 58 | B&R | MC Funds / General Quota | MC Funds |  | Laying OGPC in Streets of Malkeet Avenue on Barewal Road Ward No. 58 | 49.87 | 43.5365 |  | 12.7 | 3567 21-04-2026 | 06/EED 07-05-2026 | M/s Soham Construction |  | 3 |  |  |  |  | Work Order Issued | Not Started
MCL-0528 | D | West | 58 | B&R | MC Funds / General Quota | MC Funds |  | Laying OGPC in Various Streets of Pink Park and Raja Garden W.No.58 | 45.43 | 33.4319 |  | 26.41 | 3568 21-04-2026 | 04/EED 07-05-2026 | M/s Somaya Infrastructure |  | 3 |  | 95 |  |  | Work in Progress | In Progress
MCL-0529 | D | West | 59 | B&R | MC Funds / General Quota | MC Funds |  | Providing & laying BM & OGPC in various streets of Mahaveer Enclave Barewal | 174.71 | 114.8544 |  | 34.26 | 3162 22-11-2024 | 03/EED 01-04-2025 | SK Const. Co. |  | 3 |  | 85 |  |  | Work in Progress | In Progress
MCL-0530 | D | West | 59 | B&R | MC Funds / General Quota | MC Funds |  | P/L OGPC in Various Streets of Ajit Villa South City | 118.16 | 115.1942 |  | 2.51 | 871 06-05-2025 | 53/EED 16-05-2024 | M/s Apex Builder |  | 4 |  | 60 |  |  | Work in Progress | In Progress
MCL-0531 | D | West | 59 | B&R | MC Funds / General Quota | MC Funds |  | Laying OGPC in various Streets of Parkash Colony W.No.-59 | 25.07 | 23.1396 |  | 7.7 | 2592 11-02-2026 | 133/EED 18-03-2026 | Soham Construction Company |  | 4 |  | 0 |  |  | Not Started | Not Started
MCL-0532 | D | West | 59 | B&R | N-CAP | N-CAP |  | Laying SDBC on Main Road From Environmental Friendly Park to Mahaveer Enclave. W. No. 59 | 30.55 | 25.0266 |  | 18.08 | 1771 13-10-2025 | 138/EED 25/03/2026 | Maruti Construction Co. |  | 3 |  | 95 |  |  | Work in progress | In Progress
MCL-0533 | D | West | 60 | B&R | MC Funds / General Quota | MC Funds |  | Laying BM & OGPC in Various Streets of Gurdev Nagar Adjoining Pakhowal Road and Ferozepur Road | 154.77 | 153.08 |  | -1.09 | 2654 Dt. 11-02-2026 | 94/EED 05-12-2025 | Vansh Engineers |  | 4 |  | 30 |  |  | Ongoing Work | In Progress
MCL-0534 | D | West | 60 | B&R | MC Funds / General Quota | MC Funds |  | Laying BM & OGPC in Various Streets of New Lajpat Nagar | 66.87 | 66.7 |  | 0.24 | 3505 Dt. 21-04-2026 | 07/EED 07-05-2026 | S.K Construction |  | 5 |  | 0 |  |  | Work Order Issued | Not Started
MCL-0535 | D | West | 65 | B&R | MC Funds / General Quota | MC Funds |  | Laying BM & OGPC in various streets of Pavittar nagar ward no 65. | 70.58 | 69.52 |  | 1.5 | 1215 11-08-25 | 100/EED 09-02-2026 | M/s Rajeev enterprises |  | 3 |  | 0 |  |  | inauguration pending | Delayed/Held Up
MCL-0536 | D | West | 65 | B&R | MC Funds / General Quota | MC Funds |  | Laying BM & OGPC in various streets of Prem Nagar,Haqiqat Nagar and New patel Nagar. | 96.18 | 89.44 |  | 7 | 692 Dt. 09-04-2025 | 152/EED 25/03/2026 | M/s Somaya Infrastructure |  | 3 |  | 90 |  |  | Work in Progress | In Progress
MCL-0537 | D | West | 65 | B&R | MC Funds / General Quota | MC Funds |  | Const of metaled roads in Joshi Nagar Part-1 W.No.81 | 95.63 | 64.88 |  |  |  | 37/EED 28-04-2025 | M/s Somaya Infrastructure |  | 4 |  | 90 |  |  | Work in progress | In Progress
MCL-0538 | D | West | 65 | B&R | MC Funds / General Quota | MC Funds |  | Const of metaled roads in Joshi Nagar Part-2 W.No.81 | 99.31 | 67.38 |  |  |  | 37/EED 28-04-2025 | M/s Somaya Infrastructure |  | 4 |  | 90 |  |  | Work in progress | In Progress
MCL-0539 | D | West | 81 | B&R | MC Funds / General Quota | MC Funds |  | Const. of metalled roads in ranjodh park, Haibowal Nagar and New Patel Nagar | 94.66 | 88.03 |  |  |  | 146/EED 25-03-2026 | M/s Durga Construction Company |  | 3 |  | 0 |  |  |  | Not Started
MCL-0540 | D | West | 69 | B&R | MC Funds / General Quota | MC Funds |  | Providing and Laying OGPC in Green Park Society adjoining Prince Hostel. Ward no. 82 | 89.49 | 83.22 |  | 7 | 3497 Dt. 21-04-2026 | 10/EED 07/05/2026 | Anil Kumar and Sons |  | 4 |  |  |  |  | Work Order Issued | Not Started
MCL-0541 | D | West | 69 | B&R | MC Funds / General Quota | MC Funds |  | Laying BM & SDBC on Saggu Chowk to Humbran Road | 152.59 | 119.63 |  | 21.6 | 629 Dt. 09-04-2025 | 162/EED 25/03/2026 | M/s NKC Construction Pvt. Ltd |  | 3 |  | 90 |  |  | Premix Work Completed, Only road furniture Pending | Delayed/Held Up
MCL-0542 | D | West | 71 | B&R | MC Funds / General Quota | MC Funds |  | Laying OGPC in streets of Officer colony and adjoining Rakh Bagh | 113.35 | 83.31 |  | 26.5 | 3009 Dt. 08-11-2024 | 43/EED 08-05-2025 | Durga Construction |  | 3 |  | 20 |  |  | Ongoing Work | In Progress
MCL-0543 | D | West | 71 | B&R | MC Funds / General Quota | MC Funds |  | P/l BM and OGPC In various streets of Ghumar Mandi. | 66.92 | 62.23 |  | 7 | 3494 Dt. 21-04-2026 | 09/EED 07-05-2026 | S.K Construction Co |  | 3 |  |  |  |  | Work Order Issued | Not Started
MCL-0544 | D | West | 72 | B&R | MC Funds / General Quota | MC Funds |  | Laying BM & OGPC in Various Streets of Friends Colony, Partap Colony and Kartar Nagar in Ward no. 72 | 68.43 | 63.64 |  | 7 | 3491 Dt. 21-04-2026 | 08/EED 07-05-2026 | Global Construction |  | 3 |  |  |  |  | Work order Issued | Not Started
MCL-0545 | D | West | 72 | B&R | MC Funds / General Quota | MC Funds |  | Laying BM & OGPC in Various Streets of Model Gram Ward no. 72 | 234.39 | 217.98 |  | 7 | 3492 Dt. 21-04-2026 | 11/EED 07-05-2026 | Ganpati Infra |  | 3 |  |  |  |  | Work order Issued | Not Started
MCL-0546 | D | West | 53 | B&R | MC Funds / General Quota | MC Funds |  | Repair and Renovation of park Nehru Nagar & Shastri Nagar Ward no. 53 | 20.22 | 15.16 |  | 25.02 | 2108 13-10-2025 | 86/EED 04-11-2025 | M/s Dynamic Tiles |  | 3 |  | 60 |  |  | Work in Progress | In Progress
MCL-0547 | D | West | 55 | B&R | MC Funds / General Quota | MC Funds |  | Repair and Renovation of Parks (7 No.s) in Block-C BRS Nagar in Ward no 55. | 68.48 | 52.7844 |  | 22.92 | 1206 11-08-2025 | 79/EED 08-10-2025 | T & G Construction Co. |  | 5 |  | 95 |  |  | Work in Progress | In Progress
MCL-0548 | D | West | 55 | B&R | MC Funds / General Quota | MC Funds |  | Repair and Renovation of Parks (5 No.s) in Block -A and Block-B BRS Nagar in Ward no 55. | 39.9 | 31.521 |  | 21 | 1205 11-08-2025 | 82/EED 04-11-2025 | GLISTEN |  | 5 |  | 70 |  |  | Work in Progress | In Progress
MCL-0549 | D | West | 55 | B&R | MC Funds / General Quota | MC Funds |  | Development of Green Belt outside Canal view apartments HIG Flats W.No.75 | 47.49 | 30.6975 |  | 35.36 | 864 06-05-2025 | 57/EED 16-05-2025 | T&G Const.Co |  | 3 |  | 0 |  |  | Not Started | Not Started
MCL-0550 | D | West | 55 | B&R | MC Funds / General Quota | MC Funds |  | Repair and Renovation of Various Parks in Sarabha Nagar & BRS Nagar. W. No. 55. | 39.98 | 37.3173 |  | 6.66 | 1203 11-08-2025 | 143&144/EED 25-03-2026 | M/s Apex Developers & K. S. Constructions |  | 3 |  | 10 |  |  | Work in progress | In Progress
MCL-0551 | D | West | 55 | B&R | MC Funds / General Quota | MC Funds |  | Providing and Fixing of Children Playing Equipments and Garden Gyms in Various Parks W. No. 55. | 26.93 | 17.7199 |  | 34.2 | 753 09-04-2025 | 137/EED 25-03-2026 | M/s Ram Parkash kakkar |  | 3 |  | 0 |  |  | Not Started | Not Started
MCL-0552 | D | West | 55 | B&R | MC Funds / General Quota | MC Funds |  | Civil work in Rose Valley on sidhwan Canal Near Jawaddi Bridge | 27.67 | 18.265 |  | 33.99 | 1512 18-01-2024 | 88/EED 29-11-2024 | The Boha Co op L&C society ltd |  | 3 |  | 90 |  |  | Work in Progress | In Progress
MCL-0553 | D | West | 56 | B&R | MC Funds / General Quota | MC Funds |  | P/F Cemented Benches in Various Parks of Ward No 56. | 2.79 | 1.782 |  | 36.13 | 1204 11-08-2025 | 76/EED 08-10-2025 | Rakesh Kumar Contractor |  | 2 |  | 25 |  |  | Work in Progress | In Progress
MCL-0554 | D | West | 57 | B&R | MC Funds / General Quota | MC Funds |  | Repair & Renovation of Park near railway line D Block BRS Nagar | 18.2 | 13.5554 |  | 25.52 | 2547 24-09-2024 | 33/EED 24-10-2024 | The Civil Engineers & Builders Co op L&C society ltd |  | 3 |  | 50 |  |  | Work in Progress | In Progress
MCL-0555 | D | West | 57 | B&R | MC Funds / General Quota | MC Funds |  | Construction of New Park in F Block BRS Nagar Near Ravidas Shamshan Ghat Ward No 72 | 24.32 | 18.2424 |  | 24.99 | 2541 05-02-2026 | 154/EED 25/03/2026 | Varinder Singh Govt. Cont. |  | 4 |  | 0 |  |  | Not started | Not Started
MCL-0556 | D | West | 57 | B&R | MC Funds / General Quota | MC Funds |  | P/F Cemented Benches in Various Parks of Ward No 57. | 9.77 | 6.2401 |  | 36.13 | 1369 11-08-2025 | 74/EED 08-10-2025 | Rakesh Kumar Contractor |  | 2 |  | 30 |  |  | Work in Progress | In Progress
MCL-0557 | D | West | 58 | B&R | MC Funds / General Quota | MC Funds |  | P/F Cemented Benches in Various Parks of Ward No 58. | 8.37 | 5.3459 |  | 36.13 | 1207 11-08-2025 | 77/EED 08-10-2025 | Rakesh Kumar Contractor |  | 2 |  | 25 |  |  | Work in Progress | In Progress
MCL-0558 | D | West | 58 | B&R | MC Funds / General Quota | MC Funds |  | Construction & Various Works of Sports Court in Parks of BRS J-Block, Near RUB. W. No. 58 | 8.84 | 7.2691 |  | 17.77 | 634 09-04-2025 | 85/EED 04-11-2025 | Subodh Batish |  | 3 |  | 95 |  |  | Work in Progress | In Progress
MCL-0559 | D | West | 58 | B&R | MC Funds / General Quota | MC Funds |  | Repair & Renovation of Various Parks in River Dale Colony in Barewal W.No. 58 | 9.79 | 7.6479 |  | 21.88 | 638 09-04-2025 | 84/EED 04-11-2025 | Subodh Batish |  | 5 |  | 25 |  |  | Work in Progress | In Progress
MCL-0560 | D | West | 58 | B&R | MC Funds / General Quota | MC Funds |  | P/F Garden Gym in Various Parks of W. No. 58 | 9.96 | 7.7698 |  | 21.99 | 642 09-04-2025 | 145/EED 25/03/2026 | M/s Khalsa Export Private Limited |  | 2 |  | 0 |  |  | Not Started | Not Started
MCL-0561 | D | West | 58 | B&R | MC Funds / General Quota | MC Funds |  | Repair & Renovation of Various Parks in J Block 64 Yards W.No.58 | 46.7 | 31.6346 |  | 32.26 | 2051 13-10-2025 | 150/EED 25/03/2026 | M/s Varinder Singh Govt. Contractor |  | 5 |  | 25 |  |  | Work in Progress | In Progress
MCL-0562 | D | West | 59 | B&R | MC Funds / General Quota | MC Funds |  | Const. of Canopies, Gym Garden, Swings in various parks W.No.74 | 48.93 | 33.2773 |  | 31.99 | 2439 23-08-2024 | 32/EED 24-10-2024 | The Akal Co op L&C Society Ltd |  | 3 |  | 60 |  |  | Work in Progress, 859 Dt. 6-5-25 PENDING | Delayed/Held Up
MCL-0563 | D | West | 59 | B&R | MC Funds / General Quota | MC Funds |  | Repair and Renvoation of various parks of sunil park, Flower Date Park, Citizen Enclave. Professor colony in Ward no 74. | 35.07 | 26.0535 |  | 25.71 | 2657 24-09-2024 | 49/EED 29-10-2024 | M/s The Saharan Majra Co-op LC Society Ltd |  | 5 |  | 90 |  |  | Work in Progress | In Progress
MCL-0564 | D | West | 59 | B&R | MC Funds / General Quota | MC Funds |  | Repair & Renovation of Eco Friendly Park in Barewal Awana W. No. 59 | 6.19 | 5.0968 |  | 17.66 | 2601 11-02-2026 | 122/EED 18-03-2026 | Varinder Singh Govt. Contractor |  | 3 |  | 0 |  |  | Not Started | Not Started
MCL-0565 | D | West | 59 | B&R | MC Funds / General Quota | MC Funds |  | Repair & Renovation of Various Parks in Parkash Colony & Madhuvan Enclave on Barewal Road W. No. 59 | 11.28 | 7.8847 |  | 30.1 | 1381 11-08-2025 | 151/EED 25/03/2026 | M/s Dynamic tiles |  | 2 |  | 10 |  |  | Work in progress | In Progress
MCL-0566 | D | West | 60 | B&R | MC Funds / General Quota | MC Funds |  | Repari and Renovation of different parks of new Lajpat Nagar in Ward no 67 (2 nos. parks) | 35.92 | 27.59 |  | 23.19 | 1169 15-11-2023 | 113/EED 21-12-2023 | M/s The Civil Engineer & Builders Co-op L/C Society Ltd |  | 3 |  | 80 |  |  | Ongoing Work | In Progress
MCL-0567 | D | West | 60 | B&R | MC Funds / General Quota | MC Funds |  | Repair & Renovation of parks (4 nos.) in Gurdev nagar (4 nos. parks) | 49.28 | 30.8 |  | 37.5 | 3004 Dt. 08-11-2024 | 34/EED 25-4-2025 | Ram Parkash Kakar |  | 3 |  | 95 |  |  | Ongoing Work | In Progress | Sprinkler needs to be fixed in Kartar Park, New Lajpat Nagar, Gurdev Nagar
MCL-0568 | D | West | 60 | B&R | MC Funds / General Quota | MC Funds |  | Repair and Renovation of Park in Ghumar Mandi (1 No. park) | 21.76 | 14.79 |  | 32 | 618 Dt. 09-04-2025 | 47/EED 28-10-2024 | Dynamic Tiles |  | 2 |  | 20 |  |  | Ongoing Work | In Progress
MCL-0569 | D | West | 60 | B&R | MC Funds / General Quota | MC Funds |  | Reapir and renovation of Murgi Farm Park and other parks of Gurdev Nagar w-60 | 36.94 | 24.52 |  | -33.6 | 1860 Dt.13-10-2025 | 125/EED 18-03-2026 | Ram Parkash Kakkar |  | 3 |  | 20 |  |  | Work in progress | In Progress
MCL-0570 | D | West | 61 | B&R | MC Funds / General Quota | MC Funds |  | Repair and Renovation of various Parks in Ward no 61. (3 Nos. parks) | 48.87 | 32.49 |  | 33.5 | 616 Dt. 09-04-2025 | 63/EED 19-05-2025 | Dynamic Tiles |  | 3 |  | 50 |  |  | work in progress | In Progress
MCL-0571 | D | West | 62 | B&R | MC Funds / General Quota | MC Funds |  | Construction of 2 new parks & Repair of other Parks in Ward No 78 | 48.19 | 64.88 |  | 41.01 | 1662 Dt. 14-02-2024 | 46/EED 15-05-2025 | M/s Dynamic tiles |  | 3 |  | 60 |  |  | Work in progress | In Progress
MCL-0572 | D | West | 63 | B&R | MC Funds / General Quota | MC Funds |  | Repair and Renovation of various parks in ward no 63. | 85.5 | 57.71 |  | 32.5 | 685 Dt. 09-04-2025 | 105/EED 16-02-2026 | M/s Dynamic tiles |  | 3 |  | 45 |  |  | Work in progress | In Progress
MCL-0573 | D | West | 64 | B&R | Other / Unspecified |  |  | Repair and renovation of corporation colony parks (2 nos.) in ward no. 78 | 57.55 | 38.79 |  | 32.59 | 323 dt 26.03.25 | 36/EED 28-04-2025 | M/S JP Builders |  | 3 |  | 95 |  |  | Work in progress | In Progress
MCL-0574 | D | West | 65 | B&R | MC Funds / General Quota | MC Funds |  | Repair and Renovation of various parks in ward no 65. | 83.28 | 53.4 |  | 35.88 | 1202 Dt. 11-08-2025 | 153/EED 25/03/2026 | M/s Naresh kumar contractor |  | 3 |  | 25 |  |  | Work in progress | In Progress
MCL-0575 | D | West | 69 | B&R | MC Funds / General Quota | MC Funds |  | Repair & renovation of various parks adjoining Cementry road W-82 (3 Nos. parks) | 28.05 | 21.46 |  | 23.46 | 3010 Dt. 08-11-2024 | 17/EED 09.04.2025 | M/s Smridhi Constructions |  | 3 |  | 90 |  |  | Ongoing Work | In Progress
MCL-0576 | D | West | 71 | B&R | MC Funds / General Quota | MC Funds |  | Repair and renovation of Rajaram park in Mall Enclave. (1 No. park) | 22.82 | 17.11 |  | 24.99 | 2671 Dt. 24-09-2024 | 41/EED 28-10-2024 | The Sunet Co op L&C society ltd |  | 3 |  | 95 |  |  | Ongoing Work | In Progress
MCL-0577 | D | West | 71 | B&R | MC Funds / General Quota | MC Funds |  | P/L Perforated interlocking tiles on side berms of various streets in Mall Enclave | 32.81 | 19.35 |  | 41 | 652 Dt. 09-04-2025 | 61/EED 19-05-2025 | Dynamic Tiles |  | 3 |  | 60 |  |  | Ongoing Work | In Progress
MCL-0578 | D | West | 72 | B&R | MC Funds / General Quota | MC Funds |  | Repair & Renovation of Park in Kochar Market and Jawahar Camp (2 Nos. parks) | 49.76 | 37.32 |  | 24.99 | 2672 Dt. 24-09-2024 | 45/EED 28-10-2024 | The Sunet Co op L&C society ltd |  | 3 |  | 95 |  |  | Work in progress | In Progress
MCL-0579 | D | West | 72 | B&R | MC Funds / General Quota | MC Funds |  | Repair and Renovation of park near potohari Gurudwara and Batra Park. (2 Nos. parks) | 40.33 | 30.25 |  | 24.99 | 2670 24-09-2024 | 51/EED 06-11-2024 | M/s The Sunet L/C Society Ltd |  | 3 |  | 95 |  |  | Work in progress | In Progress
MCL-0580 | D | West | 72 | B&R | MC Funds / General Quota | MC Funds |  | Repair and renovation of parks (6 Nos.) In Model Gram Partap Colony & Friends Colony in Ward no. 72 (6 Nos. parks) | 47.41 | 31.76 |  | 33 | Dt. 09-04-2025 | 59/EED 19-05-2025 | Dynamic Tiles |  | 3 |  | 30 |  |  | Work in progress | In Progress
MCL-0581 | D | West | 72 | B&R | MC Funds / General Quota | MC Funds |  | Construction of an entrance gate in jawahar nagar camp | 18.37 | 17.41 |  | 5.2 | 2672 Dt. 11-02-2026 | 106/EED 03-03-2026 | Asis Builders |  | 3 |  | 30 |  |  | Work in progress | In Progress
MCL-0582 | D | West | 73 | B&R | MC Funds / General Quota | MC Funds |  | Repair and Renovation of Various Parks in Ward No 65 (3 Nos. parks) | 48.97 | 31.39 |  | 35.88 | 321 26-03-2025 | 13/EED 09-04-2024 | M/s Naresh Kumar Contarctor |  | 3 |  | 30 | 0 |  | Ongoing Work | In Progress | Pavement done (concrete), canopies, benches done in 1 park. Gym area, jhule pending.
MCL-0583 | D | West | 53 | B&R | MC Funds / General Quota | MC Funds |  | Providing and Laying of 60mm thick interlocking tiles on side berms of Model Town Extension (Ishmeet Singh road) | 43.03 | 27.68 |  | 35.66 | 2660 24-09-2024 | 55/EED 06-11-2024 | M/s The Boha Co-op |  | 5 |  | 75 |  |  | Work in Progress | In Progress
MCL-0584 | D | West | 54 | B&R | MC Funds / General Quota | MC Funds |  | P/L interlocking tiles on side berms of road in New Punjab Mata Nagar W.No.70 | 56.96 | 33.6007 |  | 41.01 | 2331 23-08-2024 | 27/EED 11-04-2025 | M/s Dynamic Tiles |  | 5 |  | 5 |  |  | Work Held up due to NGT Guidelines | Delayed/Held Up
MCL-0585 | D | West | 54 | B&R | MC Funds / General Quota | MC Funds |  | P/Laying interlocking tiles on side berms of roads in Karnail Singh Nagar Ph-II | 95.93 | 64.9926 |  | 32.25 | 1288 20-11-2023 | 118/EED 05-01-2024 | M/s J.P Builders |  | 5 |  | 30 |  |  | Work Held up due to NGT Guidelines, Moreover Case Sent to F&CC for Change of Site - PENDING 858 Dt. 6-5-25 | Delayed/Held Up
MCL-0586 | D | West | 56 | B&R | MC Funds / General Quota | MC Funds |  | P/Laying Inter-locking tiles on side berms of roads in Vikas Nagar & Gobind Nagar Ward No 71 | 223.68 | 192.7003 |  | 13.85 | 6869 07-09-2022 | 10/EED 26-12-2022 | M/s Aglow Builders |  | 5 |  | 95 |  |  | Work in Progress, Revised vide F&CC Res. no. 880 dt. 06.05.2025 | In Progress
MCL-0587 | D | West | 56 | B&R | MC Funds / General Quota | MC Funds |  | P/L 80mm Thick Interlocking Tiles in Victoria Colony on 200' Road W. No. 56 | 52.38 | 36.4355 |  | 30.44 | 2850 19-02-2026 | 134/EED 18-03-2026 | T&G Construction |  | 4 |  | 70 |  |  | Work in progress | In Progress
MCL-0588 | D | West | 57 | B&R | MC Funds / General Quota | MC Funds |  | P & Laying Interlocking Tiles on side Berms In D Block BRS Nagar Ward No 72 | 98.63 | 56.3375 |  | 42.88 | 1660 14-02-2024 | 25/EED 11-04-2025 | Varinder Singh Govt. Cont. |  | 4 |  | 80 |  |  | Work in Progress | In Progress
MCL-0589 | D | West | 57 | B&R | MC Funds / General Quota | MC Funds |  | P/L 80mm thick interlocking tiles in village Sunet | 17.33 | 10.2455 |  | 40.88 | 419 26-03-2025 | 11/EED 09-04-2025 | Varinder Singh Govt. Cont. |  | 4 |  | 70 |  |  | Work in Progress | In Progress
MCL-0590 | D | West | 57 | B&R | MC Funds / General Quota | MC Funds |  | P & Laying Interlocking Tiles on side Berms In L Block BRS Nagar Ward No 72 | 62.66 | 35.7914 |  | 42.88 | 1624 14-02-2024 | 24/EED 11-04-2025 | Varinder Singh Govt. Cont. |  | 3 |  | 0 |  |  | Work Held up due to Upgradation of Sewer Line | Delayed/Held Up
MCL-0591 | D | West | 57 | B&R | MC Funds / General Quota | MC Funds |  | P/L 80mm Thick Interlocking Tiles in Various Streets of Sunet. W. No. 57 | 35.18 | 21.4141 |  | 39.13 | 1202 11-08-2025 | 75/EED 08-10-2025 | Rakesh Kumar Contractor |  | 5 |  | 0 |  |  | Work Held up due to Upgradation of Sewer Line | Delayed/Held Up
MCL-0592 | D | West | 57 | B&R | MC Funds / General Quota | MC Funds |  | P/L 60mm thick relaying tiles in streets of village Sunet near Shitla Mata Mandir W.No. 57 | 23.06 | 13.2226 |  | 42.66 | 2587 11-02-2026 | 135/EED 18-03-2026 | Navdeep Gupta and Company |  | 3 |  | 0 |  |  | work not started | Not Started
MCL-0593 | D | West | 58 | B&R | MC Funds / General Quota | MC Funds |  | P/L 60mm Thick Perforated Interlocking Tiles on Side Berms of Barewal Sua Road W. No. 58 | 62.29 | 41.1176 |  | 33.99 | 1200 11-08-2025 | 78/EED 08-10-2025 | Dynamic Tiles |  | 5 |  | 5 |  |  | Work in Progress | In Progress
MCL-0594 | D | West | 58 | B&R | MC Funds / General Quota | MC Funds |  | P/L 60mm Thick Perforated Interlocking Tiles on Side Berms of Magnet Resort Road W. No. 58 | 82.56 | 52.0458 |  | 36.96 | 1773 13-10-2025 | 93/EED 02-12-2025 | R. K. Construction Co. |  | 5 |  | 5 |  |  | Work in Progress | In Progress
MCL-0595 | D | West | 59 | B&R | MC Funds / General Quota | MC Funds |  | Providing and Laying interlocking tiles on side berms of road in Mahaveer nagar Ward no 74. | 65.29 | 40.4863 |  | 37.99 | 860 06-05-2025 | 48/EED 29-10-2024 | M/s Apex Developers |  | 3 |  | 80 |  |  | Work in Progress & Case Approved by F&CC Res. no.860 Dt. 6-5-25 for Change of Site for Motar Wali Gali | In Progress
MCL-0596 | D | West | 61 | B&R | MC Funds / General Quota | MC Funds |  | Prov. and laying perforated interlocking tiles in various streets of w. no. 76 | 69.54 | 47.22 |  | 32 | 3006 Dt. 08-11-2024 | 42//EED 08-05-2025 | Glisten |  | 3 |  | 30 |  |  | work in progress | In Progress
MCL-0597 | D | West | 63 | B&R | MC Funds / General Quota | MC Funds |  | Prov. and fixing of 60mm thick interlocking tiles on side berms of different area Kitchlu Nagar Block E, F and G W. No. 77 | 80.08 | 50.45 |  | 37 | 2386 Dt. 23-08-2024 | 35/EED 28-04-2025 | M/s Dynamic tiles |  | 4 |  | 40 |  |  | Work in progress | In Progress
MCL-0598 | D | West | 65 | B&R | MC Funds / General Quota | MC Funds |  | P/F of 60mm Interlocking Tiles in various streets of Prem Nagar ward no 65. | 66.54 | 41.93 |  | 36.99 | 1216 Dt. 11-08-2025 | 99/EED 09-02-2026 | M/s Apex developers |  | 3 |  | 0 |  |  | Work in Progress | Not Started
MCL-0599 | D | West | 71 | B&R | MC Funds / General Quota | MC Funds |  | P/L Perforated interlocking tiles on side berms of Collage Road and Hira Singh Road | 49.62 | 32.25 |  | 35 | 651 Dt. 09-04-2025 | 62/EED 19-05-2025 | Dynamic Tiles |  | 3 |  | 90 |  |  | Ongoing Work | In Progress
MCL-0600 | D | West | 71 | B&R | MC Funds / General Quota | MC Funds |  | P/L Perforated interlocking tiles on side berms of various streets in Mall Enclave | 32.81 | 19.35 |  | 41 | 652 Dt. 09-04-2025 | 61/EED 19-05-2025 | Dynamic Tiles |  | 3 |  | 60 |  |  | Ongoing Work | In Progress
MCL-0601 | D | West | 57 | B&R | MC Funds / General Quota | MC Funds |  | P/L RMC (M-30) in Various Streets of Sunet. W. No. 57 | 49.89 | 28.6069 |  | 42.66 | 2591 11-02-2026 | 118/EED 18-03-2026 | M/s Navdeep gupta & company |  | 3 |  | 60 |  |  | Work in Progress | In Progress
MCL-0602 | D | West | 62 | B&R | MC Funds / General Quota | MC Funds |  | P/Laying of RMC M-30 in streets of Mandeep Nagar ward no 62 | 99.3 | 57.91 |  | 41.68 | 840 06.05.2025 | 98/EED 05.02.2026 | M/s Navdeep gupta & company |  | 4 |  | 80 |  |  | Work in progress | In Progress
MCL-0603 | D | West | 62 | B&R | MC Funds / General Quota | MC Funds |  | P/L of RMC M-30 in balance streets of Punj Peer road ward no 62 | 30.31 | 17.63 |  | 41.82 | 839 06.05.2025 | 97/EED 05.02.2026 | M/s Navdeep gupta & company |  | 3 |  | 5 |  |  | Work in progress | In Progress
MCL-0604 | D | West | 63 | B&R | MC Funds / General Quota | MC Funds |  | P/L of RMC M-30 in Haqiqat nagar ward no 63. | 33.67 | 22.05 |  | 34.51 | 690 Dt. 09-04-2025 | 58/EED 19-05-2025 | M/s K.S Constructions |  | 3 |  | 80 |  |  | Work in progress | In Progress
MCL-0605 | D | West | 55 | B&R | Rangla Punjab | Rangla Punjab |  | Repair and renovation of various parks and sprinkler system in parks w. no. 55 | 20 | 18.45 |  | 7.77 | In Anticipation | 28/EED 13-05-2026 | M/s Subodh Batish |  | 3 |  | 10 |  |  | Work Order Issued | In Progress
MCL-0606 | D | West | 59 | B&R | Rangla Punjab | Rangla Punjab |  | Repair and renovation by laying 60mm Thick Interlocking Tiles in streets of sanjha sahib gurudwara to village barewal T point of W. no. 59 | 10 | 8.79 |  | 12.12 | In Anticipation | 29/EED 13-05-2026 | M/s Kohinoor Builders |  | 1 |  | 50 |  |  | Work in Progress | In Progress
MCL-0607 | D | West | 60 | B&R | Rangla Punjab | Rangla Punjab |  | Construction of Public Library in Gurdev Nagar in W. no. 60 | 12 | 11.75 |  | -2.05 | In Anticipation | 27/EED 13-05-2025 | M/s Kohinoor Builders |  | 2 |  |  |  |  | Work Order Issued | Not Started | Site not clear, Councillor ro provide clear land. SE/Xen to follow up and finalise. Proposed to be made in ward.
MCL-0608 | D | West | 60 | B&R | Rangla Punjab | Rangla Punjab |  | Construction of Cricket Play ground Gurdev Nagar in W. no. 60 | 5 | 4.8 |  | -3.99 | In Anticipation | 24/EED 13-05-2025 | MAA Chintpurani Construction |  | 2 |  |  |  |  | Work Order Issued | Not Started | Land Issue, Councillor to provide land by 10/07/26
MCL-0609 | D | West | 63 | B&R | Rangla Punjab | Rangla Punjab Scheme |  | Construction of Joybox or Playground at Green Belt opp. Polytechnic College ward no 63. | 27.23 | 22.63 |  | 16.89 | In Anticipation | 26/EED 13-05-2026 | M/s Teg Builders |  | 3 |  | 5 |  |  | Work in progress | In Progress
MCL-0610 | D | West | 72 | B&R | Rangla Punjab | Rangla Punjab-1 |  | Construction of additional rooms at Ayurvedic Dispensary jawahar nagar camp near bus stand in W. no. 72 | 15 | 13.68 |  | 8.77 | In Anticipation | 25/EED 13-05-2026 | M/s Smridhi Construction |  | 2 |  | 10 |  |  | Work in progress | In Progress
MCL-0611 | D | West | New Ward No | B&R | Viveki Funds | Head |  | Name of Work | Est. Amount (In Lacs) | Tender Amount (In Lacs) |  | OAS (%) | TAC/F&CC resolution no. | Work Order No. & Date | Name of Agency |  | Time Limit (in Months) |  |  |  |  | Remarks/Status | Not Started
MCL-0612 | D | West | 54 | B&R | Viveki Funds | Viveki Funds |  | Repair & Renovation of Jawaddi Dharmshalla | 16.66 | 13.3113 |  | 20.1 | 2548 24-09-2024 | 22/EED 11-04-2025 | M/s Smridhi Const. |  | 6 |  | 90 |  |  | Work in Progress | In Progress
MCL-0613 | D | West | 57 | B&R | Viveki Funds | Viveki Funds |  | Repair & Renovation of Ravidass Dharmshalla Village Sunet | 16.67 | 13.3193 |  | 20.1 | 2548 24-09-2024 | 20/EED 11-04-2025 | M/s Smridhi Const. |  | 2 |  | 90 |  |  | Work in Progress | In Progress
MCL-0614 | D | West | 57 | B&R | Viveki Funds | Viveki Funds |  | Repair & Renovation of Dharmshalla Near Masjid | 16.67 | 13.5394 |  | 18.78 | 274 26-03-2025 | 21/EED 11-04-2025 | M/s Smridhi Const. |  | 2 |  | 60 |  |  | Work in Progress | In Progress
MCL-0615 | D | West | 55 | B&R | N-CAP | N-CAP |  | Laying SDBC on Main Road from Zone-D Office to FZR Road Ward No.55 | 73.08 | 54.01 |  | 26.09 | 1861 13-10-2025 | 141/EED 25-03-2026 | Maruti Construction Co. |  | 5 |  | 95 |  |  | Work in progress | In Progress
MCL-0616 | D | West | 59 | B&R | N-CAP | N-CAP |  | Laying SDBC on Main Road From Environmental Friendly Park to Mahaveer Enclave. W. No. 59 | 30.55 | 25.0266 |  | 18.08 | 1771 13-10-2025 | 138/EED 25/03/2026 | Maruti Construction Co. |  | 3 |  | 95 |  |  | Work in progress | In Progress
MCL-0617 | D2 | West | 53 | B&R | MPLAD Funds | MPLAD Funds |  | Construction Old Rooms In Guru Teg Bahadur Hospital,Shastri Nagar,Model Town,Ludhiana | 10 | 9.56 |  | 4.44 |  | 15/EED 07/05/2026 | M/s Kohinoor Builders | [6 empty] | Work Order Issue | Not Started
MCL-0618 | D3 | West | 55 | B&R | MPLAD Funds | MPLAD Funds |  | Installation of Swings & Development of Parks in GEE Green Welfare Society Park, 97-G BRS Nagar W. No. 55 | 5 | 4.744 |  | 5.12 |  | 107/EED 05/03/2026 | M/s Kohinoor Builders |  |  |  | 15 |  |  | Work Order Issue | In Progress
MCL-0619 | D3 | West | 55 | B&R | MPLAD Funds | MPLAD Funds |  | Construction of Canopy and Benches in Flowerdale Park, B-Block BRS Nagar W. No. 55 | 5 | 4.9435 |  | 1.13 |  | 108/EED 05/03/2026 | M/s Varinder Singh Govt. Contractor |  |  |  | 70 |  |  | Work Order Issue | In Progress
MCL-0620 | D3 | West | 55 | B&R | MPLAD Funds | MPLAD Funds |  | Development of Public Parks with Swings, Foothpath, Benches & Grills W. No. 55 (E, F, H, I, J Blocks of Sarabha Nagar and C Block of BRS Nagar) | 10 | 8.9 |  | 11 |  | 109/EED 05/03/2026 | M/s Ram Parkash kakkar | [6 empty] | Work Order Issue | Not Started
MCL-0621 | D3 | West | 55 | B&R | MPLAD Funds | MPLAD Funds |  | Development of Public Parks with Installation of Swings & Benches etc. in Park No. 245 BRS Nagar W. No. 55 | 3 | 2.8635 |  | 4.55 |  | 110/EED 05/03/2026 | M/s Kohinoor Builders |  |  |  | 100 |  |  | Work Order Issue | Completed
MCL-0622 | D3 | West | 56 | B&R | MPLAD Funds | MPLAD Funds |  | Development of Public Parks with Installation of Steel Benches & Swings W. No. 56 (Vikas & SBS Nagar, G & D Block SBS Nagar, Housefed Flats) | 10 | 8.9 |  | 11 |  | 111/EED 05/03/2026 | M/s Ram Parkash kakkar |  |  |  | 60 |  |  | Work Order Issue | In Progress
MCL-0623 | D3 | West | 56 | B&R | MPLAD Funds | MPLAD Funds |  | Installation of Swings and Steel (Cast Iron) Benches in F-Block SBS Nagar W. No. 56 | 3 | 2.5203 |  | 15.99 |  | 112/EED 05/03/2026 | M/s Maa Chintpurni Construction |  |  |  | 30 |  |  | Work Order Issue | In Progress
MCL-0624 | D3 | West | 58 | B&R | MPLAD Funds | MPLAD Funds |  | Development of Public Parks with Installation of Swings W. No. 58 (A to D Blocks of Rajguru Nagar and J Block of BRS Nagar, Housing Board, B Block Aggar Nagar) | 10 | 8.9 |  | 11 |  | 113/EED 05/03/2026 | M/s Ram Parkash kakkar |  |  |  | 10 |  |  | Work Order Issue | In Progress
MCL-0625 | D3 | West | 58 | B&R | MPLAD Funds | MPLAD Funds |  | Development of Public Parks with Swings, Foothpath, Canopy, Benches, Boundary Wall W. No. 58 (J Block Park Opp. Lodhi Club) | 10 | 9.288 |  | 7.12 |  | 114/EED 05/03/2026 | M/s Kohinoor Builders |  |  |  | 30 |  |  | Work Order Issue | In Progress
MCL-0626 | D3 | West | 58 | B&R | MPLAD Funds | MPLAD Funds |  | Installation of Cement Benches and Construction of Shed (10' x 8') in Public Places, Gate No. 1 Verka Plant W. No. 58 | 1 | 0.93 |  | 6.66 |  | 14/EED 07/05/2026 | M/s Kohinoor Builders | [6 empty] | Work Order Issue | Not Started
MCL-0627 | D3 | West | 58 | B&R | MPLAD Funds | MPLAD Funds |  | Installation of Swings & Benches in B-Block Aggar Nagar W. No. 58 | 1.5 | 1.4535 |  | 3.1 |  | 115/EED 05/03/2026 | M/s Kohinoor Builders |  |  |  | 100 |  |  | Work Order Issue | Completed
MCL-0628 | D3 | West | 58 | B&R | MPLAD Funds | MPLAD Funds |  | Construction of Badminton Court in B-Block Aggar Nagar, 524 - B W. No. 58 | 4 | 3.71 |  | 7.17 |  | 17/EED 07/05/2026 | M/s Kohinoor Builders |  |  |  | 40 |  |  | Work Order Issue | In Progress
MCL-0629 | D3 | West | 58 | B&R | MPLAD Funds | MPLAD Funds |  | Installation of Cement Benches W. No. 58 | 0.29 | 0.27 |  | 7.77 |  | 13/EED 07/05/2026 | M/s Kohinoor Builders | [6 empty] | Work Order Issue | Not Started
MCL-0630 | D3 | West | 59 | B&R | MPLAD Funds | MPLAD Funds |  | Installation of Swings & Benches in Parks A-Block Aggar Nagar W. No. 59 | 1.5 | 1.4532 |  | 3.12 |  | 116/EED 05/03/2026 | M/s Kohinoor Builders |  |  |  | 100 |  |  | Work Order Issue | Completed
MCL-0631 | D-4 | West | 60 | B&R | MPLAD Funds | MPLAD Funds |  | Repair & Renovation of Kumra Park in Gurdev Nagar w no 60 | 3 | 2.77 |  | 7.77 |  | 16/EED 07/05/2026 | M/s Kohinoor Builders | 2026-06-29 |  |  | 20 |  |  | Work Order Issue | In Progress
MCL-0632 | D1 | West | 62 | B&R | MPLAD Funds | MPLAD Funds |  | (Installation of swings, open gym and jogging tracks, construction of boundary wall, installation of 25 benches.) Develpoment of different public parks in W. no. 62 | 10 | 7.76 |  | 22.41 |  | 158/EED 25/03/2026 | Bharat Nirman Infracon |  |  |  | 10 |  |  | Work Order Issue | In Progress
MCL-0633 | D-1 | West | 63 | B&R | MPLAD Funds | MPLAD Funds |  | Development of public park w.no.63. | 10 | 7.5 |  | 24.93 |  | 159/EED 25/03/2026 | Bharat Nirman Infracon |  |  |  | 10 |  |  | Work Order Issue | In Progress
MCL-0634 | D-1 | West | 64 | B&R | MPLAD Funds | MPLAD Funds |  | Development of different public park W. no. 64.(Providing open Gym and benches.) | 4 | 3 |  | 24.99 |  | 160/EED 25/03/2026 | Bharat Nirman Infracon |  |  |  | 100 |  |  | Work Order Issue | Completed
MCL-0635 | D-1 | West | 64 | B&R | MPLAD Funds | MPLAD Funds |  | Construction of rooms at Adarsh Public school Kapil Park W no 64 | 15 | 14.23 |  | 5.15 |  | 21/EED 07/05/2026 | M/s Kohinoor Builders | [6 empty] | Work Order Issue | Not Started
MCL-0636 | D-1 | West | 65 | B&R | MPLAD Funds | MPLAD Funds |  | Development of different public parks in w.no.65.(P/F mini mast lights and swings, footpath, benches, boundry walls, open gym, w.no. 65) | 10 | 7.65 |  | 23.49 |  | 161/EED 25/03/2026 | Bharat Nirman Infracon |  |  |  | 10 |  |  | Work Order Issue | In Progress
MCL-0637 | D-4 | West | 69 | B&R | MPLAD Funds | MPLAD Funds |  | P& Fixing Benches and Open Gym equipment in parks of Officer colony, Tagore Nagar, Kitchlu Nagar, Malerkotla House, Green Park, Police Line and Rajpura Pind W.No.69 | 10 | 7.52 |  | 24.8 |  | 157/EED 25/03/2026 | M/s Ram Parkash kakkar |  |  |  | 10 |  |  | Work Order Issue | In Progress
MCL-0638 | D-4 | West | 71 | B&R | MPLAD Funds | MPLAD Funds |  | Construction of Rooms at Goverment Collage for Girls Fzr Road Ldh | 25 | 23.18 |  | 7.26 |  | 18/EED 07/05/2026 | M/s Kohinoor Builders | [6 empty] | Work Order Issue | Not Started
MCL-0639 | D-4 | West | 71 | B&R | MPLAD Funds | MPLAD Funds |  | Repair & Renovation of Park in Park Streets Collage Road W no 71 | 1 | 0.944 |  | 5.55 |  | 19/EED 07/05/2026 | M/s Kohinoor Builders |  |  |  | 40 |  |  | Work Order Issue | In Progress
MCL-0640 | D-4 | West | 71 | B&R | MPLAD Funds | MPLAD Funds |  | Repair & Renovation of park on Sangat road Backside Church Yard | 1 | 0.943 |  | 5.66 |  | 20/EED 07/05/2026 | M/s Kohinoor Builders |  |  |  | 40 |  |  | Work Order Issue | In Progress
MCL-0641 | D-4 | West | 73 | B&R | MPLAD Funds | MPLAD Funds |  | Providing Water Tanker in w no 73 of west Constituency Ludhiana | 2 | 1.82 |  | 8.88 |  | 12/EED 07/05/2026 | M/s Kohinoor Builders | [6 empty] | Work Order Issue | Not Started
MCL-0642 | D-4 | West | 73 | B&R | MPLAD Funds | MPLAD Funds |  | P & Fixing Benches and open Gym Equipment in parks of Ashok Nagar,Sham Nagar W.No.73 | 8 | 7.77 |  | 2.89 |  | 156/EED 25/03/2026 | M/s Varinder Singh Govt. Contractor | [6 empty] | Work Order Issue | Not Started
MCL-0643 |  | West |  | B&R | MPLAD Funds |  |  | TOTAL | 173.29 | 153.523 | [12 empty] | Not Started

## Dates (SASCI) V1 (hidden)
Sr. No. | District | Responsible CE | Fund (SASCI/MDF) | Name of Corporation | Name of the Work | Total Length (Km) | Work Order Issued (Yes/No) | Work Start Date | Work Completion Date | Work Started (Yes/No) | Work Completed (Yes/No)
1 | Gurdaspur | Ashwani Chaudhary | SASCI | Batala | Upgradation of Road from MC Batala office to Hansli Bridge Jalandhar road, Dera baba nanak road both sides under flyover, Achli gate to baba Darshan dass Dera, and Murgi Mohalla from railway line to lakha karyana store with RMC M-30 | 3.5 | Yes | 2026-02-12 | 31/03/2026 | Yes | No | TRUE
2 | Gurdaspur | Ashwani Chaudhary | SASCI | Batala | Upgradation of Road with RMC M-30 from SSMS Chowk to Kahnuwan Road and from Delux Pulley road upto aliwal road | 1.82 | Yes | 28/01/2026 | 31/03/2026 | Yes | No | FALSE
3 | Gurdaspur | Ashwani Chaudhary | SASCI | Batala | Upgradation of Road with RMC M-30 from from City road Hansli Bridge to bakarkhana to disposal to bypass | 2.5 | Yes | 26/01/2026 | 31/03/2026 | Yes | No | FALSE
4 | Gurdaspur | Ashwani Chaudhary | SASCI | Batala | Upgradation of Road with RMC M-30 from Kahnuwan Road to Police line new Judicial Court Complex in MC Batala | 2.99 | Yes | 26/01/2026 | 31/03/2026 | Yes | No | FALSE
5 | Kapurthala | Mukesh Kumar Garg | SASCI | Kapurthala | Upgradation of CC and Bituminous roads work in city area in ward no 6, 8, 9,1 0, 11, 13, 17, 18, 19, 22, 24, 25, 29, 32,34, 36, 37, 38, 39,47,48 | 10 | No | - | - | No | No | FALSE
6 | Ludhiana | Ravinder Kumar Garg | SASCI | Ludhiana | Construction of Various Roads in South Constituency Zone-C Ludhiana. | 4 | Yes | 20/02/2026 | 31/03/2026 | Yes | No | FALSE
7 | Ludhiana | Ravinder Kumar Garg | SASCI | Ludhiana | Upgradation of RMC Roads in various wards of Central Constituency. | 10.68 | Yes | 2026-03-03 | 31/03/2026 | Yes | No | TRUE
8 | Ludhiana | Ravinder Kumar Garg | SASCI | Ludhiana | Upgradation of Elevated Road from Jagraon Bridge to Chand Cinema by laying Mastic Asphalt. | 4.88 | Yes | 23/02/2026 | 31/03/2026 | Yes | No | FALSE
9 | Ludhiana | Ravinder Kumar Garg | SASCI | Ludhiana | Upgradation of various Roads with RMC in Ward No.1, Ludhiana | 7.25 | Yes | 22/02/2026 | 31/03/2026 | Yes | No | FALSE
10 | Ludhiana | Ravinder Kumar Garg | SASCI | Ludhiana | Upgradation of Main Metro Road from Jamalpur Chowk to Kangaroo Industry, Jaswant Singh Dental College to Delhi road via Sethi Sweets, Internal Roads of Sec-39,Road from Primary Govt School to NRI Police Station in Sec-39, Main Jain Colony road from Rahon Road to Swastik Enclave and Main Road of Guru Arjun Dev Nagar from GT Road upto Greenland School, Sabji Mandi Road from Chd road to Puda road, EWS colony main road from Jacha Bacha Hospital upto Tajpur road. | 13.52 | Yes | 20/02/2026 | 31/03/2026 | Yes | No | FALSE
11 | Ludhiana | Ravinder Kumar Garg | SASCI | Ludhiana | Upgradation of Roads with RMC in Area Bharti Colony, Akash Nagar adjoining Jalandhar Byepass, Ludhiana | 7.46 | Yes | 20/02/2026 | 31/03/2026 | Yes | No | FALSE
12 | Ludhiana | Ravinder Kumar Garg | SASCI | Ludhiana | Upgradation of Various Main Roads with RMC in North Constituency Zone-A Ludhiana. | 7.01 | Yes | 23/02/2026 | 31/03/2026 | Yes | No
13 | Ludhiana | Ravinder Kumar Garg | SASCI | Ludhiana | Upgradation of various Roads with RMC in Ward No.95, Ludhiana | 7.44 | Yes | 20/02/2026 | 31/03/2026 | Yes | No
14 | Ludhiana | Ravinder Kumar Garg | SASCI | Ludhiana | Upgradation of Gurudwara road urban estate phase 1&2 from Metro road to Jeewan Nagar chowk, Road along budha nallah from NHAI to MC limit ,Main Bhadur Ke Road from Sabji Mandi upto MC Limit, Main New Azad Nagar 30' Road from Kainth Property Dealer upto Gaur Property Dealer and Roads of Onkar Vihar. | 7.46 | Yes | 18/02/2026 | 31/03/2026 | Yes | No
15 | Ludhiana | Ravinder Kumar Garg | SASCI | Ludhiana | Upgradation and development of various roads in different ward of West Constituency | 22.64 | Tender Reinvited | - | -
16 | Ludhiana | Ravinder Kumar Garg | SASCI | Ludhiana | Upgradation of road from shamshan ghat pully and malhi pully backside New Deep nagar ward no. 91 | 0.4 | Yes | 18/02/2026 | 15/05/2026 | Yes | No
17 | Ludhiana | Ravinder Kumar Garg | SASCI | Ludhiana | Construction of Various Roads in Industrial Area C & Focal Point in South Constituency Zone-C Ludhiana. | 3.35 | Yes | 18/02/2026 | 31/03/2026 | Yes | No
18 | Ludhiana | Ravinder Kumar Garg | SASCI | Ludhiana | Upgradation of various road of Atam Nagar Constituency Zone C. (RMC) | 1.82 | Yes | 20/02/2026 | 31/03/2026 | Yes | No
19 | Ludhiana | Ravinder Kumar Garg | SASCI | Ludhiana | Upgradation of Roads with RMC in Area Guru Har Rai Nagar, Nagesh Hosiery Road adjoining Jalandhar Byepass, Ludhiana | 3.68 | Yes | 2026-11-03 | 30/04/2026 | Yes | No
20 | Ludhiana | Ravinder Kumar Garg | SASCI | Ludhiana | Upgradation of various roads in different wards with RMC & Bitumen in sub zone D1 North Constituency. | 9.11 | Yes | 2026-10-03 | 31/05/2026 | Yes | No
21 | Ludhiana | Ravinder Kumar Garg | SASCI | Ludhiana | Upgradation of various road of Atam Nagar Constituency Zone C. (Bituminous) | 3 | Yes | 2026-05-03 | 31/05/2026 | Yes | No
22 | Ludhiana | Ravinder Kumar Garg | SASCI | Ludhiana | Upgradation of Various Bitumen Main Roads in North Constituency Zone-A Ludhiana | 9.7 | Tender Reinvited
23 | Ludhiana | Ravinder Kumar Garg | SASCI | Ludhiana | Laying BM and SDBC on road in Sub Zone D2 Atam Nagar Halka | 3.2 | Tender Reinvited
24 | Ludhiana | Ravinder Kumar Garg | SASCI | Ludhiana | Upgradation of Bituminious Roads in various wards of Central Constituency. | 5.98 | Tender Reinvited
25 | Ludhiana | Ravinder Kumar Garg | SASCI | Ludhiana | Upgradation of Main Bhamian Road from Chandigarh road to upto MC Limit, Main Phirni of Village Mundian Kalan from Chd road to Sunder Nagar 33' Road and from Chd Road to Rasila Nagar Back side Blind School. | 4.9 | Tender Reinvited
26 | Patiala | Rajiv Kumar | SASCI | Patiala
27 | Patiala | Rajiv Kumar | SASCI | Patiala
28 | Patiala | Rajiv Kumar | SASCI | Patiala
29 | Pathankot | Ashwani Chaudhary | SASCI | Pathankot | Upgradation of various roads in M.C. Pathankot | 15 | Yes | 22/01/2026 | 31/03/2026 | Yes
30 | Amritsar | Ashwani Chaudhary | SASCI | Amritsar | Construction of roads and Widening in the area of Centre, South and West Constituency along with the signages, thermoplastic and cat Eyes | 120 | Yes | 2025-10-09 | 31/03/2026
31 | Amritsar | Ashwani Chaudhary | SASCI | Amritsar | Providing and Laying RMC, BM, SDBC and DBM & BC at various streets and roads in North and East Constituency | 50 | Yes | 2025-09-11 | 31/03/2026
32 | Amritsar | Ashwani Chaudhary | SASCI | Amritsar | Upgradation of roads with 80 mm interlocking tiles and p/l of 50 mm thick dbm and 30 mm bc at various roads of west constituency. | 14 | Yes | 24/1/2026 | 31/03/2026
33 | Amritsar | Ashwani Chaudhary | SASCI | Amritsar | Upgradation of streets and widening portion with Rmc and 80mm Interlocking Tiles at Central constituency. | 14 | Yes | 24/01/2026 | 31/03/2026
34 | Amritsar | Ashwani Chaudhary | SASCI | Amritsar | Upgradation of roads interlocking tiles and dbm & bc at various roads and streets of south constituency | 12 | Yes | 24/01/2026 | 31/03/2026
35 | Amritsar | Ashwani Chaudhary | SASCI | Amritsar | Upgradation of roads RMC M-30, Interlocking tiles, BM & SDBC, DBM & BC, widening of different roads and other civil works in different streets/roads of East Constituency | 16 | Yes | 24/01/2026 | 31/03/2026
36 | Amritsar | Ashwani Chaudhary | SASCI | Amritsar | Upgradation of streets and widening portion with Rmc and Interlocking Tiles and Carpeting with BM , SDBC ,DBM and BC of various streets in north constituency. | 15 | Yes | 24/01/2026 | 31/03/2026
37 | Phagwara | Mukesh Kumar Garg | SASCI | Phagwara | Upgradation of Roads with Improved Surface, Parking Facilities, and Pedestrian Infrastructure along with Public Spaces in Phagwara City, Punjab. | 3.27 | NO | - | - | - | -
38 | Phagwara | Mukesh Kumar Garg | SASCI | Phagwara | Upgradation of roads with Bituminous wearing course and road furniture in Phagwara city internal roads | 13.5 | Yes | 22/01/2026 | 22/04/26 | Yes | No
39 | Jalandhar | Mukesh Kumar Garg | SASCI | Jalandhar | Upgradation of City roads with Bitumen in city area in w. no. 10 & 22 Municipal Corporation Jalandhar (Road length 07.00 Km) | 7 | CE/C/141 13.12.2025 | 13/12/2025 | 2026-12-03 | Yes | No
40 | Jalandhar | Mukesh Kumar Garg | SASCI | Jalandhar | Upgradation of Roads with Premix in various Colony in Ward No.18,37,38 Municipal Corporation Jalandhar (Road length 15.00 Km) | 15 | ce/cantt/138 13.12.2025 | 13/12/2025 | 28/03/2026 | Yes | No
41 | Jalandhar | Mukesh Kumar Garg | SASCI | Jalandhar | Upgradation of Street with Cement Concrete Flooring in Ward No. 40 , 51,53,54,57,58,59,60 Municipal Corporation Jalandhar (Road length 17.00 Km) | 17 | Yes 13.02.2026 | 16/02/2026 | 26/03/2026 | Yes | No
42 | Jalandhar | Mukesh Kumar Garg | SASCI | Jalandhar | Upgradation of Bituminous roads work in city Area in ward no .1,2,3,4,81 Municipal Corporation Jalandhar (Road length 12.00 Km) | 12 | ce/north/237 13.12.2025 | 13/12/2025 | 2026-12-03 | Yes | No
43 | Jalandhar | Mukesh Kumar Garg | SASCI | Jalandhar | Upgradation of cc roads work in city Area in Ward no. 1,2,3,4,79,63,83,84,85 | 22 | ce/north/14 27.01.2026 | 27/01/2026 | 27/04/2026 | Yes | No
44 | Jalandhar | Mukesh Kumar Garg | SASCI | Jalandhar | Upgradation of city roads with CC in Ward no. 5, 8, 9,10, 20, 21, 22, 30, 65, 66 & 67 | 4 | CE/C/213 27.01.2026 | 27/01/2026 | 27/04/2026 | Yes | No
45 | Jalandhar | Mukesh Kumar Garg | SASCI | Jalandhar | Upgradation of Streets with Cement Concrete Flooring in Ward No.15, 34, 37, 38, 60, 61, 62, 53, 83 | 18 | yes 13.02.2026 | 13/02/2026 | 13/05/2026 | Yes | No
46 | Jalandhar | Mukesh Kumar Garg | SASCI | Jalandhar | Upgradation of Roads with Premix in Ward No. 15, 16, 17, 32, 33, 34, 35, 36 | 13 | ce/cantt/150 27.01.2026 | 27/01/2026 | 27/04/2026 | Yes | No
47 | Jalandhar | Mukesh Kumar Garg | SASCI | Jalandhar | Upgradation of Streets with Cement Concrete Flooring in Ward No. 51,57,40,60 and Gen in West and Kartarpur Constituency. | 17 | ce/west/314 27.01.2026 | 27/01/2026 | 27/04/2026 | Yes | No
48 | Fazilka | Naresh Batta | SASCI | Abohar | UPGRADATION OF NEW ROADS OF CITY ROADS AND BUCHRI COMPLEX AT ABHOAR | 4 | Yes | 2026-09-01 | 31/03/2026 | Yes | No
49 | Bathinda | Rajinder Rai | SASCI | Bathinda | Upgradation of Various Roads in Bathinda | 27.25 | Yes | 2026-10-02 | 31/03/2026 | Yes | No
50 | Bathinda | Rajinder Rai | SASCI | Bathinda | Upgradation of streets & Roads of Bathinda City Zone 7 and 1 (Part-I) (including WBM, PC 20mm thick) | 24.14 | Yes | 2026-03-02 | 2026-02-05 | Yes | No
51 | Bathinda | Rajinder Rai | SASCI | Bathinda | Upgradation of streets & Roads of Bathinda City Zone 7 and 1 (Part-II) (including Interlocking Tiles, BC 30mm thick and PC 20mm thick) | 15.75 | Yes | 2026-03-02 | 2026-02-05 | Yes | No
52 | Bathinda | Rajinder Rai | SASCI | Bathinda | Upgradation of streets & Roads of Bathinda City Zone No. 2 | 12.81 | Yes | 2026-10-02 | 31/03/2026 | Yes | No
53 | Bathinda | Rajinder Rai | SASCI | Bathinda | Upgradation of streets & Roads of Bathinda City Zone No. 6 | 22.38 | Yes | 2026-10-02 | 31/03/2026 | Yes | No
54 | Bathinda | Rajinder Rai | SASCI | Bathinda | Upgradation of streets & Roads of Bathinda City Zone No. 4, 8 | 33.64 | Yes | 2026-06-02 | 31/03/2026 | Yes | No
55 | Bathinda | Rajinder Rai | SASCI | Bathinda | Upgradation of streets & Roads of Bathinda City Zone No. 3 and 5 | 31.71 | Yes | 2026-10-02 | 31/03/2026 | Yes | No
56 | Moga | Naresh Batta | SASCI | Moga | Upgradation of roads with WBM Laying BM and 20 m thick open graded PC on various roads in Moga City | 24.69 | Yes | 26/02/2026 | 31/03/2026 | Yes | No
57 | SAS Nagar | Naresh Batta | SASCI | SAS Nagar | Upgradation of various roads in M.C. Mohali | 18.09 | Yes | 23/02/2026 | 31/03/2026 | Yes | No
58 | Barnala | Rajinder Rai | SASCI | Barnala | Providing laying of BC in area Dhanaula road ward No. 21,22,23 Barnala | 2.04 | Tender recalled date 23.03.2026
59 | Barnala | Rajinder Rai | SASCI | Barnala | Providing laying of BC and road gully chamber in area Sekha (Sekha phatak to Sekha Kanchian) road streets ward no. 18, 19, 20 Barnala | 1.07 | Tender recalled date 23.03.2026
60 | Barnala | Rajinder Rai | SASCI | Barnala | Const. of metal road khudi road to budda ke dalip wali road ward no. 24 | 1.71 | Tender recalled date 23.03.2026
61 | Barnala | Rajinder Rai | SASCI | Barnala | Const. of metal (Widening) road thikriwala chowk to sandhu patti Barnala | 0.88 | Tender recalled date 23.03.2026
62 | Barnala | Rajinder Rai | SASCI | Barnala | Const. of metal road Bhagat singh chowk to Nehru Chowk, Sadar Bazar Barnala | 0.55 | Tender recalled date 23.03.2026
63 | Barnala | Rajinder Rai | SASCI | Barnala | Const. of metal road Sanghera to Sandhu patti (Internal Sanghera road in MC Limit) | 0.62 | Tender recalled date 23.03.2026
64 | Barnala | Rajinder Rai | SASCI | Barnala | Const. of metal road road Vadda Gurdwara to Bala Patti Dharmshala Sanghera | 0.5 | Tender recalled date 23.03.2026
65 | Barnala | Rajinder Rai | SASCI | Barnala | Const. of metal road road Raikot road to Bahrli haweli Dhamshala Sanghera (Main Gurdwara Gali) | 0.18 | Tender recalled date 23.03.2026
66 | Barnala | Rajinder Rai | SASCI | Barnala | Const. of metal road BDPO office to Nanaksar Gurdwara sahib Barnala | 0.47 | Tender recalled date 23.03.2026
67 | Barnala | Rajinder Rai | SASCI | Barnala | Const. of metal road Ekta colony khudi road Barnala | 1.22 | Tender recalled date 23.03.2026
68 | Barnala | Rajinder Rai | SASCI | Barnala | Const. of metal road Grain market road RK Book depot to Bajakhana road | 1.37 | Tender recalled date 23.03.2026
69 | Barnala | Rajinder Rai | SASCI | Barnala | Const. of metalroad SD college to Alal Market (KC Road) Barnala | 1.52 | Tender recalled date 23.03.2026
70 | Barnala | Rajinder Rai | SASCI | Barnala | Const. of metal road Pakka college road Fly over to Railway station to Old cinema Barnala | 1.54 | Tender recalled date 23.03.2026
71 | Barnala | Rajinder Rai | SASCI | Barnala | Const. of metal road near trident factory branch streets Barnala | 0.12 | Tender recalled date 23.03.2026
72 | Barnala | Rajinder Rai | SASCI | Barnala | Const. of metal road Baba Aala Singh School Patti road Barnala | 0.15 | Tender recalled date 23.03.2026
73 | Barnala | Rajinder Rai | SASCI | Barnala | Const. of metal road Guru Ram Dass Nagar Dhanaula road Barnala | 0.95 | Tender recalled date 23.03.2026
74 | Barnala | Rajinder Rai | SASCI | Barnala | Const. of metal road Grid road to Gulab de ghar tak Barnala | 1 | Tender recalled date 23.03.2026
75 | Barnala | Rajinder Rai | SASCI | Barnala | Const. of metal road Dhanaula road to Sanghera road (Prem Nagar) Barnala | 0.46 | Tender recalled date 23.03.2026
76 | Barnala | Rajinder Rai | SASCI | Barnala | Const. of metal road 22 acre patti road to Verka booth Barnala | 0.33 | Tender recalled date 23.03.2026
77 | Barnala | Rajinder Rai | SASCI | Barnala | Const. of metal road Lakhy colony to Gill Nagar & Kinu wala bagh to court road & Sub streets Barnala | 2.32 | Tender recalled date 23.03.2026
78 | Barnala | Rajinder Rai | SASCI | Barnala | Const. of metal road Sardar Handloom to patti road (Baba Aala Singh Nagar) Barnala | 0.36 | Tender recalled date 23.03.2026

## Dates (MDF) V1 (hidden)
Sr. No. | District | Responsible CE | Fund (SASCI/MDF) | Name of Corporation | Name of the Work | Total Length (Km) | Work Order Issued (Yes/No) | Start Date | End Date | Work Started (Yes/No) | Work Completed (Yes/No) | Remarks (if any)
1 | Kapurthala | Mukesh Kumar Garg | MDF | Kapurthala | P/L of BM & PC from DC Chownk to Sainik School, Sainik School to Shiv Mandir & other streets of MC Kapurthala | 3.13 | Yes | - | - | - | - | Work of laying of Sewerage lines under AMRUT scheme is going on.
2 | Kapurthala | Mukesh Kumar Garg | MDF | Kapurthala | Coonstruction of metalled road from Kotu Chownk to dandupur road | 1.92 | Yes | - | - | - | - | -do-
3 | Kapurthala | Mukesh Kumar Garg | MDF | Kapurthala | Shalimarbagh's inner road | 1.58 | Yes | - | - | - | - | -do-
4 | Kapurthala | Mukesh Kumar Garg | MDF | Kapurthala | Adarsh Nagar main road | 0.75 | Yes | - | - | - | - | -do-
5 | Fazilka | Naresh Batta | MDF | Abohar | Recarpating of city Roads at Abohar | 4.4 | Yes | 09.01.2026 | 08.07.2026 | Yes | No
6 | Fazilka | Naresh Batta | MDF | Abohar | Construction of different streets | 4.5 | Yes | 13.11.2025 | 12.05.2026 | Yes | No
7 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | CONSTRUCTION OF METALLED ROAD IN DIFFERENT STREETS OF WARD NO. 1, HOSHIARPUR (Main Street Shiwalik Enclave, Amit Marwaha Wali, Harbans Lal Wali, Krishan Wali ) | 0.59 | Yes | 25..02.2026 | 31.03.2026 | Yes | No
8 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | CONSTRUCTION OF METALLED ROAD OF SWARG ASHRAM ROAD AND ADJOIN AREA, HOSHIARPUR ( Swarg Ashram Road And Adj Area) | 0.766 | Yes | 25..02.2026 | 31.03.2026 | Yes | No
9 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | Construction of Metalled Road in Different streets of Mohalla Amrit Nagar, Adamwal Road Near Sai Baba Mandir Hoshiarpur. ( H/o Rajinder Rattan Wali, Sagar Niwas Wali , Sodhi Niwas Wali Adj Kali Mata Mandir, H/o Satish Wali Infron Shiv Mandir wali) | 0.72 | Yes | 25..02.2026 | 31.03.2026 | Yes | No
10 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR AND RESURFACING OF METALLED ROAD GREEN NURSING WALI BIRBAL NAGAR HOSHIARPUR. (Green Nursary Wali) | 0.495 | Yes | 25..02.2026 | 31.03.2026 | Yes | No
11 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR AND RESURFACING OF METALLED ROAD POST OFFICE & PWD WALI HOSHIARPUR (Post Office & PWD wali) | 0.67 | Yes | 25..02.2026 | 31.03.2026 | Yes | No
12 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | Repair and Resurfacing of Road from Shiv Ji Chowk to Church Hoshiarpur (Shiv Ji Chowk to Church ) | 0.26 | Yes | 25..02.2026 | 15.05.2026 | Yes | No
13 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | Construction of Metalled Road and Repair/Resurfacing in different Streerts of Bullanwari, Hoshiarpur (HP Gas Agency Wali H/o Rakesh Vohra Adj Street 1 and 2, Dogra Niwas to Main Road, H/o Neeraj Sharma Wali Street in front H/o Nirmal singh H/o Jarnail Singh wali) | 0.64 | Yes | 25..02.2026 | 31.03.2026 | Yes | No
14 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR AND RESURFACING OF DIFFERENT STREETS OF MOHALLA AJIT NAGAR AND SHANTI NAGAR, HOSHIARPUR (H/o Kirpal Singh Street Dhiman Wali Guru Kirpa Nagar, Gobind Nagar, Street Jeet Ram Master Wali, Street Kaka Dairy Wali Street Mohinder Singh Kant Wali, Street Gurdayal Singh Wali) | 0.825 | Yes | 25..02.2026 | 31.03.2026 | Yes | No
15 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR AND RESURFACING OF DIFFERENT ROADS OF MOHALLA ASLAMABAD HOSHIARPUR. (Balasa Ram Park to Kamal, Water Tank Wali Adj wali) | 0.576 | Yes | 25..02.2026 | 31.03.2026 | Yes | No
16 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR AND RESURFACING OF DIFFERENT STREETSOFWARD NO 9 , HOSHIARPUR ( Bibi Puro wali, Surjit Wali, Bibi Jagiro Wali, Gujjran wali, Naranjan Ashram Wali, Karyana Store Wali) | 0.77 | Yes | 25..02.2026 | 31.03.2026 | Yes | No
17 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR AND RESURFACING OF DIFFERENT STREETS OF WARD NO 8 AND 9 , HOSHIARPUR (street Kala Taal Wali, Rinku Wali, Joginder DJ Wali, Street in Front Chowdhary Blasa Ram Park, Ex MC Sidhu Wali, SHO KK Bali Wali) | 0.792 | Yes | 25..02.2026 | 31.03.2026 | Yes | No
18 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | Repair/Resurfacing of Metalled Road at Main Road of Mohalla Gurdit Nagar, Hoshiarpur (Main Road Mohall Gurdit Nagar) | 0.685 | Yes | 25..02.2026 | 31.03.2026 | Yes | No
19 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR AND RESURFACING OF METALLED ROAD IN DIFFERENT STREETS OF SHIVALIK ENCLAVE & AKASH NAGAR HOSHIARPUR. (Street Manak Niwas Wali, Street H/o Pathak Wali near MC T/well Akash Nagar) | 0.45 | Yes | 25..02.2026 | 31.03.2026 | Yes | No
20 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR / RESURFACING OF METALLED ROAD IN DIFFERENT STREETS OF SHIVALIK ENCLAVE, WARD NO.10, HOSHIARPUR ( Street H/o Bitu Wali, Street in front H/o Dess Raj, Street Adj Chechi Medical store, Street in front Soni Park, Anmol Villa to Rattan Niwas) | 0.815 | Yes | 25..02.2026 | 31.03.2026 | Yes | No
21 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | CONSTRUCTION OF METALLED ROAD IN DIFFERENT STREETS OF SCHEME NO. 10 (Street Scheme No 10) | 0.658 | Yes | 25..02.2026 | 31.03.2026 | Yes | No
22 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR AND RESURFACING OF METALLED ROAD IN DIFFERENT STREETS MOHALLA GURU NANAK NAGAR & BASANT VIHAR HOSHIARPUR. ( Subhash Cont Wali, HP Petrol Pump wali, h/o Rashpal New Civil Line Eng Sanjeev Wali, Palli wali Dr Sagar Wali Gali No 1Guru Nanak Nagar) | 0.55 | Yes | 25..02.2026 | 31.03.2026 | Yes | No
23 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | CONSTRUCTION AND REPAIR / RESURFACING OF METALLED ROAD IN DIFFERENT STREETS OF WARD NO. 12 HOSHIARPUR ( Street Pyar Chand Wali, Street No. 3 Sethi Dairy Wali, street No. 4 Ravidass Nagar, Street Bhatoya Niwas Wali) | 0.445 | Yes | 25..02.2026 | 31.03.2026 | Yes
24 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | Repair and Resurfacing of Road From Gaushala Bazar to Khanpuri Gate, Hoshiarpur (Gaushala Bazar to Khanpuri Gate) | 0.32 | Yes | 25..02.2026 | 15.05.2026 | Yes
25 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR AND RESURFACING OF METALLED LINK ROAD MOHALLA RAVIDAS NAGAR WARD 12,16, HOSHIARPUR (Gujjran Di Dairy to Dr Goldy, Mandir Wali, Sukha Baba Wali, Jujhhar Singh Wali, Beaso Wali, Atta chakki Wali) | 1.235 | Yes | 25..02.2026 | 31.03.2026 | Yes
26 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | Repair and Resurfacing of Road Main Fatehgarh Road upto Drug Rehabilitation Centre, Hoshiarpur (Main Fatehgarh Road upto Drug Rehabilitation Centre,) | 1.266 | Yes | 25..02.2026 | 15.05.2026 | Yes
27 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR AND RESURFACING OF METALLED ROAD FROM DESH BHAGAT ITI TO BEGAMPURA HOSHIARPUR. (Desh Bhagat ITI to Begampura ) | 0.335 | Yes | 25..02.2026 | 31.03.2026 | Yes
28 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | CONSTRUCTION OF METALLED ROAD IN DIFFERENT STREETS OF WARD NO. 17 HOSHIARPUR ( Strret in Front H/o Darra, Street Old MC T/well Wali) | 0.365 | Yes | 25..02.2026 | 31.03.2026 | Yes
29 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR / RESURFACING OF OLD ROAD AND NEW CONSTRUCTION OF METALLED ROAD IN DIFFERENT STREETS OFWARDNO.16, HOSHIARPUR ( Street B/s dhillo niwas, adj saini Tailor, Street Badwal Niwas Wali, Street Harpreet Singh Wali Opp Prince Auto Service Sanya Medical Store, Sahota Niwas Wali, H/o MC Wali) | 1.03 | Yes | 25..02.2026 | 31.03.2026 | Yes
30 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR AND RESURFACING OF BANNE SHAH ROAD, HOSHIARPUR ( Banne Shah Road) | 1.2 | Yes | 25..02.2026 | 31.03.2026 | Yes
31 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | Construction of Metalled Road of Different Streets of Mohalla Gugga Peer, Hoshiarpur (Kalsi Niwas Wali H/o Sohan Singh wali, Street Mahant Wali, Street Ram Singh Wali, Street Tirath Dairy Wali) | 0.9 | Yes | 25..02.2026 | 31.03.2026 | Yes
32 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR / RESURFACING OF OLD ROAD IN DIFFERENT STREET OF WARD NO. 45, HOSHIARPUR. (West Enclave) | 0.685 | Yes | 25..02.2026 | 31.03.2026 | Yes
33 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | CONSTRUCTION OF METALLED ROAD IN DIFFERENT STREET OFWARD NO. 48, HOSHIARPUR. (Street Mandir Wali, T/well Wali) | 0.591 | Yes | 25..02.2026 | 31.03.2026 | Yes
34 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR AND RESURFACING OF MAIN TAGORE NAGAR ROAD HOSHIARPUR. (Main Tagore Nagar Road) | 0.88 | Yes | 25..02.2026 | 31.03.2026 | Yes
35 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR AND RESURFACING OF METALLED ROAD OF DIFFERENT STREET JAIMAL SINGH NAGAR,W.NO.48 HOSHIARPUR ( Jaimal Singh Nagar) | 0.213 | Yes | 25..02.2026 | 31.03.2026 | Yes
36 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR / RESURFACING OF METALLED ROAD ARJUN NAGAR SONU WALI GALI,HOSHIARPUR ( Sonu Wali Arjan Nagar) | 0.301 | Yes | 25..02.2026 | 31.03.2026 | Yes
37 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | Repair and Resurfacing of Link Road From Hariana Road to Main Road near BSNL Exchange via Shivpuri, Hoshiarpur ( Hariana Road to Main Road near BSNL Exchange via Shivpuri) | 0.76 | Yes | 25..02.2026 | 15.05.2026 | Yes
38 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | CONSTRUCTION OF METALLED ROAD IN DIFFERENT STREETS OF WARD NO. 20 HOSHIARPUR ( Street Glamlox wali, Street Rajput street wali) | 0.205 | Yes | 25..02.2026 | 31.03.2026 | Yes
39 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | CONSTRUCTION OF METALLED ROAD IN DIFFERENT STREETS NEAR H/O GANESH CHAND PAPPU, PURHIRAN HOSHIARPUR ( Street Near H/o Ganesh Chand Pappu, Honey Wali, Jasveer Wali) | 0.365 | Yes | 25..02.2026 | 31.03.2026 | Yes
40 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | CONSTRUCTION OF METALLED ROAD IN DIFFERENT STREETS OF WARD NO. 22 HOSHIARPUR ( Street Bank Manager Paramjit Singh Wali, Street H/o Beant Swaran Singh Capt Harmel singh Wali) | 0.554 | Yes | 25..02.2026 | 31.03.2026 | Yes
41 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR / RESURFACING OF METALLED ROAD IN DIFFERENT STREETS OF , WARD NO. 23 HOSHIARPUR (Master Parminder Wali, Saini Cottage Wali, Adj Street No. 1 and 2, Bassan Niwas Wali, H/o Varinder Kumar Adia Wali Street Tirath Ram Wali, Street No. 9, H/o Bakhshish Singh Wali, Street No. 2 Tibba Sahib) | 0.7 | Yes | 25..02.2026 | 31.03.2026 | Yes
42 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR AND RESURFACING OF METALLED ROAD FROM FOOTBALL GROUND DAGANA ROAD VIA SAINI KARYANA STORE HOSHIARPUR. (Football Ground Dagana Road Via Saini Karyana Store) | 0.48 | Yes | 25..02.2026 | 31.03.2026 | Yes
43 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR / RESURFACING OF METALLED ROAD IN DIFFERENT STREETS OF , WARD NO. 24 HOSHIARPUR ( Street No 3 and 3 A Dashmesh Nagar, Street PSPCL Wali, Street No. 12 C, Adj Street No. 1 to 3, Street Go Fast Visa wali) | 0.715 | Yes | 25..02.2026 | 31.03.2026 | Yes
44 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR AND RESURFACING OF METALLED ROAD OF GOAL KOTHI ROAD DASHMESH NAGAR, HOSHIARPUR ( Gol Kothi Road Dashmesh Nagar) | 0.64 | Yes | 25..02.2026 | 31.03.2026 | Yes
45 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR AND RESURFACING OF METALLED ROAD IN DIFFERENT STREETS OF MOHALLA DASHMESH NAGAR HOSHIARPUR. (Street No 5 /1 Dashmesh Nagar street H/o Sidhu Wali, Govt School Wali, H/o Balwinder Singh, H/o Ranjit Singh) | 0.495 | Yes | 25..02.2026 | 31.03.2026 | Yes
46 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR & SURFACING OF METALLED ROAD OPP. GURUDWARA SHAHIDAN DAGANA ROAD HOSHIARPUR. ( Opp Gurudwara Shahidan Dagana Road) | 0.43 | Yes | 25..02.2026 | 31.03.2026 | Yes
47 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR AND RESURFACING OF METALLED ROAD IN DIFFERENT STREET OF WARD NO. 26, HOSHIARPUR. ( Street No. 1, Gurudwara Wali Gokal Nagar) | 0.59 | Yes | 25..02.2026 | 31.03.2026 | Yes
48 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR & RESURFACING OF OLD ROAD AND NEW CONST OF METTALED ROAD IN DIFFERENT STREETS OF WARD NO.27, HOSHIARPUR ( Street No 1 New Deep Nagar, GGS Nagar Street No 1 near MC ) | 0.416 | Yes | 25..02.2026 | 31.03.2026 | Yes
49 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR AND RESURFACING OF MAIN ROAD AT MOHALLA MOUNT AVENUE, HOSHIARPUR ( Main Road Mohalla Mount Avenue) | 0.83 | Yes | 25..02.2026 | 31.03.2026 | Yes
50 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR / RESURFACING OF OLD ROAD AND NEW CONSTRUCTION OF METALLED ROAD IN DIFFERENT STREET OF WARD NO.29, HOSHIARPUR. ( Side Street No. 3 Ranjit Nagar, Nakha Wala Bag, Vikram Enclave Side Street MC Wali Royal Enclave Side Street Kehad Wali) | 0.946 | Yes | 25..02.2026 | 31.03.2026 | Yes
51 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR / RESURFACING OF OLD ROAD IN DIFFERENT STREET OF WARD NO. 30, HOSHIARPUR. (Near H/o Janak Raj Lakshmi Enclave) | 0.27 | Yes | 25..02.2026 | 31.03.2026 | Yes
52 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | CONSTRUCTION OF METALLED ROAD IN STREET NEW COLONY TO ADHARMI MOHALLA BAHADURPUR HOSHIARPUR ( New Colony to Adharmi Mohalla Bahadurpur) | 0.27 | Yes | 25..02.2026 | 31.03.2026 | Yes
53 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR AND RESURFACING OF METALLED ROAD OF DIFFERENT STREET WARD NO. 31, HOSHIARPUR ( Street Giani Wali Central Town, Subedar wali) | 0.232 | Yes | 25..02.2026 | 31.03.2026 | Yes
54 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR AND RECONSTRUCTION OF ROAD LEADING TO SANTOKH NAGAR FROM MAIN PHAGWARA ROAD HOSHIARPUR. (Santokh Nagar from Main Phagwara Road) | 0.8 | Yes | 25..02.2026 | 31.03.2026 | Yes
55 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR / RESURFACING OF METALLED ROAD IN DIFFERENT STREETS OF WARD NO. 11, HOSHIARPUR ( Street No. 4, New Civil Line Adj Park to Street No .2, Street No. 1 C, Basan Vihar Main Road, H/o Santokh Wali, Guru Nanak Aveneu) | 0.924 | Yes | 25.06.2025 | 26.09.2025 | Yes | Yes
56 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | CONSTRUCTION AND REPAIR / RESURFACING OF METALLED ROAD IN DIFFERENT STREETS OF WARDNO.14, HOSHIARPUR ( Street H/o Santokh Kaur Wali, Bala Ji Niwas Wali Ad Street No 1, 2, Street H/o Rajesh Kumar Wali, Adj Street Chetan Wali, Pt Shashi Kant Wali) | 0.49 | Yes | 25..02.2026 | 31.03.2026 | Yes
57 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR / RESURFACING OF METALLED ROAD IN DIFFERENT STREETS OF WARD NO. 19, HOSHIARPUR ( Street H/o Sewa Singh to H/o Pawan and Narinder Singh, Govt School Wali, Bachan Singh Bains Wali, H/o Poonam Wali, Infront of Basket Ball Ground wali) | 0.65 | Yes | 25..02.2026 | 31.03.2026 | Yes
58 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | RECONST OF METTALED LINK ROAD FROM MAHARANA PARTAP BHAWAN TO BULLANWARI HOSHIARPUR ( Maharana Partap Bhawan to Bulanwari) | 0.685 | Yes | 26.06.2025 | 30.09.2025 | Yes | Yes
59 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | CONST OF METTALED ROAD IN DIFFERENT STREETS OF WARD NO. 21, HOSHIARPUR (Street Bal Niwas Wali, Street Dhami Niwas Adj Bharaj Street H/o Charanjit Lal Mann Singh Khalsa Niwas Wali Jhahar Niwas Wali) | 0.77 | Yes | 10.06.2025 | 06.10.2025 | Yes | Yes
60 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR/ RESURFACING OF METTALED ROAD IN MOHALLA PARGATI LANE WARD NO. 49, HOSHIARPUR ( Pargati Lane) | 0.29 | Yes | 25..02.2026 | 31.03.2026 | Yes
61 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | CONSTRUCTION OF METALLED ROAD IN DIFFERENT STREETS ADJOINING GURUDWARA ZAHRA HAZOOR, PURHIRAN HOSHIARPUR (Street Adj Zahra Hazoor Purhiran) | 0.683 | Yes | 16.06.2025 | 31.03.2026 | Yes | No
62 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR & RESURFACING OF METAL ROAD HOUSE OF EX MC BALJIT SINGH WALI GALI, SURYA ENCLAVE HOSHIARPUR. (H/o Ex MC Baljit Singh Wali gali Surya Enclave) | 0.14 | Yes | 25..02.2026 | 31.03.2026 | Yes
63 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | CONSTRUCTION OF METALLED ROAD IN DIFFERENT STREETS B/S SATGURU ELECTRICAL, OLD TANDA ROAD, HOSHIARPUR (B/s Satgutu Electrical wali) | 0.199 | Yes | 25..02.2026 | 31.03.2026 | Yes
64 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/LAYING SDBC IN STREET ASI ROSHAN LAL WALI GURDIT NAGAR ST -18, HOSHIARPUR (Street ASI Roshan Lal Wali Street No 18) | 0.175 | Yes | 20.06.2025 | 31.03.2026 | Yes | No
65 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR / RESURFACING OF METALLED ROAD IN DIFFERENT STREETS OF SIKH LINE (BLOCK-A),HOSHIARPUR ( Sikh Line Block A H/o Krishan Singh Dadwal, H/o Ranvir singh Wali, H/o Harjinder Sodhi Wali) | 0.561 | Yes | 21.06.2025 | 31.03.2026 | Yes | No
66 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR AND RESURFACING OF METALLED ROAD IN STREET RAJINDER SINGH TO PARAMJIT SINGH NEW FATEHGARH WARD 14,15, HOSHIARPUR ( Street Rajinder Singh to Paramjit Singh, New Fatehgarh) | 0.34 | Yes | 25..02.2026 | 31.03.2026 | Yes
67 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR AND RESURFACING OF METALLED ROAD IN STREET BHARAJ HOSPITAL (DR. RASHPAL) WALI, HOSHIARPUR (street Bharaj Wali) | 0.235 | Yes | 21.06.2025 | 31.03.2026 | Yes | No
68 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | ESTIMATE FOR RESURFACING OF ROAD FROM JALANDHAR ROAD TO NIARA ROAD AND DAGANA ROAD, HOSHIARPUR ( Jallandhar Road to Niara Road Adj Dagana Road) | 1.7 | Yes | 19.06.2025 | 31.03.2026 | Yes | No
69 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR AND RESURFACING OF CANAL COLONY ROAD UPTO MC LIMIT, HOSHIARPUR ( Canal Colony road upto MC Limit) | 1.4 | Yes | 10.11.2025 | 31.03.2026 | Yes | No
70 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | RECONSTRUCTION OF SUKHIYABAD MAIN ROAD, HOSHIARPUR ( Sukhiabad Main Road) | 0.5 | Yes | 18.06.2025 | 31.03.2026 | Yes | No
71 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR AND RESURFACING OF METALLED ROAD FROM MAIN GATE PURHIRAN TO GURU DWARA SAHIB ZAHRA HAZOOR, HOSHIARPUR ( Mani Gate Purhiran to Gurudwara Sahib Zahra Hazoor) | 1.35 | Yes | 25..02.2026 | 31.03.2026 | Yes
72 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | CONSTRUCTION OF METTALED ROAD IN DIFFERENT STREETS OF NEW GOBIND NAGAR WARD NO. 50, HOSHIARPUR ( New Gobind Nagar) | 1.5 | Yes | 16.06.205 | 31.03.2026 | Yes | No
73 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR AND RESURFACING OF METALLED ROAD POLICE LINE WALI HOSHIARPUR (Police Line Wali) | 0.79 | Yes | 25.01.2026 | 31.03.2026 | Yes | No
74 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | CONSTRUCTION OF METALLED ROAD IS STREET ADJOINING GURUDWARA RAVIDASS JI, MOHALLA BHIM NAGAR HOSHIARPUR. (Street Adj Gurudwara Ravidass ji ) | 0.09 | Yes | 11.07.2025 | 06.10.2025 | Yes | Yes
75 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR AND RESURFACING OF METALLED ROAD FROM SHANI DEV MANDIR TO ALLMARIYAN WALA CHOWK HOSHIARPUR (SHani Dev Mandir to Almarian Wala Chowk) | 0.47 | Yes | 25..02.2026 | 31.03.2026 | Yes
76 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR AND RESURFACING OF MAIN DC ROAD HOSHIARPUR ( Main DC Road) | 0.515 | Yes | 25..02.2026 | 31.03.2026 | Yes
77 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | RECONSTRUCTION OF RED ROAD HOSHIARPUR. ( Red Road) | 0.9 | Yes | 25..02.2026 | 31.03.2026 | Yes
78 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR AND RESURFACING OF BAL KISHAN ROAD HOSHIARPUR (Bal Kishan Road) | 0.78 | Yes | 25..02.2026 | 31.03.2026 | Yes
79 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR AND RESURFACING OF RAILWAY STATION ROAD HOSHIARPUR. ( Railway Station Road) | 0.28 | Yes | 20.06.2025 | 31.03.2026 | Yes | No
80 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR AND RESURFACING SHIMLA PAHARI TO JAIL CHOWK HOSHIARPUR. (Shimla Pahadi To Jail Chowk) | 1.03 | Yes | 24.06.2025 | 31.03.2026 | Yes | No
81 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | RECONSTRUCTION OF GAUSHALA ROAD HOSHIARPUR. ( Main Gaushala Road) | 0.57 | Yes | 30.10.2025 | 31.03.2026 | Yes | No
82 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | Construction of Metalled Road and Repair/Resurfacing in different Streerts of Suraj Nagar and Narayan Nagar, Hoshiarpur (Suraj Nagar and Narayan Nagar) | 1.25 | Yes | 10.11.2025 | 31.03.2026 | Yes | No
83 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | Construction of Metalled Road and Repair/Resurfacing in Streert of Agyapal Singh Sahni & Other streets Mohalla Gautam Nagar, Hoshiarpur ( Street No. 6, 1, 2, 3 link street no 1 to 4, Street Agyapal Singh Sahni wali gali no 6) | 0.945 | Yes | 20.10.2025 | 31.03.2026 | Yes | No
84 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | Construction of Metalled Road of Main STP Road, Hoshiarpur ( Main STP Road) | 0.75 | Yes | 25..02.2026 | 31.03.2026 | Yes
85 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/LAYING INTERLOCKING PAVER BLOCKS IN DIFFERENT STREETS OF ,WARD NO. 2 HOSHIARPUR ( Street Jaswant Kala Wali, Street H/o Manjit Kumar Wali, Street Adj Kalyugi Mandir) | 0.255 | Yes | 25..02.2026 | 15.03.2026 | Yes
86 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS IN DIFFERENT STREETS OF WARD NO. 3, HOSHIARPUR (From H/o Sumant, (Saini Sabha) Prasher Sweet Shop wali, Vipan Wali, Punj Piplai Mandir to Almaria Wala Chowk) | 0.631 | Yes | 10.12.2025 | 15.01.2026 | Yes | Yes
87 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/LAYING INTERLOCKING PAVER BLOCKS IN DIFFERENT STREETS OF ,WARD NO. 4 HOSHIARPUR (Channe Wali Street No. 5, Street No. 5 A) | 0.209 | Yes | 25..02.2026 | 15.03.2026 | Yes
88 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS IN DIFFERENT STREETS OF WARD NO. 5, HOSHIARPUR (Kuldeep Wali Street Arya Nagar, C.M Puri to Badyal House, K.S. Sharma Wali Ramesh Nagar, Anmol Wali B/s DAV School, Gupta Meision Wali) | 0.216 | Yes | 25..02.2026 | 15.03.2026 | Yes
89 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/LAYING INTERLOCKING PAVER BLOCKS IN STREET NO.4 AND 8 IN MOHALLA KRISHANA NAGAR,WARD NO.6, HOSHIARPUR ( Street No 4, 8, Mohalla Krishna Nagar) | 0.255 | Yes | 25..02.2026 | 15.03.2026 | Yes
90 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS IN DIFFERENT STREETS OF, WARD NO. 7, HOSHIARPUR (H/o Neeraz to Jyoti, Vinod Wali, Gali No 9 Shalimar Nagar) | 0.19 | Yes | 25..02.2026 | 15.03.2026 | Yes
91 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS IN DIFFERENT STREET OF , WARD NO. 8 HOSHIARPUR (Bilu Karyana Store Wali , Buta Ram Wali, Thandia Wali) | 0.42 | Yes | 18.11.2025 | Completed | Yes | Yes
92 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/LAYING INTERLOCKING PAVER BLOCKS IN DIFFERENT STREETS OF,WARD NO. 12 HOSHIARPUR (Bimla Karyan Store To Sant Ram, Street No. 3, Ravidass Nagar) | 0.14 | Yes | 25..02.2026 | 15.03.2026 | Yes
93 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS IN DIFFERENT STREETS OF WARD NO. 13, HOSHIARPUR (Sadhu Singh Wali, Satinder Wali, Pt Janak Wali, satwinder wali,st -10 ram sharnam wali) | 0.38 | Yes | 25..02.2026 | 15.03.2026 | Yes
94 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS IN DIFFERENT STREETS OF WARD NO. 15, HOSHIARPUR( MC T/well wali, Gali no. 2 Nirmla Devi Wali, Jatinder Karyana Store Wali, Street no 4 to 13 and Adjoin Street No. 1 to 4) | 0.41 | Yes | 28.11.2025 | 15.03.2026 | Yes | No
95 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS IN DIFFERENT STREETS IN WARD NO.17, HOSHIARPUR ( Adjoin Cause Way Bheem Nagar, Lailla Wali, Old MC T/well) | 0.1 | Yes | 25..02.2026 | 15.03.2026 | Yes
96 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/LAYING INTERLOCKING PAVER BLOCKS IN DIFFERENT STREETS OF WARD NO. 18, HOSHIARPUR ( Moh Purhiran) | 0.345 | Yes | 25..02.2026 | 15.03.2026 | Yes
97 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS IN DIFFERENT STREETS OF WARD NO. 20, HOSHIARPUR ( Street H/o Mistri Manjit Singh Wali, Adjoin Street No. 1 and 2) | 0.14 | Yes | 13.11.2025 | 15.03.2026 | Yes | No
98 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS IN DIFFERENT STREETS OF WARD NO. 25, HOSHIARPUR (Front of H/o Balwant Singh Street No. 4 Subhash Nagar, Street No. 5, Labh Nagar adjoi H/o Eng Manjit singh Street No. 5, Tagore Nagar) | 0.37 | Yes | 18.11.2025 | 15.03.2026 | Yes | No
99 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING PAVER BLOCKS IN STREETS MOHAN LAL WALI WARD NO. 27, HOSHIARPUR (Mohan Lal Wali) | 0.06 | Yes | 25..02.2026 | 15.03.2026 | Yes
100 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS IN STREET SETHI & BHRIGU WALI OF WARD NO. 31, HOSHIARPUR. (Street Sethi Wali and Bhrigu Wali) | 0.57 | Yes | 25..02.2026 | 15.03.2026 | Yes
101 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS IN DIFFERENT STREET OF WARD NO. 33, HOSHIARPUR.(Premgarh) | 0.36 | Yes | 25..02.2026 | 15.03.2026 | Yes
102 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS IN DIFFERENT STREET OF WARD NO. 36, HOSHIARPUR. (Street No. A to D) | 0.25 | Yes | 25..02.2026 | 15.03.2026 | Yes
103 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS IN DIFFERENT STREET OF WARD NO. 37, HOSHIARPUR.(Keshav Nagar, Ashok Steel Wali) | 0.26 | Yes | 08.11.2025 | 15.03.2026 | Yes | No
104 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS IN DIFFERENT STREET OF WARD NO.41, HOSHIARPUR. BSNL Exchange Wali, Lab wali, Naseeb Wali) | 0.26 | Yes | 25..02.2026 | 15.03.2026 | Yes
105 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS IN DIFFERENT STREET AT WARD NO. 42, HOSHIARPUR. (Raju Wali, Mandir Wali) | 0.24 | Yes | 15.11.2025 | 15.03.2026 | Yes | No
106 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS IN DIFFERENT STREET OF WARD NO.44, HOSHIARPUR. ( Opp Harbhajan Wood Works) | 0.1 | Yes | 25..02.2026 | 15.03.2026 | Yes
107 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS IN STREET OF H/O JASWANTAT ADJOINNING JAGDISH CHANDER SCRAP WALI OF WARD NO. 45, HOSHIARPUR. (Jaswant Wali, JAgdish Wali) | 0.05 | Yes | 25..02.2026 | 15.03.2026 | Yes
108 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXINGINTERLOCKINGPAVERBLOCKSINDIFFERENT STREET OF WARD NO.47, HOSHIARPUR. (Narinder Singh Wali, Baba Balak Nath Mandir wali, B/s Gurudwara wali) | 0.24 | Yes | 25..02.2026 | 15.03.2026 | Yes
109 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXINGINTERLOCKINGPAVERBLOCKSINDIFFERENT STREETS OF WADR NO. 50, HOSHIARPUR. (Partap Nagar) | 0.38 | Yes | 25..02.2026 | 15.03.2026 | Yes
110 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | PROVIDING AND FIXING INTERLOCKING PAVER BLOCKS IN DIFFERENT STREETS IN MOHALLA SHALIMAR NAGAR,WARD NO. 7, HOSHIARPUR (MDF) (Street H/o Manjit Singh, Street H/o Veen Wali, Shalimar Nagar, Gurudwara Sahib Shalimar Nagar) | 0.25 | Yes | 25..02.2026 | 15.03.2026 | Yes
111 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | PROVIDING AND FIXING INTERLOCKING PAVER BLOCKS IN DIFFERENT STREETS OF WARD NO. 27, HOSHIARPUR (MDF) ( Guru Gobind Singh Nagar Gali No 5, New Deep Nagar Gali No 1, Bhupinder Wali Gali Bo 7, Kirti Nagar) | 0.27 | Yes | 28.01.2026 | 15.03.2026 | Yes | Yes
112 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/LAYING INTERLOCKING PAVER BLOCKS IN STREET NO. 2 H/O LAMBER WALI, ANMOL NAGAR WARD NO. 50 HOSHIARPUR (H/o Lamber Wali) | 0.25 | Yes | 25..02.2026 | 15.03.2026 | Yes
113 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | PROVIDING AND FIXING INTERLOCKING PAVER BLOCKS IN STREET H/O BALJIT SINGH, MOHALLA AJIT NAGAR,WARD NO. 9, HOSHIARPUR (H/o Baljit singh Wali) | 0.06 | Yes | 25..02.2026 | 15.03.2026 | Yes
114 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS IN STREET SURINDER KUMAR WALI RALIWAY MANDI WARDNO.44, HOSHIARPUR (Surinder Kumar Wali) | 0.04 | Yes | 25..02.2026 | 15.03.2026 | Yes
115 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/LAYING INTERLOCKING PAVER BLOCKS IN STREET GOL GAPPE WALI FROM DHIMAN ELECTRICAL,W.NO.32 HOSHIARPUR ( Gol Gappe Wali From Dhiman Electricals Ward No. 32) | 0.15 | Yes | 25..02.2026 | 15.03.2026 | Yes
116 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/LAYING INTERLOCKING PAVER BLOCKS IN STREET IN FRONT BANTU KARYANA STORE NEAR BANNE SHAH ROAD, HOSHIARPUR Bantu Karyana Store Near Banne Shah Road) | 0.08 | Yes | 25..02.2026 | 15.03.2026 | Yes
117 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/LAYING INTERLOCKING PAVER BLOCKS IN STREET NO.3 MOHALLA RANJIT NAGAR, HOSHIARPUR (Ranjit Nagar Street No. 3) | 0.36 | Yes | 25..02.2026 | 15.03.2026 | Yes
118 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/LAYING INTERLOCKING PAVER BLOCKS IN STREETS POST OFFICE WALI PREMGARH, HOSHIARPUR ( Street Post Office Wali, Premgarh) | 0.25 | Yes | 25..02.2026 | 15.03.2026 | Yes
119 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/LAYING INTERLOCKING PAVER BLOCKS IN DIFFERENT STREETS NEAR SONDHI TENT HOUSE PIPLAWALA , HOSHIARPUR (Street Jaswinder Kumar to dharamvir) | 0.18 | Yes | 25..02.2026 | 15.03.2026 | Yes
120 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS IN DIFFERENT STREETS OF WARD NO. 8 AND 9, HOSHIARPUR ( Street Chowdhry Blasa Ram Wali, Adjoi Street no. 1 and 2) | 0.24 | Yes | 25..02.2026 | 15.03.2026 | Yes
121 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS ON MAIN ROAD AND LINK ROAD SUNDER NAGAR WARD 13,15 HOSHIARPUR ( Main Sunder Nagar, Street Adjo Old MC T/well, Street Peeran Wali, Street Adjo Jatinder Karyana Store) | 0.48 | Yes | 30.11.2025 | 15.03.2026 | Yes | No
122 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS ON BERMS WARD NO. 29 HOSHIARPUR (Berms ) | 1.2 | Yes | 25..02.2026 | 15.03.2026 | Yes
123 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/LAYING INTERLOCKING PAVER BLOCKS IN DIFFERENT STREETS OF ,WARD NO. 6 & 34 HOSHIARPUR ( Street Raj Sharma Wali, Balwinder Singh and Santokh Singh Wali Street) | 0.26 | Yes | 25..02.2026 | 15.03.2026 | Yes
124 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/LAYING INTERLOCKING PAVER BLOCKS ON SIDE BERMS FROM MC OFFICE DERA BABA CHARAN SHAH JI, HOSHIARPUR ( MC Office to Dera Baba Charan Shah Ji) | 0.39 | Yes | 15.01.2026 | 15.03.2026 | Yes | No
125 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/LAYING INTERLOCKING PAVER BLOCKS STREET H/O CHIRAG OHRI TO H/O VIVEK GUPTA, AKASH NAGAR, HOSHIARPUR ( Street H/o Chirag Ohri To H/o Vivek Gupta) | 0.13 | Yes | 25..02.2026 | 15.03.2026 | Yes
126 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/LAYING INTERLOCKING PAVER BLOCKS IN DIFFERENT STREETS OF ,WARD NO. 15 & 14 HOSHIARPUR ( Street No. 1 Rahimpur, Street Adjoi Expert Tailer Sunder Nagar, Shiv Mandir Wali, Sant Gurmail Dass Wali) | 0.24 | Yes | 10.11.2025 | 20.12.2025 | Yes | Yes
127 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS IN DIFFERENT STREET NEAR BANNE SHAH, HOSHIARPUR (H/o Balkar Singh Wali adj Banne Shah) | 0.29 | Yes | 25..02.2026 | 15.03.2026 | Yes
128 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS IN STREET NEAR SATRNAM HOSPITOL, SURJIT UNION BANK WALI HOSHIARPUR (Satnam Hospitol, Surjit Union Bank Wali) | 0.14 | Yes | 25..02.2026 | 15.03.2026 | Yes
129 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS IN STREET FROM ATTA CHAKKI TO MUNICIPAL LAND OF MOHALLA PURHIRAN HOSHIARPUR (ATTA CHAKKI TO MUNICIPAL LAND OF MOHALLA PURHIRAN) | 0.4 | Yes | 25..02.2026 | 15.03.2026 | Yes
130 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/LAYING INTERLOCKING PAVER BLOCKS ON BERMS OF ROAD JATHEREYAN WALI AND STREET H/O HAPPY PANDIT WALI MOHALLA, PURHIRAN, HOSHIARPUR ( Happy Pandit Wali, Street H/o Ram Parkash Wali) | 0.65 | Yes | 25..02.2026 | 15.03.2026 | Yes
131 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/LAYING INTERLOCKING PAVER BLOCKS IN ST.NO.1-C GAUTAM NAGAR, HOSHIARPUR (Gali No.1 C Gautam Nagar) | 0.1 | Yes | 25..02.2026 | 15.03.2026 | Yes
132 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/LAYING INTERLOCKING PAVER BLOCKS ON SIDE BERMS AT RAHIMPUR CHOWK, HOSHIARPUR ( Rahimpur Chowk) | 0.07 | Yes | 25..02.2026 | 15.03.2026 | Yes
133 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/LAYING INTERLOCKING PAVER BLOCKS IN STREET ADJOIN COFFIE CAFE NEAR ITI, HOSHIARPUR. ( Adjo Coffe Caffe Near ITI) | 0.1 | Yes | 25..02.2026 | 15.03.2026 | Yes
134 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING PAVER BLOCK FOR TRACK IN DASHMESH PARK AND EKTA NAGAR PARK, WARD NO. 11 HOSHIARPUR. (Dashmesh PArk and Ekta Nagar Park) | 0.4 | Yes | 25..02.2026 | 15.03.2026 | Yes
135 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS IN STREET,NO.9 VIJAY NAGAR HOSHIARPUR. (Street No. 9 Vijay Nagar) | 0.1 | Yes | 25.11.2025 | 30.12.2025 | Yes | Yes
136 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS IN DIFFERENT STREET OF WARD NO. 28, HOSHIARPUR. ( Juice Wali, Peera Wali Street) | 0.41 | Yes | 25..02.2026 | 15.03.2026 | Yes
137 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS IN STREET GURU KIRPA WALI NEAR BOHAD WALA CHOWK, BAHADURPUR HOSHIARPUR. ( Guru Kirpa wali, Bohad Wala Chowk) | 0.11 | Yes | 25..02.2026 | 15.03.2026 | Yes
138 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS ON BERMS WARD NO. 34 HOSHIARPUR ( On Berms) | 0.53 | Yes | 25..02.2026 | 15.03.2026 | Yes
139 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS IN CHOWK KAPILA JATHERE SEELIAN MOHALLA & OTHER STREET WARD NO. 38 HOSHIARPUR ( Kapila Jathera Wali, Seelian Mohalla, Sheetla Mandir) | 0.18 | Yes | 14.11.2025 | 15.03.2026 | Yes | No
140 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS IN DIFFERENT STREETS IN WARD NO. 31 HOSHIARPUR ( Ohri Wali, Main Street) | 0.43 | Yes | 17.12.2025 | 15.03.2026 | Yes | No
141 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS & RECONSTRUCTION OF DRAIN IN DIFFERENT STREETS IN WARD NO. 46 HOSHIARPUR ( Dairy Wali) | 0.3 | Yes | 25..02.2026 | 15.03.2026 | Yes
142 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS STREETS IN DIFFERENT OF MOHALLA FATEHGARH, RAM SHARNAM ASHRAM & MOHALLA BAZIGAR HOSHIARPUR ( Fatehgarh, Mohalla Ram Sharnam, Bazigar, Street Pintu di chakki Wali,Adj Shop of Om Parkash, H/o Ganga Parshad) | 0.19 | Yes | 25..02.2026 | 15.03.2026 | Yes
143 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS IN STREETS AIRMAN WALI ASLAMABAD HOSHIARPUR ( Street Airman wali, Main Chandigarh Road Storm sewer Cutt, Street Hari Chand wali) | 0.48 | Yes | 15.01.2026 | 15.03.2026 | Yes | No
144 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS IN DIFFERENT STREETS OF MOHALLA TIBBA SAHIB HOSHIARPUR. (Johal Wali, Jassi Wali , Brothers Computer wali) | 0.37 | Yes | 25..02.2026 | 15.03.2026 | Yes
145 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS IN STREETS NUMBER 8 & MAIN ROAD OF MOHALLA TIBBA SAHIB HOSHIARPUR. (Main Road Tibba Sahib) | 0.34 | Yes | 26.12.2025 | 15.03.2026 | Yes | No
146 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS IN DIFFERENT STREET OF MOHALLA EKTA NAGAR & CIVIL LINE HOSHIARPUR. ( Street Opp H/o Dua, Street H/o Palli Wali) | 0.08 | Yes | 13.11.2025 | 06.03.2026 | Yes | Yes
147 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS IN STREET H/o NEELAM SHARMA & RAM MILAN YADAV WALI BASANT NAGAR HOSHIARPUR ( H/o Ram Milan Yadav, Basant Nagar, H/o Neelam Sharma Wali Adj street) | 0.12 | Yes | 17.11.2025 | 15.03.2026 | Yes | No
148 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS IN STREET NO. 11 & 7 OF DASHMESH NAGAR HOSHIARPUR. ( Sreet MC Residence Wali, Adj Street No 7, Dashmesh Nagar) | 0.15 | Yes | 25..02.2026 | 15.03.2026 | Yes
149 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/FIXING INTERLOCKING PAVER BLOCKS IN DASHMESH NAGAR GALI NO. 11 HOSHIARPUR (Gali No 11, Dashmesh Nagar) | 0.06 | Yes | 30.09.2025 | 02.12.2025 | Yes | Yes
150 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/LAYING INTERLOCKING PAVER BLOCKS IN STREET NO.1 NEW SHASTRI NAGAR WARD NO. 48 HOSHIARPUR. (StreetNo 1 New Shashtri Nagar) | 0.04 | Yes | 25..02.2026 | 15.03.2026 | Yes
151 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/LAYING PAVER BLOCKS IN STREET AMB WALI B/S SSP RESIDENCE HOSHIARPUR. (Amb Wali B/s SSP Resi) | 0.23 | Yes | 28.01.2026 | 15.03.2026 | Yes | No
152 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/LAYING PAVER BLOCKS IN STREET H/O AMARJEET SINGH WALI & NEAR SHIV MANDIR WALI WARD NO. 19, HOSHIARPUR. (Amarjeet Singh Wali adj Shiv Mandir Wali) | 0.31 | Yes | 25..02.2026 | 15.03.2026 | Yes
153 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/LAYING PAVER BLOCKS IN STREET NO.6 A NEW CIVIL LINE HOSHIARPUR. (Street No. 6, A Civil Line) | 0.2 | Yes | 25..02.2026 | 15.03.2026 | Yes
154 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR & RESTROATION OF PAVEMENT IN STREET FROM YOG SADHNA KENDRA TO STREET NO. 3 OPP. SAI BABA MANDIR ADAMWAL ROAD HOSHIARPUR. ( Yog Sadhna Kender to Street No. 3 Opp Sai Baba Mandir) | 0.75 | Yes | 25..02.2026 | 15.03.2026 | Yes
155 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/Fixing Interlocking Paver Blocks in Streets Mohalla New Fatehgarh and Gobind Nagar, Ward No. 13 Hoshiarpur (H/o Amarjeet Singh Wali, H/o Ashwani Gujjar Wali, Near Shiv Mandir) | 0.17 | Yes | 25..02.2026 | 15.03.2026 | Yes
156 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/Laying Interlocking Paver Blocks in Street No.3,ShalimarNagar, Hoshiarpur ( StreetNo. 3 Shalimar Nagar) | 0.2 | Yes | 05.02.2026 | 15.03.2026 | Yes | No
157 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/Fixing Interlocking Paver Blocks in street House of Baldev Raj wali backside cremation ground Aslamabad, Hoshiarpur. (Street H/o Baldev Raj Wali B/s Cremation Ground wali) | 0.06 | Yes | 25..02.2026 | 15.03.2026 | Yes
158 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/Fixing Interlocking Paver Blocks in street Pawan Rishi wali Near Sant Nagar Park of Ward No 31, Hoshiarpur. ( Street PAwan Rishi Wali) | 0.13 | Yes | 02.03.2026 | 15.03.2026 | Yes | No
159 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/LAYING OF RMC IN DIFFERENT STREET OF WARD NO.35, HOSHIARPUR.(MC Wali, side Street and Main Street) | 0.25 | Yes | 25..02.2026 | 15.03.2026 | Yes
160 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/LAYING OF RMC IN DIFFERENT STREET OF WARD NO.43, HOSHIARPUR (Rishi Wali, Chakki Wali, Gurudwara Wali) | 0.41 | Yes | 25..02.2026 | 15.03.2026 | Yes
161 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/LAYING RMC IN STREET D.A.V SENIOR SECONDARY SCHOOL NEAR HARI BAWA MANDIR, HOSHIARPUR (street DAV Sen Sec wali near Hari Baba Mandir) | 0.04 | Yes | 15.11.2025 | 04.02.2026 | Yes | Yes
162 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/LAYING OF RMC IN STREET NEAR CIA STAFF AND ADJOINING PANJ PIPLI MANDIR, HOSHIARPUR (Near CIA Staff and Ad Panj Pipla Wali, Kabir Panthi Mohall) | 0.25 | Yes | 25..02.2026 | 15.03.2026 | Yes
163 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/LAYING RMC IN ROAD ADJOIN MAHAVIR SPINNING MILL, HOSHIARPUR (Adj Mahavir Spining Mil) | 0.31 | Yes | 25..02.2026 | 15.03.2026 | Yes
164 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/LAYING OF RMC IN STREET PEERAN WALI GALI ADHARMI MOHALLA, BAHADURPUR HOSHIARPUR. ( Street Peeran wali) | 0.18 | Yes | 25..02.2026 | 15.03.2026 | Yes
165 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | REPAIR AND CC FLOOR IN DIFFERENT STREETS IN WARD NO. 38, HOSHIARPUR. ( Street A,B,C) | 0.49 | Yes | 25..02.2026 | 15.03.2026 | Yes
166 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | Rough Cost Estimate for Re Bore Tubewell Size 300mm X 200mm i/d with 250mtr Depth with Reverse Rorary Rig at Mohalla Adarsh Colony Ward No. 20, Hoshiarpur (Mohalla Adarsh Colony) |  | Yes | 25..02.2026 | 15.03.2026 | Yes
167 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | Rough Cost Estimate for New Tubewell Size 300mm X 200mm i/d with 250mtr Depth with Reverse Rorary Rig at Kokla Vihar (Shivalik Enclave) Ward No. 1,Hoshiarpur (Shiwalik Enclave) |  | Yes | 11.11.2025 | 15.03.2026 | Yes | No
168 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | Rough Cost Estimate for Re Bore Tubewell Size 300mm X 200mm i/d with 250mtr Depth with Reverse Rorary Rig at Shivpuri Bhim Nagar Ward No. 17, Hoshiarpur (Shivpuri Bhim Nagar) |  | Yes | 08.08.2025 | 15.03.2026 | Yes | No
169 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | Rough Cost Estimate for Re Bore Tubewell Size 300mm X 200mm i/d with 250mtr Depth with Reverse Rorary Rig at Purhiran Near Basket Ball Ground Ward No. 19, Hoshiarpur (Near Basket Ball Ground) |  | Yes | 20.08.2025 | 15.03.2026 | Yes | No
170 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | Rough Cost Estimate for Re Bore Tubewell Size 300mm X 200mm i/d with 250mtr Depth with Reverse Rorary Rig at Roshan Ground Near Post Office Ward No. 41, Hoshiarpur ( Roshan Ground near Post Office) |  | Yes | 25..02.2026 | 15.03.2026 | Yes
171 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/ERECTION OF STREET LIGHT POINTS FROM PARBHAT CHOWK TO CLOCK TOWER, HOSHIARPUR (PARBHAT CHOWK TO CLOCK TOWER) |  | Yes | 20.02.2026 | 15.03.2026 | Yes
172 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/ERECTION OF STREET LIGHT POINTS FROM TO CLOCKTOWER TO SESSION CHOWK, HOSHIARPUR (CLOCKTOWER TO SESSION CHOWK) |  | Yes | 20.02.2026 | 15.03.2026 | Yes
173 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/ERECTION OF STREET LIGHT POINTS FROM SESSION CHOWK TO FATEHGARH CHUNGI, HOSHIARPUR (SESSION CHOWK TO FATEHGARH CHUNGI) |  | Yes | 20.02.2026 | 15.03.2026 | Yes
174 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/ERECTION OF STREET LIGHT POINTS FROM D.A.V COLLEGE TO RAHIMPUR CHOWK, HOSHIARPUR (D.A.V COLLEGE TO RAHIMPUR CHOWK,) |  | Yes | 20.02.2026 | 15.03.2026 | Yes
175 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/ERECTION OF STREET LIGHT POINTS FROM RAHIMPUR CHOWK TO PHAGWARA CHOWK UPTO MC LIMIT, HOSHIARPUR (RAHIMPUR CHOWK TO PHAGWARA CHOWK UPTO MC LIMIT,) |  | Yes | 20.02.2026 | 15.03.2026 | Yes
176 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/ERECTION OF STREET LIGHT POINTS FROM RAHIMPUR CHOWK TO GOVT. COLLEGE CHOWK, HOSHIARPUR (RAHIMPUR CHOWK TO GOVT. COLLEGE CHOWK) |  | Yes | 20.02.2026 | 15.03.2026 | Yes
177 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/ERECTION OF STREET LIGHT POINTS FROM I.T.I TO KFC CHOWK, HOSHIARPUR (I.T.I TO KFC CHOWK,) |  | Yes | 20.02.2026 | 15.03.2026 | Yes
178 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/ERECTION OF STREET LIGHT POINTS FROM KFC CHOWK PHAGWARA CHOWK, HOSHIARPUR (KFC CHOWK PHAGWARA CHOWK) |  | Yes | 01.11.2025 | 15.03.2026 | Yes | No
179 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/ ERECTION OF STREET LIGHT POINTS FROM DAV COLLEGE TO CHANDIGARH ROAD UPTO MC LIMIT, HOSHIARPUR (DAV COLLEGE TO CHANDIGARH ROAD UPTO MC LIMIT,) |  | Yes | 23.10.2025 | 15.03.2026 | Yes | No
180 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/ERECTION OF STREET LIGHT POINTS FROM DHOBI GHAT TO ADAMWAL ROAD UPTO MC LIMIT, HOSHIARPUR (DHOBI GHAT TO ADAMWAL ROAD UPTO MC LIMIT) |  | Yes | 13.11.2025 | 15.03.2026 | Yes | No
181 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/ERECTION OF STREET LIGHT POINTS FROM ROSHAN LAL PAINT SHOP BHANGI CHOE BRIDGE, HOSHIARPUR (ROSHAN LAL PAINT SHOP BHANGI CHOE BRIDGE) |  | Yes | 18.11.2025 | 15.03.2026 | Yes | No
182 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/ERECTION OF STREET LIGHTS FROM PHAGWARA BYE PASS CHOWK TO DHAN GURU RAM DASS LANGER SEWA,PURHIRAN HOSHIARPUR (PHAGWARA BYE PASS CHOWK TO DHAN GURU RAM DASS LANGER SEWA,PURHIRAN) |  | Yes | 23.10.2025 | 15.03.2026 | Yes | No
183 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/ERECTION OF STREET LIGHT POINTS FROM BHANGI CHOW TO BANJARBAG (BHARWAYI ROAD), HOSHIARPUR ( BHANGI CHOW TO BANJARBAG (BHARWAYI ROAD) |  | Yes | 3.11.2025 | 15.03.2026 | Yes | No
184 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/ERECTION OF STREET LIGHT POINTS FROM CHOW BANDH TO BHARWAYI ROAD, SUKHIABAD HOSHIARPUR (CHOW BANDH TO BHARWAYI ROAD, SUKHIABAD) |  | Yes | 20.02.2026 | 15.03.2026 | Yes
185 | Hoshiarpur | Mukesh Kumar Garg | MDF | Hoshiarpur | P/ ERECTION OF STREET LIGHT POINTS FROM MATA VAISHNO DHAM TO CREAMATION GROUND,HOSHIARPUR (MATA VAISHNO DHAM TO CREAMATION GROUND) |  | Yes | 8.11.2025 | 15.03.2026 | Yes | No
186 | Batala | Ashwani Chaudhary | MDF | Batala | Const of various streets from Ward no. 1 to Ward no. 29 | 30.41 | Yes | 10.01.2026 | 30.06.2026
187 | Batala | Ashwani Chaudhary | MDF | Batala | P/L New RMC Road circular road M.C Batala | 2.54 | Yes | 10.01.2026 | 30.06.2026
188 | Batala | Ashwani Chaudhary | MDF | Batala | Providing & Fixing GI Poles & LED Street Lights in Greater Kailash, Jharianwala & unique avenue of ward no 19 (Rs. 5137767) | N.A | Yes | 10.01.2026 | 30.06.2026
189 | Moga | Naresh Batta | MDF | Moga | Relaying /Renovation of Road alog kingwag Distributry, Bukkanwala Road, Dhalleke Road, Kothe Patti Mohabbat Road, Bahona Road | 9.1 | Yes | 12.11.2025 | 15.05.2026 | Yes | No
190 | Moga | Naresh Batta | MDF | Moga | Beautification of Partap Road | 1 | Yes | 17-03-2026 | 15-07-2026 | No
191 | Moga | Naresh Batta | MDF | Moga | Relaying and renovation with 20 mm thick open graded PC on various roads of Moga City | 8.2 | Yes | 14.11.2025 | 20.05.2026 | Yes | No
192 | Moga | Naresh Batta | MDF | Moga | Relaying and renovation 30 mm SDBC on various roads of Moga City | 4.05 | Yes | 20.02.2026 | 30.05.2026 | Yes | No
193 | Moga | Naresh Batta | MDF | Moga | Relaying 20 mm thick open graded PC on Preet Nagar main road, Sardar Nagar road no. 4, Sandhuanwala road and other streets of Moga City | 3 | Yes | 20.02.2026 | 31.03.2026 | Yes | No
194 | Bathinda | Rajinder Rai | MDF | Bathinda | Recarpetting of roads in Civil Station Area | 5.35 | Yes | 20-03-2026 | 15-04-2026 | No | No
195 | Bathinda | Rajinder Rai | MDF | Bathinda | Recarpetting of roads of Green city | 1.6 | Yes | 2026-05-04 | 15-04-2026 | No | No
196 | Pathankot | Ashwani Chaudhary | MDF | Pathankot | P/L open water supply GI pipe line 2" and 3" in Moh.Ghartholi, Mohalla Sarain, Jandriya Mohalla bajri Co., Jattan Mohalla , Dhangu Peer, Mudhut Colony in M.C.Ptk. | NA | Yes | 04.12.2025 | 03.04.2026
197 | Pathankot | Ashwani Chaudhary | MDF | Pathankot | Beautification of Chowks in M.C.Ptk. | NA | Yes | 04.12.2025 | 03.04.2026
198 | Pathankot | Ashwani Chaudhary | MDF | Pathankot | Beautification of Circular Road in M.C.Ptk. | 0.548 | Yes | 04.12.2025 | 03.04.2026
199 | Pathankot | Ashwani Chaudhary | MDF | Pathankot | Purchase of Mini Jetting Machine with 1 No. of storage tank complete set for MC Pathankot. | NA | Yes | 11.03.2026 | 30.04.2026
200 | Pathankot | Ashwani Chaudhary | MDF | Pathankot | P/L 50 mm thick BM and 20 mm PC on Shere Dugger Road to Bhadroya M.C.Ptk. | 1.253 | Yes | 10.03.2026 | 25.06.2026
201 | Pathankot | Ashwani Chaudhary | MDF | Pathankot | Const. of Community Halls in different area of M.C.Ptk. | NA | Yes | 04.12.2025 | 03.06.2026
202 | Pathankot | Ashwani Chaudhary | MDF | Pathankot | Const. of road from Dehriwal to Jamalpur in M.C.Ptk. | 0.849 | Yes | 04.12.2025 | 03.06.2026
203 | Pathankot | Ashwani Chaudhary | MDF | Pathankot | Const. of road from Kothi Pandita to Jamalpur in M.C.Ptk. | 0.862 | Yes | 04.12.2025 | 03.06.2026
204 | Pathankot | Ashwani Chaudhary | MDF | Pathankot | Upgradatoin of various green spaces in M.C.Ptk | NA | Yes | 22.01.2026 | 21.07.2026
205 | Pathankot | Ashwani Chaudhary | MDF | Pathankot | P/F streets light in various wards of MC.Ptk. | NA | Yes | 11.03.2026 | 30.04.2026
206 | Pathankot | Ashwani Chaudhary | MDF | Pathankot | Const. of streets in various wards of Zone No. 1 in MC Ptk | 3.399 | Yes | 04.12.2025 | 03.11.2025
207 | Pathankot | Ashwani Chaudhary | MDF | Pathankot | Const. of streets in various wards of Zone No. 2 in MC Ptk | 4.06 | Yes | 04.12.2025 | 03.11.2025
208 | Pathankot | Ashwani Chaudhary | MDF | Pathankot | Const. of streets in various wards of Zone No. 3 in MC Ptk | 4.314 | Yes | 04.12.2025 | 03.11.2025
209 | Pathankot | Ashwani Chaudhary | MDF | Pathankot | Const. of streets in various wards of Zone No. 4 in MC Ptk | 4.07 | Yes | 04.12.2025 | 03.11.2025
210 | Pathankot | Ashwani Chaudhary | MDF | Pathankot | Const. of streets in Vijay Nagar Ward No. 45 | 0.37 | Yes | 04.12.2025 | 03.03.2026
211 | Pathankot | Ashwani Chaudhary | MDF | Pathankot | Installation of 20 No. semi high mast lights in MC. Ptk. | NA | Yes | 10.03.2026 | 30.04.2026
212 | Pathankot | Ashwani Chaudhary | MDF | Pathankot | Providing and Installation Of 12 no shallow T/wells in Various Wards of MC Pathankot. | NA | Yes | 04.12.2025 | 03.04.2026
213 | Pathankot | Ashwani Chaudhary | MDF | Pathankot | Providing and Installation of 4 No. New Tubewell in different wards of MC.Ptk. | NA | Yet to start | - | -
214 | SAS Nagar | Naresh Batta | MDF | SAS Nagar | P/L of BC 40 mm thick on 66/67 dividing road | 2.2 | Yes | 04.11.2025 | 11.03.2026 | Yes | Yes
215 | SAS Nagar | Naresh Batta | MDF | SAS Nagar | P/L of BC 40 mm thick on 67/68 dividing road | 2.2 | Yes | 04.11.2025 | 31-3-2026 | Yes | No
216 | SAS Nagar | Naresh Batta | MDF | SAS Nagar | P/L of BC 40 mm thick on 68/69 dividing road | 2.2 | Yes | 04.11.2025 | 06.03.2026 | Yes | Yes
217 | SAS Nagar | Naresh Batta | MDF | SAS Nagar | P/L of BC 40 mm thick on YPS School road | 1.3 | Yes | 04.11.2025 | 11.03.2026 | Yes | Yes
218 | SAS Nagar | Naresh Batta | MDF | SAS Nagar | P/L of BC 40 mm thick on Franco to PTL chowk | 1.05 | Yes | 04.11.2025 | 31-3-2026 | Yes | No
219 | SAS Nagar | Naresh Batta | MDF | SAS Nagar | P/L of BC 30 mm thick on village Mohali to Fire brigade traffic Light | 2.82 | Yes | 01.01.2026 | 31-3-2026 | Yes | No
220 | SAS Nagar | Naresh Batta | MDF | SAS Nagar | P/L of BC 40 mm thick on phase 1/6 dividing road to Bus stand | 0.5 | Yes | 04.11.2025 | 31-3-2026 | Yes | No
221 | SAS Nagar | Naresh Batta | MDF | SAS Nagar | P/L of BC 40 mm thick on phase Railway station road | 1.24 | Yes | 04.11.2025 | 31-3-2026 | Yes | No
222 | SAS Nagar | Naresh Batta | MDF | SAS Nagar | R/C estimate for laying of BM and BC in various areas of industrial area phase 1, 3 & 7 MC S.A.S Nagar | 1.3 | Yes | 04.11.2025 | 31.03.2026 | Yes | No
223 | SAS Nagar | Naresh Batta | MDF | SAS Nagar | Scarifying of existing damaged bituminous surface and laying SDBC 30mm thick on c road phase 3B2 | 1.25 | Yes | 28.01.2026 | 31.03.2026 | Yes | No
224 | SAS Nagar | Naresh Batta | MDF | SAS Nagar | Scarifying of existing damaged bituminous surface and laying SDBC 30mm thick on c road phase 3B1 | 3.83 | Yes | 28.01.2026 | 31.03.2026 | Yes | No
225 | SAS Nagar | Naresh Batta | MDF | SAS Nagar | Construction of Road at Jagatpura Dumpsite | 1.1 | Yes | 09.01.2026 | 31.03.2026 | Yes | No
226 | Barnala | Rajinder Rai | MDF | Barnala | Providing laying of BC and road gully chamber in ramgariya road Railway phatak to raikot road ward no. 18 Barnala | 0.54 | Yes | 30.10.2025 | 15.04.2026 | Yes | No
227 | Barnala | Rajinder Rai | MDF | Barnala | Providing laying main street DB paving and branch streets interlock tiles Babbran wala pha ward No. 3 Barnala | 1.69 | Yes | 27.10.2025 | 15.04.2026 | Yes | No
228 | Barnala | Rajinder Rai | MDF | Barnala | Providing laying interlocking tiles in street area gill nagar street no. 12,17,19 and branch streets ward no. 10 Barnala | 0.77 | Yes | 23.10.2025 | 15.04.2026 | Yes | No

## Sheet11 (hidden)
Municipal Corporations - SASCI & MDF |  |  |  |  | 14-03-2026 |  | 16-03-2026
District | Corporation Name | Responsible CE | No of Works | Total Length (Km) | Works yet to be Awarded | Works yet to be started | Works yet to be Awarded | Works yet to be started
Fazilka | Abohar | Naresh Batta | 3 | 12.9 | 0 | 1 | 0 | 1
Amritsar | Amritsar | Ashwani Chaudhary | 7 | 245 | 0 | 0 | 0 | 0
Barnala | Barnala | Rajinder Rai | 24 | 22.36 | 21 | 21 | 21 | 21
Batala | Batala | Ashwani Chaudhary | 7 | 43.95 | 0 | 0 | 0 | 0
Bathinda | Bathinda | Rajinder Rai | 9 | 159.02 | 0 | 2 | 0 | 2
Hoshiarpur | Hoshiarpur | Mukesh Kumar Garg | 179 | 72.36 | 0 | 116 | 0 | 116
Jalandhar | Jalandhar | Mukesh Kumar Garg | 9 | 125 | 0 | 2 | 0 | 2
Kapurthala | Kapurthala | Mukesh Kumar Garg | 5 | 17.38 | 1 | 5 | 1 | 5
Ludhiana | Ludhiana | Ravinder Kumar Garg | 20 | 140.76 | 5 | 5 | 5 | 5
Moga | Moga | Naresh Batta | 6 | 50.35 | 0 | 1 | 0 | 1
Pathankot | Pathankot | Ashwani Chaudhary | 19 | 34.13 | 0 | 1 | 0 | 0
Patiala | Patiala | Rajiv Kumar | 3 | 36 | 0 | 0 | 0 | 0
Kapurthala | Phagwara | Mukesh Kumar Garg | 2 | 17 | 1 | 1 | 1 | 1
SAS Nagar | SAS Nagar | Naresh Batta | 13 | 38.99 | 0 | 0 | 0 | 0
Total |  |  | 306 | 1015.2 | 28 | 155 | 28 | 154

## Sheet8 (hidden)
Municipal Corporations - SASCI & MDF (10.02.2026)
|  | Total Works |  |  | Cumulative Progress till date (Today)
Municipal Corporation Name | Responsible CE | Fund (SASCI/ MDF) | No of Works | Total Length (Km) | works awarded | Number of work started | Length (Km) (Started) | Works Awarded but not started
Batala | Ashwani Chaudhary | SASCI | 4 | 11 | 4 | 4 | 11 | 0
Kapurthala | Mukesh Kumar Garg | SASCI | 1 | 10 | 0 | 0 | 0 | 0
Ludhiana | Ravinder Kumar Garg | SASCI | 20 | 140.76 | 15 | 13 | 80.6 | 2
Patiala | Rajiv Kumar | SASCI | 3 | 36 | 3 | 3 | 34.44 | 0
Pathankot | Ashwani Chaudhary | SASCI | 1 | 14.4 | 1 | 1 | 14 | 0
Amritsar | Ashwani Chaudhary | SASCI | 7 | 245 | 7 | 7 | 245 | 0
Phagwara | Mukesh Kumar Garg | SASCI | 2 | 17 | 1 | 1 | 8 | 0
Jalandhar | Mukesh Kumar Garg | SASCI | 9 | 125 | 9 | 7 | 90 | 2
Abohar | Naresh Batta | SASCI | 1 | 4 | 1 | 1 | 4 | 0
Bathinda | Rajinder Rai | SASCI | 7 | 152.07 | 7 | 7 | 152 | 0
Moga | Naresh Batta | SASCI | 1 | 25 | 1 | 1 | 25 | 0
SAS Nagar | Naresh Batta | SASCI | 1 | 18 | 1 | 1 | 18 | 0
Barnala | Rajinder Rai | SASCI | 21 | 19.36 | 0 | 0 | 0 | 0
Total |  | SASCI | 78 | 817.59 | 50 | 46 | 682.04 | 4
0
Kapurthala | Mukesh Kumar Garg | MDF | 4 | 7.38 | 4 | 0 | 0 | 4
Abohar | Naresh Batta | MDF | 2 | 8.9 | 2 | 1 | 4.5 | 1
Hoshiarpur | Mukesh Kumar Garg | MDF | 179 | 72.36 | 179 | 63 | 28.72 | 116
Batala | Ashwani Chaudhary | MDF | 3 | 32.95 | 3 | 3 | 33 | 0
Moga | Naresh Batta | MDF | 5 | 25.35 | 5 | 2 | 17.3 | 3
Bathinda | Rajinder Rai | MDF | 2 | 6.95 | 2 |  |  | 2
Pathankot | Ashwani Chaudhary | MDF | 18 | 19.73 | 18 | 17 | 19.73 | 1
SAS Nagar | Naresh Batta | MDF | 12 | 20.99 | 12 | 7 | 10.75 | 5
Barnala | Rajinder Rai | MDF | 3 | 3 | 3 | 3 | 3 | 0
Total |  | MDF | 228 | 197.61 | 228 | 96 | 117 | 132

## 6 corporations (hidden)
Municipal Corporations - SASCI & MDF - 11-03-2026
| - | मान
| 75.48 | [17 empty] | कुल योग
| No of Works | Cumulative works awarded | Cumulative Number of Work Started | Cumulative Number of Work Completed | Cumulative Length (Km) Completed | Number of Works Awarded Today | Number of Work Started Today | Works Completed Today | Length of work Completed Today (KM) | No of Works | Cumulative works awarded | Cumulative Number of Work Started | Cumulative Number of Work Completed | Cumulative Length (Km) Completed | Number of Works Awarded Today | Number of Work Started Today | Works Completed Today | Length of work Completed Today (KM) | No of Works | Cumulative works awarded | Cumulative Number of Work Started | Cumulative Number of Work Completed | Cumulative Length (Km) Completed | Number of Works Awarded Today | Number of Work Started Today | Works Completed Today | Length of work Completed Today (KM)
| 0 | 0 | 0 | 0 | 1.6 | 0 | 0 | 0 | 3.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6 | 0 | 0 | 0 | 3.77
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Progress (hidden)
Municipal Corporations - SASCI & MDF
|  | Total Works |  |  | Cumulative Progress till 26-02-2026 |  |  |  |  | Cumulative Progress till 05/03/2026 | [5 empty] | Cumulative Progress till 06/03/2026
Municipal Corporation Name | Responsible CE | Fund (SASCI/ MDF) | No of Works | Total Length (Km) | works awarded | Number of work started | Length (Km) (Started) | Number of Work Complete d | Length (Km) (Completed) | works awarded | Number of work started | Length (Km) (Started) | Work Awarded but not started | Number of Work Completed | Length (Km) (Completed) | works awarded | Number of work started | Length (Km) (Started) | Work Awarded but not started | Number of Work Completed | Length (Km) (Completed)
Batala | Ashwani Chaudhary | SASCI | 4 | 11 | 4 | 4 | 11 |  |  | 4 | 4 | 11 | 0 |  |  | 4 | 4 | 11 | 0
Ludhiana | Ravinder Kumar Garg | SASCI | 20 | 141 | 13 | 7 | 40.34 | 0 | 0 | 13 | 10 | 62.93 | 3 | 0 | 0 | 13 | 10 | 62.93 | 3 | 0 | 0
Patiala | Rajiv Kumar | SASCI | 3 | 36 | 3 | 3 | 34.44 |  |  | 3 | 3 | 34.44 | 0 |  |  | 3 | 3 | 34.44 | 0
Pathankot | Ashwani Chaudhary | SASCI | 1 | 14 | 1 | 1 | 14 |  |  | 1 | 1 | 14 | 0 |  |  | 1 | 1 | 14 | 0
Amritsar | Ashwani Chaudhary | SASCI | 7 | 245 | 7 | 7 | 245 |  |  | 7 | 7 | 245 | 0 |  |  | 7 | 7 | 245 | 0
Phagwara | Mukesh Kumar Garg | SASCI | 2 | 17 | 1 | 1 | 8 |  |  | 1 | 1 | 8 | 0 |  |  | 1 | 1 | 8 | 0
Jalandhar | Mukesh Kumar Garg | SASCI | 9 | 125 | 9 | 6 | 2.6 |  |  | 9 | 7 | 90 | 2 |  |  | 9 | 7 | 90 | 2
Abohar | Naresh Batta | SASCI | 1 | 4 | 1 | 1 | 4 |  |  | 1 | 1 | 4 | 0 |  |  | 1 | 1 | 4 | 0
Bathinda | Rajinder Rai | SASCI | 7 | 152 | 7 | 7 | 152 |  |  | 7 | 7 | 152 | 0 |  |  | 7 | 7 | 152 | 0
Moga | Naresh Batta | SASCI | 1 | 25 | 1 | 1 | 25 |  |  | 1 | 1 | 25 | 0 |  |  | 1 | 1 | 25 | 0
SAS Nagar | Naresh Batta | SASCI | 1 | 18 | 1 | 1 | 18 |  |  | 1 | 1 | 18 | 0 |  |  | 1 | 1 | 18 | 0
Barnala | Rajinder Rai | SASCI | 21 | 19 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
Total |  | SASCI | 77 | 808 | 48 | 39 | 554.38 | 0 | 0 | 48 | 43 | 664.37 | 5 | 0 | 0 | 48 | 43 | 664.37 | 5 | 0 | 0
Kapurthala | Mukesh Kumar Garg | MDF | 4 | 7 | 4 | 0 | 0 |  |  | 4 | 0 | 0 | 4 |  |  | 4 | 0 | 0 | 4
Abohar | Naresh Batta | MDF | 2 | 9 | 2 | 1 | 4.5 |  |  | 2 | 1 | 4.5 | 1 |  |  | 2 | 1 | 4.5 | 1
Hoshiarpur | Mukesh Kumar Garg | MDF | 179 | 72 | 179 | 53 | 20.56 | 13 | 4.51 | 179 | 63 | 28.72 | 116 | 13 | 4.51 | 179 | 63 | 28.72 | 116 | 13 | 4.51
Batala | Ashwani Chaudhary | MDF | 3 | 33 | 3 | 3 | 33 |  |  | 3 | 3 | 33 | 0 |  |  | 3 | 3 | 33 | 0
Moga | Naresh Batta | MDF | 5 | 25.35 | 5 | 2 | 17.3 |  |  | 5 | 2 | 17.3 | 3 |  |  | 5 | 2 | 17.3 | 3
Bathinda | Rajinder Rai | MDF | 2 | 6.95 | 2 |  |  |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2
Pathankot | Ashwani Chaudhary | MDF | 18 | 20 | 18 | 16 | 18 |  |  | 18 | 16 | 18 | 2 |  |  | 18 | 16 | 18 | 2
SAS Nagar | Naresh Batta | MDF | 12 | 20.99 | 12 | 5 | 7.25 | 1 | 1.3 | 12 | 5 | 7.25 | 7 | 1 | 1.3 | 12 | 5 | 7.25 | 7 | 1 | 1.3
Barnala | Rajinder Rai | MDF | 3 | 3 | 3 | 3 | 3 |  |  | 3 | 3 | 3 | 0 |  |  | 3 | 3 | 3 | 0
Total |  | MDF | 228 | 198 | 228 | 83 | 103.61 | 14 | 5.81 | 228 | 93 | 111.77 | 135 | 14 | 5.81 | 228 | 93 | 111.77 | 135 | 14 | 5.81

## Pivot Table 7 (hidden)
मान
|  |  | 0.4 |  | 3.2 |  | 3.68 |  | 4 |  | 4.9 |  | 5.98 |  | 7.46 |  | 9.7 |  | 13.52 |  | 22.64 |  | 75.48
| SUM of Works awarded | SUM of No. of work started | SUM of Works awarded | SUM of No. of work started | SUM of Works awarded | SUM of No. of work started | SUM of Works awarded | SUM of No. of work started | SUM of Works awarded | SUM of No. of work started | SUM of Works awarded | SUM of No. of work started | SUM of Works awarded | SUM of No. of work started | SUM of Works awarded | SUM of No. of work started | SUM of Works awarded | SUM of No. of work started | SUM of Works awarded | SUM of No. of work started | SUM of Works awarded | SUM of No. of work started | SUM of Works awarded | SUM of No. of work started
| 0 | 0 | [20 empty] | 0 | 0
Construction of Various Roads in South Constituency Zone-C Ludhiana. | [8 empty] | 0 | 0
Laying BM and SDBC on road in Sub Zone D2 Atam Nagar Halka |  |  |  |  | 0 | 0
Upgradation and development of various roads in different ward of West Constituency | [20 empty] | 0 | 0
Upgradation of Bituminious Roads in various wards of Central Constituency. | [12 empty] | 0 | 0
Upgradation of Gurudwara road urban estate phase 1&2 from Metro road to Jeewan Nagar chowk, Road along budha nallah from NHAI to MC limit ,Main Bhadur Ke Road from Sabji Mandi upto MC Limit, Main New Azad Nagar 30' Road from Kainth Property Dealer upto Gaur Property Dealer and Roads of Onkar Vihar. | [14 empty] | 0 | 0
Upgradation of Main Bhamian Road from Chandigarh road to upto MC Limit, Main Phirni of Village Mundian Kalan from Chd road to Sunder Nagar 33' Road and from Chd Road to Rasila Nagar Back side Blind School. | [10 empty] | 0 | 0
Upgradation of Main Metro Road from Jamalpur Chowk to Kangaroo Industry, Jaswant Singh Dental College to Delhi road via Sethi Sweets, Internal Roads of Sec-39,Road from Primary Govt School to NRI Police Station in Sec-39, Main Jain Colony road from Rahon Road to Swastik Enclave and Main Road of Guru Arjun Dev Nagar from GT Road upto Greenland School, Sabji Mandi Road from Chd road to Puda road, EWS colony main road from Jacha Bacha Hospital upto Tajpur road. | [18 empty] | 0 | 0
Upgradation of road from shamshan ghat pully and malhi pully backside New Deep nagar ward no. 91 |  |  | 0 | 0
Upgradation of Roads with RMC in Area Guru Har Rai Nagar, Nagesh Hosiery Road adjoining Jalandhar Byepass, Ludhiana | [6 empty] | 0 | 0
Upgradation of Various Bitumen Main Roads in North Constituency Zone-A Ludhiana | [16 empty] | 0 | 0
कुल योग | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Table 1
Region: Ludhiana Corporation: Ludhiana
ABSTRACT (Road Works under the Municipal Corporation Ludhiana Limits)
Sr. No. | Description of Project | Type of Roads | Source of Funding | Total Works | Total Cost (Crores) | Total Length (KM) | Total length completed as on 29th july | % length completed as on 29th july | Total length completed as on 6th Aug. | % length completed as on 6th Aug | White Line Target (km) | White Line Completion (km) | Date of Completion along with Remarks (if any)
1 | PWD (B&R) Roads with in Municpal Limits of Ludhiana | -Nil-
2 | PMB Roads with in Municpal Limits of Ludhiana | -Nil-
3 | Roads Being Executed by Municipal Corporation | Bituminous | MDF-2 (SASCI to MDF) | 2 | 10.66 | 7.88 | 4.5 | 57.11% | 4.52 | 57.36% | 7.88 | 0 | Work is in progress which will be completed by 15.08.2026. Bitumen work delay due to rainy season
4 | Roads Being Executed by Municipal Corporation | RMC | MDF-2 (SASCI to MDF) | 7 | 44.18 | 45.01 | 30.37 | 67.47% | 30.4 | 67.54% | 0 | 4.40 Km (Yellow line on RMC Work) | 2 works will be completed by 31-07-2026 4 Works will be completed by 15-08-2026 1 work is delayed due to 24x7 water supply project
5 | Roads Being Executed by Municipal Corporation | Bituminous & RMC | MDF-2 (SASCI to MDF) | 1 | 4.45 | 9.11 | 4.25 | 46.65% | 4.38 | 48.08% | 5.3 | 3.00 Km (Yellow line on RMC Work) | Work is in progress which will be completed by 15.08.2026 . Bitumen work delay due to rainy season
6 | Roads Being Executed by Municipal Corporation | RMC | SASCI | 2 | 10.38 | 7.68 | 3.48 | 45.31% | 3.58 | 46.61% | 0 |  | Work will be completed by 15-08-2026
7 | Roads Being Executed by Municipal Corporation | Bituminous | SASCI | 2 | 12.05 | 20.98 | 4.84 | 23.07% | 4.84 | 23.07% | 20.98 | 0 | Total No. of Works = 7 Awarded Work = 2 (Work is in progress which will be completed by 30.09.2026. Bitumen work delay due to rainy season, 24x7 water supply project and Storm Sewer Issue) Under Litigation Work = 5 (Report mentioned below) 4 no. works were recalled for due date 03.03.2026, But tender not opened due to Procedure stop by Hon'ble High Court, Hearing for the same is on dated 22-07-2026, Next date of hearing is 30-07-2026 1 no work were recalled for due date 13.03.2026. But tender not opened due to Procedure stop by Hon'ble High Court, Hearing for the same is on dated 03-09-2026. Now the date of hearing is 08-07-2026, then to 16/7/26, next date of hearing is 09-09- 2026
8 | Roads Being Executed by Municipal Corporation | Bituminous & RMC | SASCI | 1 | 6.22 | 1.5 | 1.45 | 96.67% | 1.5 | 100% | 1.5 | 0 | Work is in progress which will be completed by 15.08.2026 . Bitumen work delay due to rainy season
Total |  |  |  | 15 | 81.72 | 90.66 | 47.44 | 52.33% | 47.72 | 52.64% | 35.66 | 7.4